## Tab A Description
Work Approval Form (WAF)
Cost Center: TBD
Job Number: 1001
Job Title: NSTX CS Upgrade PFCs
Job Manager: Kelsey Tresemer
Description:
Provide adequate thermal coverage for the center stack via tiles. Design diagnostic housing and tile mounting schemes. Generate proper documentation.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: TBD
Job Number: 1001
Job Title: NSTX CS Upgrade PFCs
Job Manager: Kelsey Tresemer
Estimate (user input)
[5 empty] | SCHEDULE | [12 empty] | FY09$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10 | [16 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-02 | 2011-07-03 | 2011-08-04 | 2011-09-05
numb | P3 cross ref (optinal) | [16 empty] | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
|  | Conceptual Design | [9 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
1 |  | Preliminary Planning/Fact Finding |  | Tresemer | 20 |  |  |  | 2009-06-29 | 2009-06-29 | 2009-07-27 | 2009-06-29 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 80
2 |  | Tile Layout/Preliminary Tile Design |  | Jariwala | 15 | 1 |  |  | 2009-07-06 | 2009-07-06 | 2009-07-27 | 2009-07-06 | 2009-07-27 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 120
3 |  | Diagnostic Layout |  | Jariwala | 10 | 2 |  |  | 2009-07-27 | 2009-07-27 | 2009-08-10 | 2009-07-27 | 2009-07-27 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 80 |  |  |  |  | 20
4 |  | PPPL Peer Review Prep |  | Tresemer | 4 | 2 | 3 |  | 2009-08-08 | 2009-08-08 | 2009-08-13 14:24 | 2009-08-08 | 2009-07-27 | 2009-08-10 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 32 |  |  |  |  | 16
5 |  | PPPL Peer Review |  | Tresemer | 1 | 4 |  |  | 2009-08-13 | 2009-08-13 | 2009-08-14 09:36 | 2009-08-13 | 2009-08-13 14:24 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 8 |  |  |  |  | 8
6 |  | Tile/Diagnostic/Hardware Reconfig, Mat. Research (R&D) |  | Tresemer | 40 | 5 |  |  | 2009-08-14 | 2009-08-14 | 2009-10-09 | 2009-08-14 | 2009-08-14 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 100 |  |  |  |  | 100
7 |  | Tile Thermal Analysis |  | Tresemer | 15 | 6 |  |  | 2009-09-14 | 2009-09-14 | 2009-10-05 | 2009-09-14 | 2009-10-09 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [6 empty] | 80 | [5 empty] | 30
8 |  | PU CDR prep |  | Tresemer | 5 | 7 | 6 |  | 2009-10-05 | 2009-10-05 | 2009-10-12 | 2009-10-05 | 2009-10-05 | 2009-10-09 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 40 |  |  |  |  | 30
9 |  | PPPL CDR |  | Tresemer | 1 | 8 |  |  | 2009-10-13 | 2009-10-13 | 2009-10-14 09:36 | 2009-10-13 | 2009-10-12 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 8 |  |  |  |  | 8
|  | Preliminary Design | [9 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
10 |  | CDR Chit Resolution |  | Tresemer | 10 | 9 |  |  |  | 2009-10-16 09:40 | 2009-10-30 09:40 | 2009-10-16 09:40 | 2009-10-14 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 30 |  |  |  |  | 40
11 |  | Tile Analysis Continued… |  | Tresemer | 30 | 10 |  |  |  | 2009-10-30 09:40 | 2009-12-11 09:40 |  | 2009-10-30 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [6 empty] | 120 | [5 empty] | 60
12 |  | FMEA Analysis |  | Tresemer | 15 | 10 |  |  |  | 2009-10-30 09:40 | 2009-11-20 09:40 | 2009-10-16 09:40 | 2009-10-30 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 60
13 |  | Prepare NEPA Form |  | Tresemer | 1 | 10 |  |  |  | 2009-10-30 09:40 | 2009-10-31 19:16 | 2009-10-16 09:40 | 2009-10-30 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 8
14 |  | Order Material Samples |  | Tresemer | 20 | 10 | 11 |  |  | 2009-12-11 09:40 | 2010-01-08 09:40 | 2009-10-16 09:40 | 2009-10-30 09:40 | 2009-12-11 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 |  | 5 |  |  | 5 | [7 empty] | 40
15 |  | Material Testing |  | Tresemer | 20 | 14 |  |  |  | 2010-01-08 09:40 | 2010-02-05 09:40 |  | 2010-01-08 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 40 | 80
16 |  | Update Cost & Schedule Estimate |  | Tresemer | 5 | 9 | 11 | 15 |  | 2010-02-05 09:40 | 2010-02-12 09:40 |  | 2009-10-14 09:36 | 2009-12-11 09:40 | 2010-02-05 09:40 | 2009-10-16 09:40 | [12 empty] | 25
17 |  | Design Drawings |  | Jariwala | 80 | 11 | 12 | 15 |  | 2010-02-05 09:40 | 2010-05-28 09:40 | 2009-10-16 09:40 | 2009-12-11 09:40 | 2009-11-20 09:40 | 2010-02-05 09:40 | 2009-10-16 09:40 | [7 empty] | 640
18 |  | PDR Prep |  | Tresemer | 10 |  |  |  | 2010-05-01 | 2010-05-01 | 2010-05-15 | 2010-05-01 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 20 |  |  |  |  | 40
19 |  | CONDUCT PDR |  | Tresemer | 1 | 18 |  |  |  | 2010-05-15 | 2010-05-16 09:36 | 2009-10-16 09:40 | 2010-05-15 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 8
[12 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
|  | Final Design | [9 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
20 |  | Disposition PDR Chits |  | Tresemer | 20 | 19 |  |  |  | 2010-05-16 09:36 | 2010-06-13 09:36 | 2009-10-16 09:40 | 2010-05-16 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 60 |  |  |  |  | 80
21 |  | Update Analyses |  | Tresemer | 25 | 20 |  |  |  | 2010-06-13 09:36 | 2010-07-18 09:36 | 2009-10-16 09:40 | 2010-06-13 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [6 empty] | 80 | [5 empty] | 50
22 |  | Update Cost & Schedule Estimate |  | Tresemer | 5 | 21 |  |  |  | 2010-07-18 09:36 | 2010-07-25 09:36 | 2009-10-16 09:40 | 2010-07-18 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 20
23 |  | Design Drawings |  | Tresemer | 250 | 21 |  |  |  | 2010-07-18 09:36 | 2011-07-03 09:36 | 2009-10-16 09:40 | 2010-07-18 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 2000
24 |  | Prep Procurement Specs |  | Tresemer | 15 | 23 |  |  |  | 2011-07-03 09:36 | 2011-07-24 09:36 | 2009-10-16 09:40 | 2011-07-03 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 60
25 |  | FDR Prep |  | Tresemer | 10 | 22 | 23 |  |  | 2011-07-03 09:36 | 2011-07-17 09:36 | 2009-10-16 09:40 | 2010-07-25 09:36 | 2011-07-03 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | [7 empty] | 16 |  |  |  |  | 40
26 |  | CONDUCT FDR |  | Tresemer | 1 | 25 |  |  |  | 2011-07-17 09:36 | 2011-07-18 19:12 | 2009-10-16 09:40 | 2011-07-17 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 8
27
|  | Procurement | [9 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
28 |  | Item 1: Tiles (CFC and any other mat) |  | Tresemer | [7 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 |  | 650
29 |  |  | Prep Requisition and procurement package | Tresemer | 4 | 26 |  |  |  | 2011-07-18 19:12 | 2011-07-24 09:36 | 2009-10-16 09:40 | 2011-07-18 19:12 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 16
30 |  |  | SUBMIT REQ TO PROCUREMENT | Tresemer | 2 | 29 |  |  |  | 2011-07-24 09:36 | 2011-07-27 04:48 | 2009-10-16 09:40 | 2011-07-24 09:36 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 8
31 |  |  | Procurement lead time (1) | Tresemer | 30 | 30 |  |  |  | 2011-07-27 04:48 | 2011-09-07 04:48 | 2009-10-16 09:40 | 2011-07-27 04:48 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
32 |  |  | AWARD | Tresemer | 1 | 31 |  |  |  | 2011-09-07 04:48 | 2011-09-08 14:24 | 2009-10-16 09:40 | 2011-09-07 04:48 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
33 |  |  | Fabricate or delivery | Tresemer | 60 | 32 |  |  |  | 2011-09-08 14:24 | 2011-12-01 14:24 | 2009-10-16 09:40 | 2011-09-08 14:24 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
34 |  |  | Machining of tiles for diagnostics | Tresemer | 20 | 33 | [6 empty] | 2011-12-01 14:24 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 |  | 15 | [11 empty] | 160
|  | Item 2: hardware, other materials | [9 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 |  | 150
35 |  |  | Prep Requisition and procurement package | Tresemer | 4 | 30 |  |  |  | 2011-07-27 04:48 | 2011-08-01 19:12 | 2009-10-16 09:40 | 2011-07-27 04:48 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 16
36 |  |  | SUBMIT REQ TO PROCUREMENT | Tresemer | 2 | 35 |  |  |  | 2011-08-01 19:12 | 2011-08-04 14:24 | 2009-10-16 09:40 | 2011-08-01 19:12 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 8
37 |  |  | Procurement lead time (1) | Tresemer | 20 | 36 |  |  |  | 2011-08-04 14:24 | 2011-09-01 14:24 | 2009-10-16 09:40 | 2011-08-04 14:24 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
38 |  |  | AWARD | Tresemer | 1 | 37 |  |  |  | 2011-09-01 14:24 | 2011-09-03 | 2009-10-16 09:40 | 2011-09-01 14:24 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
39 |  |  | Fabricate or delivery | Tresemer | 30 | 38 |  |  |  | 2011-09-03 | 2011-10-15 | 2009-10-16 09:40 | 2011-09-03 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
40 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
41 |  | Fab/Assembly | [9 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
42 |  | Fab/Assy Procedure |  | Tresemer | 20 | 31 | 37 |  |  | 2011-09-07 04:48 | 2011-10-05 04:48 | 2009-10-16 09:40 | 2011-09-07 04:48 | 2011-09-01 14:24 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 80
43 |  | Shop Fabrication |  | Tresemer | 20 | 42 |  |  |  | 2011-10-05 04:48 | 2011-11-02 04:48 | 2009-10-16 09:40 | 2011-10-05 04:48 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [13 empty] | 120
44 |  | Assembly |  | Tresemer | 20 | 33 | 39 | 42 |  | 2011-12-01 14:24 | 2011-12-29 14:24 | 2009-10-16 09:40 | 2011-12-01 14:24 | 2011-10-15 | 2011-10-05 04:48 | 2009-10-16 09:40 | [13 empty] | 120
45 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
46 |  | Installation | [9 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
47 |  | Installation Procedure |  |  | 25 | 26 |  |  |  | 2011-07-18 19:12 | 2011-08-22 19:12 | 2009-10-16 09:40 | 2011-07-18 19:12 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 90
48 |  | Machine Installation |  |  | 45 | 44 | 39 |  |  | 2011-12-29 14:24 | 2012-03-01 14:24 | 2009-10-16 09:40 | 2011-12-29 14:24 | 2011-10-15 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 60 | 360
49 |  | Tile re-fit and additional machining |  |  | 20 | 44 |  |  |  | 2011-12-29 14:24 | 2012-01-26 14:24 | 2009-10-16 09:40 | 2011-12-29 14:24 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | [12 empty] | 40 | 160
50 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
51 |  | OTHER TASKS | [9 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
52 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
53 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
54 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
55 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
56 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
57 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
58 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
59 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
60 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
61 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
62 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
63 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
64 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
65 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
66 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
67 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
68 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
69 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
70 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
71 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
72 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
73 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
74 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
75 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
76 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
77 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
78 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
79 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
80 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
81 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
82 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
83 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
84 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
85 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
86 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
87 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
88 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
89 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
90 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
91 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
92 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
93 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
94 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
95 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
96 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
97 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
98 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
99 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
100 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
101 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
102 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
103 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
104 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
105 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
106 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
107 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
108 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
109 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
110 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
111 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
112 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
113 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
114 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
115 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
116 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
117 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
118 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
119 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
120 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
121 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
122 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
123 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
124 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
125 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
126 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
127 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
128 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
129 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
130 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
131 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
132 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
133 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
134 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
135 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
136 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
137 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
138 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
139 | [11 empty] | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40 | 2009-10-16 09:40
140
[18 empty] | 820 | 0 | 0 | 5 | 0 | 280 | 3154 | 0 | 0 | 0 | 0 | 1189 | 1000 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTALS | [15 empty] | 1000.4 | 0 | 0 | 5.5 | 0 | 51.94 | 394.5339 | 0 | 0 | 0 | 0 | 196.6249 | 145.35 | 0 | 0 | 0 | 0 | 0 | 0
CATEGORIZATION CODES:
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1794.3488 | [21 empty] | 1 - National Standards
| Notes: | [25 empty] | 2 - Engineering Judgement/Experience
|  | (1) Procurement lead time: | [8 empty] | Weeks | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Purchase orders-Commercial, off-the-shelf items | [7 empty] | 3 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Purchase orders-Noncommercial items | [7 empty] | 5 | [15 empty] | 5 - Prototype Data/Test Results
|  |  | Subcontracts (non construction) | [7 empty] | 8 | [15 empty] | 6 - Catelogue Price/Vendor Quote
|  |  | Construction subcontracts | [7 empty] | 9 | [15 empty] | 7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: TBD
Job Number: 1001
Job Title: NSTX CS Upgrade PFCs
Job Manager: Kelsey Tresemer
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X |  | strykowsky estimate
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## M & S breakdown
Material Cost Breakdown
TILES
Approx. 600 tiles
|  |  |  | Spare Parts |  | Handling Loss
| No. of tiles | Avg Dimensions | Volume (in^3) | No. of tiles, +20% | Volume (in^3) | No. of tiles, +10% | Volume (in^3)
Upper
Row 1 | 24 | 2"x7"x7' | 2352 | 30 | 2940 | 33 | 3234
Row 2 - 4 | 72 | 1"x4.5"x4" | 1296 | 87 | 1566 | 95.7 | 1722.6
Row 5 | 24 | 1"x10"x3.7" | 888 | 30 | 1110 | 33 | 1221
Center
Tow 6 - 20 | 360 | .75"x3.4"x5.8" | 5324.4 | 430 | 6359.7 | 473 | 6995.67
Lower
Row 1 | 24 | 2"x7"x7' | 2352 | 30 | 2940 | 33 | 3234
Row 2 - 4 | 72 | 1"x4.5"x4" | 1296 | 87 | 1566 | 95.7 | 1722.6
Row 5 | 24 | 1"x10"x3.7" | 888 | 30 | 1110 | 33 | 1221
Total | 600 |  | 14396.4 | 724 | 17591.7 | 796.4 | 19350.87
|  | Vol/section (in^3) | Vol/section (cm^3) | Density(g/cm^3) | Lbs
Rows 1-5: Silicon Carbide |  | 7900.2 | 129461.083 | 2.7 | 770.6146
Rows 6-20: CFRC |  | 11450.67 | 187642.8621 | 1.45 | 599.8385
SiC Costs: $100 - $500/lb
Cost:
@$100 | 77061.4646
@$500 | 385307.3232
CFRC Costs: $200 - $350/lb
@200 | 119967.6925
@350 | 209943.4619
Worst case: |  | If all CFRC: @$350 | If all CFRC: @$200
595250.7851 |  | 479658.5882 | 274090.6218
Billets for spare parts (not tiles):
50000 |  | 50000 | 50000
TOTAL |  | total | total
645250.7851 |  | 529658.5882 | 324090.6218
~$650,000.00
Hardware
Compared M&S data from old Job Cost Reports (circa 1997 - 2001)
tax adjust
1997 | 0 | 0
1998 | 59720 | 76823.808
1999 | 7070 | 8959.811
2000 | 0 | 0
2001 | 28974 | 34977.4128
TOTAL | 95764 | 120761.0318
Reflect a 25% increase due to increase in sheer amount of material increase
TOTAL
150951.2897
~$150,000.00