## Tab A Description
Work Approval Form (WAF)
Cost Center: | cost center 1170
Job Number: | Job Number 1300
Job Title: | Title: Centerstack Design Support
Job Manager: | Job Manager: James H. Chrzanowski
Description:
This job provides CAD design support for the overall assembly drawings asociated with the CS upgrades. CAD design support for individual components is included in the specific component jobs. It also includes some time for space allocation studies associated with the magnet upgrades.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | cost center 1170
| Job Number: |  |  | Job Number 1300
| Job Title: |  |  | Title: Centerstack Design Support
| Job Manager: |  |  | Job Manager: James H. Chrzanowski
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1 |  | Physics Requirements | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
2 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
3 |  | Conceptual Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
4 |  | PREPARE WORK PLANNING FORM | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
5 |  | Prep System Description | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
6 |  | Prep System Requirements | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
7 |  | R&D | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
8 |  | Ananlysis | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
9 |  | CDR | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
10 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
11 |  | Preliminary Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
12 |  | Thermal Analysis | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
13 |  | Seismic Analysis | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
14 |  | FMEA Analysis | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
15 |  | Prepare NEPA Form | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
16 |  | Update Cost & Schedule Estimate | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
17 |  | Design Drawings | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
18 |  | PDR Prep | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
19 |  | CONDUCT PDR | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
20 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
21 |  | Final Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
22 |  | Disposition PDR Chits | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
23 |  | Design Drawings | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
24 |  | Update Analyses | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
25 |  | Update Cost & Schedule Estimate | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
26 |  | Prep Procurement Specs | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
27 |  | FDR Prep | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
28 |  | CONDUCT FDR | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
29 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
30 |  | Procurement | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
31 |  | Item 1: | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 |  |  | Prep Requisition and procurement package | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
33 |  |  | SUBMIT REQ TO PROCUREMENT | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
34 |  |  | Procurement lead time (1) | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
35 |  |  | AWARD | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
36 |  |  | Fabricate or delivery | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
37 |  | Item 2: | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
38 |  |  | Prep Requisition and procurement package | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
39 |  |  | SUBMIT REQ TO PROCUREMENT | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
40 |  |  | Procurement lead time (1) | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
41 |  |  | AWARD | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
42 |  |  | Fabricate or delivery | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
43 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
44 |  | Fab/Assembly | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
45 |  | Fab/Assy Procedure | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
46 |  | Shop Fabrication | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
47 |  | Assembly | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
48 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
49 |  | Installation | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
50 |  | Installation Procedure | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
51 |  | Machine Installation | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
52 |  | PTP Testing | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
54 |  | OTHER TASKS | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
55 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
56 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
57 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
58 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
59 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
60 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
61 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
62 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
63 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
64 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
65 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
66 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
67 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
68 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
69 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
70 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
71 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
72 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
73 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
74 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
75 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
76 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
77 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
78 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
79 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
80 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
81 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
82 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
83 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
84 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
85 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
86 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
87 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
88 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
89 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
90 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
91 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
92 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
93 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
94 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
95 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
96 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
97 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
98 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
99 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
100 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
101 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
102 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
103 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
104 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
105 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
106 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
107 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
108 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
109 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
110 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
111 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
112 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
113 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
114 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
115 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
116 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
117 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
118 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
119 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
120 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
121 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
122 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
123 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
124 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
125 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
126 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
127 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
128 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
129 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
130 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
131 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
132 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
133 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
134 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
135 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
136 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
137 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
138 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
139 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
140 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
141 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
142 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [24 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [6 empty] | Weeks | [16 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [5 empty] | 3 | [16 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [5 empty] | 5 | [16 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [5 empty] | 8 | [16 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [5 empty] | 9 | [16 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | cost center 1170
Job Number: |  | Job Number 1300
Job Title: |  | Title: Centerstack Design Support
Job Manager: |  | Job Manager: James H. Chrzanowski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  |  |  | LOE as required
Design Complexity
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | cost center 1170
Job Number: | Job Number 1300
Job Title: | Title: Centerstack Design Support
Job Manager: | Job Manager: James H. Chrzanowski
Materials and Subcontracts (M&S) |  | Basis of Estimate
n/a

## CSU BASELINE ESTIMATE
Cost | Work |  | Activity Name | Responsible Cog Engr | Start | End | Duration | EAEM1 | EAEM2 | EAEM3 | EAEM4 | EAEM5 | EAEM6 | EAEM7 | EAEM | EAEM | EMEM1 | EMEM2 | EMEM3 | EMEM4 | EMEM5 | EEEM | EASB1 | EASB2 | EASB3 | EASB4 | EASB5 | EASB6 | EASB7 | EASB8 | EMSM1 | EMSM2 | EMSM3 | EMTB1 | EMTB2 | EMTB3 | EMTB4 | EMTB5 | M&S | OS | Travel | Stkrm. | Subtotal
Center | Package | Job # | [5 empty] | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs |  |  |  |  | M&S
|  |  |  | [Bold] | Date | Date | (Weeks) | (Chrzan.) | (Titus) | (Zhang) | (Zolfaghari) | (Avasarala) | (Brooks) | (Raftopoul.) | (general) | (Myatt) | (Mangra) | (Tresmer) | (Willard) | (Prinski) | (Simmons) |  | (Paul) | (Morris) | (Martinelli) | (Upcavage) | (Jariwala) | (Wojtowicz) | (Paluzzi) | (Elect) | (Meighan) | (Jurcz.) |  | (Technician) | (Machinist) | (Welder) | (electrical) | (General) | K$ | k$ | k$ | k$ | k$
1170 | 1*** | 1000 | CSU Analytical Support | P. Titus
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01
|  |  | 96 Scenarios Loads, Process Results |  | 2009-10-01 | 2010-06-01 |  |  | 100
|  |  | Agreed Power Supply Limit Currents |  | 2009-10-01 | 2010-06-01 |  |  | 100
|  |  | Maintain Model - Scenario Design Changes |  | 2009-10-01 | 2010-06-01 |  |  | 100
|  |  | Engineering System Requirements Document |  | 2009-10-01 | 2010-06-01 |  |  | 60
|  |  | Review Calculations |  | 2009-10-01 | 2010-06-01 | [8 empty] | 30
|  |  | Analysis Reserve - Analyze Problem areas |  | 2009-10-01 | 2010-06-01
|  |  | Documentation-calculations |  | 2009-10-01 | 2010-06-01 | [14 empty] | 10
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | 96 Scenarios Loads, Process Results |  | 2010-06-01 | 2010-11-01 |  |  | 100
|  |  | Agreed Power Supply Limit Currents |  | 2010-06-01 | 2010-11-01 |  |  | 100
|  |  | Maintain Model - Scenario Design Changes |  | 2010-06-01 | 2010-11-01 |  |  | 100
|  |  | Engineering System Requirements Document |  | 2010-06-01 | 2010-11-01 |  |  | 80
|  |  | Review Calculations |  | 2010-06-01 | 2010-11-01 | [8 empty] | 120
|  |  | Analysis Reserve - Analyze Problem areas |  | 2010-06-01 | 2010-11-01 | [8 empty] | 360
|  |  | Documentation-calculations |  | 2010-06-01 | 2010-11-01 | [14 empty] | 10
1170 | 1*** | 1001 | CS- PLASMA FACING COMPONENTS- Design & Fabrication | Tresemer
|  |  | Preliminary Design Activities |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | Tile, Hardware reconfig & material research- R&D |  | 2009-09-28 | 2009-10-12 | 2 | [10 empty] | 80 | [8 empty] | 80 | [15 empty] | 0
|  |  | Disposition CDR chits | [14 empty] | 40 | [8 empty] | 30 | [15 empty] | 0
|  |  | Complete Tile Analysis | [9 empty] | 220 |  |  |  |  | 120 | [24 empty] | 0
|  |  | Documentation-calculations | [17 empty] | 10
|  |  | Prepare Cad design drawings |  | 2010-02-01 | 2010-04-12 | 10 | [19 empty] | 400 | [15 empty] | 0
|  |  | Procure carbon material samples |  | 2009-12-07 | 2010-01-11 | 5 | [35 empty] | 0
|  |  | Test carbon samples | [14 empty] | 40 | [15 empty] | 80 | [8 empty] | 0
|  |  | Prepare for PDR |  | 2010-05-01 | 2010-05-15 | 2 | [10 empty] | 40 | [8 empty] | 24 | [15 empty] | 0
0
Final Design Activities
|  |  | Disposition PDR Chits |  | 2010-05-17 | 2010-06-14 | 4 | [10 empty] | 80 | [8 empty] | 60 | [15 empty] | 0
|  |  | Update analysis |  | 2010-06-14 | 2010-07-19 | 5 | [5 empty] | 180 |  |  |  |  | 80 | [24 empty] | 0
|  |  | Documentation-calculations | [17 empty] | 10
|  |  | Complete design drawings |  | 2010-07-19 | 2010-09-27 | 10 | [19 empty] | 400 | [15 empty] | 0
|  |  | Prepare for FDR |  | 2010-09-27 | 2010-11-08 | 6 | [10 empty] | 16 | [8 empty] | 40 | [15 empty] | 0
0
M&S and Contract
|  |  | Prepare Specs for procurement |  | 2010-09-27 | 2010-11-08 | 6 | [10 empty] | 60 | [24 empty] | 0
|  |  | Prep requisition & submit to procurement |  | 2011-01-10 | 2011-01-17 | 1 | [10 empty] | 8 | [24 empty] | 0
|  |  | Bid & award order |  | 2011-01-17 | 2011-02-28 | 6 | [32 empty] | 650 |  |  | 650
|  |  | Fabricate tiles [outside vendor] |  | 2011-02-28 | 2011-08-29 | 26 | [10 empty] | 24 | [22 empty] | 5 |  | 5
|  |  | Prep requisition & submit to procurement |  |  |  | 1 | [10 empty] | 8 | [24 empty] | 0
|  |  | Procure mounting hardware |  |  |  | 8 | [10 empty] | 8 | [20 empty] | 20 | 100 |  |  | 120
0
In house Fab & Assembly
|  |  | Machine special tiles for diag |  |  |  | 6 | [27 empty] | 400 |  |  |  | 5 |  | 0.5 |  | 5.5
|  |  | Generate Fab/Assembly procedure |  |  |  | 1 | [10 empty] | 80 | [24 empty] | 0
|  |  | Pre-assemble tile packages |  |  |  | 4 | [26 empty] | 240 | [8 empty] | 0
Installation of tiles
|  |  | Generate Installation Procedure |  |  |  | 2 | [10 empty] | 90 | [24 empty] | 0
|  |  | Mount tiles to CS casing [@ CS Assembly station] |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 60 |  |  |  |  | 0 | 0 |  | 0 | [12 empty] | 0 |  |  |  | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 0
1170 | 1*** | 1102 | Passive Plate Analysis and Upgrade Activities | Titus |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | Check Time Points - Re-run |  | 2009-10-01 | 2010-06-01 | [5 empty] | 40
|  |  | Check Currents With Ron Hatcher Opera |  | 2009-10-01 | 2010-06-01 | [5 empty] | 40
|  |  | Mesh Passive Plate Cad Model |  | 2009-10-01 | 2010-06-01 | [5 empty] | 40
|  |  | Run rest of disruption cases |  | 2009-10-01 | 2010-06-01 | [5 empty] | 120
|  |  | Halo Current Analysis of Passive Plates |  | 2009-10-01 | 2010-06-01 | [5 empty] | 20
|  |  | Design Reinforcements |  | 2009-10-01 | 2010-06-01 | [5 empty] | 40
|  |  | Analyze/Confirm Reinforcement Design |  | 2009-10-01 | 2010-06-01 | [5 empty] | 40
|  |  | Propose/Design/Monitor Diagnostic |  | 2009-10-01 | 2010-06-01 | [5 empty] | 40
|  |  | Lithium Divertor Analysis |  | 2009-10-01 | 2010-06-01 | [5 empty] | 40
|  |  | Spark or Opera Benchmark |  | 2009-10-01 | 2010-06-01 | [6 empty] | 40
|  |  | Documentation-calculations |  | 2009-10-01 | 2010-06-01 | [14 empty] | 10
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Check Time Points - Re-run |  | 2010-06-01 | 2010-11-01 | [5 empty] | 40
|  |  | Check Currents With Ron Hatcher Opera |  | 2010-06-01 | 2010-11-01 | [5 empty] | 40
|  |  | Mesh Passive Plate Cad Model |  | 2010-06-01 | 2010-11-01 | [5 empty] | 40
|  |  | Run rest of disruption cases |  | 2010-06-01 | 2010-11-01 | [5 empty] | 120
|  |  | Halo Current Analysis of Passive Plates |  | 2010-06-01 | 2010-11-01 | [5 empty] | 80
|  |  | Design Reinforcements |  | 2010-06-01 | 2010-11-01 | [5 empty] | 40
|  |  | Analyze/Confirm Reinforcement Design |  | 2010-06-01 | 2010-11-01 | [5 empty] | 40
|  |  | Propose/Design/Monitor Diagnostic |  | 2010-06-01 | 2010-11-01 | [5 empty] | 100
|  |  | Lithium Divertor Analysis |  | 2010-06-01 | 2010-11-01 | [5 empty] | 60
|  |  | Spark or Opera Benchmark |  | 2010-06-01 | 2010-11-01 | [6 empty] | 40
|  |  | Documentation-calculations |  | 2010-06-01 | 2010-11-01
1170 | 1*** | 1200 | VACUUM VESSEL & STRUCTURAL SUPPORTS | Chrzanowski
|  |  | Metrology- to support design all Structural Supports |  | 2009-10-01 | 2010-06-01 | [13 empty] | 288 | [13 empty] | 144 |  |  |  |  | 30 |  |  |  | 30
|  |  | Rapid prototyping to support design activities |  | 2009-10-01 | 2010-06-01 | [18 empty] | 100 | [13 empty] | 20 |  |  |  | 20
1170 | 1*** | 1201 | Outer TF Structures | Mangra
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01
|  |  | Complete design of OTF structures |  | 2009-10-01 | 2010-06-01 | [10 empty] | 400
|  |  | Outer TF Check other PF currents – Only two current cases have been considered |  | 2009-10-01 | 2010-06-01 |  |  |  | 120
|  |  | Tangential radius rods Clevis Shell Intersection |  | 2009-10-01 | 2010-06-01 |  |  | 40
|  |  | Tangential radius rods – interference with support columns, Weldment vs clevis/pin support. |  | 2009-10-01 | 2010-06-01 |  |  | 40
|  |  | Neutral Beam Vacuum Loads |  | 2009-10-01 | 2010-06-01 |  |  | 40
|  |  | Documentation-calculations |  | 2009-10-01 | 2010-06-01 | [14 empty] | 4
|  |  | Generate Cad detail and assembly drawings |  | 2009-10-01 | 2010-06-01 | [18 empty] | 200
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Complete design of OTF structures |  | 2010-06-01 | 2010-11-01
|  |  | Outer TF Check other PF currents – Only two current cases have been considered |  | 2010-06-01 | 2010-11-01 |  |  |  | 120
|  |  | Tangential radius rods Clevis Shell Intersection |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Tangential radius rods – interference with support columns, Weldment vs clevis/pin support. |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Neutral Beam Vacuum Loads |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Documentation-calculations |  | 2010-06-01 | 2010-11-01 | [14 empty] | 4
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 | [18 empty] | 850 | [17 empty] | 0
|  |  | Purchase & Fabrication | [39 empty] | 0
|  |  | Prep requisition & submit to procurement |  |  |  | 1
|  |  | Bid & award OTF structures |  |  |  | 6
|  |  | Fabricate components |  |  |  | 18 | [32 empty] | 335 | 3 |  | 338
|  |  | Inspect components prior to shipment | [13 empty] | 8 | [23 empty] | 2 |  | 2
|  |  | Installation costs will be included in M. Viola's installation estimate | [39 empty] | 0
0
1170 | 1*** | 1202 | Outer PF Coil Structures | Mangra | [38 empty] | 0
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Analysis- Outer PF support – include PF3? What loads |  | 2009-10-01 | 2010-06-01 |  |  | 160
|  |  | Analysis- Local Model of Support Beam/Vessel Intersection |  | 2009-10-01 | 2010-06-01 |  |  | 20
|  |  | Analysis- Outer PF supports – elastomer vs sliding block |  | 2009-10-01 | 2010-06-01 |  |  | 40
|  |  | Analysis- PF2 PF1c Umbrella Load Dome Analysis |  | 2009-10-01 | 2010-06-01 |  |  | 40
|  |  | Documentation-calculations |  | 2009-10-01 | 2010-06-01 | [14 empty] | 4
|  |  | Generate Cad detail and assembly drawings |  | 2009-10-01 | 2010-06-01 | [18 empty] | 400
|  |  | Complete design of Outer PF structures |  | 2009-10-01 | 2010-06-01 | [10 empty] | 720
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Analysis- Outer PF support – include PF3? What loads |  | 2010-06-01 | 2010-11-01 |  |  | 160
|  |  | Analysis- Local Model of Support Beam/Vessel Intersection |  | 2010-06-01 | 2010-11-01 |  |  | 20
|  |  | Analysis- Outer PF supports – elastomer vs sliding block |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Analysis- PF2 PF1c Umbrella Load Dome Analysis |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Documentation-calculations |  | 2010-06-01 | 2010-11-01 | [14 empty] | 4
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 | [18 empty] | 1100 | [17 empty] | 0
|  |  | Purchase & Fabrication | [39 empty] | 0
|  |  | Prep requisition & submit to procurement |  |  |  | 1 | [9 empty] | 8
|  |  | Bid & award outer PF cage |  |  |  | 4
|  |  | Fabricate Outer PF Cage [PF-3/4/5] |  |  |  | 18 | [9 empty] | 24 | [22 empty] | 120 | 3 |  | 123
|  |  | Prep requisition & submit to procurement |  |  |  | 1 | [9 empty] | 8
|  |  | Bid & award outer PF cage |  |  |  | 4
|  |  | Fabricate PF-2 support modifications |  |  |  | 12 | [9 empty] | 16 | [22 empty] | 48 | 1 |  | 49
0
|  |  | Installation costs will be included in M. Viola's installation estimate | [39 empty] | 0
0
1170 | 1*** | 1203 | Umbrella Structural Reinforcement | Mangra
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Analysis- Umbrella Arch Reinforcement |  | 2009-10-01 | 2010-06-01 |  |  |  | 40
|  |  | Complete design of umbrella structure upgrades |  | 2009-10-01 | 2010-06-01 | [10 empty] | 60
|  |  | Generate Cad detail and assembly drawings |  | 2009-10-01 | 2010-06-01 | [18 empty] | 120
|  |  | Complete design of upper and lower umbrella lids |  | 2009-10-01 | 2010-06-01 | [10 empty] | 40 | [7 empty] | 40
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Analysis- Umbrella Arch Reinforcement |  | 2010-06-01 | 2010-11-01 |  |  |  | 40
|  |  | Complete design of umbrella structure upgrades |  | 2010-06-01 | 2010-11-01 | [10 empty] | 100
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 | [18 empty] | 190 | [17 empty] | 0
|  |  | Complete design of upper and lower umbrella lids |  | 2010-06-01 | 2010-11-01 | [10 empty] | 80 | [7 empty] | 80 | [17 empty] | 0
Purchase & Fabrication
|  |  | Prep requisition & submit to procurement |  |  |  | 1 | [9 empty] | 8
|  |  | Bid & award PO |  |  |  | 5
|  |  | Fabricate structural components |  |  |  | 8 | [32 empty] | 14.4 |  |  | 14.4
|  |  | Fabricate umbrella lids |  |  |  | 10 | [32 empty] | 30 |  |  | 30
0
Installation costs will be included in M. Viola's installation estimate
1170 | 1*** | 1204 | CS Support Pedestal | Mangra
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Engineering design support |  | 2009-10-01 | 2010-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 120 | [6 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | Generate Cad detail and assembly drawings |  | 2009-10-01 | 2010-06-01 | [18 empty] | 120
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Engineering design support |  | 2010-06-01 | 2010-11-01 | [10 empty] | 200
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 | [18 empty] | 200
Purchase & Fabrication
|  |  | Prep requisition & submit to procurement |  |  |  | 1 | [9 empty] | 8 | [25 empty] | 0
|  |  | Bid & award PO |  |  |  | 5
|  |  | Fabricate pedestal |  |  |  | 8 | [9 empty] | 40 | [22 empty] | 25 |  |  | 25
|  |  | Engr support during installation | [13 empty] | 200 | [25 empty] | 0
0
1170 | 1*** | 1300 | CENTERSTACK DESIGN SUPPORT | Chrzanowski
|  |  | Provide Cad design support for upgrading overall CS assembly drawings and document space allocation |  | 2009-10-01 | 2010-12-30 | [22 empty] | 300
1170 | 1*** | 1301 | OUTER TOROIDAL FIELD COILS | Chrzanowski
|  |  | Generate engineering plan for fabricating (2) new OTF coil |  |  |  |  | 40 | [20 empty] | 120 | 80 | 16
0
Purchase & Fabrication
|  |  | OTF Conductor | [39 empty] | 0
|  |  | Procure copper conductor for OTF [10 bars] | [27 empty] | 8 | [7 empty] | 10 |  |  |  | 10
|  |  | Prep requisition for machining & submit to procurement | [27 empty] | 8 | [11 empty] | 0
|  |  | Place order for machining cooling groove in copper conductor | [39 empty] | 0
|  |  | Machine conductors | [27 empty] | 40 | [8 empty] | 30 | 1 |  | 31
|  |  | Prep requisition for rolling & submit to procurement | [27 empty] | 8 | [11 empty] | 0
|  |  | Place order to Form OTF conductors | [39 empty] | 0
|  |  | Roll conductors | [27 empty] | 40 | [8 empty] | 30 | 1 |  | 31
|  |  | Miscellaneous parts and materials | [37 empty] | 1 |  | 1
|  |  | Procure aluminum castings and S.S. support clamps | [27 empty] | 16 | [7 empty] | 20 |  |  |  | 20
|  |  | Procure hardware, epoxy/glass for blocks, misc | [27 empty] | 24 | [7 empty] | 20 |  |  |  | 20
|  |  | Procure B-stage insulation | [27 empty] | 8 | [7 empty] | 20 |  |  |  | 20
|  |  | Copper leads & fittings, etc | [27 empty] | 8 |  |  |  | 120 |  |  |  | 5 |  |  |  | 5
In-house Fabrication
|  |  | Modify oven to accommodate OTF molds | [25 empty] | 120 | 240 |  |  |  | 320 |  |  | 560 |  | 20 |  |  |  | 20
|  |  | Setup oven and mold fixtures in work area | [39 empty] | 0
|  |  | Fabricate OTF Assy | [27 empty] | 160 |  |  | 1280 |  | 240 |  |  | 7 |  |  | 5 | 12
|  |  | Install alum blocks & SS support clamps | [27 empty] | 160 |  |  | 320 | [8 empty] | 0
1170 | 1*** | 1302 | CENTERSTACK ASSEMBLY | Chrzanowski
|  |  | Cad support for setup of centerstack assembly area | [25 empty] | 200
|  |  | Generate CS Assembly procedure |  | 2011-05-07 | 2012-06-11 |  | 80
|  |  | Generate CS Installation procedure |  | 2012-11-05 | 2012-12-17 |  | 80
|  |  | Setup Assembly Area |  |  | 2012-06-11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [7 empty] | 24 |  |  | 360 |  |  | 200 |  | 10 |  |  | 2 | 12
|  |  | Modify CS Assy. Fixture |  |  | 2012-06-11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [10 empty] | 160 |  | 120 |  |  | 10 |  |  | 1 | 11
|  |  | Assemble Centerstack |  | 2012-06-11 | 2012-12-17 | 24 | 432 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [7 empty] | 432 |  |  | 4320 |  |  |  |  | 20 |  |  | 10 | 30
Assembly includes TF/OH, mounting of OH surface diagnostics; micro-therm insulation; casing and Inner PF coils. Installation of PFC's
|  |  | Tear down assembly area |  | 2013-01-07 | 2013-02-04 | 4 | [23 empty] | 24 |  |  | 360 |  |  | 80 | [5 empty] | 0
1170 | 1*** | 1303 | TF Joint Test Stand & Performance of Test | Kozub
|  |  | Being provided by Tom Kozub | [39 empty] | 0
1170 | 1*** | 1304 | INNER TF BUNDLE- Design & Fabrication | Chrz/Titus
|  |  | Prepare for CDR |  | 2009-10-05 | 2009-10-19 | 2 | 40 | 40 | [13 empty] | 40
|  |  | Preliminary Design Activities | [39 empty] | 0
|  |  | Preliminary design of TF bundle and components |  | 2009-10-01 | 2010-06-01 | 34 | 432 | [34 empty] | 0
|  |  | Generate Detail and assembly Cad drawings [TF bundle, joint and components] |  | 2009-10-01 | 2010-06-01 | 34 | [15 empty] | 360 |  |  |  |  | 1000 | [14 empty] | 0
|  |  | Analysis of Revised Flag/Flex Geometry |  | 2009-10-01 | 2010-06-01 | [12 empty] | 60 | [23 empty] | 0
|  |  | Check Electromagnetic loads assumption of 1 T – replace with either exact solution of Lorentz forces. |  | 2009-10-01 | 2010-06-01 | [12 empty] | 20 | [23 empty] | 0
|  |  | Fatigue Calcs for less than .3T Vert Field |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Heat-up if flags are BeCu |  | 2009-10-01 | 2010-06-01 |  |  |  | 40 | [32 empty] | 0
|  |  | TF De-Wedging due to thermal stress, develop tension wrap with CTD. |  | 2009-10-01 | 2010-06-01 |  |  | 40 | [33 empty] | 0
|  |  | [TS torsional shear stress – Wooley work. Dick Reed ] |  | 2009-10-01 | 2010-06-01 |  |  | 80 | [33 empty] | 0
|  |  | Coupled Elect Resist/Thermal Contact Axisymmetric |  | 2009-10-01 | 2010-06-01 | [12 empty] | 40 | [23 empty] | 0
|  |  | Coupled Analisis of Large TF Flag Model |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Documentation-calculations |  | 2009-10-01 | 2010-06-01 | [14 empty] | 10 | [21 empty] | 0
|  |  | Perform additional Friction Stir Weld Trials | [36 empty] | 20 | 0.5 |  | 20.5
0
|  |  | Prepare for PDR |  | 2010-05-01 | 2010-05-15 | 2 | 40 | 40 | [18 empty] | 40 | [14 empty] | 0
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01 | [36 empty] | 0
|  |  | Check Electromagnetic loads assumption of 1 T – replace with either exact solution of Lorentz forces. |  | 2010-06-01 | 2010-11-01 | [12 empty] | 20 | [23 empty] | 0
|  |  | Fatigue Calcs for less than .3T Vert Field |  | 2010-06-01 | 2010-11-01 | [12 empty] | 80 | [23 empty] | 0
|  |  | Heat-up if flags are BeCu |  | 2010-06-01 | 2010-11-01 |  |  |  | 40 | [32 empty] | 0
|  |  | TF De-Wedging due to thermal stress, develop tension wrap with CTD. |  | 2010-06-01 | 2010-11-01 |  |  | 40 | [33 empty] | 0
|  |  | [TS torsional shear stress – Wooley work. Dick Reed ] |  | 2010-06-01 | 2010-11-01 |  |  | 80 | [33 empty] | 0
|  |  | Coupled Elect Resist/Thermal Contact Axisymmetric |  | 2010-06-01 | 2010-11-01 | [36 empty] | 0
|  |  | Coupled Analisis of Large TF Flag Model |  | 2010-06-01 | 2010-11-01 | [12 empty] | 120 | [23 empty] | 0
|  |  | Documentation-calculations |  | 2010-06-01 | 2010-11-01 | [14 empty] | 10 | [21 empty] | 0
|  |  | Complete detail and assembly Cad drawings [TF bundle, joint and components] |  | 2010-06-01 | 2010-11-01 | [36 empty] | 0
|  |  | Prepare for FDR |  | 2010-09-27 | 2010-11-08 | 6 | 40 | 40 | [18 empty] | 40 | [14 empty] | 0
0
|  |  | HOLD TF CONDUCTOR PEER REVIEW [to allow early procurement] |  | 2010-01-11 | 2010-01-15 | 1 | 16 | [34 empty] | 0
Purchase & Fabrication
TF Conductor
|  |  | Prep requisition/SOW & submit to procurement |  | 2010-02-01 | 2010-02-08 | 1 | 8 | [34 empty] | 0
|  |  | Bid & Award conductor extrusion order [80 pcs] |  | 2010-02-08 | 2010-03-08 | 4 | 8 | [34 empty] | 0
|  |  | Manufacture Copper extrusions [80] |  | 2010-03-08 | 2010-07-12 | 18 | 16 | [30 empty] | 242 |  |  |  | 242
|  |  | Prep requisition & submit to procurement |  | 2010-06-21 | 2010-06-28 | 1 | 8 | [34 empty] | 0
|  |  | Bid & Award conductor machining [40 pcs] |  | 2010-06-28 | 2010-07-26 | 4 | 8 | [34 empty] | 0
|  |  | Machine conductors [cooling grooves, lead area]- 40 |  | 2010-07-26 | 2010-10-25 | 13 | 24 | [31 empty] | 250 | 5 |  | 255
|  |  | Prep requisition & submit to procurement |  | 2010-10-04 | 2010-10-11 | 1 | 8 | [34 empty] | 0
|  |  | Bid & award lead welding [40 pcs] |  | 2010-10-11 | 2010-11-08 | 4 | 8 | [34 empty] | 0
|  |  | Friction Stir-Weld coil leads to conductors- 40 |  | 2010-11-08 | 2011-01-10 | 9 | 24 | [31 empty] | 250 | 3 |  | 253
Flex Bus [Inner to Outer TF]
|  |  | Prep requisition & submit to procurement |  |  |  |  | 8 | [34 empty] | 0
|  |  | Bid & award flex bus order [80 pcs] |  |  |  |  | 8 | [34 empty] | 0
|  |  | Fabricate Flex bus |  |  |  |  | 18 | [31 empty] | 65 | 3 |  | 68
|  |  | Procure TF jumpers [OTF to flex] | [36 empty] | 40 |  |  | 40
|  |  | Procure supports for TF jumpers | [36 empty] | 25 |  |  | 25
|  |  | Procure lower TF coil to bus jumpers & supports | [36 empty] | 12 |  |  | 12
|  |  | Miscellaneous parts | [39 empty] | 0
|  |  | Procure Cu-Cr-Zr lead extensions for welding | [36 empty] | 50 |  |  | 50
|  |  | Procure joint & support hardware |  |  |  |  | 8 | [30 empty] | 100 |  |  |  | 100
|  |  | Procure Copper spacers for upper leads |  |  |  |  | 8 | [31 empty] | 25 |  |  | 25
|  |  | Procure upper & lower OH/TF support structures | [36 empty] | 30 |  |  | 30
1170 | 1*** | 1305 | OHMIC HEATING COIL (OH) - Design & Fabrication | Chrz/Titus
|  |  | Preliminary Design Activities | [39 empty] | 0
|  |  | Design support for OH coil |  | 2009-10-01 | 2010-06-01 |  | 200 | [34 empty] | 0
|  |  | Generate detail and assembly Cad drawings |  | 2009-10-01 | 2010-06-01 | [16 empty] | 500 |  |  | 80 | [16 empty] | 0
|  |  | Complete Axisymmetric CS Model |  | 2009-10-01 | 2010-06-01 |  |  |  |  | 100 | [31 empty] | 0
|  |  | Size Bellevilles,Spacers,Retaining Bolts |  | 2009-10-01 | 2010-06-01 |  |  |  |  | 40 | [31 empty] | 0
|  |  | OH Stress due to PF1A |  | 2009-10-01 | 2010-06-01 |  |  |  |  | 40 | [31 empty] | 0
|  |  | OH Tension Stress Due to End Fixity |  | 2009-10-01 | 2010-06-01 |  |  |  |  | 10 | [31 empty] | 0
|  |  | Fixture Analyses |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Documentation-calculations |  | 2009-10-01 | 2010-06-01 | [14 empty] | 10 | [21 empty] | 0
|  |  | Prepare for PDR |  |  |  |  | 40 | [14 empty] | 40 | [19 empty] | 0
|  |  | Final Design Activities | [39 empty] | 0
|  |  | Design support for OH coil |  | 2010-06-01 | 2010-11-01 |  | 240 | [34 empty] | 0
|  |  | Complete Axisymmetric CS Model |  | 2010-06-01 | 2010-11-01 |  |  |  |  | 100 | [31 empty] | 0
|  |  | Size Bellevilles,Spacers,Retaining Bolts |  | 2010-06-01 | 2010-11-01 |  |  |  |  | 40 | [31 empty] | 0
|  |  | OH Stress due to PF1A |  | 2010-06-01 | 2010-11-01 |  |  |  |  | 40 | [31 empty] | 0
|  |  | OH Tension Stress Due to End Fixity |  | 2010-06-01 | 2010-11-01 |  |  |  |  | 10 | [31 empty] | 0
|  |  | Fixture Analyses |  | 2010-06-01 | 2010-11-01 | [8 empty] | 40 | [27 empty] | 0
|  |  | Documentation-calculations |  | 2010-06-01 | 2010-11-01 | [14 empty] | 10 | [21 empty] | 0
|  |  | Complete detail and assembly Cad drawings |  | 2010-06-01 | 2010-11-01 | [16 empty] | 600 | [19 empty] | 0
|  |  | Prepare for FDR |  |  |  |  | 40 | [14 empty] | 40 | [19 empty] | 0
|  |  | Purchase & Fabrication | [39 empty] | 0
|  |  | Conductor | [39 empty] | 0
|  |  | Generate SOW for conductor |  | 2010-11-22 | 2010-12-06 | 2 | 12 | [34 empty] | 0
|  |  | Prep requisition & submit to procurement |  | 2010-12-06 | 2010-12-13 | 1 | 8
|  |  | Bid & award conductor order [220%] |  | 2010-12-13 | 2011-01-17 | 5
|  |  | Manufacture Copper conductor [extrusion] |  | 2011-01-17 | 2011-04-25 | 14 | 16 | [31 empty] | 105.6 |  |  | 105.6
Miscellaneous parts
|  |  | Prep requisition & submit to procurement [insulation] |  | 2010-11-08 | 2010-11-15 | 1 | [23 empty] | 8 | [7 empty] | 25 |  |  |  | 25
|  |  | Procure Kapton/glass co-wound insulation |  | 2010-11-15 | 2011-01-10 | 10 | [23 empty] | 8
|  |  | Prep requisition & submit to procurement [belleville] |  | 2011-04-05 | 2011-04-12 | 1 | 8
|  |  | Bid & Award belleville washer assembly |  | 2011-04-12 | 2011-06-07 | 8 | 8 | [31 empty] | 35 |  |  | 35
|  |  | Procure miscellaneous parts |  | 2010-11-15 | 2011-06-06 |  | 24 | [30 empty] | 15 |  |  |  | 15
0
|  |  | TF/OH PROCUREMENT | [39 empty] | 0
Note: The OH/TF bundle will be fabricated together as one unit.
|  |  | TF Bundle/OH Solenoid | [39 empty] | 0
|  |  | Generate SOW & Manufacturing SPEC |  | 2010-10-25 | 2010-11-08 | 2 | 40 | [34 empty] | 0
|  |  | Prep requisition & submit to procurement |  | 2010-11-08 | 2010-11-15 | 1 | 8 | [34 empty] | 0
|  |  | RFQ and SPEB review to fabricate TF bundle/OH Solenoid |  | 2010-11-15 | 2011-01-10 | 10 | 24 | [34 empty] | 0
|  |  | Award Contract for TF/OH bundle |  | 2011-01-10 | 2011-01-17 | 1 | [32 empty] | 1481.5557 |  |  | 1481.5557
|  |  | Fabricate Inner TF/OH Coil Assembly |  | 2011-01-17 | 2012-03-19 | 60 | 600 | [22 empty] | 400 | [9 empty] | 5 |  | 5
1170 | 1*** | 1306 | INNER POLOIDAL FIELD COILS (Shaping) | Chrz/Titus
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Design PF Coils |  | 2009-10-01 | 2010-06-01 |  | 120 | [34 empty] | 0
|  |  | Generate Cad detail and assembly drawings of Inner PF coils & supports |  | 2009-10-01 | 2010-06-01 | [17 empty] | 240 | [18 empty] | 0
|  |  | Prepare for PDR |  |  |  |  | 16 | [15 empty] | 20 | [18 empty] | 0
|  |  | Final Design Activities | [39 empty] | 0
|  |  | Lorentz Force Stress Analyses | [7 empty] | 60 | [31 empty] | 0
|  |  | Fixture analysis | [11 empty] | 20 | [27 empty] | 0
|  |  | Design activities |  |  |  |  | 120 | [34 empty] | 0
|  |  | Complete Cad detail and assembly drawings of Inner PF coils & supports | [20 empty] | 300 | [18 empty] | 0
|  |  | Prepare for FDR |  |  |  |  | 16 | [15 empty] | 24 | [18 empty] | 0
|  |  | Purchase & Fabrication | [39 empty] | 0
Conductor
|  |  | Generate SOW for conductor |  | 2010-11-22 | 2010-12-06 | 2 | 12 | [34 empty] | 0
|  |  | Prep requisition & submit to procurement |  | 2010-12-06 | 2010-12-13 | 1 | 8
|  |  | Bid & award conductor order [220%] |  | 2010-12-13 | 2011-01-17 | 5
|  |  | Manufacture Copper conductor [extrusion] |  | 2011-01-17 | 2011-04-25 | 14 | 16 | [31 empty] | 105.6 |  |  | 105.6
Miscellaneous parts
|  |  | Procure Kapton/glass co-wound insulation | [27 empty] | 8 | [11 empty] | 0
|  |  | Prep requisition & submit to procurement [insulation] |  | 2010-11-08 | 2010-11-15 | 1 | [23 empty] | 8
|  |  | Procure Kapton/glass co-wound insulation |  | 2010-11-15 | 2011-01-10 | 10 | [31 empty] | 20
0
Coil Fabrication- 6 coils
|  |  | Generate SOW & Manufacturing SPEC |  | 2011-02-21 | 2011-03-14 | 3 | 40 | [34 empty] | 0
|  |  | Prep requisition & submit to procurement |  | 2011-03-14 | 2011-03-21 | 1 | 8 | [34 empty] | 0
|  |  | Review bids and award contract |  | 2011-03-21 | 2011-05-02 | 6
|  |  | Fabricate Inner [6] Inner PF coils |  | 2011-05-02 | 2012-02-06 | 40 | 200 | [22 empty] | 120 | [8 empty] | 180 |  |  | 180
0
1170 | 1*** | 1307 | CS CASING Assembly- Design & Fabrication | Chrzanowski
Scope: includes casing, bellows, ceramic break assembly, CHI leads on casing,
|  |  | Preliminary Design Activities | [39 empty] | 0
|  |  | Design & generate Cad detail and assembly drawings |  | 2009-10-01 | 2010-06-01 |  | 40 | [15 empty] | 300 | [18 empty] | 0
|  |  | Create 3D Model of Organ Pipes Leads Coolant Lines |  | 2009-10-01 | 2010-06-01 | [12 empty] | 40 | [23 empty] | 0
|  |  | CS Support structure design/analysis |  | 2009-10-01 | 2010-06-01 | [9 empty] | 20 | [26 empty] | 0
|  |  | Prepare for PDR | [39 empty] | 0
|  |  | Final Design Activities | [39 empty] | 0
|  |  | Design & complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 |  | 80 | [15 empty] | 420 | [18 empty] | 0
|  |  | 3D Model of Organ Pipes Leads Coolant Lines | [15 empty] | 120 | [23 empty] | 0
|  |  | Bellow (EJMA Standards) Analysis | [12 empty] | 40 | [26 empty] | 0
|  |  | Perform Tile Stod/shell Stress Analysis | [12 empty] | 40 | [26 empty] | 0
|  |  | CS Support | [12 empty] | 40 | [26 empty] | 0
|  |  | Prepare for FDR |  |  |  |  | 20 | [15 empty] | 24 | [18 empty] | 0
Purchase & Fabrication
|  |  | Prepare requisitions and submit to procurement |  | 2011-01-03 | 2011-02-28 | 8 | 40 | [34 empty] | 0
|  |  | Oversee procurement of components |  | 2011-02-28 | 2011-05-23 | 12 | 40 | [32 empty] | 1 |  | 1
|  |  | Procure Inconel Tube |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 50 |  |  |  | 50
|  |  | Procure Inconel Bellows |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 35 | 0 |  |  | 35
|  |  | Rotatable Flanges |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 0 | 17.1494 |  |  | 17.1494
|  |  | Inconel Upper forgings and Rings |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 60.2179 |  |  |  | 60.2179
|  |  | Inconel flange machining |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 0 | 40 |  |  | 40
|  |  | Diagnostic/ Gas Injection feed-thru's |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 10 | 0 |  |  | 10
|  |  | CHI copper Leads- upper & lower [For vessel bakeout] |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 0 | 16 |  |  | 16
|  |  | Procure Inconel Weld Studs |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 7 | 0 |  |  | 7
|  |  | CS support legs |  | 2011-02-28 | 2011-05-23 | 12 | [32 empty] | 25 |  |  | 25
|  |  | Procure Weld material |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 5 |  |  |  | 5
|  |  | Miscellaneous M&S |  | 2011-02-28 | 2011-05-23 | 12 | [31 empty] | 5 |  |  |  | 5
In-house Fabrication
|  |  | Design stud installation fixture | [20 empty] | 80 | [10 empty] | 40 | [7 empty] | 0
|  |  | Fabricate Fixture for Stud installation | [30 empty] | 80 | 40 |  |  |  | 1 |  |  | 1 | 2
|  |  | Assemble and weld case components [Inconel tubes, forgings, bellows, organ pipes, bakeout tubing] | [32 empty] | 432 |  | 288 | 5 |  |  | 2 | 7
|  |  | Install inconel weld studs | [30 empty] | 240 | [7 empty] | 0.5 | 0.5
|  |  | Mount PF1b coil and support to CS casing [top and bottom] | [30 empty] | 120 |  | 80 | [6 empty] | 0
0
Ceramic Break Assembly
|  |  | DESIGN | [39 empty] | 0
|  |  | Complete design of ceramic break assembly |  |  |  |  | 80 | [34 empty] | 0
|  |  | Complete cad design and details | [20 empty] | 120 | [18 empty] | 0
0
|  |  | Purchase & Fabrication | [39 empty] | 0
|  |  | Procure Ceramic Rings | [35 empty] | 55 | 0 |  |  | 55
|  |  | Procure CHI Shields | [35 empty] | 0 | 30 |  |  | 30
|  |  | Fabricate Ceramic break SS structure | [35 empty] | 0 | 30 |  |  | 30
|  |  | Procure Viton "O" rings | [35 empty] | 5 |  |  |  | 5
|  |  | In-house Fabrication | [39 empty] | 0
|  |  | Assemble and Test Ceramic Breaks | [34 empty] | 144 | 1 | 0 | 1 |  | 2
0
1170 | 5*** | 5501 | COIL BUS RUNS | Raftopoulos
|  | SCOPE | TF air-cooled [From TC water fall to bottom of machine]
OH Coax [Inside umbrella]
Reposition & terminate OH cable to bottom of machine
Inner PF coils [U/L PF1a, 1b and 1c]
CHI/bakeout [Lower ring bus & ring to VV bus
|  |  | Preliminary Design Activities | [39 empty] | 0
|  |  | Design bus systems |  | 2010-01-04 | 2010-06-01 | [7 empty] | 300 | [7 empty] | 240 | [20 empty] | 0
|  |  | Complete Cad details and assemblies |  | 2010-01-04 | 2010-06-01 | [22 empty] | 300 | [13 empty] | 0
Final Design Activities
|  |  | Design bus systems |  | 2010-06-01 | 2010-11-01 | [7 empty] | 300 | [7 empty] | 240
|  |  | Complete Cad details and assemblies |  | 2010-06-01 | 2010-11-01 | [22 empty] | 400
|  |  | Bus Loren tz Forces/Support Stress Analysis |  | 2010-06-01 | 2010-11-01 | [8 empty] | 144 | [27 empty] | 0
Purchase & Fabrication
|  |  | Copper |  | 2011-01-10 | 2011-05-23 | [24 empty] | 8 | [7 empty] | 20 |  |  |  | 20
|  |  | Insulation & epoxy |  | 2011-01-10 | 2011-05-23 | [24 empty] | 8 | [7 empty] | 10 |  |  |  | 10
|  |  | Hardware |  | 2011-01-10 | 2011-05-23 | [24 empty] | 8 | [7 empty] | 5 |  |  |  | 5
|  |  | Braze material |  | 2011-01-10 | 2011-05-23 | [24 empty] | 8 | [7 empty] | 1 |  |  |  | 1
|  |  | G-10/Phenolic |  | 2011-01-10 | 2011-05-23 | [24 empty] | 8 | [7 empty] | 15 |  |  |  | 15
|  |  | Miscellaneous |  | 2011-01-10 | 2011-05-23 | [24 empty] | 16 | [7 empty] | 15 |  |  |  | 15
0
Fabrication Bus & Supports
|  |  | TF air-cooled [From TC water fall to bottom of machine] |  | 2011-05-23 | 2011-12-12 | [7 empty] | 24 | [16 empty] | 24 |  |  | 500 | 200 | [6 empty] | 2 | 2
|  |  | OH Coax [Inside umbrella] |  | 2011-05-23 | 2011-12-12 | [7 empty] | 40 | [16 empty] | 24 |  |  | 240 | 160 | [6 empty] | 0.5 | 0.5
|  |  | Reposition & terminate OH cable to bottom of machine |  | 2011-05-23 | 2011-12-12 | [7 empty] | 16 | [16 empty] | 24 |  |  | 80 |  |  |  |  | 1 |  |  | 0.5 | 1.5
|  |  | Inner PF coils [U/L PF1a, 1b and 1c] |  | 2011-05-23 | 2011-12-12 | [7 empty] | 24 | [16 empty] | 24 |  |  | 500 | 160 | [6 empty] | 0.5 | 0.5
|  |  | CHI/bakeout [Lower ring bus & ring to VV bus |  | 2011-05-23 | 2011-12-12 | [7 empty] | 24 | [16 empty] | 24 |  |  | 400 | 166 |  |  |  | 5 |  |  | 0.5 | 5.5
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  |  | 0
[5 empty] | 2009-10-01 | 2013-01-07 |  | 3486 | 1860 | 400 | 440 | 980 | 480 | 728 | 714 | 140 | 2040 | 834 | 500 | 288 | 106 | 480 | 1580 | 1528 | 3400 | 80 | 1034 | 1080 | 1440 | 320 | 1704 | 0 | 0 | 9744 | 1286 | 872 | 840 | 432 | 930.2179 | 4215.3052 | 36 | 25.5 | 5187.0231
|  |  | Costs do not include installation | [5 empty] | EAEM | Total hrs. | 9228 | [5 empty] | EMEM | Total hrs. |  | 3768 |  | 480 | EADM | 10142 | Total Hrs | [5 empty] | 1704 | Total Hrs | EMSM | EMTB | Total Hrs | 13174 |  |  |  |  | Total M&S$ | 5187.0231 | w/0 G&A
[10 empty] | Rate | 185.27 | [6 empty] | Rate |  | 165.16 |  | 175.71 | Rate | 124.95 | Rate | [6 empty] | Rate | 145.16 |  | Rate | 90.36 |  |  |  |  | Total Labor | 5121.3334
EEEM
[11 empty] | 1709671.56 | [6 empty] | 622322.88 |  |  |  | 84340.8 |  | 1267242.9 | [7 empty] | 247352.64 |  |  |  | 1190402.64 |  |  |  |  | Total | 10308.3565 | does not include G&A
or contingency
[5 empty] | FY2009 Hourly Rates |  |  | 39
[5 empty] | EA//EM | 1900-07-03 06:29 |  | 5616
[5 empty] | EM//EM | 1900-06-13 03:50
[5 empty] | EE//EM | 1900-06-23 17:02
[5 empty] | EAD/SB | 1900-05-03 22:48
[5 empty] | EM//SM | 1900-05-24 03:50
[5 empty] | EM//SB | 1900-04-28 05:31
[5 empty] | EM//TB | 1900-03-30 08:38
[5 empty] | M&S | 1899-12-31 06:45

## WORKSHEET
|  | 1997 $ | Inflator % | 2009 $ | x4 k$ | # Orig | # Upgrade
OH solenoid |  | 136.3 | 1.2992 | 177.081 | 708.3238 | 2340 | 6400 | 3
Conductor assume $7.5/lb | 7.5 | 48000 | 2.2 | 105600 | 105.6
OH conductor |  | 40 | 1.2992 | 51.968 | 155.904 | 6400 | 2.2 | 5
|  | FY97 cost | Escal |  |  | 12800 | 92.16
TF bundle |  | 83 | 1.2992 | 107.8336 | 431.3344
1139.6582
[5 empty] | 1481.5557 | 30% | difficulty
OTF Conductor |  |  |  | 2 x 3 | 23 #/ft | 3450# | 25 ft/length | 6
Rotable flanges |  | 13.2 | 1.2992 | 17.1494
Inconel Forgings |  | 30.9 | 1.2992 | 40.1453 | 1.5 | 60.2179
6400
|  | width | Height | Hole Dia | Hole Area | Area | Coil R | Turn | Length/Turn | Length/Coil | Length/Coil |  | Wt/coil
PF Conductors |  | in | in | in | in2 | in2 | in |  | in | in | ft | x 2 | lb | x 2
PF1a |  | 0.591 | 0.591 | 0.217 | 0.118 | 0.23128 | 12.571 | 120 | 78.9459 | 9473.5056 | 789.4588 | 1578.9176 | 701.1334 | 1402.2668
PF1b |  | 0.22 | 0.22 | 0.098 | 0.0024 | 0.046 | 15.763 | 180 | 98.9916 | 17818.4952 | 1484.8746 | 2969.7492 | 262.2882 | 524.5765
PF1c |  | 0.22 | 0.22 | 0.098 | 0.0024 | 0.046 | 21.674 | 162 | 136.1127 | 22050.2606 | 1837.5217 | 3675.0434 | 324.5798 | 649.1597
[15 empty] | x 2.2 | 7.5
[14 empty] | 2576.003 | 5667.2065 | 42.504 | k
[8 empty] | Pi | 3.14
[8 empty] | 0.32 | #/Cu in