## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 1303
Job Title: | TF Joint Test Stand & Performance Test
Job Manager: | T. Kozub
Description:
Design and fabrication of a test stand to measure the required performance parameters on the new NSTX TF joint design. Perform test parameter measurements and cyclic lifetime tests as required. Compile and report testing data. Modify test stand configuration for revised design configurations as needed. Repeat tests for revised design configurations as needed. Compile comprehensive final test report including all test data.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1170
| Job Number: |  |  | 1303
| Job Title: |  |  | TF Joint Test Stand & Performance of Test
| Job Manager: |  |  | T. Kozub
Estimate (user input)
[5 empty] | SCHEDULE | [13 empty] | FY09$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT | [5 empty] | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) |  |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
numb | P3 cross ref (optinal) | [17 empty] | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
1 |  | Physics Requirements |  |  | 20 |  |  |  |  | 2009-10-05 | 2009-10-20 09:43 | 2009-11-17 09:43 | 2009-10-05 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 40
2 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
3 |  | Conceptual Design | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
4 |  | PREPARE WORK PLANNING FORM |  |  | 10 | 1 |  |  |  | 2009-11-02 | 2009-11-02 | 2009-11-16 | 2009-11-02 | 2009-11-17 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 16
5 |  | Prep System Description |  |  | 10 | 1 |  |  |  | 2009-11-02 | 2009-11-02 | 2009-11-16 | 2009-11-02 | 2009-11-17 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 24
6 |  | Prep System Requirements |  |  | 10 | 1 |  |  |  | 2009-11-02 | 2009-11-02 | 2009-11-16 | 2009-11-02 | 2009-11-17 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 24
7 |  | R&D |  |  | 5 | 4 | 5 | 6 |  |  | 2009-11-16 | 2009-11-23 | 2009-10-20 09:43 | 2009-11-16 | 2009-11-16 | 2009-11-16 | 2009-10-20 09:43 | [12 empty] | 24
8 |  | Ananlysis | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
9 |  | CDR |  |  | 5 | 7 |  |  |  |  | 2009-11-23 | 2009-11-30 | 2009-10-20 09:43 | 2009-11-23 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 16
10 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
11 |  | Preliminary Design | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
12 |  | Thermal Analysis | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
13 |  | Seismic Analysis | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
14 |  | FMEA Analysis | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
15 |  | Prepare NEPA Form |  |  | 5 | 9 |  |  |  |  | 2009-11-30 | 2009-12-07 | 2009-10-20 09:43 | 2009-11-30 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 16
16 |  | Update Cost & Schedule Estimate |  |  | 5 | 9 |  |  |  |  | 2009-11-30 | 2009-12-07 | 2009-10-20 09:43 | 2009-11-30 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 8
17 |  | Design Drawings |  |  | 20 | 9 |  |  |  |  | 2009-11-30 | 2009-12-28 | 2009-10-20 09:43 | 2009-11-30 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [7 empty] | 40 |  |  |  |  | 40
18 |  | PDR Prep |  |  | 10 | 9 |  |  |  |  | 2009-11-30 | 2009-12-14 | 2009-10-20 09:43 | 2009-11-30 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 40
19 |  | CONDUCT PDR |  |  | 5 | 15 | 16 | 17 | 18 |  | 2009-12-28 | 2010-01-04 | 2009-10-20 09:43 | 2009-12-07 | 2009-12-07 | 2009-12-28 | 2009-12-14 | [12 empty] | 8
20 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
21 |  | Final Design | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
22 |  | Disposition PDR Chits |  |  | 5 | 19 |  |  |  |  | 2010-01-04 | 2010-01-11 | 2009-10-20 09:43 | 2010-01-04 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 24
23 |  | Design Drawings |  |  | 20 | 22 |  |  |  |  | 2010-01-11 | 2010-02-08 | 2009-10-20 09:43 | 2010-01-11 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [7 empty] | 80 |  |  |  |  | 16
24 |  | Update Analyses | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
25 |  | Update Cost & Schedule Estimate |  |  | 2 | 22 |  |  |  |  | 2010-01-11 | 2010-01-13 19:12 | 2009-10-20 09:43 | 2010-01-11 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 8
26 |  | Prep Procurement Specs |  |  | 3 | 22 |  |  |  |  | 2010-01-11 | 2010-01-15 04:48 | 2009-10-20 09:43 | 2010-01-11 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 16
27 |  | FDR Prep |  |  | 10 | 22 |  |  |  |  | 2010-01-11 | 2010-01-25 | 2009-10-20 09:43 | 2010-01-11 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 40
28 |  | CONDUCT FDR |  |  | 1 | 24 | 25 | 26 | 27 |  | 2010-01-25 | 2010-01-26 09:36 | 2009-10-20 09:43 |  | 2010-01-13 19:12 | 2010-01-15 04:48 | 2010-01-25 | [12 empty] | 8
29 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
30 |  | Procurement | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
31 |  | Item 1: | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
32 |  |  | Prep Requisition and procurement package | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
33 |  |  | SUBMIT REQ TO PROCUREMENT | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
34 |  |  | Procurement lead time (1) | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
35 |  |  | AWARD | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
36 |  |  | Fabricate or delivery | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
37 |  | Item 2: | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
38 |  |  | Prep Requisition and procurement package | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
39 |  |  | SUBMIT REQ TO PROCUREMENT | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
40 |  |  | Procurement lead time (1) | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
41 |  |  | AWARD | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
42 |  |  | Fabricate or delivery | [9 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
43 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
44 |  | Fab/Assembly | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
45 |  | Fab/Assy Procedure |  |  | 20 | 28 |  |  |  |  | 2010-01-26 09:36 | 2010-02-23 09:36 | 2009-10-20 09:43 | 2010-01-26 09:36 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 24 | 40
46 |  | Shop Fabrication |  |  | 20 | 45 |  |  |  |  | 2010-02-23 09:36 | 2010-03-23 09:36 | 2009-10-20 09:43 | 2010-02-23 09:36 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 |  | 30 | 30 | [8 empty] | 40 | 16 | 80
47 |  | Assembly |  |  | 30 | 46 |  |  |  |  | 2010-03-23 09:36 | 2010-05-04 09:36 | 2009-10-20 09:43 | 2010-03-23 09:36 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 |  | 10 | 10 | [9 empty] | 40 | 40
48 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
49 |  | Installation | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
50 |  | Installation Procedure | [10 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
51 |  | Machine Installation |  |  | 30 | 47 |  |  |  |  | 2010-05-04 09:36 | 2010-06-15 09:36 | 2009-10-20 09:43 | 2010-05-04 09:36 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [11 empty] | 40 | 120 | 80
52 |  | PTP Testing |  |  | 60 | 51 |  |  |  |  | 2010-06-15 09:36 | 2010-09-07 09:36 | 2009-10-20 09:43 | 2010-06-15 09:36 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [12 empty] | 240 | 160
53 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
54 |  | OTHER TASKS | Final Report & Presentation |  | 15 | 52 |  |  |  |  | 2010-09-07 09:36 | 2010-09-28 09:36 | 2009-10-20 09:43 | 2010-09-07 09:36 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | [7 empty] | 40 |  |  |  |  | 120
55 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 |  | 40 | 40 |  |  |  | 0 | 160 | 0 | 0 | 0 | 80 | 928 | 400 | 0 | 0 | 0 | 0 | 0 | 0
56 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
57 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
58 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
59 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
60 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
61 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
62 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
63 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
64 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
65 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
66 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
67 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
68 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
69 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
70 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
71 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
72 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
73 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
74 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
75 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
76 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
77 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
78 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
79 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
80 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
81 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
82 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
83 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
84 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
85 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
86 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
87 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
88 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
89 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
90 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
91 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
92 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
93 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
94 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
95 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
96 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
97 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
98 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
99 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
100 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
101 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
102 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
103 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
104 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
105 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
106 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
107 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
108 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
109 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
110 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
111 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
112 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
113 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
114 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
115 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
116 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
117 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
118 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
119 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
120 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
121 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
122 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
123 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
124 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
125 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
126 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
127 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
128 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
129 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
130 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
131 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
132 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
133 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
134 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
135 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
136 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
137 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
138 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
139 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
140 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
141 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
142 | [12 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
[13 empty] | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43 | 2009-10-20 09:43
|  | TOTALS | [16 empty] | 80 | 80 | 0 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 160 | 1856 | 800 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 682.6067 | [13 empty] | 97.6 | 97.6 | 0 | 0 | 0 | 0 | 40.0288 | 0 | 0 | 0 | 24.1712 | 306.9267 | 116.28 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [26 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [9 empty] | Weeks | [15 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [8 empty] | 3 | [15 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [8 empty] | 5 | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [8 empty] | 8 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [8 empty] | 9 | [15 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 1303
Job Title: |  | TF Joint Test Stand & Performance Test
Job Manager: |  | T. Kozub
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  | 20 | Similar tests have been performed before successfully. The designs will be new and different although similar. It is expected that as the design is analyzed and tested that it will change and this will be an iterative development with several design, fabricate and test cycles.
| Design Complexity |  | X |  | 20 | Similar tests have been performed before successfully. The designs will be new and different although similar.
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Significant change in TF design concept |  |  |  | 25% | Perform additional work |  |  | Past testing jobs | 10 | 50 | 2 | 10
2 | Increased number of redesign/retest cycles |  |  |  | 25% | Perform additional work |  |  | Past testing jobs | 10 | 50 | 2 | 10
3 | Unexpected technical challenges in implementing testing apparatus and procedures |  |  |  | 10% | Perform additional work |  |  | Past testing jobs | 0 | 30 | 2 | 4
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Sheet1
Cost Center: | 1170
Job Number: | 1303
Job Title: | TF Joint Test Stand & Performance Test
Job Manager: | T. Kozub
Materials and Subcontracts (M&S) | K$ | Basis of Estimate
Description:
CATEGORIZATION CODES:
| 1 - National Standards |  | 1 | 0 | #DIV/0!
| 2 - Engineering Judgement/Experience |  | 2 | 0 | #DIV/0!
| 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | #DIV/0!
| 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | #DIV/0!
| 5 - Prototype Data/Test Results |  | 5 | 0 | #DIV/0!
| 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | #DIV/0!
| 7 - Placed Contracts |  | 7 | 0 | #DIV/0!
| 8 - Actual experience for NCSX Work |  | 8 | 0 | #DIV/0!
| 9 - Other |  | 9 | 0 | #DIV/0!
|  | TOTALS |  | 0 | #DIV/0!