## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1180
Job Number: | 2425
Job Title: | NSTX BL2 Relocation
Job Manager: | M. Denault
Description:
Move neutral beam beam line and ancillary equipment into NSTX test cell. This includes HVEs and complete beam box.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1180
| Job Number: |  |  | 2425
| Job Title: |  |  | NSTX BL2 Relocation
| Job Manager: |  |  | M. Denault
Estimate (user input)
[5 empty] | SCHEDULE | [12 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [16 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1
2
3 |  | Conceptual Design |  | Denault | [7 empty] | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
4 |  | PREPARE WORK PLANNING FORM |  |  | 1 |  |  |  | 2009-09-24 | 2009-09-24 | 2009-09-25 09:36 | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | [13 empty] | Experience
5 |  | Prep System Description |  |  | 2 | 4 |  |  |  | 2009-09-25 09:36 | 2009-09-28 04:48 | 2007-10-01 | 2009-09-25 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
6 |  | Prep System Requirements |  |  | 3 | 5 |  |  |  | 2009-09-28 04:48 | 2009-10-02 09:36 | 2007-10-01 | 2009-09-28 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 24 | [13 empty] | Experience
7 |  | R&D |  |  | 20 | 6 |  |  |  | 2009-10-02 09:36 | 2009-10-30 09:36 | 2007-10-01 | 2009-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 160 | [13 empty] | Experience
8 |  | Analysis |  |  | 20 | 7 |  |  |  | 2009-10-30 09:36 | 2009-11-27 09:36 | 2007-10-01 | 2009-10-30 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 |  |  |  |  | 40 |  |  |  | 160 | [13 empty] | Experience
9 |  | CDR |  |  | 2 | 8 |  |  |  | 2009-11-27 09:36 | 2009-11-30 04:48 | 2007-10-01 | 2009-11-27 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
10 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
11 |  | Preliminary Design |  | Denault | [7 empty] | 2010-08-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
12 |  | Thermal Analysis |  |  | 5 |  |  |  | 2010-08-03 | 2010-08-03 | 2010-08-10 | 2010-08-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 40 | [13 empty] | Experience
13 |  | Seismic Analysis |  |  | 10 | 12 |  |  |  | 2010-08-10 | 2010-08-24 | 2007-10-01 | 2010-08-10 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [8 empty] | 80 | [13 empty] | Experience
14 |  | FMEA Analysis |  |  | 10 | 13 |  |  |  | 2010-08-24 | 2010-09-07 | 2007-10-01 | 2010-08-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [8 empty] | 80 | [13 empty] | Experience
15 |  | Prepare NEPA Form |  |  | 2 | 14 |  |  |  | 2010-09-07 | 2010-09-09 19:12 | 2007-10-01 | 2010-09-07 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
16 |  | Update Cost & Schedule Estimate |  |  | 10 | 15 |  |  |  | 2010-09-09 19:12 | 2010-09-23 19:12 | 2007-10-01 | 2010-09-09 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [6 empty] | 80 | [6 empty] | Experience
17 |  | Design Drawings |  |  | 20 | 16 |  |  |  | 2010-09-23 19:12 | 2010-10-21 19:12 | 2007-10-01 | 2010-09-23 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 160 |  |  |  | 80 |  |  |  | 80 | [13 empty] | Experience
18 |  | PDR Prep |  |  | 5 | 17 |  |  |  | 2010-10-21 19:12 | 2010-10-28 19:12 | 2007-10-01 | 2010-10-21 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [13 empty] | Experience
19 |  | CONDUCT PDR |  |  | 2 | 18 |  |  |  | 2010-10-28 19:12 | 2010-10-31 14:24 | 2007-10-01 | 2010-10-28 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
|  | Layman Review |  |  | 5 |  |  |  | 2010-12-15 | 2010-12-15 | 2010-12-22 | 2010-12-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [13 empty] | Experience
20 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
21 |  | Final Design |  | Denault | [7 empty] | 2011-01-28 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
22 |  | Disposition PDR Chits |  |  | 2 | 21 |  |  | 2011-01-28 | 2011-01-28 | 2011-01-30 19:12 | 2011-01-28 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
23 |  | Design Drawings |  |  | 10 | 22 |  |  |  | 2011-01-30 19:12 | 2011-02-13 19:12 | 2007-10-01 | 2011-01-30 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 |  |  |  | 40 |  |  |  | 20 | [13 empty] | Experience
24 |  | Update Analyses |  |  | 5 | 23 |  |  |  | 2011-02-13 19:12 | 2011-02-20 19:12 | 2007-10-01 | 2011-02-13 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [8 empty] | 40 | [13 empty] | Experience
25 |  | Update Cost & Schedule Estimate |  |  | 5 | 24 |  |  |  | 2011-02-20 19:12 | 2011-02-27 19:12 | 2007-10-01 | 2011-02-20 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [6 empty] | 40 | [6 empty] | Experience
26 |  | Prep Procurement Specs |  |  | 5 | 25 |  |  |  | 2011-02-27 19:12 | 2011-03-06 19:12 | 2007-10-01 | 2011-02-27 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [13 empty] | Experience
27 |  | FDR Prep |  |  | 5 | 26 |  |  |  | 2011-03-06 19:12 | 2011-03-13 19:12 | 2007-10-01 | 2011-03-06 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [13 empty] | Experience
28 |  | CONDUCT FDR |  |  | 2 | 27 |  |  |  | 2011-03-13 19:12 | 2011-03-16 14:24 | 2007-10-01 | 2011-03-13 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
29 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
30 |  | Procurement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
31 |  | Steel and Parts | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [23 empty] | 0 | [5 empty] | Experience
32 |  |  | Prep Requisition and procurement package |  | 1 | 28 |  |  | 2011-06-10 | 2011-06-10 | 2011-06-11 09:36 | 2011-06-10 | 2011-03-16 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
33 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 32 |  |  |  | 2011-06-11 09:36 | 2011-06-12 19:12 | 2007-10-01 | 2011-06-11 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
34 |  |  | Procurement lead time (1) |  | 30 | 33 |  |  |  | 2011-06-12 19:12 | 2011-07-24 19:12 | 2007-10-01 | 2011-06-12 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
35 |  |  | AWARD |  | 1 | 34 |  |  |  | 2011-07-24 19:12 | 2011-07-26 04:48 | 2007-10-01 | 2011-07-24 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
36 |  |  | Fabricate or delivery |  | 30 | 35 |  |  |  | 2011-07-26 04:48 | 2011-09-06 04:48 | 2007-10-01 | 2011-07-26 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
37 |  | Lifting Equip. | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
38 |  |  | Prep Requisition and procurement package |  | 2 | 28 |  |  | 2011-06-10 | 2011-06-10 | 2011-06-12 19:12 | 2011-06-10 | 2011-03-16 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
39 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 38 |  |  |  | 2011-06-12 19:12 | 2011-06-14 04:48 | 2007-10-01 | 2011-06-12 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
40 |  |  | Procurement lead time (1) |  | 30 | 39 |  |  |  | 2011-06-14 04:48 | 2011-07-26 04:48 | 2007-10-01 | 2011-06-14 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
41 |  |  | AWARD |  | 1 | 40 |  |  |  | 2011-07-26 04:48 | 2011-07-27 14:24 | 2007-10-01 | 2011-07-26 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
42 |  |  | Fabricate or delivery |  | 30 | 41 |  |  |  | 2011-07-27 14:24 | 2011-09-07 14:24 | 2007-10-01 | 2011-07-27 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
43 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
44 |  | Fab/Assembly |  | Denault | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
45 |  | Fab/Assy Procedure | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
46 |  | Shop Fabrication | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
47 |  | Assembly | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
48 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
49 |  | Installation |  | Denault | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
50 |  | Installation Procedure | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
51 |  | Machine Installation | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
52 |  | PTP Testing | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
54 |  | Engineering 1 Days Per Week title III |  | 1 | 280 |  |  |  | 2011-02-01 | 2011-02-01 | 2012-02-28 | 2011-02-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 160 |  |  |  | 448 | [13 empty] | Experience
55 |  | Engineering Support 1/2 Days Per Week title III |  | 0.5 | 280 |  |  |  | 2011-02-02 | 2011-02-02 | 2012-02-29 | 2011-02-02 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 224 | [13 empty] | Experience
56 |  | Drafting Support 1/2 day/week title III |  | 0.5 | 280 |  |  |  | 2011-02-03 | 2011-02-03 | 2012-03-01 | 2011-02-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 224 | [20 empty] | Experience
57
58 |  | Path | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 15
59 |  |  | Road |  | 5 |  |  |  | 2012-01-01 | 2012-01-01 | 2012-01-08 | 2012-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 40 | 160 | [11 empty] | Experience
60 |  |  | Duct Removal |  | 2 | 59 |  |  | 2012-01-01 | 2012-01-08 | 2012-01-10 19:12 | 2012-01-01 | 2012-01-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
61 |  |  | Lintel Removal |  | 3 | 60 |  |  |  | 2012-01-10 19:12 | 2012-01-15 | 2007-10-01 | 2012-01-10 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 16 | 8 | 24 | 96 | [11 empty] | Experience
62 |  |  | Lintel Install |  | 2 | 107 |  |  |  | 2010-01-30 09:36 | 2010-02-02 04:48 | 2007-10-01 | 2010-01-30 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 16 | 8 | 16 | 64 | [11 empty] | Experience
63 |  |  | Duct Install |  | 2 | 62 |  |  |  | 2010-02-02 04:48 | 2010-02-05 | 2007-10-01 | 2010-02-02 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
64 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
65 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
66 |  | Metrology | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 3
67 |  |  | Setup |  | 5 |  |  |  | 2009-10-01 | 2009-10-01 | 2009-10-08 | 2009-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 |  | 80 | [11 empty] | Experience
68 |  |  | Measure |  | 15 | 67 |  |  |  | 2009-10-08 | 2009-10-29 | 2007-10-01 | 2009-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 240 |  | 240 | [11 empty] | Experience
69 |  |  | Model |  | 5 | 68 |  |  |  | 2009-10-29 | 2009-11-05 | 2007-10-01 | 2009-10-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 | [7 empty] | 80 | [13 empty] | Experience
70 |  |  | Lay out |  | 5 | 69 |  |  |  | 2009-11-05 | 2009-11-12 | 2007-10-01 | 2009-11-05 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 |  | 80 | [11 empty] | Experience
71 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
72 |  | Labyrinth Removal |  |  | 10 |  |  |  | 2010-06-01 | 2010-06-01 | 2010-06-15 | 2010-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10 | [12 empty] | 32 |  | 80 | 160 | [11 empty] | Experience
73 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
74 |  | Lift Fixtures | [15 empty] | 15
75 |  |  | Construction |  | 20 |  |  |  | 2010-01-10 | 2010-01-10 | 2010-02-07 | 2010-01-10 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [17 empty] | 480 | [11 empty] | Experience
76 |  |  | Load Test |  | 5 | 75 |  |  |  | 2010-02-07 | 2010-02-14 | 2007-10-01 | 2010-02-07 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | 40 | 120 | [11 empty] | Experience
77 |  |  | Move |  | 1 | 76 |  |  |  | 2010-02-14 | 2010-02-15 09:36 | 2007-10-01 | 2010-02-14 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [17 empty] | 24 | [11 empty] | Experience
78 |  |  | Trial Runs |  | 5 | 77 |  |  |  | 2010-02-15 09:36 | 2010-02-22 09:36 | 2007-10-01 | 2010-02-15 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | 40 | 120 | [11 empty] | Experience
79 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
80 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
81
82
83
84
85 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
86 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
87 |  | Box Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2
88 |  |  | Lift onto Rollers |  | 1 | 95 | 155 | 19 | 2012-01-01 | 2012-01-01 | 2012-01-02 09:36 | 2012-01-01 | 2010-01-02 09:36 |  | 2010-10-31 14:24 | 2007-10-01 | [15 empty] | 152 | 8 | 48 | [11 empty] | Experience
89 |  |  | Move IN |  | 1 | 88 |  |  |  | 2012-01-02 09:36 | 2012-01-03 19:12 | 2007-10-01 | 2012-01-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | Experience
90 |  |  | Over Wall |  | 1 | 89 |  |  |  | 2012-01-03 19:12 | 2012-01-05 04:48 | 2007-10-01 | 2012-01-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | Experience
91 |  |  | Placement |  | 10 | 90 |  |  |  | 2012-01-05 04:48 | 2012-01-19 04:48 | 2007-10-01 | 2012-01-05 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | 80 | 480 | [11 empty] | Experience
92 |  |  | Metrology |  | 10 | 91 |  |  |  | 2012-01-19 04:48 | 2012-02-02 04:48 | 2007-10-01 | 2012-01-19 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | 80 | 160 | [11 empty] | Experience
93 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
94 |  | Source Platform | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
95 |  |  | Off |  | 1 |  |  |  | 2010-01-01 | 2010-01-01 | 2010-01-02 09:36 | 2010-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 24 | [11 empty] | Experience
96 |  |  | Move |  | 1 | 95 |  |  |  | 2010-01-02 09:36 | 2010-01-03 19:12 | 2007-10-01 | 2010-01-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 16 | [11 empty] | Experience
97 |  |  | Lift |  | 1 | 96 |  |  |  | 2010-01-03 19:12 | 2010-01-05 04:48 | 2007-10-01 | 2010-01-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | Experience
98 |  |  | On |  | 1 | 97 |  |  |  | 2010-01-05 04:48 | 2010-01-06 14:24 | 2007-10-01 | 2010-01-05 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | Experience
99 |  |  | Metrology |  | 10 | 98 |  |  |  | 2010-01-06 14:24 | 2010-01-20 14:24 | 2007-10-01 | 2010-01-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 160 | 80 | 320 | [11 empty] | Experience
100 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
101 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
102 |  | Lid Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 5
103 |  |  | Stabilize |  | 3 | 99 |  |  |  | 2010-01-20 14:24 | 2010-01-24 19:12 | 2007-10-01 | 2010-01-20 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 24 | 24 | 120 | [11 empty] | Experience
104 |  |  | Lift onto Rollers |  | 1 | 103 |  |  |  | 2010-01-24 19:12 | 2010-01-26 04:48 | 2007-10-01 | 2010-01-24 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | Experience
105 |  |  | Move IN |  | 1 | 104 |  |  |  | 2010-01-26 04:48 | 2010-01-27 14:24 | 2007-10-01 | 2010-01-26 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | Experience
106 |  |  | Over Wall |  | 1 | 105 |  |  |  | 2010-01-27 14:24 | 2010-01-29 | 2007-10-01 | 2010-01-27 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | Experience
107 |  |  | Placement |  | 1 | 106 |  |  |  | 2010-01-29 | 2010-01-30 09:36 | 2007-10-01 | 2010-01-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 16 | [11 empty] | Experience
108 |  |  | Metrology |  | 1 | 107 |  |  |  | 2010-01-30 09:36 | 2010-01-31 19:12 | 2007-10-01 | 2010-01-30 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | 8 | 48 | [11 empty] | Experience
109 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
110 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
111 |  | Component Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2
112 |  |  | 90in Flange |  | 2 | 108 |  |  |  | 2010-01-31 19:12 | 2010-02-03 14:24 | 2007-10-01 | 2010-01-31 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
113 |  |  | Magnet |  | 2 | 112 |  |  |  | 2010-02-03 14:24 | 2010-02-06 09:36 | 2007-10-01 | 2010-02-03 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | Experience
114 |  |  | Ion Dump |  | 2 | 113 |  |  |  | 2010-02-06 09:36 | 2010-02-09 04:48 | 2007-10-01 | 2010-02-06 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | Experience
115 |  |  | Exit Spool |  | 2 | 114 |  |  |  | 2010-02-09 04:48 | 2010-02-12 | 2007-10-01 | 2010-02-09 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
116 |  |  | TIV |  | 2 | 115 |  |  |  | 2010-02-12 | 2010-02-14 19:12 | 2007-10-01 | 2010-02-12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
117 |  |  | Calorimeter |  | 2 | 116 |  |  |  | 2010-02-14 19:12 | 2010-02-17 14:24 | 2007-10-01 | 2010-02-14 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | Experience
118 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
119 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
120 |  | Source Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
121 |  |  | Move 1 |  | 2 | 99 |  |  |  | 2010-01-20 14:24 | 2010-01-23 09:36 | 2007-10-01 | 2010-01-20 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
122 |  |  | Align 1 |  | 4 | 121 |  |  |  | 2010-01-23 09:36 | 2010-01-29 | 2007-10-01 | 2010-01-23 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 64 | 32 | 128 | [11 empty] | Experience
123 |  |  | Move 2 |  | 2 | 122 |  |  |  | 2010-01-29 | 2010-01-31 19:12 | 2007-10-01 | 2010-01-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
124 |  |  | Align 2 |  | 4 | 123 |  |  |  | 2010-01-31 19:12 | 2010-02-06 09:36 | 2007-10-01 | 2010-01-31 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 64 | 32 | 128 | [11 empty] | Experience
125 |  |  | Move 3 |  | 2 | 124 |  |  |  | 2010-02-06 09:36 | 2010-02-09 04:48 | 2007-10-01 | 2010-02-06 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
126 |  |  | Align 3 |  | 4 | 125 |  |  |  | 2010-02-09 04:48 | 2010-02-14 19:12 | 2007-10-01 | 2010-02-09 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 64 | 32 | 128 | [11 empty] | Experience
127 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
128 |  | HVE 1 Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
129 |  |  | Move |  | 2 |  | 19 |  | 2011-06-01 | 2011-06-01 | 2011-06-03 19:12 | 2011-06-01 | 2007-10-01 | 2010-10-31 14:24 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | Experience
130 |  |  | Disassemble |  | 2 | 129 |  |  |  | 2011-06-03 19:12 | 2011-06-06 14:24 | 2007-10-01 | 2011-06-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
131 |  |  | Move to Crain Access |  | 2 | 130 |  |  |  | 2011-06-06 14:24 | 2011-06-09 09:36 | 2007-10-01 | 2011-06-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
132 |  |  | Lift into TFTR |  | 1 | 131 |  |  |  | 2011-06-09 09:36 | 2011-06-10 19:12 | 2007-10-01 | 2011-06-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | Experience
133 |  |  | Move In |  | 1 | 132 |  |  |  | 2011-06-10 19:12 | 2011-06-12 04:48 | 2007-10-01 | 2011-06-10 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | Experience
134 |  |  | Over Wall |  | 2 | 133 |  |  |  | 2011-06-12 04:48 | 2011-06-15 | 2007-10-01 | 2011-06-12 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 80 | [11 empty] | Experience
135 |  |  | Reassemble |  | 2 | 134 |  |  |  | 2011-06-15 | 2011-06-17 19:12 | 2007-10-01 | 2011-06-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
136 |  |  | Placement |  | 3 | 135 |  |  |  | 2011-06-17 19:12 | 2011-06-22 | 2007-10-01 | 2011-06-17 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 24 | 96 | [11 empty] | Experience
137 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
138 |  | HVE 2 Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
139 |  |  | Move |  | 2 |  |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | Experience
140 |  |  | Disassemble |  | 2 | 139 |  |  |  | 2007-10-03 19:12 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
141 |  |  | Move to Crain Access |  | 2 | 140 |  |  |  | 2007-10-06 14:24 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
142 |  |  | Lift into TFTR |  | 1 | 141 |  |  |  | 2007-10-09 09:36 | 2007-10-10 19:12 | 2007-10-01 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | Experience
143 |  |  | Move In |  | 1 | 142 |  |  |  | 2007-10-10 19:12 | 2007-10-12 04:48 | 2007-10-01 | 2007-10-10 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | Experience
144 |  |  | Over Wall |  | 2 | 143 |  |  |  | 2007-10-12 04:48 | 2007-10-15 | 2007-10-01 | 2007-10-12 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 80 | [11 empty] | Experience
145 |  |  | Reassemble |  | 2 | 144 |  |  |  | 2007-10-15 | 2007-10-17 19:12 | 2007-10-01 | 2007-10-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
146 |  |  | Placement |  | 3 | 145 |  |  |  | 2007-10-17 19:12 | 2007-10-22 | 2007-10-01 | 2007-10-17 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 24 | 96 | [11 empty] | Experience
147 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
148 |  | HVE 3 Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
149 |  |  | Move |  | 2 |  |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | Experience
150 |  |  | Disassemble |  | 2 | 149 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
151 |  |  | Move to Crain Access |  | 2 | 150 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
152 |  |  | Lift into TFTR |  | 1 | 151 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | Experience
153 |  |  | Move In |  | 1 | 152 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | Experience
154 |  |  | Over Wall |  | 2 | 153 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 80 | [11 empty] | Experience
155 |  |  | Reassemble |  | 2 | 154 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | Experience
156 |  |  | Placement |  | 3 | 155 |  |  |  | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 24 | 96 | [11 empty] | Experience
157
[12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [15 empty] | 56 | 0 | 0 | 0 | 0 | 360 | 320 | 224 | 0 | 0 | 320 | 0 | 0 | 64 | 3116 | 1232 | 5736 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1654.6832 | [12 empty] | 68.656 | 0 | 0 | 0 | 0 | 67.896 | 39.968 | 31.2928 | 0 | 0 | 55.488 | 0 | 0 | 5.4016 | 498.2484 | 185.9088 | 683.7312 | 0 | 0 | 0 | 0 | 18.0924 |  | 0 | 0
| Notes: | [26 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [8 empty] | Weeks | [16 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [7 empty] | 3 | [16 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [7 empty] | 5 | [16 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [7 empty] | 8 | [16 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [7 empty] | 9 | [16 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
[18 empty] | 56 | 0 | 0 | 0 | 0 | 360 | 320 | 224 | 0 | 0 | 320 | 0 | 0 | 64 | 3116 | 1232 | 5736 | 0 | 0 | 0 | 0 | 120 | 0 | 0
67492

## Tab C Risk and uncertainty
Cost Center: |  | 1180
Job Number: |  | 2425
Job Title: |  | NSTX BL2 Relocation
Job Manager: |  | M. Denault
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1180
Job Number: | 2425
Job Title: | NSTX BL2 Relocation
Job Manager: | M. Denault
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Pipe |  |  | Vendor Pricing
Parts |  |  | Vendor Pricing
MISC |  |  | Experience
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1 | 0 | #DIV/0!
|  | 2 - Engineering Judgement/Experience |  | 2 | 0 | #DIV/0!
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | #DIV/0!
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | #DIV/0!
|  | 5 - Prototype Data/Test Results |  | 5 | 0 | #DIV/0!
|  | 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | #DIV/0!
|  | 7 - Placed Contracts |  | 7 | 0 | #DIV/0!
|  | 8 - Actual experience for NCSX Work |  | 8 | 0 | #DIV/0!
|  | 9 - Other |  | 9 | 0 | #DIV/0!
|  |  | TOTALS |  | 0 | #DIV/0!