## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1180
Job Number: | 2450
Job Title: | NSTX BL2 Services
Job Manager: | M. Denault
Description:
Provide services to the new neutral beam beam line and ancillary equipment in NSTX test cell. This includes cooling water, cryo systems, gas supplies, and vacuum lines.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1180
| Job Number: |  |  | 2450
| Job Title: |  |  | NSTX BL2 Services
| Job Manager: |  |  | M. Denault
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1
2
3 |  | Conceptual Design |  | Denault | [5 empty] | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
4 |  | PREPARE WORK PLANNING FORM |  |  | 1 |  | 2009-09-24 | 2009-09-24 | 2009-09-25 09:36 | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | [13 empty] | Experience
5 |  | Prep System Description |  |  | 2 | 4 |  | 2009-09-25 09:36 | 2009-09-28 04:48 | 2007-10-01 | 2009-09-25 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
6 |  | Prep System Requirements |  |  | 3 | 5 |  | 2009-09-28 04:48 | 2009-10-02 09:36 | 2007-10-01 | 2009-09-28 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 24 | [13 empty] | Experience
7 |  | R&D |  |  | 10 | 6 |  | 2009-10-02 09:36 | 2009-10-16 09:36 | 2007-10-01 | 2009-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [13 empty] | Experience
8 |  | Analysis |  |  | 20 | 7 |  | 2009-10-16 09:36 | 2009-11-13 09:36 | 2007-10-01 | 2009-10-16 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 |  |  |  |  | 80 |  |  |  | 160 | [13 empty] | Experience
9 |  | CDR |  |  | 2 | 8 | 2009-01-11 | 2009-11-13 09:36 | 2009-11-16 04:48 | 2009-01-11 | 2009-11-13 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
10 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
11 |  | Preliminary Design |  | Denault | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
12 |  | Thermal Analysis |  |  | 10 | 9 |  | 2009-11-16 04:48 | 2009-11-30 04:48 | 2007-10-01 | 2009-11-16 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 80 | [13 empty] | Experience
13 |  | Seismic Analysis |  |  | 10 | 12 |  | 2009-11-30 04:48 | 2009-12-14 04:48 | 2007-10-01 | 2009-11-30 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 80 | [13 empty] | Experience
14 |  | FMEA Analysis |  |  | 5 | 13 |  | 2009-12-14 04:48 | 2009-12-21 04:48 | 2007-10-01 | 2009-12-14 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 40 | [13 empty] | Experience
15 |  | Prepare NEPA Form |  |  | 2 | 14 |  | 2009-12-21 04:48 | 2009-12-24 | 2007-10-01 | 2009-12-21 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
16 |  | Update Cost & Schedule Estimate |  |  | 10 | 15 |  | 2009-12-24 | 2010-01-07 | 2007-10-01 | 2009-12-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [6 empty] | 80 | [6 empty] | Experience
17 |  | Design Drawings |  |  | 60 | 16 |  | 2010-01-07 | 2010-04-01 | 2007-10-01 | 2010-01-07 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 480 |  |  |  | 160 |  |  |  | 240 | [13 empty] | Experience
18 |  | PDR Prep |  |  | 10 | 17 |  | 2010-04-01 | 2010-04-15 | 2007-10-01 | 2010-04-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [13 empty] | Experience
19 |  | CONDUCT PDR |  |  | 2 | 18 | 2010-05-01 | 2010-05-01 | 2010-05-03 19:12 | 2010-05-01 | 2010-04-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
20 |  | Lehman Review |  |  | 5 | 19 |  | 2010-05-03 19:12 | 2010-05-10 19:12 | 2007-10-01 | 2010-05-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [13 empty] | Experience
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
21 |  | Final Design |  | Denault | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
22 |  | Disposition PDR Chits |  |  | 2 | 20 |  | 2010-05-10 19:12 | 2010-05-13 14:24 | 2007-10-01 | 2010-05-10 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
23 |  | Design Drawings |  |  | 10 | 22 |  | 2010-05-13 14:24 | 2010-05-27 14:24 | 2007-10-01 | 2010-05-13 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 |  |  |  | 80 |  |  |  | 20 | [13 empty] | Experience
24 |  | Update Analyses |  |  | 5 | 23 |  | 2010-05-27 14:24 | 2010-06-03 14:24 | 2007-10-01 | 2010-05-27 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [8 empty] | 40 | [13 empty] | Experience
25 |  | Update Cost & Schedule Estimate |  |  | 10 | 24 |  | 2010-06-03 14:24 | 2010-06-17 14:24 | 2007-10-01 | 2010-06-03 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [6 empty] | 80 | [6 empty] | Experience
26 |  | Prep Procurement Specs |  |  | 10 | 25 |  | 2010-06-17 14:24 | 2010-07-01 14:24 | 2007-10-01 | 2010-06-17 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [13 empty] | Experience
27 |  | FDR Prep |  |  | 10 | 26 |  | 2010-07-01 14:24 | 2010-07-15 14:24 | 2007-10-01 | 2010-07-01 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [13 empty] | Experience
28 |  | CONDUCT FDR |  |  | 2 |  | 2010-10-01 | 2010-10-01 | 2010-10-03 19:12 | 2010-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | Experience
29 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
30 |  | Procurement | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
31 |  | Cryo parts | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
32 |  |  | Prep Requisition and procurement package |  | 1 | 28 | 2011-01-01 | 2011-01-01 | 2011-01-02 09:36 | 2011-01-01 | 2010-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
33 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 32 |  | 2011-01-02 09:36 | 2011-01-03 19:12 | 2007-10-01 | 2011-01-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
34 |  |  | Procurement lead time (1) |  | 30 | 33 |  | 2011-01-03 19:12 | 2011-02-14 19:12 | 2007-10-01 | 2011-01-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
35 |  |  | AWARD |  | 1 | 34 |  | 2011-02-14 19:12 | 2011-02-16 04:48 | 2007-10-01 | 2011-02-14 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
36 |  |  | Fabricate or delivery |  | 90 | 35 |  | 2011-02-16 04:48 | 2011-06-22 04:48 | 2007-10-01 | 2011-02-16 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
37 |  | Pipe and misc. | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
38 |  |  | Prep Requisition and procurement package |  | 2 | 28 | 2011-01-01 | 2011-01-01 | 2011-01-03 19:12 | 2011-01-01 | 2010-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
39 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 38 |  | 2011-01-03 19:12 | 2011-01-05 04:48 | 2007-10-01 | 2011-01-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
40 |  |  | Procurement lead time (1) |  | 30 | 39 |  | 2011-01-05 04:48 | 2011-02-16 04:48 | 2007-10-01 | 2011-01-05 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
41 |  |  | AWARD |  | 1 | 40 |  | 2011-02-16 04:48 | 2011-02-17 14:24 | 2007-10-01 | 2011-02-16 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
42 |  |  | Fabricate or delivery |  | 30 | 41 |  | 2011-02-17 14:24 | 2011-03-31 14:24 | 2007-10-01 | 2011-02-17 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Experience
43 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
44 |  | Fab/Assembly |  | Denault | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
45 |  | Fab/Assy Procedure | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
46 |  | Shop Fabrication | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
47 |  | Assembly | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
48 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
49 |  | Installation |  | Denault | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
50 |  | Installation Procedure | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
51 |  | Machine Installation | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
52 |  | PTP Testing | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  |  | Engineering |  | 500 |  | 2011-01-01 | 2011-01-01 | 2012-12-01 | 2011-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 80 |  |  |  | 2400 | [13 empty] | Experience
|  |  | Engineering Support | 800 Hours | 500 |  | 2011-01-01 | 2011-01-01 | 2012-12-01 | 2011-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 80 | [27 empty] | Experience
|  |  | Drafting Support |  | 500 |  | 2011-01-01 | 2011-01-01 | 2012-12-01 | 2011-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 800 | [21 empty] | Experience
54 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
56 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
57 |  |  | Helium Transfer Lines |  | 160 |  | 2011-10-01 | 2011-10-01 | 2012-05-12 | 2011-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 480 |  |  | 3200
58 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 0
59 |  |  | Nitrogen Transfer Lines |  | 120 |  | 2011-11-15 | 2011-11-15 | 2012-05-01 | 2011-11-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 210 |  |  | 1400
60 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
61 |  |  | SF6 Transfer Lines |  | 30 |  | 2012-04-01 | 2012-04-01 | 2012-05-13 | 2012-04-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10 | [12 empty] | 82.5 |  |  | 550 | [11 empty] | Vendor Pricing
62 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
63 |  |  | HVE Water Lines |  | 65 |  | 2011-11-15 | 2011-11-15 | 2012-02-14 | 2011-11-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 100 | [12 empty] | 195 |  |  | 1300 | [11 empty] | Vendor Pricing
64 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
65 |  |  | Ion Dump Water Lines |  | 100 |  | 2011-07-01 | 2011-07-01 | 2011-11-18 | 2011-07-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 135 | [12 empty] | 435 |  |  | 2900 | [11 empty] | Vendor Pricing
66 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
67 |  |  | Ion Source Water Lines |  | 80 |  | 2011-09-01 | 2011-09-01 | 2011-12-22 | 2011-09-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 90 | [12 empty] | 315 |  |  | 2100 | [11 empty] | Vendor Pricing
72 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
73 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
74 |  |  | Vacuum Lines |  | 30 |  | 2012-05-01 | 2012-05-01 | 2012-06-12 | 2012-05-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 85 | [12 empty] | 86.25 |  |  | 575 | [11 empty] | Vendor Pricing
84 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
85 |  |  | Stack 8 Vacuum Lines |  | 30 |  | 2011-06-01 | 2011-06-01 | 2011-07-13 | 2011-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 50 | [12 empty] | 60 |  |  | 400 | [11 empty] | Vendor Pricing
92 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
93 |  |  | Gas System |  | 25 |  | 2010-06-01 | 2010-06-01 | 2010-07-06 | 2010-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 15 | [12 empty] | 56.25 |  |  | 375 | [11 empty] | Vendor Pricing
97 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
98 |  |  | Legs |  | 12 |  | 2011-06-01 | 2011-06-01 | 2011-06-17 19:12 | 2011-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10 | [12 empty] | 30 |  |  | 200
102 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | Vendor Pricing
103 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
104 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
105 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
106 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
107 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
108 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
109 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
110 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
111 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
112 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
113 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
114 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
115 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
116 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
117 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
118 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
119 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
120 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
121 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
122 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
123 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
124 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
125 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
126 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
127 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
128 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
129 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
130 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
131 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
132 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
133 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
134 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
135 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
136 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
137 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
138 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
139 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
140 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
141 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
142 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [13 empty] | 575 | 0 | 0 | 0 | 0 | 280 | 1360 | 0 | 0 | 0 | 400 | 0 | 0 | 1950 | 3708 | 0 | 13000 | 0 | 0 | 0 | 0 | 160 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 3328.1944 | [10 empty] | 704.95 | 0 | 0 | 0 | 0 | 52.808 | 169.864 | 0 | 0 | 0 | 69.36 | 0 | 0 | 164.58 | 592.9092 | 0 | 1549.6 | 0 | 0 | 0 | 0 | 24.1232 | 0 | 0
| Notes: | [24 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [6 empty] | Weeks | [16 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [5 empty] | 3 | [16 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [5 empty] | 5 | [16 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [5 empty] | 8 | [16 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [5 empty] | 9 | [16 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 1180
Job Number: |  | 2450
Job Title: |  | NSTX BL2 Services
Job Manager: |  | M. Denault
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X
| Design Complexity |  |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Heat Load may be too high, remake He lines | [8 empty] | 50 | 50 | 10 | 55
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1180
Job Number: | 2450
Job Title: | NSTX BL2 Services
Job Manager: | M. Denault
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Pipe |  |  | Vendor Pricing
Parts |  |  | Vendor Pricing
MISC |  |  | Experience
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1 | 0 | #DIV/0!
|  | 2 - Engineering Judgement/Experience |  | 2 | 0 | #DIV/0!
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | #DIV/0!
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | #DIV/0!
|  | 5 - Prototype Data/Test Results |  | 5 | 0 | #DIV/0!
|  | 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | #DIV/0!
|  | 7 - Placed Contracts |  | 7 | 0 | #DIV/0!
|  | 8 - Actual experience for NCSX Work |  | 8 | 0 | #DIV/0!
|  | 9 - Other |  | 9 | 0 | #DIV/0!
|  |  | TOTALS |  | 0 | #DIV/0!

## Breakdown of work
|  |  |  | SCHEDULE | FY09$K | HOURS (priced at FY09 rates)
USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT | 1.308 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | M&S (41) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer)
P3 cross ref (optinal) |  |  |  |  | 1.226 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77
Helium Transfer Lines
|  | Welding |  | 60 | [12 empty] | 1440
|  | Machining |  | 25 | [12 empty] | 400
|  | Insulation |  | 25 | [12 empty] | 400
|  | Leak Checking |  | 12 | [12 empty] | 288
|  | Scaffold |  | 5 | [12 empty] | 80
|  | High Lift Operator |  | 10 | [12 empty] | 80
|  | Wall Hanger - Platform |  | 10 | [12 empty] | 240
|  | Penetrations |  | 12 | [12 empty] | 192
|  | Misc |  |  | 8
Nitrogen Transfer Lines
|  | Welding |  | 18 | [12 empty] | 432
|  | Machining |  | 8 | [12 empty] | 128
|  | Insulation |  | 8 | [12 empty] | 128
|  | Leak Checking |  | 10 | [12 empty] | 240
|  | Scaffold |  | 5 | [12 empty] | 80
|  | High Lift Operator |  | 10 | [12 empty] | 80
|  | Wall Hanger - Platform |  | 5 | [12 empty] | 80
|  | Penetrations |  | 12 | [12 empty] | 192
|  | Misc |  |  | 8
SF6 Transfer Lines
|  | Welding |  | 10 | [12 empty] | 240
|  | Machining |  | 3 | [12 empty] | 48
|  | Leak Checking |  | 2 | [12 empty] | 32
|  | Scaffold |  | 1 | [12 empty] | 16
|  | Wall Hanger - Platform |  | 5 | 2 | [11 empty] | 80
|  | Pipe |  |  | 5
|  | Penetrations |  | 6 | [12 empty] | 96
|  | Misc |  |  | 2
HVE Water Lines
|  | Welding |  | 30 | [12 empty] | 720
|  | Machining |  | 3 | [12 empty] | 48
|  | Leak Checking |  | 2 | [12 empty] | 32
|  | Scaffold |  | 7 | [12 empty] | 112
|  | Wall Hanger - Platform |  | 5 | 5 | [11 empty] | 80
|  | Pipe |  |  | 45
|  | Penetrations |  | 6 | [12 empty] | 96
|  | Bringing Pumps Online |  | 10 | 40 | [11 empty] | 160
|  | Misc |  |  | 5
Ion Dump Water Lines
|  | Welding |  | 70 | [12 empty] | 1680
|  | Helper |  | 70 | [12 empty] | 560
|  | Machining |  | 3 | [12 empty] | 48
|  | Leak Checking |  | 2 | [12 empty] | 32
|  | Scaffold |  | 5 | [12 empty] | 80
High Lift Operator
|  | Wall Hanger - Platform |  |  | 5
|  | Pump Install |  | 10 | 20 | [11 empty] | 160
|  | Pipe |  |  | 50
|  | Penetrations |  | 6 | [12 empty] | 96
|  | Misc |  |  | 5
Ion Source Water Lines
|  | Welding |  | 50 | [12 empty] | 1200
|  | Helper |  | 50 | [12 empty] | 400
|  | Machining |  | 3 | [12 empty] | 48
|  | Leak Checking |  | 2 | [12 empty] | 32
|  | Scaffold |  | 5 | [12 empty] | 80
|  | Wall Hanger - Platform |  |  | 5
|  | Pump Install |  | 10 | 25 | [11 empty] | 160
|  | Pipe |  |  | 45
|  | Penetrations |  | 6 | [12 empty] | 96
|  | Misc |  |  | 5
Vacuum Lines
|  | Welding |  | 15 | [12 empty] | 360
|  | Machining |  | 7 | [12 empty] | 112
|  | Leak Checking |  | 2 | [12 empty] | 32
|  | Scaffold |  | 1 | [12 empty] | 16
|  | Wall Hanger - Platform |  | 2 | 2 | [11 empty] | 32
|  | Parts (Mark) |  |  | 60
|  | Pipe |  |  | 15
Penetrations
|  | Misc |  |  | 3
|  | Stack 8 Vacuum Lines |  |  | 50
|  | Duct Work |  | 15 | [12 empty] | 240
|  | Scaffold |  | 3 | [12 empty] | 48
|  | Wall Hanger - Platform |  | 3 | 3 | [11 empty] | 48
|  | Penetrations |  | 3 | [12 empty] | 48
|  | Trunks |  |  | 5
|  | Misc |  |  | 2
Gas System
|  | Remove |  | 5 | [12 empty] | 80
|  | Install |  | 15 | 15 | [11 empty] | 240
|  | Penetrations |  | 3 | [12 empty] | 48
|  | Legs |  |  | 8
|  | Construction |  | 6 | [12 empty] | 96
|  | Move |  | 1 | [12 empty] | 16
|  | Weld (Attach) |  | 5 | [12 empty] | 80
| TOTALS |  |  |  | 443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12408 | 0 | 0 | 0 | 0 | 0
TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 2022.1516 | 543.118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1479.0336 | 0 | 0 | 0 | 0 | 0
Notes: | [10 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: | [9 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items | [8 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items | [8 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) | [8 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts | [8 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other