## Tab A Description
Work Approval Form (WAF)
Cost Center: 1180 ****
Job Number: 2460
Job Title: NBI Armor
Job Manager: Craig Priniski
Description:
Design, Fabrication, and Installation of upgraded and relocated neutral beam armor including cooling and instrumentation work
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: 1180 ****
Job Number: 2460
Job Title: NBI Armor
Job Manager: Craig Priniski
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY09$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
numb | P3 cross ref (optinal) | [14 empty] | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
|  | Physics Requirements | [7 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55
[10 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55
|  | Conceptual Design | [7 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55
1 |  | Armor Layout |  | PRINISKI | 2 |  |  | 2009-10-23 12:55 | 2009-10-26 08:07 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 8 |  |  |  |  | 8 | [7 empty] | 16
2 |  | Thermal Annalysis of Second Beam |  | TRESEMER | 10 | 1 | 2009-10-26 08:07 | 2009-10-26 08:07 | 2009-11-09 08:07 | 2009-10-26 08:07 | 2009-10-26 08:07 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 40 | [7 empty] | 40
3 |  | CD of Supports and plates |  | PRINISKI | 15 | 2 | 2009-08-10 | 2009-08-10 | 2009-08-31 | 2009-08-10 | 2009-11-09 08:07 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 60 |  |  |  |  | 60 | [7 empty] | 120
4 |  | Tile modifications |  | TRESEMER | 10 | 3 | 2009-07-30 | 2009-07-30 | 2009-08-13 | 2009-07-30 | 2009-08-31 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 40 |  |  |  |  | 40 | [7 empty] | 80
5 |  | Molly "Backstop" Design |  | TRESEMER | 5 | 4 | 2009-09-20 | 2009-09-20 | 2009-09-27 | 2009-09-20 | 2009-08-13 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 20 |  |  |  |  | 20 | [7 empty] | 40
7 |  | Bay H Port Cover Design |  | PRINISKI-WINKLEMAN | 10 | 4 | 2009-09-15 | 2009-09-15 | 2009-09-29 | 2009-09-15 | 2009-08-13 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 40 |  |  |  |  | 40 | [7 empty] | 80
6 |  | PPPL CDR |  | PRINISKI | 1 | 5 | 1900-09-21 | 1900-09-21 | 1900-09-22 09:36 | 1900-09-21 | 2009-09-27 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
7 |  | Prep for PU CDR |  | PRINISKI | 5 | 6 | 2009-09-15 | 2009-09-15 | 2009-09-22 | 2009-09-15 | 1900-09-22 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 40 |  |  |  |  | 40 | [7 empty] | 80
8 |  | Prep for DOE CDR |  | PRINISKI | 8 | 7 |  | 2009-10-23 12:55 | 2009-11-03 17:43 |  | 2009-09-22 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 16 |  |  |  |  | 16 | [7 empty] | 32
0
|  | Preliminary Design | [7 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
9 |  | CDR Chit Resolution |  | PRINISKI | 30 | 8 | 2009-11-03 | 2009-11-03 | 2009-12-15 |  | 2009-11-03 17:43 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 20 |  |  |  |  | 62 | [7 empty] | 82
10 |  | FMEA Analysis |  | PRINISKI | 10 | 9 |  | 2009-12-15 | 2009-12-29 | 2009-10-23 12:55 | 2009-12-15 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [6 empty] | 30 | [5 empty] | 50 | [7 empty] | 80
11 |  | Prepare NEPA Form |  | PRINISKI | 1 | 9 |  | 2009-12-15 | 2009-12-16 09:36 | 2009-10-23 12:55 | 2009-12-15 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 2 | [7 empty] | 2
12 |  | Update Cost & Schedule Estimate |  | PRINISKI | 5 | 9 |  | 2009-12-15 | 2009-12-22 | 2009-10-23 12:55 | 2009-12-15 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 24 | [7 empty] | 24
13 |  | Design Drawings |  | PRINISKI | 60 | 9 |  | 2009-12-15 | 2010-03-09 | 2009-10-23 12:55 | 2009-12-15 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 96 |  |  |  |  | 32 | [7 empty] | 128
14 |  | PDR Prep |  | PRINISKI | 40 | 13 | 2010-06-07 | 2010-06-07 | 2010-08-02 | 2010-06-07 | 2010-03-09 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 16 |  |  |  |  | 40 | [7 empty] | 56
15 |  | CONDUCT PDR |  | PRINISKI | 1 | 14 | 2010-08-04 | 2010-08-04 | 2010-08-05 09:36 | 2010-08-04 | 2010-08-02 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 8 | [7 empty] | 8
[10 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
[10 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
|  | Final Design | [7 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
16 |  | Disposition PDR Chits |  | PRINISKI | 20 | 15 |  | 2010-08-05 09:36 | 2010-09-02 09:36 | 2009-10-23 12:55 | 2010-08-05 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 16 |  |  |  |  | 60 | [7 empty] | 76
17 |  | Design Drawings |  | PRINISKI | 18 | 16 |  | 2010-09-02 09:36 | 2010-09-27 14:24 | 2009-10-23 12:55 | 2010-09-02 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 80 |  |  |  |  | 32 | [7 empty] | 112
18 |  | Update Cost & Schedule Estimate |  | PRINISKI | 10 | 16 |  | 2010-09-02 09:36 | 2010-09-16 09:36 | 2009-10-23 12:55 | 2010-09-02 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 16 | [7 empty] | 16
19 |  | Prep Procurement Specs |  | PRINISKI | 20 | 18 |  | 2010-09-16 09:36 | 2010-10-14 09:36 | 2009-10-23 12:55 | 2010-09-16 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 40 | [7 empty] | 40
20 |  | FDR Prep |  | PRINISKI | 10 | 19 | 2011-01-03 | 2011-01-03 | 2011-01-17 | 2011-01-03 | 2010-10-14 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [7 empty] | 6 |  |  |  |  | 30 | [7 empty] | 36
21 |  | CONDUCT FDR |  | PRINISKI | 1 | 20 | 2011-02-08 | 2011-02-08 | 2011-02-09 09:36 | 2011-02-08 | 2011-01-17 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 8 | [7 empty] | 8
[10 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
|  | Procurement | [7 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
22 |  | Item 1: Armor Tiles ATJ & Poss. CFC |  | PRINISKI | [5 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 |  | 35 | [18 empty] | 0
23 |  |  | Prep Requisition and procurement package | PRINISKI | 5 | 21 |  | 2011-02-09 09:36 | 2011-02-16 09:36 | 2009-10-23 12:55 | 2011-02-09 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 20 | [7 empty] | 20
24 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 | 23 |  | 2011-02-16 09:36 | 2011-02-17 19:12 | 2009-10-23 12:55 | 2011-02-16 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 4 | [7 empty] | 4
25 |  |  | Procurement lead time (1) | PRINISKI | 25 | 24 |  | 2011-02-17 19:12 | 2011-03-24 19:12 | 2009-10-23 12:55 | 2011-02-17 19:12 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
26 |  |  | AWARD | PRINISKI | 1 | 25 |  | 2011-03-24 19:12 | 2011-03-26 04:48 | 2009-10-23 12:55 | 2011-03-24 19:12 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
27 |  |  | Fabricate or delivery | PRINISKI | 60 | 26 |  | 2011-03-26 04:48 | 2011-06-18 04:48 | 2009-10-23 12:55 | 2011-03-26 04:48 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
28 |  | Bay-H Port Cover - Armor Suppotts |  | PRINISKI | [5 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 |  | 50 | [18 empty] | 0
29 |  |  | Prep Requisition and procurement package | PRINISKI | 2 | 24 |  | 2011-02-17 19:12 | 2011-02-20 14:24 | 2009-10-23 12:55 | 2011-02-17 19:12 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 8 | [7 empty] | 8
30 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 | 29 |  | 2011-02-20 14:24 | 2011-02-22 | 2009-10-23 12:55 | 2011-02-20 14:24 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 4 | [7 empty] | 4
31 |  |  | Procurement lead time (1) | PRINISKI | 25 | 30 |  | 2011-02-22 | 2011-03-29 | 2009-10-23 12:55 | 2011-02-22 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
32 |  |  | AWARD | PRINISKI | 1 | 31 |  | 2011-03-29 | 2011-03-30 09:36 | 2009-10-23 12:55 | 2011-03-29 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
33 |  |  | Fabricate or delivery | PRINISKI | 30 | 32 |  | 2011-03-30 09:36 | 2011-05-11 09:36 | 2009-10-23 12:55 | 2011-03-30 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
[10 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
33 |  | Armor Removal |  | PRINISKI | [5 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
34 |  | Procedure |  | PRINISKI | 20 | 21 |  | 2011-02-09 09:36 | 2011-03-09 09:36 | 2009-10-23 12:55 | 2011-02-09 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 70 | [7 empty] | 70
35 |  | In Vessel Work Remove Armor, Remove and Save Bay H port |  | PRINISKI | 30 | 21 | 2011-08-20 | 2011-08-20 | 2011-10-01 | 2011-08-20 | 2011-02-09 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 40 | 200 | [6 empty] | 240
36 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
37 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
38 |  | Installation |  | PRINISKI | [5 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 |  | 6 | [18 empty] | 0
39 |  | Installation Procedure |  | PRINISKI | 20 | 21 |  | 2011-02-09 09:36 | 2011-03-09 09:36 | 2009-10-23 12:55 | 2011-02-09 09:36 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 90 | [7 empty] | 90
40 |  | Refurbishment of NB Armor |  | PRINISKI | 60 | 35 |  | 2011-10-01 | 2011-12-24 | 2009-10-23 12:55 | 2011-10-01 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 24 | 200 | [6 empty] | 224
41 |  | Machine Installation (Supports, Armor, Port Cover) |  | PRINISKI | 30 | 40 |  | 2011-12-24 | 2012-02-04 | 2009-10-23 12:55 | 2011-12-24 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [12 empty] | 10 | 24 | [6 empty] | 34
42 |  | PTP Testing |  | PRINISKI | 3 | 41 |  | 2012-02-04 | 2012-02-08 04:48 | 2009-10-23 12:55 | 2012-02-04 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
43 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
44 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
45 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
46 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
47 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
48 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
49 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
50 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
51 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
52 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
53 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
54 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
55 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
56 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
57 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
58 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
59 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
60 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
61 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
62 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
63 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
64 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
65 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
66 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
67 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
68 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
69 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
70 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
71 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
72 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
73 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
74 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
75 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
76 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
77 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
78 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
79 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
80 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
81 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
82 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
83 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
84 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
85 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
86 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
87 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
88 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
89 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
90 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
91 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
92 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
93 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
94 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
95 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
96 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
97 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
98 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
99 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
100 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
101 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
102 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
103 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
104 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
105 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
106 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
107 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
108 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
109 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
110 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
111 | [9 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
[10 empty] | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | 2009-10-23 12:55 | [20 empty] | 0
0
|  | TOTALS | [13 empty] | 91 | 0 | 0 | 0 | 0 | 30 | 458 | 0 | 0 | 0 | 0 | 938 | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 1850
91000
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 390.6217 | [10 empty] | 111.02 | 0 | 0 | 0 | 0 | 5.565 | 57.2912 | 0 | 0 | 0 | 0 | 155.1171 | 61.6284 | 0 | 0 | 0 | 0 | 0 | 0 | 92850
| Notes: | [23 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [6 empty] | Weeks | [15 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [5 empty] | 3 | [15 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [5 empty] | 5 | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [5 empty] | 8 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [5 empty] | 9 | [15 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: 1180 ****
Job Number: 2460
Job Title: NBI Armor
Job Manager: Craig Priniski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended