## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1180
Job Number: | 2470
Job Title: | NB Power System
Job Manager: | S. Ramakrishnan
Description:
NB2 is planned to be powered from the TFTR NB4 A,B, & C line ups. The electrical equipment in these line ups will be reactivated. The TFTR NB4 HVEs will be relocated to the NSTX Test Cell. New triax cables will be installed with terminations from the Modregs to the HVEs. New Decel coaxial cables will be installed from the Decel supplies to the Sources. The Arc, Filament, Magnet , and the 208 feeds, to HVEs cables, will be spliced in the TFTR Test Cell basement to new cabling designed and installed from the TFTR Basement to the NSTX Test Cell. The fiber cables also will be spliced with additional lengths recovered from other TFTR line ups. The AC auxiliaries and Grounding for the NB2 will be designed and installed.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1180****2470 |  |  | See cost spreadsheet attached separately
Job Number:
| Job Title: |  |  | NB Power System
| Job Manager: |  |  | S. Ramakrishnan
Estimate (user input)
[5 empty] | SCHEDULE | [11 empty] | FY09$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
numb | P3 cross ref (optinal) | [15 empty] | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
1 |  | Physics Requirements | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
2 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
3 |  | Conceptual Design | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
4 |  | PREPARE WORK PLANNING FORM | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
5 |  | Prep System Description | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
6 |  | Prep System Requirements | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
7 |  | R&D | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
8 |  | Ananlysis | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
9 |  | CDR | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
10 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
11 |  | Preliminary Design | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
12 |  | Thermal Analysis | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
13 |  | Seismic Analysis | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
14 |  | FMEA Analysis | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
15 |  | Prepare NEPA Form | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
16 |  | Update Cost & Schedule Estimate | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
17 |  | Design Drawings | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
18 |  | PDR Prep | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
19 |  | CONDUCT PDR | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
20 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
21 |  | Final Design | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
22 |  | Disposition PDR Chits | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
23 |  | Design Drawings | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
24 |  | Update Analyses | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
25 |  | Update Cost & Schedule Estimate | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
26 |  | Prep Procurement Specs | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
27 |  | FDR Prep | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
28 |  | CONDUCT FDR | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
29 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
30 |  | Procurement | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
31 |  | Item 1: | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
32 |  |  | Prep Requisition and procurement package | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
33 |  |  | SUBMIT REQ TO PROCUREMENT | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
34 |  |  | Procurement lead time (1) | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
35 |  |  | AWARD | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
36 |  |  | Fabricate or delivery | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
37 |  | Item 2: | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
38 |  |  | Prep Requisition and procurement package | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
39 |  |  | SUBMIT REQ TO PROCUREMENT | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
40 |  |  | Procurement lead time (1) | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
41 |  |  | AWARD | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
42 |  |  | Fabricate or delivery | [7 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
43 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
44 |  | Fab/Assembly | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
45 |  | Fab/Assy Procedure | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
46 |  | Shop Fabrication | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
47 |  | Assembly | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
48 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
49 |  | Installation | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
50 |  | Installation Procedure | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
51 |  | Machine Installation | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
52 |  | PTP Testing | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
53 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
54 |  | OTHER TASKS | [8 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
55 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
56 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
57 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
58 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
59 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
60 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
61 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
62 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
63 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
64 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
65 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
66 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
67 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
68 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
69 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
70 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
71 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
72 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
73 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
74 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
75 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
76 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
77 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
78 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
79 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
80 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
81 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
82 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
83 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
84 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
85 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
86 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
87 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
88 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
89 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
90 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
91 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
92 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
93 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
94 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
95 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
96 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
97 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
98 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
99 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
100 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
101 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
102 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
103 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
104 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
105 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
106 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
107 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
108 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
109 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
110 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
111 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
112 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
113 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
114 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
115 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
116 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
117 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
118 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
119 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
120 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
121 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
122 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
123 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
124 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
125 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
126 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
127 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
128 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
129 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
130 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
131 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
132 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
133 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
134 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
135 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
136 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
137 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
138 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
139 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
140 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
141 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
142 | [10 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
[11 empty] | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26 | 2009-10-15 10:26
|  | TOTALS | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [24 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [7 empty] | Weeks | [15 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [6 empty] | 3 | [15 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [6 empty] | 5 | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [6 empty] | 8 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [6 empty] | 9 | [15 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 1180****2470
Job Number:
Job Title: |  | NB Power System
Job Manager: |  | S. Ramakrishnan
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | x
| Design Complexity |  | x
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact |  | Remarks
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Old Varian tubes are being used and may need tune up |  |  |  | low | Based on further assessment this risk has been retied since we have enough spares. |  |  | Budgetary quotes received for Triax and other cables and used in estimate
2 | Old 100 micron fiber cables that are proposed to be used may not be in good condition |  |  |  | low | Test a prototype with a 62.5 micron cable fused to 100 micron cable |  |  | Past experience in installing the NB1 line up for NSTX |  | 50
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## NSTX NB2 PWR SYST COST
NSTX NB2 Power System | [14 empty] | M&S | [5 empty] | Design/ Procurement |  | Inst |  |  |  | Commissioning |  |  | Line Total | Contingency |  |  |  | Total Cost
2009-07-28 | 40073 |  |  |  |  | Start | Finish | Start date | Finish date | Mult | Qty | excl factor | Qnty | Units | Qty | Units | Unit Cost | Cost | Spare Units | Spare Cost | EEEM | Dm | EEEM | EESM | EETB | SC | EEEM | EESM | EETB |  | Tech | Cost | Schedule | Total
[17 empty] | (k$/unit) | ($K) |  | ($K) | (md) | (md) | (md) | (md) | (md) | ($K) | (md) | (md) | (md) | ($K) | (%) | (%) | (%) | (%) | ($K)
21- AC Auxiliaries | 93.9113 | 331.6676
|  | 93.9113 | 331.6676
| 211 - AC Aux |  | PPs,etc. |  |  | 2011-10-11 | 2012-06-11 |  |  | 1 |  | 1 |  |  | 1 | lot | 20 | 20 |  | 1 | 12 | 30 | 5 | 5 | 50 | 25 | 1 | 2 | 2 | 150.1736 | 0 | 0 | 0 | 0 | 150.1736
| 212 - Grounding |  | Misc. grounding |  |  | 2011-10-11 | 2012-06-11 |  |  | 1 |  | 1 |  |  | 1 | lot | 10 | 10 |  |  | 5 | 20 | 3 | 2 | 40 | 15 | 1 | 2 | 2 | 93.9113 | 0 | 0 | 0 | 0 | 93.9113
22 - Reactivation | 237.7564 | 237.7564
| Reactivation of Equipment | 237.7564 | 237.7564 | [6 empty] | 1 |  | 1 | [22 empty] | 0
|  |  | Switchyard | Maintenance | Reactivation | 2011-04-11 | 2011-10-11 |  |  | 1 |  | 1 |  |  | 3 |  | 2 | 6 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 |  | 5 | 10 | 45 | 58.4101 | 0 | 0 | 0 | 0 | 58.4101
|  |  | Surge Room | Maintenance | Reactivation | 2011-04-11 | 2011-10-11 |  |  | 1 |  | 1 |  |  | 3 |  | 3 | 9 | 1 | 3 | 0.5 | 1 | 0 | 10 | 24 |  | 5 | 10 | 15 | 70.1127 | 0 | 0 | 0 | 0 | 70.1127
|  |  | Mod-Reg | Maintenance | Reactivation | 2011-04-11 | 2011-10-11 |  |  | 1 |  | 1 |  |  | 3 |  | 1.5 | 4.5 | 1 | 1.5 | 0.5 | 1 | 0 | 0 | 0 |  | 5 | 10 | 20 | 39.6971 | 0 | 0 | 0 | 0 | 39.6971
|  |  | Arc/Filament/Magnet | Maintenance | Reactivation | 2011-04-11 | 2011-10-11 |  |  | 1 |  | 1 |  |  | 3 |  | 1 | 3 | 1 | 1 | 0.5 | 1 | 0 | 0 | 0 |  | 5 | 6 | 18 | 31.6784 | 0 | 0 | 0 | 0 | 31.6784
|  |  | LCC | Maintenance | Reactivation | 2011-04-11 | 2011-10-11 |  |  | 1 |  | 1 |  |  | 3 |  | 1 | 3 | 1 | 1 | 0.5 | 1 | 0 | 0 | 0 |  | 5 | 10 | 20 | 37.8581 | 0 | 0 | 0 | 0 | 37.8581
24 - Cabling | 1788.2385 | 1876.4288
|  | 1788.2385 | 1876.4288
|  | Penetrations | Misc |  |  | 2011-09-11 | 2011-09-30 |  |  | 1 |  | 1 | 5 |  | 5 |  | 1 | 5 |  | 0 | 1 | 5 | 1 | 4 | 8 | 15 |  |  |  | 41.9186 | 0 | 0 | 0 | 0 | 41.9186
|  | Removing cabling | Misc |  |  | 2011-06-11 | 2011-11-11 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | 5 | 15 | 1 | 5 | 15 |  | 2 | 2 | 5 | 46.2717 | 0 | 0 | 0 | 0 | 46.2717
|  | 4/C-500mcm Arc/ Fil. cables * | Six (6) Cables |  |  | 2012-01-15 | 2012-05-15 |  |  | 1 |  | 1 | 3 |  | 1800 | ft | 0.03 | 162 |  | 0 | 5 | 15 | 2 | 10 | 15 |  | 2 | 2 | 5 | 252.3273 | 0 | 0 | 0 | 0 | 252.3273
|  | 4/C- 500 mcm Magnet cables* | Three (3) Cables |  |  | 2012-01-15 | 2012-05-15 |  |  | 1 |  | 1 | 3 |  | 900 | ft | 0.03 | 81 |  | 0 | 5 | 15 | 2 | 10 | 15 |  | 2 | 2 | 5 | 153.0213 | 0 | 0 | 0 | 0 | 153.0213
|  | HVDC Triax cables** | Three (3) Cables |  |  | 2012-01-15 | 2012-05-15 |  |  | 1 |  | 1 | 3 |  | 310 | ft | 0.11 | 102.3 |  | 0 | 5 | 15 | 2 | 10 | 15 | 5 | 10 | 10 | 20 | 216.3002 | 0 | 0 | 0 | 0 | 216.3002
|  | HVDC Triax cables terminations | Six (6) terminations |  |  | 2012-01-15 | 2012-05-15 |  |  | 1 |  | 1 | 1 |  | 6 | unit | 5 | 30 |  | 0 | 5 | 15 | 2 | 10 | 15 | 20 | 10 | 10 | 20 | 146.0504 | 0 | 0 | 0 | 0 | 146.0504
|  | 4-C #8 ,208V Cables for NB * | Three (3) Cables |  |  | 2012-01-15 | 2012-05-15 |  |  | 1 |  | 1 | 3 |  | 900 | ft | 0.01 | 27 |  | 0 | 5 | 15 | 2 | 10 | 15 |  | 2 | 2 | 5 | 86.8173 | 0 | 0 | 0 | 0 | 86.8173
|  | RG 218U Decel Cables* | Three (3) cables |  |  | 2012-01-15 | 2012-05-15 |  |  | 1 |  | 1 | 3 |  | 550 | ft | 0.006 | 9.9 |  | 0 | 5 | 15 | 2 | 10 | 15 |  | 2 | 2 | 5 | 65.8527 | 0 | 0 | 0 | 0 | 65.8527
|  | 8 channel Fiber Cables | Eighteen (18) Cables |  |  | 2012-01-15 | 2012-05-15 |  |  | 1 |  | 1 | [5 empty] | 10 |  | 0 | 5 | 15 | 2 | 40 | 40 |  | 2 | 2 | 5 | 119.0725 | 0 | 0 | 0 | 0 | 119.0725
|  | Fiber Cables | Prototype test of fusion splices |  |  | 2012-01-15 | 2012-05-15 |  |  | 1 |  | 1 | [5 empty] | 0.3 |  | 0 | 1 | 1 | 1 | 5 | 5 |  | 0.5 | 1 | 2 | 16.7244 | 0 | 0 | 0 | 0 | 16.7244
|  | Raceways/ installation/pulling/termintation | 1 lot |  |  | 2012-01-15 | 2012-05-15 |  |  | 1 |  | 1 | [5 empty] | 30 |  | 0 | 5 | 15 | 2 | 40 | 40 | 480 | 2 | 2 | 5 | 732.0725 | 0 | 0 | 0 | 0 | 732.0725
25 - Transmission Line | 116.9583 | 116.9583
|  | 116.9583 | 116.9583
|  |  | Install transmission line | [6 empty] | 1 |  | 1 |  |  | 3 |  | 3 | 9 |  | 0 | 3 | 15 | 2 | 15 | 25 | 35 | 2 | 2 | 4 | 116.9583 | 0 | 0 | 0 | 0 | 116.9583
[18 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
28- System Design and Integration | 259.3106 | 259.3106
|  | 188.7755 | 188.7755
|  |  | Design Drawings & Drawings changes , as-builts | New drawings & Misc. updates |  | 2009-08-15 | 2012-10-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 30; Design/ Procurement Dm: 40 | 77.0432 | 0 | 0 | 0 | 0 | 77.0432
|  |  | CDR Power system | power system |  | 2009-10-15 | 2009-10-30 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.3884 | 0 | 0 | 0 | 0 | 11.3884
|  |  | PDR Power system | power system |  | 2010-06-15 | 2010-07-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.3884 | 0 | 0 | 0 | 0 | 11.3884
|  |  | FDR Cabling | power system |  | 2010-12-01 | 2011-01-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.3884 | 0 | 0 | 0 | 0 | 11.3884
|  |  | Calculations | Calculations - documentation |  | 2010-11-01 | 2010-11-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5 | 7.032 | 0 | 0 | 0 | 0 | 7.032
| 552 - System Testing | 70.5351 | 70.5351
|  |  | Procedures PTPs, ISTPs | New Procedures |  | 2012-03-15 | 2012-05-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 10 | 15.7448 | 0 | 0 | 0 | 0 | 15.7448
|  |  |  | DC Hipots |  | 2012-04-15 | 2012-05-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Commissioning EEEM: 3; Commissioning EETB: 8 | 16.6509 | 0 | 0 | 0 | 0 | 16.6509
|  |  |  | Electrical Interlock Testing |  | 2012-04-15 | 2012-09-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 1; Commissioning EEEM: 3; Commissioning EETB: 8 | 11.0253 | 0 | 0 | 0 | 0 | 11.0253
|  |  |  | Kirk Key Interlock Testing |  | 2012-04-15 | 2012-09-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 1; Commissioning EEEM: 2; Commissioning EETB: 3 | 6.2441 | 0 | 0 | 0 | 0 | 6.2441
|  |  |  | Instrumentation Test & Calibration |  | 2012-04-15 | 2012-09-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 1; Commissioning EEEM: 2; Commissioning EETB: 2 | 5.5691 | 0 | 0 | 0 | 0 | 5.5691
|  |  |  | Control System Testing |  | 2012-04-15 | 2012-09-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 1; Commissioning EEEM: 3; Commissioning EETB: 3 | 7.6505 | 0 | 0 | 0 | 0 | 7.6505
|  |  |  | Coil Protection System Testing |  | 2012-04-15 | 2012-09-15 |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 1; Commissioning EEEM: 3; Commissioning EETB: 3 | 7.6505 | 0 | 0 | 0 | 0 | 7.6505
|  |  | TOTALS | [14 empty] | 522 |  | 9.5 | 134.5 | 276 | 29 | 186 | 337 | 595 | 79.5 | 87 | 230 | 2664.0039 |  |  |  |  | 2664.0039
IN MAN HOURS | [20 empty] | 1076 | 2208 | 232 | 1488 | 2696 |  | 636 | 696 | 1840
RATES FY09 | [16 empty] | M&S --> | 522 | Spares--> | 9.5 | Inst EETB: SC -->; Inst SC: 729.47
|  | FY2009 Hourly Rates | [27 empty] | ∑MD | Rate | $K | ∑FTE | Years | FTE/yr
EEEM | 1.4064 | 175.8 | 1.4064 | 1.368 |  |  | 1.4064 | [10 empty] | 639.972 |  |  | 429.6341 |  | 492.831 |  |  | 729.47 | 372.0969 | cross check | EEEM | 243 | 1.4064 | 341.7552 | 1.1045 | 4 | 0.27614
EESM | 1.2074 | 150.93 | 1.2074 | 1.16 |  |  | 1.2074 | [13 empty] | Commissioning EETB: EESM | 273 | 1.2074 | 329.6311 | 1.2409 | 2 | 0.62045
EETB | 0.67496 | 84.37 | 0.67496 | 0.64 |  |  | 0.67496 | [13 empty] | Design/ Procurement EEEM: 2664.0039; Commissioning EETB: EETB | 567 | 0.67496 | 382.7023 | 2.5773 | 2 | 1.2886
G&A (MHX) | 1.226 | 1.226 |  | 1.226 | [13 empty] | 2664.0039 |  |  | Commissioning EETB: EADM | 276 | 0.87128 | 240.4733 | 1.2545 | 3 | 0.41818
DM | 0.87128 | 108.91 | 0.87128 | 0.99 |  |  | 0.87128 | [13 empty] | Commissioning EETB: M&Sk$ | 522 | 1.226 | 639.972
[21 empty] | Commissioning EETB: Subcon | 595 | 1.226 | 729.47
Notes: | [20 empty] | Commissioning EETB: Total |  |  | 2664.0039
SCOPE COVERED
2 Sub-contract estimates based on bids and a projected increase of costs
4. Cost in 09 Dollars
5. SCHEDULE WILL AFFECT COST