## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1180
Job Number: | 2490
Job Title: | NTC Equipment Removals / Relocations
Job Manager: | Tony Langella
Description:
This scope covers the move of racks and diagnostics to clear space in the NSTX Test Cell for the second Neutral Beamline. Racks to be removed and re-installed in a new location are #419, 431-435, 440-445, 447-449, 488. Racks 456 and 489 will be removed and excessed. This scope also includes the fabrication and installation of five sections of platform at elevation 118' on the west side of the NTC to accomodate the racks being re-installed in the Test Cell. Racks #441-445 will be relocated to the Gallery east of the NTC. Diagnostics to be removed are those from the midplanes of Bay J and Bay K as well as those on the present pump duct. The diagnostics from Bay J will be re-installed ~5" outboard of their present position. IR windows and the Transmission Grating Spectrometer will be relocated to the new NB duct. Ion gages, filaments and the RGA will be relocated to the new pump duct under the NB2 duct. SPRED and LOWEUS will be relocated to Bay L. The Thomson Scattering Beam Dump Window will be relocated to between Bays K and L.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: |  |  | 1180
Job Number: |  |  | 2490
Job Title: |  |  | NTC Equipment Removals / Relocations
Job Manager: |  |  | Tony Langella
Removals and Re-installations for NB2 on NSTX
|  |  |  | Start | Duration | Crew Size | EMEM | EMSM | EMDM | EMTB | M&S
[5 empty] | days | persons | MD | MD | MD | MD | $K
Removal of Racks
419 | UCLA Reflectometer |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 4 | 2 |  | 1 |  | 8 | 0.1
431 - 435 | VV T/C & magnetics |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 15 | 2 |  | 4 |  | 30 | 0.1
436 - 439 | Firetip, High K |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 15 | 2 |  | 4 |  | 30 | 0.1
440 | SPREAD and VIPS |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 8 | 2 |  | 2 |  | 16 | 0.1
441 - 445 | VV ion gages, RGA |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 15 | 2 |  | 4 |  | 30 | 0.1
447 - 448 | Fiber Optics |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 5 | 2 |  | 2 |  | 10 | 0.1
449 | Glow Discharge |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 10 | 2 |  | 3 |  | 20 | 0.1
456 | XCS |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 7 | 2 |  | 2 |  | 14 | 0.1
488 | Deposition monitor, fast x-ray, NPA |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 7 | 2 |  | 2 |  | 14 | 0.1
489 | NPA |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 10 | 2 |  | 3 |  | 20 | 0.1
| PSI Camera |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 2 | 2 |  | 1 |  | 4 | 0.1
| Ultra Fast X-ray Camera |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 2 | 2 |  | 1 |  | 4 | 0.1
| Transmission Grating Spectrometer |  | Prepare procedure |  |  |  |  | 3
|  |  | Remove rack |  | 3 | 2 |  | 1 |  | 6 | 0.1
Removal of Equipment
From Bay J
| Two Gas Injectors |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 2 |  |  |  | 2 | 0.1
| Reflectometer |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 2 |  |  |  | 2 | 0.1
| Bolometer |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 2 |  |  |  | 2 | 0.1
| RF Probe |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 2 |  |  |  | 2 | 0.1
| S-Flip |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 2 |  |  |  | 2 | 0.1
| SSNPA |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 1 |  |  |  | 1 | 0.1
| Re-entrant Window |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 1 |  |  |  | 1 | 0.1
From Bay K
| High K Scattering |  | Prepare procedure |  |  |  | 5
|  |  | Remove |  | 10 | 4 |  |  |  | 40 | 0.1
| Fire Tips |  | Prepare procedure |  |  |  | 5
|  |  | Remove |  | 5 | 4 |  |  |  | 20 | 0.1
| PSI Camera |  | Prepare procedure |  |  |  | 3
|  |  | Remove |  | 4 | 4 |  |  |  | 16 | 0.1
| NPA |  | Prepare procedure |  |  |  | 5
|  |  | Remove |  | 10 | 4 |  |  |  | 40 | 0.1
| Ultra Fast X-ray Camera |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 1 |  |  |  | 1 | 0.1
| IR Windows for Camera |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 1 |  |  |  | 1 | 0.1
| Transmission Grating Spectrometer |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 1 |  |  |  | 1 | 0.1
From Bay L pump duct
| Vac Vessel Ion Gages, Filaments, Micro Ion Gages |  | Prepare procedure |  |  |  | 2
|  |  | Remove |  | 2 | 2 |  |  |  | 4 | 0.1
| X-ray Crystal Spectrometer |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 3 |  |  |  | 3 | 0.1
| SPRED |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 2 |  |  |  | 2 | 0.1
| RGA |  | Prepare procedure |  |  |  | 2
|  |  | Remove |  | 3 | 2 |  |  |  | 6 | 0.1
| LOWEUS |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 2 |  |  |  | 2 | 0.1
| MPTS Beam Dump Window |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 1 | 1 |  |  |  | 1 | 0.1
| Remove Pump Duct (incl turbos) |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 4 | 4 |  | 2 |  | 16 | 0.2
Miscellaneous Removals
| Gas Delivery Systems |  | Prepare procedure |  |  |  | 1
|  |  | Remove |  | 4 | 4 |  | 2 |  | 16 | 1
| Remove NW section of 109' platform |  | Prepare procedure |  |  |  | 2
|  |  | Remove |  | 6 | 4 |  | 3 |  | 24 | 6
| Convenience outlets |  | Prepare procedure |  |  |  | 5
|  |  | Relocate |  | 10 | 2 |  | 3 |  | 20 | 1
| Cat 3 and Cat 4 bus |  | Prepare procedure |  |  |  | 5
|  |  | Relocate |  | 5 | 2 |  | 2 |  | 10 | 2
| Lights, E-stops, fire alarms |  | Prepare procedure |  |  |  | 6
|  |  | Relocate |  | 13 | 2 |  | 4 |  | 26 | 3
| Glow Discharge splice box & discnts |  | Prepare procedure |  |  |  | 2
|  |  | Relocate |  | 2 | 2 |  | 1 |  | 4 | 1
Re-installation of Racks
| Reconfigure AC and Diagnostic Trays |  | Design |  |  |  |  | 6 | 45 |  | 16
|  |  | Prepare Procedure |  |  |  |  | 1 | 5
|  |  | Install |  |  |  |  | 8 |  | 60 | 1
419 | UCLA Reflectometer |  | Design |  |  |  |  | 2 | 17 |  | 2
|  |  | Prepare procedure |  |  |  |  | 1 | 3
|  |  | Install | [6 empty] | 12 | 0.2
431 - 435 | VV T/C & magnetics |  | Design |  |  |  |  | 6 | 45 |  | 10
|  |  | Prepare procedure |  |  |  |  | 1 | 5
|  |  | Install |  |  |  |  | 8 |  | 60 | 1
440 | SPRED |  | Design |  |  |  |  | 2 | 13 |  | 2
|  |  | Prepare procedure |  |  |  |  | 1 | 3
|  |  | Install | [6 empty] | 15 | 1.5
441 - 445 | VV ion gages, RGA |  | Design |  |  |  |  | 6 | 46 |  | 5
|  |  | Prepare procedure |  |  |  |  | 1 | 5
|  |  | Install | [6 empty] | 45 | 1
447 - 448 | Fiber Optics |  | Design |  |  |  |  | 2 | 17 |  | 2
|  |  | Prepare procedure |  |  |  |  | 1 | 3
|  |  | Install | [6 empty] | 15 | 0.5
449 | Glow Discharge |  | Design |  |  |  |  | 6 | 45 |  | 8
|  |  | Prepare procedure |  |  |  |  | 1 | 5
|  |  | Install | [6 empty] | 30 | 3
488 | Deposition monitor, fast x-ray |  | Design |  |  |  |  | 3 | 20 |  | 2
|  |  | Prepare procedure |  |  |  |  | 1 | 5
|  |  | Install | [6 empty] | 21 | 2
| PSI Camera |  | Design |  |  |  |  | 3 | 20 |  | 2
|  |  | Prepare procedure |  |  |  |  | 1 | 5
|  |  | Install | [6 empty] | 20 | 2
| Ultra Fast X-ray Camera |  | Design |  |  |  |  | 3 | 20 |  | 2
|  |  | Prepare procedure |  |  |  |  | 1 | 5
|  |  | Install | [6 empty] | 20 | 2
| Transmission Grating Spectrometer |  | Design |  |  |  |  | 1 | 13
|  |  | Prepare procedure |  |  |  |  | 1 | 3 |  | 2
|  |  | Install | [6 empty] | 14 | 1.4
| IR Camera at Bay L |  | Design |  |  |  |  | 2 | 12 |  | 2
|  |  | Prepare procedure |  |  |  |  | 1 | 3
|  |  | Install | [6 empty] | 8 | 1
| IR Camera at Bay K |  | Design |  |  |  |  | 3 | 24 |  | 8
|  |  | Prepare procedure |  |  |  |  | 1 | 3
|  |  | Install | [6 empty] | 30 | 3
Moing Equipment In and Out of NTC | [7 empty] | 2 |  | 12
Re-install Equipment
Bay J
| Two Gas Injectors |  | Prepare procedure |  |  |  | 10
|  |  | Install |  | 10 | 2 |  |  |  | 20 | 2
| Reflectometer |  | Prepare procedure |  |  |  | 5
|  |  | Install |  | 20 | 2 |  | 5 |  | 40 | 4
| Bolometer |  | Prepare procedure |  |  |  | 5
|  |  | Install |  | 20 | 2 |  | 5 |  | 40 | 4
| RF Probe |  | Prepare procedure |  |  |  | 5
|  |  | Install |  | 20 | 2 |  | 5 |  | 40 | 4
| S-Flip |  | Prepare procedure |  |  |  | 5
|  |  | Install |  | 20 | 2 |  | 5 |  | 40 | 4
| SSNPA |  | Prepare procedure |  |  |  | 5
|  |  | Install |  | 20 | 2 |  | 5 |  | 40 | 4
| Re-entrant Window |  | Prepare procedure |  |  |  | 5
|  |  | Install |  | 1 | 1 |  |  |  | 1 | 0.1
NB2 Duct
| IR Windows for Camera |  | Prepare procedure |  |  |  | 5
|  |  | Install |  | 3 | 1 |  |  |  | 3 | 0.3
| Transmission Grating Spectrometer |  | Prepare procedure |  |  |  | 5
|  |  | Install |  | 20 | 2 |  | 5 |  | 40 | 4
New Pump Duct
NOTE: Installation of new pump duc, turbos and lines to roughing pumps is covered in NB duct job
| Vac Vessel Ion Gages, Filaments, Micro Ion Gages |  | Prepare procedure |  |  |  | 5
|  |  | Install |  | 20 | 2 |  | 5 |  | 40 | 4
| RGA |  | Preliminary Design |  |  |  | 10 |  | 10
|  |  | Final Design |  |  |  | 10 |  | 10
|  |  | Prepare procedure |  |  |  | 1 |  | 5
|  |  | Procurements |  |  |  | 1 |  |  |  | 8
|  |  | Install |  | 20 | 2 |  |  |  | 40 | 4
| Tank farm, TMB system, Gas solenoid box & diconnects |  | Preliminary Design |  |  |  | 20
|  |  | Final Design |  |  |  | 20
|  |  | Prepare procedure |  |  |  | 10
|  |  | Procurements | [7 empty] | 14
|  |  | Install |  | 50 | 2 |  | 13 |  | 100
Bay L
| SPRED |  | Design |  |  |  | 5 |  | 10
|  |  | Prepare procedure |  |  |  | 1 |  | 3
|  |  | Procurements |  |  |  | 1 |  |  |  | 2
|  |  | Fabrications | [6 empty] | 10
|  |  | Install |  | 20 | 2 |  |  |  | 40 | 4
| LOWEUS |  | Design |  |  |  | 5 |  | 10
|  |  | Prepare procedure |  |  |  | 1 |  | 3
|  |  | Procurements |  |  |  | 1
|  |  | Fabrications | [6 empty] | 10
|  |  | Install |  | 20 | 2 |  |  |  | 40 | 4
| IR Camera at L |  | Design |  |  |  |  | 6 | 6
|  |  | Prepare procedure |  |  |  |  | 3
|  |  | Procurements | [7 empty] | 2
|  |  | Install | [6 empty] | 15 | 2
| Glow Discharge |  | Design |  |  |  | 5 |  | 10
|  |  | Prepare procedure |  |  |  | 1 |  | 3
|  |  | Procurements |  |  |  | 1 |  |  |  | 2
|  |  | Fabrications | [6 empty] | 10
|  |  | Install | [6 empty] | 40 | 4
Between Bays K and L
| MPTS Beam Dump Window |  | Design |  |  |  | 4 |  | 6
|  |  | Prepare procedure |  |  |  | 2
|  |  | Fabrications | [6 empty] | 10 | 4
|  |  | Install |  | 1 | 2 |  |  |  | 2 | 1
Fab and Install Five Sections of Platform at EL 118' on West Side of NTC
|  |  | Design |  |  |  | 10 |  | 4
|  |  | Prepare procedure |  |  |  | 3
|  |  | Fabrications |  |  |  | 5 |  |  | 40 | 8
|  |  | Install |  |  |  | 5 |  |  | 10 | 4
Platform Power (recept), grounding and lighting
|  |  | Final Design |  |  |  |  | 3 | 20 |  | 4
|  |  | Prepare procedure |  |  |  |  | 1 | 5
|  |  | Procurements | [7 empty] | 4
|  |  | Install | [6 empty] | 20 | 2
Install New 42 Ckt Panel in NTC and 30 Ckt Panel in Gallery
|  |  | Design |  |  |  |  | 4 | 25
|  |  | Prepare procedure |  |  |  |  | 1 | 3
|  |  | Procurements | [7 empty] | 60
|  |  | Install |  |  |  |  | 5 |  | 40 | 4
Health Physics Coverage |  | 1 HP Tech per shift of EMTB => |  | 391 | MD | put into HP job
Test Cell Oversight/Coordination |  | 1 EMSM per shift of EMTB => |  | 391 | MD
EMSM
|  |  | TOTAL |  |  | 391 | 235 | 233 | 523 | 1564 | 267.5
|  |  |  | Hours | 0 | 3128 | 1880 | 1864 | 4184 | 12512 | 267500
|  |  |  | Rate/hour | 134.76 | 145.2 | 165.2 | 145.2 | 119.26 | 90.38 | 1.23
|  |  |  | Cost | 0 | 454185.6 | 310576 | 270652.8 | 498983.84 | 1130834.56 | 329025
[10 empty] | Sum | 2994257.8

## Tab C Risk and uncertainty
Cost Center: |  | 1180
Job Number: |  | 2490
Job Title: |  | NTC Equipment Removals / Relocations
Job Manager: |  | Tony Langella
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X |  | The design maturity for the mechanical portions of the four diagnostics listed below (High K, SPRED, LOWEUS, and MPTS Beam Dump) is LOW.
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | SPRED re-design and re-installation may require more effort than estimated due to the physical constraints in the area of Bay L. |  |  |  | medium | Start design work immediately so potential schdule impact can be accomodated if necessary. |  |  | manager's estimate (low): 20MD EMEM, 20MD EMSM, 40MD EMTB, $11K M&S | 98 | 147 | 4 | 7
2 | LOWEUS re-design and re-installation may require more effort than estimated due to the physical constraints in the area of Bay L |  |  |  | medium | Start design work immediately so potential schdule impact can be accomodated if necessary. |  |  | manager's estimate (low): 80MD EMEM, 80MD EMSM, 160MD EMTB, $41K M&S | 98 | 147 | 4 | 7
3 | MPTS Beam Dump Window re-design and re-installation may require more effort than estimated due to the physical constraints in the area of Bay L |  |  |  | medium | Start design work immediately so potential schdule impact can be accomodated if necessary. |  |  | manager's estimate (low): 80MD EMEM, 80MD EMSM, 160MD EMTB, $41K M&S | 98 | 147 | 4 | 7
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1180
Job Number: | 2490
Job Title: | NTC Equipment Removals / Relocations
Job Manager: | Tony Langella
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1 | 0 | #DIV/0!
|  | 2 - Engineering Judgement/Experience |  | 2 | 0 | #DIV/0!
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | #DIV/0!
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | #DIV/0!
|  | 5 - Prototype Data/Test Results |  | 5 | 0 | #DIV/0!
|  | 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | #DIV/0!
|  | 7 - Placed Contracts |  | 7 | 0 | #DIV/0!
|  | 8 - Actual experience for NCSX Work |  | 8 | 0 | #DIV/0!
|  | 9 - Other |  | 9 | 0 | #DIV/0!
|  |  | TOTALS |  | 0 | #DIV/0!