## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 3200
Job Title: | Water Cooling System for CSU
Job Manager: | M. Denault
Description:
Provide services to the new center stack and ancillary equipment in NSTX test cell.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1170
| Job Number: |  |  | 3200
| Job Title: |  |  | Water Cooling System for CSU
| Job Manager: |  |  | M. Denault
Estimate (user input)
[5 empty] | SCHEDULE | [11 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [15 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1
2
3 |  | Conceptual Design |  | Denault | [6 empty] | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
4 |  | PREPARE WORK PLANNING FORM |  |  | 1 |  |  | 2009-09-24 | 2009-09-24 | 2009-09-25 09:36 | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8
5 |  | Prep System Description |  |  | 2 | 4 |  |  | 2009-09-25 09:36 | 2009-09-28 04:48 | 2007-10-01 | 2009-09-25 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16
6 |  | Prep System Requirements |  |  | 3 | 5 |  |  | 2009-09-28 04:48 | 2009-10-02 09:36 | 2007-10-01 | 2009-09-28 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 24
7 |  | R&D |  |  | 10 | 6 |  |  | 2009-10-02 09:36 | 2009-10-16 09:36 | 2007-10-01 | 2009-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80
8 |  | Analysis |  |  | 10 | 7 |  |  | 2009-10-16 09:36 | 2009-10-30 09:36 | 2007-10-01 | 2009-10-16 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 |  |  |  |  | 20 |  |  |  | 80
9 |  | CDR |  |  | 2 | 8 |  |  | 2009-10-30 09:36 | 2009-11-02 04:48 | 2007-10-01 | 2009-10-30 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16
10 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
11 |  | Preliminary Design |  | Denault | [6 empty] | 2010-08-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
12 |  | Thermal Analysis |  |  | 5 |  |  | 2010-08-03 | 2010-08-03 | 2010-08-10 | 2010-08-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 40
13 |  | Seismic Analysis |  |  | 5 | 12 |  |  | 2010-08-10 | 2010-08-17 | 2007-10-01 | 2010-08-10 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 40
14 |  | FMEA Analysis |  |  | 5 | 13 |  |  | 2010-08-17 | 2010-08-24 | 2007-10-01 | 2010-08-17 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 40
15 |  | Prepare NEPA Form |  |  | 2 | 14 |  |  | 2010-08-24 | 2010-08-26 19:12 | 2007-10-01 | 2010-08-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16
16 |  | Update Cost & Schedule Estimate |  |  | 5 | 15 |  |  | 2010-08-26 19:12 | 2010-09-02 19:12 | 2007-10-01 | 2010-08-26 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [6 empty] | 40
17 |  | Design Drawings |  |  | 20 | 16 |  |  | 2010-09-02 19:12 | 2010-09-30 19:12 | 2007-10-01 | 2010-09-02 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 160 |  |  |  | 40 |  |  |  | 80
18 |  | PDR Prep |  |  | 5 | 17 |  |  | 2010-09-30 19:12 | 2010-10-07 19:12 | 2007-10-01 | 2010-09-30 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40
19 |  | CONDUCT PDR |  |  | 2 | 18 |  |  | 2010-10-07 19:12 | 2010-10-10 14:24 | 2007-10-01 | 2010-10-07 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16
|  | Layman Review |  |  | 5 |  |  | 2010-12-15 | 2010-12-15 | 2010-12-22 | 2010-12-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40
20 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
21 |  | Final Design |  | Denault | [6 empty] | 2011-01-28 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
22 |  | Disposition PDR Chits |  |  | 2 | 21 |  | 2011-01-28 | 2011-01-28 | 2011-01-30 19:12 | 2011-01-28 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16
23 |  | Design Drawings |  |  | 10 | 22 |  |  | 2011-01-30 19:12 | 2011-02-13 19:12 | 2007-10-01 | 2011-01-30 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 |  |  |  | 20 |  |  |  | 20
24 |  | Update Analyses |  |  | 5 | 23 |  |  | 2011-02-13 19:12 | 2011-02-20 19:12 | 2007-10-01 | 2011-02-13 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 40
25 |  | Update Cost & Schedule Estimate |  |  | 5 | 24 |  |  | 2011-02-20 19:12 | 2011-02-27 19:12 | 2007-10-01 | 2011-02-20 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [6 empty] | 40
26 |  | Prep Procurement Specs |  |  | 5 | 25 |  |  | 2011-02-27 19:12 | 2011-03-06 19:12 | 2007-10-01 | 2011-02-27 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40
27 |  | FDR Prep |  |  | 5 | 26 |  |  | 2011-03-06 19:12 | 2011-03-13 19:12 | 2007-10-01 | 2011-03-06 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40
28 |  | CONDUCT FDR |  |  | 2 | 27 |  |  | 2011-03-13 19:12 | 2011-03-16 14:24 | 2007-10-01 | 2011-03-13 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16
29 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
30 |  | Procurement | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
31 |  | Pumps | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 |  |  | Prep Requisition and procurement package |  | 1 | 28 |  | 2011-06-10 | 2011-06-10 | 2011-06-11 09:36 | 2011-06-10 | 2011-03-16 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01
33 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 32 |  |  | 2011-06-11 09:36 | 2011-06-12 19:12 | 2007-10-01 | 2011-06-11 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01
34 |  |  | Procurement lead time (1) |  | 30 | 33 |  |  | 2011-06-12 19:12 | 2011-07-24 19:12 | 2007-10-01 | 2011-06-12 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
35 |  |  | AWARD |  | 1 | 34 |  |  | 2011-07-24 19:12 | 2011-07-26 04:48 | 2007-10-01 | 2011-07-24 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
36 |  |  | Fabricate or delivery |  | 30 | 35 |  |  | 2011-07-26 04:48 | 2011-09-06 04:48 | 2007-10-01 | 2011-07-26 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01
37 |  | Valves, Hose, Pipe | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
38 |  |  | Prep Requisition and procurement package |  | 2 | 28 |  | 2011-06-10 | 2011-06-10 | 2011-06-12 19:12 | 2011-06-10 | 2011-03-16 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01
39 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 38 |  |  | 2011-06-12 19:12 | 2011-06-14 04:48 | 2007-10-01 | 2011-06-12 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
40 |  |  | Procurement lead time (1) |  | 30 | 39 |  |  | 2011-06-14 04:48 | 2011-07-26 04:48 | 2007-10-01 | 2011-06-14 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01
41 |  |  | AWARD |  | 1 | 40 |  |  | 2011-07-26 04:48 | 2011-07-27 14:24 | 2007-10-01 | 2011-07-26 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01
42 |  |  | Fabricate or delivery |  | 30 | 41 |  |  | 2011-07-27 14:24 | 2011-09-07 14:24 | 2007-10-01 | 2011-07-27 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01
43 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
44 |  | Fab/Assembly |  | Denault | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
45 |  | Fab/Assy Procedure | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
46 |  | Shop Fabrication | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
47 |  | Assembly | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
48 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
49 |  | Installation |  | Denault | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
50 |  | Installation Procedure | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
51 |  | Machine Installation | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
52 |  | PTP Testing | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
54 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
55 |  |  | Engineering Support |  | 39 |  | 42 | 2012-07-24 | 2012-07-24 | 2012-09-16 14:24 | 2012-07-24 | 2007-10-01 | 2011-09-07 14:24 | 2007-10-01 | 2007-10-01 | [11 empty] | 10 |  |  |  | 62.4
56 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
57 |  |  | Remove Existing System |  | 5 |  | 42 | 2012-07-24 | 2012-07-24 | 2012-07-31 | 2012-07-24 | 2007-10-01 | 2011-09-07 14:24 | 2007-10-01 | 2007-10-01 | [14 empty] | 16 |  |  |  | 120
58 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
59 |  |  | Install Pumps |  | 10 | 57 | 42 |  | 2012-07-31 | 2012-08-14 | 2007-10-01 | 2012-07-31 | 2011-09-07 14:24 | 2007-10-01 | 2007-10-01 |  | 30 | [12 empty] | 80 |  |  |  | 80
60 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
61 |  |  | Modify Manifold |  | 20 | 59 | 42 |  | 2012-08-14 | 2012-09-11 | 2007-10-01 | 2012-08-14 | 2011-09-07 14:24 | 2007-10-01 | 2007-10-01 |  | 10 | [16 empty] | 480
62 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
63 |  |  | Connect Lines |  | 2 | 61 | 42 | 2012-11-21 | 2012-11-21 | 2012-11-23 19:12 | 2012-11-21 | 2012-09-11 | 2011-09-07 14:24 | 2007-10-01 | 2007-10-01 |  | 2 | [16 empty] | 48
64 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
65 |  |  | Leak Check |  | 2 | 63 | 42 |  | 2012-11-23 19:12 | 2012-11-26 14:24 | 2007-10-01 | 2012-11-23 19:12 | 2011-09-07 14:24 | 2007-10-01 | 2007-10-01 | [18 empty] | 32
66 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
67 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
72 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
73 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
74 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
84 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
85 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
92 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
93 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
97 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
98 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
102 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
103 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
104 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
105 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
106 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
107 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
108 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
109 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
110 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
111 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
112 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
113 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
114 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
115 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
116 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
117 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
118 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
119 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
120 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
121 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
122 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
123 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
124 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
125 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
126 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
127 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
128 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
129 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
130 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
131 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
132 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
133 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
134 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
135 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
136 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
137 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
138 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
139 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
140 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
141 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
142 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [14 empty] | 42 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | 0 | 0 | 90 | 0 | 0 | 96 | 850.4 | 0 | 0 | 760 | 0 | 0 | 0 | 80 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 367.109 | [11 empty] | 51.492 | 0 | 0 | 0 | 0 | 45.264 | 29.976 | 0 | 0 | 0 | 15.606 | 0 | 0 | 8.1024 | 135.979 | 0 | 0 | 68.628 | 0 | 0 | 0 | 12.0616 | 0 | 0
| Notes: | [25 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [7 empty] | Weeks | [16 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [6 empty] | 3 | [16 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [6 empty] | 5 | [16 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [6 empty] | 8 | [16 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [6 empty] | 9 | [16 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 3200
Job Title: |  | Water Cooling System for CSU
Job Manager: |  | M. Denault
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1170
Job Number: | 3200
Job Title: | Water Cooling System for CSU
Job Manager: | M. Denault
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Pipe |  |  | Vendor Pricing
Parts |  |  | Vendor Pricing
MISC |  |  | Experience
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1 | 0 | #DIV/0!
|  | 2 - Engineering Judgement/Experience |  | 2 | 0 | #DIV/0!
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | #DIV/0!
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | #DIV/0!
|  | 5 - Prototype Data/Test Results |  | 5 | 0 | #DIV/0!
|  | 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | #DIV/0!
|  | 7 - Placed Contracts |  | 7 | 0 | #DIV/0!
|  | 8 - Actual experience for NCSX Work |  | 8 | 0 | #DIV/0!
|  | 9 - Other |  | 9 | 0 | #DIV/0!
|  |  | TOTALS |  | 0 | #DIV/0!