## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 5500 (Covers elements 5200 - 5500)
Job Title: | NSTX Center Stack Upgrade - Power System
Job Manager: | S. Ramakrishnan
Description:
The Center stack upgrade entails the TF feed to be 1kV, 129.8kA for 7.45 seconds every 2400 seconds. Design shall be such that the pulse period can be reduced to 1200 seconds. This requires complete redesign of the TF power system. Replacement of the fault detector (FD) and the Firing generator (FG) is required for fast and reliable response to fault conditions. The HCS will be upgraded with a PLC. The OH power supply will be also redesigned to have the capabiity of 8kV, +/-24kA; the FD and FG of the OH system will also be changed. OH CLRs will be replaced with calculated optimum requirements.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1170
| Job Number: |  |  | 5500 (Covers elements 5200 - 5500)
| Job Title: |  |  | NSTX Center Stack Upgrade - Power System
| Job Manager: |  |  | S. Ramakrishnan
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1 |  | Physics Requirements | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
2 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
3 |  | Conceptual Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
4 |  | PREPARE WORK PLANNING FORM | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
5 |  | Prep System Description | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
6 |  | Prep System Requirements | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
7 |  | R&D | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
8 |  | Ananlysis | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
9 |  | CDR | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
10 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
11 |  | Preliminary Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
12 |  | Thermal Analysis | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
13 |  | Seismic Analysis | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
14 |  | FMEA Analysis | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
15 |  | Prepare NEPA Form | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
16 |  | Update Cost & Schedule Estimate | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
17 |  | Design Drawings | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
18 |  | PDR Prep | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
19 |  | CONDUCT PDR | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
20 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
21 |  | Final Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
22 |  | Disposition PDR Chits | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
23 |  | Design Drawings | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
24 |  | Update Analyses | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
25 |  | Update Cost & Schedule Estimate | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
26 |  | Prep Procurement Specs | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
27 |  | FDR Prep | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
28 |  | CONDUCT FDR | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
29 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
30 |  | Procurement | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
31 |  | Item 1: | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 |  |  | Prep Requisition and procurement package | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
33 |  |  | SUBMIT REQ TO PROCUREMENT | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
34 |  |  | Procurement lead time (1) | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
35 |  |  | AWARD | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
36 |  |  | Fabricate or delivery | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
37 |  | Item 2: | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
38 |  |  | Prep Requisition and procurement package | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
39 |  |  | SUBMIT REQ TO PROCUREMENT | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
40 |  |  | Procurement lead time (1) | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
41 |  |  | AWARD | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
42 |  |  | Fabricate or delivery | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
43 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
44 |  | Fab/Assembly | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
45 |  | Fab/Assy Procedure | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
46 |  | Shop Fabrication | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
47 |  | Assembly | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
48 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
49 |  | Installation | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
50 |  | Installation Procedure | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
51 |  | Machine Installation | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
52 |  | PTP Testing | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
54 |  | OTHER TASKS | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
55 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
56 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
57 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
58 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
59 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
60 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
61 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
62 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
63 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
64 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
65 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
66 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
67 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
68 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
69 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
70 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
71 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
72 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
73 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
74 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
75 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
76 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
77 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
78 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
79 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
80 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
81 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
82 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
83 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
84 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
85 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
86 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
87 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
88 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
89 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
90 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
91 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
92 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
93 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
94 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
95 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
96 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
97 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
98 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
99 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
100 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
101 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
102 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
103 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
104 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
105 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
106 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
107 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
108 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
109 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
110 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
111 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
112 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
113 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
114 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
115 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
116 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
117 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
118 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
119 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
120 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
121 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
122 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
123 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
124 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
125 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
126 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
127 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
128 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
129 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
130 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
131 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
132 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
133 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
134 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
135 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
136 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
137 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
138 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
139 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
140 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
141 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
142 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [24 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [6 empty] | Weeks | [16 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [5 empty] | 3 | [16 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [5 empty] | 5 | [16 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [5 empty] | 8 | [16 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [5 empty] | 9 | [16 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 5500 (Covers elements 5200 - 5500)
Job Title: |  | NSTX Center Stack Upgrade - Power System
Job Manager: |  | S. Ramakrishnan
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | x
| Design Complexity |  | x
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1170
Job Number: | 5500 (Covers elements 5200 - 5500)
Job Title: | NSTX Center Stack Upgrade - Power System
Job Manager: | S. Ramakrishnan
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1 | 0 | #DIV/0!
|  | 2 - Engineering Judgement/Experience |  | 2 | 0 | #DIV/0!
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | #DIV/0!
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | #DIV/0!
|  | 5 - Prototype Data/Test Results |  | 5 | 0 | #DIV/0!
|  | 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | #DIV/0!
|  | 7 - Placed Contracts |  | 7 | 0 | #DIV/0!
|  | 8 - Actual experience for NCSX Work |  | 8 | 0 | #DIV/0!
|  | 9 - Other |  | 9 | 0 | #DIV/0!
|  |  | TOTALS |  | 0 | #DIV/0!

## M&S REV1
WBS 5 BREAKDOWN WITH COST WITHOUT CONTINGENCY |  |  |  |  | k$ | k$
Ø51 | AC POWER |  |  |  | 62.6
| Ø511 | Experimental AC Power |  |  |  | 62.6
Ø52 | AC/DC CONVERTERS |  |  |  | 48.9
| Ø521 | Reactivate Converters |  |  |  | 48.9
Ø53 | DC SYSTEMS |  |  |  | 1689
| Ø531 | FCPC DC Systems
|  | Ø531.1 | NSTX PF1a PS loop changes |  |  | 255.3
|  | Ø531.2 | TF PS Power Cabling/Changes |  |  | 799.8
|  | Ø531-3 | Removing Cabling |  |  | 89.2
|  | Ø531.4 | DC Reactors |  |  | 387
|  | Ø531.5 | TA Cabling Changes |  |  | 53
| Ø532 | TA to NTC and NTC changes
|  | Ø532.1 | PCTS Changes |  |  | 104.8
Ø54 | CONTROL & PROTECTION SYSTEM |  |  |  | 4337
| Ø541 | Electrical Interlocks |  |  |  | 691.9
| Ø542 | Kirk Key Ingterlocks |  |  |  | 76.3
| Ø543 | Real Time Control |  |  |  | 168.8
| Ø544 | PC Link/FD/FG Changes |  |  |  | 2643.7
| Ø545 | Instrumentation |  |  |  | 577.6
| Ø546 | Coil Protection |  |  |  | 178.7
Ø55 | System Design & Integration |  |  |  | 612.9
| Ø551 | System Design |  |  |  | 442.7
| Ø552 | System Testing |  |  |  | 170.2
|  |  |  | GRAND TOTAL | 6750.4 | 6750.5

## NSTX CS COST
NSTX CENTER STACK UPGRADE - PS CHANGES 130kA part capability 8 parallels ------- 091509 | [12 empty] | M&S | [5 empty] | Design/ Procurement |  | Inst |  |  |  | Commissioning |  |  | Line Total
1. TF WILL BE PULSED AT 129.778kA FOR 7.6 SECONDS EVERY 2400 SECONDS | [5 empty] | Start date | Finish date | Mult | Qty | excl factor | Qnty | Units | Qty | Units | Unit Cost | Cost | Spare Units | Spare Cost | EEEM | Dm | EEEM | EESM | EETB | SC | EEEM | EESM | EETB
[15 empty] | (k$/unit) | ($K) |  | ($K) | (md) | (md) | (md) | (md) | (md) | ($K) | (md) | (md) | (md) | ($K)
51- AC Power | 62.5955
| 511- Experimental AC Power | 62.5955
|  |  | Grounding |  | Misc. grounding |  |  | 1 |  | 1 |  |  | 1 | lot | 1 | 3 |  | 1 | 1 | 2 | 1 | 2 | 5 |  | 1 | 2 | 2 | 19.1942
|  |  | D-site Pulsed AC Power Distribution |  | Lockouts/protection/reactivate |  |  | 1 |  | 1 |  |  | 1 | lot | 5 | 5 |  | 0 | 3 | 3 | 2 | 8 | 10 |  | 3 | 3 | 5 | 43.4013
52 - AC/DC Converters | 48.8921
| 521 - Reactivation Converters | 48.8921 | [5 empty] | 1 |  | 1
|  |  | Coil Power Supplies | Transrex PS Maintenance | Reactivation |  |  | 1 |  | 1 |  |  | 12 | PSS | 1 | 12 | 1 | 1 | 0.5 | 1 | 0 | 0 | 0 |  | 5 | 10 | 20 | 48.8921
53 - DC Systems | 1689.1339
| 531-FCPC DC Changes | 1689.1339
| 531.1 PF1a Changes | 255.3234
|  |  | NSTX PF1a Changes | Design & Supervision |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | 10 | 20 | 5 | 5 | 5 |  | 5 | 5 | 10 | 67.7524
|  |  | NSTX PF1a Changes | Task of removing Ripple reactors & Recabling |  |  |  | 1 |  | 1 |  |  |  | 0 | 1 | 1 |  | 0 | 3 | 4 | 2 | 5 | 20 | 50 | 1 | 1 | 2 | 96.5433
|  |  | NSTX PF1a Changes | task of TF reactor enclosures |  |  |  | 1 |  | 1 |  |  |  | 0 | 1 | 20 |  | 0 | 4 | 4 | 2 | 15 | 30 | 10 | 1 | 1 | 2 | 91.0277
531 - FCPC TF DC Systems | 799.8102
| 531.2- TF Changes | 799.8102
|  |  | TF DC Changes FCPC | Design & Supervision |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | 40 | 40 | 5 | 5 | 15 |  | 5 | 5 | 10 | 134.1196
|  |  |  | Materials & Installation | 1000MCM 5kV Cable For PSS |  |  | 1 | 40 | 1 | 100 | ft/PSS | 4500 | ft | 0.03 | 135 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 176.8984
[5 empty] | Cable Tray in FCPC |  |  | 1 |  | 1 |  |  | 150 | ft | 0.05 | 7.5 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2 | 13.7504
[5 empty] | Install Tray in FCPC |  |  | 1 |  | 1 |  |  | 150 | ft | 0.1 | 15 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2 | 22.9454
|  |  | NSTX TF Power cabling changes | Task of NSTX TF PS cabling changes |  |  |  | 1 |  | 1 | [5 empty] | 10 |  | 0 | 3 | 4 | 2 | 5 | 40 | 320 | 1 | 1 | 2 | 452.0965
| 531.3- Removing cabling | 89.1873 | Removing cabling | Misc |  |  |  | 1 |  | 1 | [5 empty] | 5 |  | 0 | 3 | 4 | 2 | 5 | 20 | 40 | 1 | 1 | 2 | 89.1873
| 531.4 DC Reactors | 386.9908 | DC Reactors for TF & OH | Design & Specification |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 6; Design/ Procurement Dm: 10 | 17.1512
|  |  |  | Procurement OH Reactors |  |  |  | 1 |  | 1 |  |  | 2 | units | 50 | 100 |  | 0 | [9 empty] | 122.6
|  |  |  | TF reactor Installation |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 |  |  | 5 | 10 | 10 | 20 | 3 | 5 | 5 | 64.0072
|  |  |  | OH Reactor Installation |  |  |  | 1 |  | 1 |  |  |  | 2 | 20 | 40 |  | 0 |  |  | 5 | 10 | 5 | 80 | 3 | 5 | 5 | 183.2324
| 531.5 TA Cabling Changes | 53.0137 | Transition area cabling PF/CHI | Misc |  |  |  | 1 |  | 1 | [5 empty] | 6 |  | 0 | 3 | 4 | 2 | 5 | 10 | 15 | 1 | 1 | 2 | 53.0137
532- TA-NTC DC Systems | 104.8086
104.8086
| 532.1 PCTS Changes |  | PCTS Changes | PCTS Changes |  |  |  | 1 |  | 1 |  |  | 1 |  | 15 | 15 |  | 0 | 3 | 15 | 2 | 10 | 20 | 30 | 1 | 1 | 2 | 104.8086
54 - Control & Protection Systems | 4337.0383
| 541 - Electrical Interlocks | 691.8657
|  |  |  | Design |  |  |  | 1 |  | 1 |  |  | 1 | units | 2 | 2 |  | 0 | Design/ Procurement EEEM: 8; Design/ Procurement Dm: 16; Inst EESM: 5; Inst EETB: 15; Inst SC: 40 | 92.8453
|  |  |  | PLC |  |  |  | 1 |  | 1 |  |  | 1 | units | 98 | 98 |  | 0 | Design/ Procurement EEEM: 180; Design/ Procurement Dm: 40; Inst EESM: 5; Inst EETB: 120 | 495.1836
|  |  |  | Install interlocks/cabling |  |  |  | 1 |  | 1 |  |  | 1 | units | 2 | 2 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 10; Inst EESM: 5; Inst EETB: 15; Inst SC: 35 | 77.2684
|  |  |  | Test Modified NSTX HCS |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Commissioning EEEM: 5; Commissioning EESM: 5; Commissioning EETB: 20 | 26.5684
| 542 - Kirk Key Interlocks | 76.3028
|  |  |  | Kirk Keys |  |  |  | 1 |  | 1 |  |  | 1 | lot | 15 | 15 |  | 0 | 5 | 10 | 2 | 5 | 15 |  | 5 | 5 | 15 | 76.3028
| 543 - Real Time Control | 168.768
|  |  |  | Develop Control Algorithms |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 120 | 168.768
| 544 -PC Link/FD/FG changes | 2643.744
|  |  |  | Control Link/FD/FG Changes | TF wing only |  |  | 1 |  | 1 | [5 empty] | 820 |  | 10 | 450 | 100 | 95 | 10 | 900 | 10 | 80 |  | 60 | 2643.744
| 545 - Instrumentation | 577.6401
|  |  | DC Current Transducers (DCCTs) |  |  |  |  | 1 |  | 1 |  |  | 2 | units | 70 | 140 | 0 | 0 | 5 | 10 | 4 | 8 | 20 |  | 3 | 3 | 15 | 234.135
|  |  | DC Current Transducers (DCCTs) |  |  |  |  | 1 |  | 1 |  |  | 8 | units | 10 | 80 | 0 | 0 | 5 | 10 | 4 | 8 | 20 |  | 3 | 3 | 15 | 160.575
|  |  | Signal Conditioning & Associated Cabling |  |  |  |  | 1 |  | 1 |  |  | 1 | lot | 9 | 9 | 0 | 0 | 15 | 10 | 5 | 0 | 20 | 80 | 10 | 5 | 5 | 182.93
| 546 - Coil Protection | 178.7178
|  |  | Overload Protection & Associated Cabling(TF) |  |  |  |  | 1 |  | 1 |  |  | 1 | units | 4 | 4 | 1 | 4 | 50 | 30 | 10 | 20 | 20 |  | 10 | 4 | 10 | 178.7178
55 - System Design and Integration | 612.9047
| 551 - System Design | 442.6844
|  |  | Design Drawings & Drawings changes , as-builts | New drawings & Misc. updates |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 50; Design/ Procurement Dm: 70 | 131.3096
|  |  |  | Analysis |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 70; Inst SC: 15 | 116.838
|  |  | CDR Power system | All power systems |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 15 | 34.1652
|  |  | PDR Power system | All power systems |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 15 | 34.1652
|  |  | FDR D-Site | Transrex D-Site |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 15 | 34.1652
|  |  | FDR Cabling | D site |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 15 | 34.1652
|  |  | Calculations | Calculations - documentation |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Inst SC: 30 | 57.876
| 552 - System Testing | 170.2203
|  |  | Procedures PTPs, ISTPs | New Procedures |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 15 | 34.1652
|  |  |  | DC Circuit Hipots and Impedance Measurements |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Commissioning EEEM: 3; Commissioning EETB: 8 | 9.6189
|  |  |  | Electrical Interlock Testing |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Commissioning EEEM: 3; Commissioning EETB: 8 | 9.6189
|  |  |  | Kirk Key Interlock Testing |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Commissioning EEEM: 2; Commissioning EETB: 3 | 4.8377
|  |  |  | Instrumentation Test & Calibration |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Commissioning EEEM: 2; Commissioning EETB: 2 | 4.1627
|  |  |  | Real Time Control System Testing |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Commissioning EEEM: 3; Commissioning EETB: 3 | 6.2441
|  |  |  | Coil Protection System Testing |  |  |  | 1 |  | 1 | [5 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Commissioning EEEM: 3; Commissioning EETB: 3 | 27.3401
|  |  |  | Coil Power Supply Dummy Load Testing |  |  |  | 1 |  | 1 |  |  | 10 | PS |  | 0 |  | 0 | 0 |  | 5 |  | 20 |  | 20 | 10 | 20 | 74.2328
|  |  | TOTALS | [12 empty] | 1544.5 |  | 16 | 1156.5 | 501 | 160 | 151 | 1355 | 775 | 183 | 76 | 256 | 6750.5645
RATES FY08 | [14 empty] | M&S --> | 1893.557 |  | 16 | 1626.5016 | 436.5113 | 225.024 | 182.3234 | 914.5708 | 950.15 | 257.3712 | 91.7654 | 172.7898 | 6766.5645
FY2009 Hourly Rates
EEEM | 1.4064 | 175.8 | [16 empty] | Inst EEEM: 1321.9182
EESM | 1.2074 | 150.93
EETB | 0.67496 | 84.37 | [15 empty] | ∑MD | Design/ Procurement EEEM: Rate; Design/ Procurement Dm: $K; Inst EEEM: ∑FTE; Inst EESM: Years; Inst EETB: FTE/yr
G&A (MHX) | 1.226 | 1.226 | [13 empty] | cross check | EEEM | 1499.5 | Design/ Procurement EEEM: 1.4064; Design/ Procurement Dm: 2108.8968; Inst EEEM: 6.8159; Inst EESM: 4; Inst EETB: 1.704
DM | 0.87128 | 108.91 | [14 empty] | EESM | 227 | Design/ Procurement EEEM: 1.2074; Design/ Procurement Dm: 274.0889; Inst EEEM: 1.0318; Inst EESM: 2; Inst EETB: 0.51591
[17 empty] | EETB | 1611 | Design/ Procurement EEEM: 0.67496; Design/ Procurement Dm: 1087.3606; Inst EEEM: 7.3227; Inst EESM: 2; Inst EETB: 3.6614
[17 empty] | EADM | 501 | Design/ Procurement EEEM: 0.87128; Design/ Procurement Dm: 436.5113; Inst EEEM: 2.2773; Inst EESM: 3; Inst EETB: 0.75909
Notes: | [16 empty] | M&S |  | Design/ Procurement Dm: 2843.707
SCOPE COVERED | [18 empty] | Design/ Procurement Dm: 6750.5645
1. TF WILL BE PULSED AT 130kA FOR 7.3 SECONDS EVERY 900 SECONDS
2 Sub-contract estimates based on bids and a projected increase of costs
3. PC LINK CHANGES INCLUDED
4. Cost in 09 Dollars
5. SCHEDULE WILL AFFECT COST