## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 7700
Job Title: | NSTX Upgrade HP Allocations
Job Manager: | Strykowsky
Description:
Health Physics allocation estimate
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1170
| Job Number: |  |  | 7700
| Job Title: |  |  | NSTX Upgrade HP Allocations
| Job Manager: |  |  | Strykowsky
Estimated NSTX Upgrade allocations (HP related)
Basis of estimate = FY09 budgets and anticipated out year allocation maps
Allocation map
|  | FY09 | FY10-13 guestimate) |  | base $
cc & annual budget | NSTX CC
5430 | 1150 | 14% | 15% |  | 58.65
391 | 1180 | 58% | 70% |  | 273.7
| 1393 | 14% | 15% |  | 58.65
| 9450 | 14% | 0% |  | 0
ESTIMATED DIRECT ALLOCATIONS FOR NSTX UPGRADES
FY09 K$
[7 empty] | FY10 | FY11 | FY12 | FY13
|  |  |  | Base ( unloaded)= | 273.7
Escalation
[6 empty] | Site Burden | 0.45 | 0.48 | 0.48 | 0.48
[6 empty] | Science Ed | 0.05
[6 empty] | G&A | 0.115 | 0.12 | 0.12 | 0.12
[6 empty] | LDRD | 0.02
[6 empty] | HP ALLOCATION ESTIMATED (loaded)= | 473.9223 | 453.6851 | 453.6851 | 453.6851
[5 empty] | Total= | 1834.9777

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 7700
Job Title: |  | NSTX Upgrade HP Allocations
Job Manager: |  | Strykowsky
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X
| Design Complexity | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Volatility of over head rates |  |  |  | L |  |  |  | -2% +2% | -65 | 65
2 | Volatility of base estimates for the allocated cost centers |  |  |  | L |  |  |  | -2% +2% | -65 | 65
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended