## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 7100 r1
Job Title: | Project Management and Integration
Job Manager: | Erik Perry
Description:
Management and engineering oversight of the NSTX Upgrade Project. This project includes the addition of a second neutral beam on NSTX and the design, fabrication and installation of a new centerstack as well as upgrades to coil structures to support the new loads. Also included is the updating of the General Arrangement Drawings for the NSTX Test Cell and funds for independent reviewers.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1170
| Job Number: |  |  | 7100 r1
| Job Title: |  |  | Project Management and Integration
| Job Manager: |  |  | Erik Perry
Estimate (user input)
[5 empty] | SCHEDULE | [5 empty] | FY09$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated |  |  | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
numb | P3 cross ref (optinal) | [9 empty] | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
Project Manager - Perry LOE
|  |  | FY10 70% | [18 empty] | 1208.2
|  |  | FY11 70% | [18 empty] | 1208.2
|  |  | FY12 100% | [18 empty] | 1726
|  |  | FY13 100% | [18 empty] | 1726
Systems Engineering Support 20% Simmons LOE
|  |  | FY10 | [12 empty] | 345.2
|  |  | FY11 | [12 empty] | 345.2
|  |  | FY12 | [12 empty] | 345.2
|  |  | FY13 | [12 empty] | 345.2
Full-Time Planner/Scheduler
|  |  | FY10 | [20 empty] | 1726
|  |  | FY11 | [20 empty] | 1726
|  |  | FY12 | [20 empty] | 1726
|  |  | FY13 | [20 empty] | 1726
Work Control Center
FY10 0%
|  |  | FY11 25% each of Winston and Langella (EMSM) | [17 empty] | 863
|  |  | FY12 50% each of Winston and Langella (EMSM) | [17 empty] | 1726
|  |  | FY13 50% each of Winston and Langella (EMSM) | [17 empty] | 1726
50% Mitchel for updating of General Arrangement drawings
|  |  | FY10 | [13 empty] | 863
|  |  | FY11 | [13 empty] | 863
|  |  | FY12 | [13 empty] | 863
|  |  | FY13 | [13 empty] | 863
two independent reviewers 80mh every 6 months plus $3K every six months for airfare, hotel and meals
|  |  | FY10 | [10 empty] | 6 |  | 160
|  |  | FY11 | [10 empty] | 6 |  | 160
|  |  | FY12 | [10 empty] | 6 |  | 160
|  |  | FY13 | [10 empty] | 6 |  | 160
|  |  | Independent reviewers 480 mh to support ORA during last two months of project | [10 empty] | 20 | [7 empty] | 480
|  | TOTALS | [8 empty] | 0 | 0 | 0 | 44 | 0 | 2020.8 | 3452 | 0 | 0 | 0 | 4315 | 6348.4 | 0 | 6904 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 3597.6871 | [5 empty] | 0 | 0 | 0 | 48.4 | 0 | 374.8584 | 431.8107 | 0 | 0 | 0 | 651.867 | 1049.8349 | 0 | 1040.9161 | 0 | 0 | 0 | 0 | 0
| Notes: | [18 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [6 empty] | Weeks | [10 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [5 empty] | 3 | [10 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [5 empty] | 5 | [10 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [5 empty] | 8 | [10 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [5 empty] | 9 | [10 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 7100 r1
Job Title: |  | Project Management and Integration
Job Manager: |  | Erik Perry
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1170
Job Number: | 7100 r1
Job Title: | Project Management and Integration
Job Manager: | Erik Perry
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
see Tab B for reviewer funds required
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1 | 0 | #DIV/0!
|  | 2 - Engineering Judgement/Experience |  | 2 | 0 | #DIV/0!
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | #DIV/0!
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | #DIV/0!
|  | 5 - Prototype Data/Test Results |  | 5 | 0 | #DIV/0!
|  | 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | #DIV/0!
|  | 7 - Placed Contracts |  | 7 | 0 | #DIV/0!
|  | 8 - Actual experience for NCSX Work |  | 8 | 0 | #DIV/0!
|  | 9 - Other |  | 9 | 0 | #DIV/0!
|  |  | TOTALS |  | 0 | #DIV/0!