## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 1200
Job Title: | Vacuum Vessel & Support Structure
Job Manager: | D. Mangra & M. Smith
REV 1 9/9/2010
Description:
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head
Includes the analytical and CAD design of the support structures associated with the Magnet upgrade activities.
Scope includes
1200-Vacuum Vessel & Structural Support
1201-Outer TF Structure
1202-PF2 Support Structure
1203-PF3 Support Structure
1204-PF4-5 Leads, Radial Support
1205-Umbrella Reinforcement
1206-Pedestal
1207-Vacuum Vessel Leg's
1208 - PF4 PF5 Verticle Support
1220-Misc
Includes the procurement and fabrication of these structures.
Does not include installation costs.

## 1201 Outer TF
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [11 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Contingency % | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [15 empty] | 1.18 | 1.18 | 1.63 | 1.1 | 0.177 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | 1201 Outer TF Structure | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 |  | Preliminary Design Activities |  |  | 77 |  |  | 2010-05-01 | 2010-05-01 | 2010-08-16 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
7 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
9 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 30 |  |  | 2010-05-01 | 2010-05-01 | 2010-06-12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 80 |  |  |  |  | 40 | [8 empty] | 36.67% | 2, 4, 9, 11
10 |  |  | Complete Preliminary CAD Models |  | 10 |  |  | 2010-06-05 | 2010-06-05 | 2010-06-19 | 2010-06-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 40 | [13 empty] | 50% | 2, 4, 9, 11
11 |  | Mockups: outer link, real estate issues (# of items approx 4) |  |  | 66 |  |  | 2010-05-01 | 2010-05-01 | 2010-08-01 09:36 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 8 | [5 empty] | 8 |  |  |  |  | 4 | 80 | [7 empty] | 50% | 2, 4, 9
12 |  | ME Analysis & CAD Model Iterations (Titus) | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 6 | [8 empty] | 10% | 2 , 4, 9
13 |  |  | Stress, EM, Thermal | Titus | 32 |  |  | 2010-05-01 | 2010-05-01 | 2010-06-14 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 101.44 | [14 empty] | 20% | 2, 4, 9, 10
14 |  |  | Analysis of Preliminary Design Approved | Titus | 0 | 13 |  |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
15 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 |  | PDR |  |  | 0 |  |  | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20%
17 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
18 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 38 | 16 |  |  | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 60 |  |  |  |  | 30 | [8 empty] | 36.67% | 2, 4, 9, 11
19 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
20 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
21 |  | DOE CD-2 (Lehman) Review |  |  | 0 |  |  | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
22 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
23 |  | Preliminary Design CAD model Completed | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
24 |  |  | Outer support ring, clamps, spring |  | 0 | 18 |  |  | 2010-12-12 13:44 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
25 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 |  | Final Design Activities | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 |  | Final Design Eng Iterations, Detailed CAD Modeling (34 models) |  |  | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 102 |  |  |  |  | 31 | [8 empty] | 40.68% | 2, 4, 9, 11
29 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
30 |  | Final Design Analysis |  | Titus | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 404 | [14 empty] | 20% | 10
31 |  | Design Drawings (13 dwg) |  |  | 35 | 28 | 30 |  | 2011-01-04 | 2011-02-22 | 2010-10-20 08:56 | 2011-01-04 | 2011-01-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 104 |  |  |  |  | 10 | [8 empty] | 46.49% | 2, 4, 9, 11
32 |  | Validation of Design Complete |  | Titus | 10 | 31 |  |  | 2011-02-22 | 2011-03-08 | 2010-10-20 08:56 | 2011-02-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 30 | [14 empty] | 25%
33 |  | Update CAD Models per Validation |  |  | 10 | 32 |  |  | 2011-03-08 | 2011-03-22 | 2010-10-20 08:56 | 2011-03-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 34 | [13 empty] | 50% | 2, 4, 9, 11
34 |  | Revise Fabrication & Assembly Drawings per Validation |  |  | 10 | 33 |  |  | 2011-03-22 | 2011-04-05 | 2010-10-20 08:56 | 2011-03-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 52 | [13 empty] | 50% | 2, 4, 9, 11
35 |  | Review, Check Drawings |  |  | 5 | 34 |  |  | 2011-04-05 | 2011-04-12 | 2010-10-20 08:56 | 2011-04-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 26 |  |  |  |  | 26 | [8 empty] | 30% | 2, 4, 9, 11
36 |  | Drawings Ready for FDR |  |  | 0 | 35 |  |  | 2011-04-12 | 2011-04-12 | 2010-10-20 08:56 | 2011-04-12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
37 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 |  | FDR |  |  | 0 |  |  | 2011-04-29 | 2011-04-29 | 2011-04-29 | 2011-04-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12%
39 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 |  | Procurement & Fabrication | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 |  | Prep Req & Procurement Package |  |  | 10 |  |  | 2011-05-01 | 2011-05-01 | 2011-05-15 | 2011-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 32 | [8 empty] | 30% | 2, 4, 9
43 |  | Submit Req to Procurement |  |  | 0 | 42 |  |  | 2011-05-15 | 2011-05-15 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20%
44 |  |  | Procurement Processing | Procurement | 22 | 43 |  |  | 2011-05-15 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
45 |  |  | Submit for Vendor Quotes |  | 0 | 44 |  |  | 2011-06-14 19:12 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
46 |  |  | Eval Quotes | Procurement | 43 | 45 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 10% | 2, 4, 9
47 |  |  | Tech Eval of Vendors |  | 43 | 45 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 16 | [8 empty] | 10% | 2, 4, 9
48 |  |  | Award / Order Approved |  | 0 | 46 | 47 |  | 2011-08-14 | 2011-08-14 | 2010-10-20 08:56 | 2011-08-14 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
49 |  |  | Vendor Oversight |  | 100 | 48 |  |  | 2011-08-14 | 2012-01-01 | 2010-10-20 08:56 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 40 | [8 empty] | 10% | 2, 4, 9
50 |  |  | Receipt of Hardware |  | 4 | 49 |  |  | 2012-01-01 | 2012-01-06 14:24 | 2010-10-20 08:56 | 2012-01-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
51 |  | QA Inspection |  |  | 10 | 50 |  |  | 2012-01-06 14:24 | 2012-01-20 14:24 | 2010-10-20 08:56 | 2012-01-06 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 9 | 48 | [7 empty] | 43.68% | 2, 4, 9
52 |  | Resolve Procurement Issues |  |  | 5 | 51 |  |  | 2012-01-20 14:24 | 2012-01-27 14:24 | 2010-10-20 08:56 | 2012-01-20 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 2 | [8 empty] | 10% | 2, 4, 9
53 |  | Documentation: Assembly Procedures |  |  | 15 | 50 |  |  | 2012-01-06 14:24 | 2012-01-27 14:24 | 2010-10-20 08:56 | 2012-01-06 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 4 |  |  |  |  | 24 | [8 empty] | 15.71% | 2, 4, 9
54 |  | Assembly of Components |  |  | 20 | 53 |  |  | 2012-01-27 14:24 | 2012-02-24 14:24 | 2010-10-20 08:56 | 2012-01-27 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 4 | 80 | [7 empty] | 48.1% | 2, 4, 9
55 |  |  | Parts ready for installation |  | 0 | 54 |  |  | 2012-02-24 14:24 | 2012-02-24 14:24 | 2010-10-20 08:56 | 2012-02-24 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
56 |  | Handling / Warehouse / Storage |  |  | 50 | 50 |  |  | 2012-01-06 14:24 | 2012-03-16 14:24 | 2010-10-20 08:56 | 2012-01-06 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [13 empty] | 96 | [7 empty] | 50% | 2, 4, 9
57 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
68 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
69 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
71 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
72 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
75 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
77 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
80 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
87 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
88 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
90 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
92 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
93 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
94 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
97 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
101 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
105 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
106 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
108 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
109 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
110 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
111 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
112 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
113 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
114 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
115 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[11 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [14 empty] | 8 | 0 | 0 | 0 | 0 | 535.44 | 510 | 0 | 0 | 0 | 0 | 282 | 304 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 234.2593 | [11 empty] | 9.44 | 0 | 0 | 0 | 0 | 94.6979 | 60.4962 | 0 | 0 | 0 | 0 | 42.551 | 27.0742 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: | [5 empty] | 2010-08-11: Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  |  | 2010-08-11: 3
|  |  | Purchase orders-Noncommercial items |  |  |  |  | 2010-08-11: 5
|  |  | Subcontracts (non construction) |  |  |  |  | 2010-08-11: 8
|  |  | Construction subcontracts |  |  |  |  | 2010-08-11: 9
The TF Outer Support consists of the: Outer support ring, TF clamp reinforcement, and vessel spring link.

## 1202 PF2 Sup
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Contingency % | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [14 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | 1202 PF2 Support Structure | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 |  | Preliminary Design Activities | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
7 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 |  | Input from Analyst Group: Preliminary Analysis of PF2 |  | Titus | 0 |  |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25% | 2, 4, 9
9 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 30 |  |  | 2010-10-20 08:56 | 2010-12-01 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 24 | [13 empty] | 50% | 2, 4, 9, 11
10 |  |  | Complete Preliminary CAD Models |  | 12 | 8 |  | 2010-10-20 08:56 | 2010-11-06 04:08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 16 | [13 empty] | 50% | 2, 4, 9, 11
11 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
12 |  | ME Analysis & CAD Model Iterations (Titus) | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
13 |  |  | Stress, EM, Thermal | Titus | 32 |  |  | 2010-10-20 08:56 | 2010-12-04 04:08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 19.84 | [14 empty] | 20% | 2, 4, 9, 10
14 |  |  | Analysis of Preliminary Design Approved | Titus | 0 | 13 |  | 2010-12-04 04:08 | 2010-12-04 04:08 | 2010-10-20 08:56 | 2010-12-04 04:08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
15 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 |  | PDR |  |  | 0 |  |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20%
17 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
18 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 38 | 16 |  | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 16 |  |  |  |  | 8 | [8 empty] | 36.67% | 2, 4, 9, 11
19 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
20 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
21 |  | DOE CD-2 (Lehman) Review |  |  | 0 |  | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
22 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
23 |  |  |  |  | 0 |  |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
24 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 |  | Final Design Activities | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
29 |  | Update CAD & Design Drawings ( 10 models, 4 dwg) |  |  | 100 |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 62 |  |  |  |  | 6 | [8 empty] | 46.47% | 2, 4, 9, 11
30 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
31 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
32 |  | Validation of Design Complete |  | Titus | 20 | 29 |  | 2011-01-04 | 2011-02-01 | 2010-10-20 08:56 | 2011-01-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 24 | 2 | [13 empty] | 20% | 2, 4, 10
33 |  | Update CAD Models per Validation |  |  | 10 | 32 |  | 2011-02-01 | 2011-02-15 | 2010-10-20 08:56 | 2011-02-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 10 | [13 empty] | 50% | 2, 4, 9, 11
34 |  | Revise Fabrication & Assembly Drawings per Validation |  |  | 10 | 33 |  | 2011-02-15 | 2011-03-01 | 2010-10-20 08:56 | 2011-02-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 16 | [13 empty] | 50% | 2, 4, 9, 11
35 |  | Review, Check Drawings |  |  | 10 | 34 |  | 2011-03-01 | 2011-03-15 | 2010-10-20 08:56 | 2011-03-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 8 |  |  |  |  | 12 | [8 empty] | 26% | 2, 4, 9, 11
36 |  | Drawings Ready for FDR |  |  | 0 | 35 |  | 2011-03-15 | 2011-03-15 | 2010-10-20 08:56 | 2011-03-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5%
37 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 |  | FDR |  |  | 0 |  | 2011-04-29 | 2011-04-29 | 2011-04-29 | 2011-04-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12%
39 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 |  | Procurement & Fabrication | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 |  | Prep Req & Procurement Package |  |  | 5 |  | 2011-05-01 | 2011-05-01 | 2011-05-08 | 2011-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 12 | [8 empty] | 10% | 2, 4, 9
43 |  | Submit Req to Procurement |  |  | 0 | 42 |  | 2011-05-08 | 2011-05-08 | 2010-10-20 08:56 | 2011-05-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
44 |  |  | Procurement Processing | Procurement | 22 | 43 |  | 2011-05-08 | 2011-06-07 19:12 | 2010-10-20 08:56 | 2011-05-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
45 |  |  | Submit for Vendor Quotes |  | 0 | 44 |  | 2011-06-07 19:12 | 2011-06-07 19:12 | 2010-10-20 08:56 | 2011-06-07 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
46 |  |  | Eval Quotes | Procurement | 43 | 45 |  | 2011-06-07 19:12 | 2011-08-07 | 2010-10-20 08:56 | 2011-06-07 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 1 | [8 empty] | 10% | 2, 4, 9
47 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
48 |  |  | Award / Order Approved |  | 0 | 46 |  | 2011-08-07 | 2011-08-07 | 2010-10-20 08:56 | 2011-08-07 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
49 |  |  | Vendor Oversight |  | 100 | 48 |  | 2011-08-07 | 2011-12-25 | 2010-10-20 08:56 | 2011-08-07 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 1 | [8 empty] | 10% | 2, 4, 9
50 |  |  | Receipt of Hardware |  | 1 | 49 |  | 2011-12-25 | 2011-12-26 09:36 | 2010-10-20 08:56 | 2011-12-25 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5%
51 |  | QA Inspection |  |  | 10 | 50 |  | 2011-12-26 09:36 | 2012-01-09 09:36 | 2010-10-20 08:56 | 2011-12-26 09:36 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 1 | 2 | [7 empty] | 36.67% | 2, 4, 9
52 |  | Resolve Procurement Issues |  |  | 5 | 51 |  | 2012-01-09 09:36 | 2012-01-16 09:36 | 2010-10-20 08:56 | 2012-01-09 09:36 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 1 | [8 empty] | 25%
53 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
54 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
55 |  |  | Parts ready for installation |  | 0 | 52 |  | 2012-01-16 09:36 | 2012-01-16 09:36 | 2010-10-20 08:56 | 2012-01-16 09:36 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5%
56 |  | Handling / Warehouse / Storage |  |  | 16 | 50 |  | 2011-12-26 09:36 | 2012-01-17 19:12 | 2010-10-20 08:56 | 2011-12-26 09:36 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [13 empty] | 1 | [7 empty] | 5% | 2, 4, 9
57 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
68 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
69 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
71 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
72 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
75 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
77 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
80 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
87 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
88 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
90 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
92 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
93 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
94 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
97 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
101 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
105 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
106 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
108 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
109 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
110 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
111 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
112 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
113 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
114 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
115 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 43.84 | 154 | 0 | 0 | 0 | 0 | 42 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 32.6256 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 7.7535 | 18.2675 | 0 | 0 | 0 | 0 | 6.3374 | 0.26718 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: |  |  |  |  | 2010-08-11: Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  | 2010-08-11: 3
|  |  | Purchase orders-Noncommercial items |  |  |  | 2010-08-11: 5
|  |  | Subcontracts (non construction) |  |  |  | 2010-08-11: 8
|  |  | Construction subcontracts |  |  |  | 2010-08-11: 9
PF2 Support consists of:
1. Increase number of clamps from 6 to 11 using existing design.

## 1203 PF3 Sup
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Contingency % | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [14 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | 1203 PF3 Support Structure | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 |  | Preliminary Design Activities | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
7 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
9 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
10 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
11 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
12 |  | ME Analysis & CAD Model Iterations (Titus) | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
13 |  |  | Stress, EM, Thermal | Titus | 32 |  | 2010-05-01 | 2010-05-01 | 2010-06-14 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 19.84 | [14 empty] | 20% | 2, 4, 9, 10
14 |  |  | Analysis of Preliminary Design Approved | Titus | 0 | 13 |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
15 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 |  | PDR |  |  | 0 |  | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20%
17 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [22 empty] | 2, 4, 10
18 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
19 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [22 empty] | 2, 4, 10
20 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [22 empty] | 2, 4, 10
21 |  | DOE CD-2 (Lehman) Review |  |  | 0 |  | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
22 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
23 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
24 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 |  | Final Design Activities | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
29 |  | Update CAD & Design Drawings ( 2 models, 2 dwg) |  |  | 100 |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 22 |  |  |  |  | 5 | [8 empty] | 42.59% | 2, 4, 9, 11
30 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
31 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
32 |  | Validation of Design Complete |  | Titus | 20 | 29 |  | 2011-01-04 | 2011-02-01 | 2010-10-20 08:56 | 2011-01-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 24 | 2 | [13 empty] | 20% | 2, 4, 10
33 |  | Update CAD Models per Validation |  |  | 10 | 32 |  | 2011-02-01 | 2011-02-15 | 2010-10-20 08:56 | 2011-02-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 2 | [13 empty] | 50% | 2, 4, 9, 11
34 |  | Revise Fabrication & Assembly Drawings per Validation |  |  | 10 | 33 |  | 2011-02-15 | 2011-03-01 | 2010-10-20 08:56 | 2011-02-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 8 | [13 empty] | 50% | 2, 4, 9, 11
35 |  | Review, Check Drawings |  |  | 10 | 34 |  | 2011-03-01 | 2011-03-15 | 2010-10-20 08:56 | 2011-03-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 4 |  |  |  |  | 6 | [8 empty] | 26% | 2, 4, 9, 11
36 |  | Drawings Ready for FDR |  |  | 0 | 35 |  | 2011-03-15 | 2011-03-15 | 2010-10-20 08:56 | 2011-03-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5%
37 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 |  | FDR |  |  | 0 |  | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12%
39 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 |  | Procurement & Fabrication | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 |  | Prep Req & Procurement Package |  |  | 5 |  | 2011-05-01 | 2011-05-01 | 2011-05-08 | 2011-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 12 | [8 empty] | 10% | 2, 4, 9
43 |  | Submit Req to Procurement |  |  | 0 | 42 |  | 2011-05-08 | 2011-05-08 | 2010-10-20 08:56 | 2011-05-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
44 |  |  | Procurement Processing | Procurement | 20 | 43 |  | 2011-05-08 | 2011-06-05 | 2010-10-20 08:56 | 2011-05-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
45 |  |  | Submit for Vendor Quotes |  | 0 | 44 |  | 2011-06-05 | 2011-06-05 | 2010-10-20 08:56 | 2011-06-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
46 |  |  | Eval Quotes | Procurement | 40 | 45 |  | 2011-06-05 | 2011-07-31 | 2010-10-20 08:56 | 2011-06-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 1 | [8 empty] | 10% | 2, 4, 9
47 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
48 |  |  | Award / Order Approved |  | 0 | 46 |  | 2011-07-31 | 2011-07-31 | 2010-10-20 08:56 | 2011-07-31 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
49 |  |  | Vendor Oversight |  | 100 | 48 |  | 2011-07-31 | 2011-12-18 | 2010-10-20 08:56 | 2011-07-31 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 1 | [8 empty] | 10% | 2, 4, 9
50 |  |  | Receipt of Hardware |  | 5 | 49 |  | 2011-12-18 | 2011-12-25 | 2010-10-20 08:56 | 2011-12-18 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5%
51 |  |  | QA Inspection |  | 10 | 50 |  | 2011-12-25 | 2012-01-08 | 2010-10-20 08:56 | 2011-12-25 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 4 | 4
52 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
53 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
54 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
55 |  |  | Parts ready for installation |  | 0 | 51 |  | 2012-01-08 | 2012-01-08 | 2010-10-20 08:56 | 2012-01-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5%
56 |  | Handling / Warehouse / Storage |  |  | 1 | 55 |  | 2012-01-08 | 2012-01-09 09:36 | 2010-10-20 08:56 | 2012-01-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [13 empty] | 1 | [7 empty] | 5% | 2, 4, 9
57 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
68 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
69 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
71 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
72 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
75 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
77 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
80 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
87 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
88 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
90 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
92 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
93 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
94 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
97 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
101 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
105 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
106 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
108 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
109 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
110 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
111 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
112 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
113 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
114 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
115 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 43.84 | 38 | 0 | 0 | 0 | 0 | 29 | 5 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 17.0822 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 7.7535 | 4.5076 | 0 | 0 | 0 | 0 | 4.3758 | 0.4453 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: |  |  |  |  | 2010-04-29: Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  | 2010-04-29: 3
|  |  | Purchase orders-Noncommercial items |  |  |  | 2010-04-29: 5
|  |  | Subcontracts (non construction) |  |  |  | 2010-04-29: 8
|  |  | Construction subcontracts |  |  |  | 2010-04-29: 9
PF3 Support consists of the existing PF3 support, but using Inconel bolts along with weld reinforcement.

## 1204 PF4-5 Radial
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Contingency % | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [14 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | 1204 PF5 Leads, PF4/5 Radial Support | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 |  | Preliminary Design Activities | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
7 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
9 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 10 |  | 2010-05-18 | 2010-05-18 | 2010-06-01 | 2010-05-18 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 40 |  |  |  |  | 24 | [8 empty] | 35% | 2, 4, 9, 11
10 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
11 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
12 |  | ME Analysis & CAD Model Iterations (Titus) | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
13 |  |  | Stress, EM, Thermal | Titus | 32 |  | 2010-05-01 | 2010-05-01 | 2010-06-14 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 9.92 | [14 empty] | 20% | 2, 4, 9, 10
14 |  |  | Analysis of Preliminary Design Approved | Titus | 0 | 13 |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
15 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 |  | PDR |  |  | 0 |  | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
17 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
18 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
19 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
20 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
21 |  | DOE CD-2 (Lehman) Review |  |  | 0 |  | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
22 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
23 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
24 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 |  | Final Design Activities | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
29 |  | Update CAD & Design Drawings ( 2 models, 2 dwg) |  |  | 100 |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 22 |  |  |  |  | 6 | [8 empty] | 41.43% | 2, 4, 9, 11
30 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
31 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20% | 2, 4, 9, 10
32 |  | Validation of Design Complete |  | Titus | 20 | 29 |  | 2011-01-04 | 2011-02-01 | 2010-10-20 08:56 | 2011-01-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 24 | [14 empty] | 25%
33 |  | Update CAD Models per Validation |  |  | 10 | 32 |  | 2011-02-01 | 2011-02-15 | 2010-10-20 08:56 | 2011-02-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 2 | [13 empty] | 50% | 2, 4, 9, 11
34 |  | Revise Fabrication & Assembly Drawings per Validation |  |  | 10 | 33 |  | 2011-02-15 | 2011-03-01 | 2010-10-20 08:56 | 2011-02-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 8 | [13 empty] | 50% | 2, 4, 9, 11
35 |  | Review, Check Drawings |  |  | 10 | 34 |  | 2011-03-01 | 2011-03-15 | 2010-10-20 08:56 | 2011-03-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 4 |  |  |  |  | 5.4 | [8 empty] | 27.02% | 2, 4, 9, 11
36 |  | Drawings Ready for FDR |  |  | 0 | 35 |  | 2011-03-15 | 2011-03-15 | 2010-10-20 08:56 | 2011-03-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
37 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 |  | FDR |  |  | 0 |  | 2011-04-29 | 2011-04-29 | 2011-04-29 | 2011-04-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
39 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
43 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
44 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
45 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
46 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
47 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
48 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
49 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
50 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
51 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
52 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
53 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
54 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
55 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
56 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
57 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
68 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
69 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
71 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
72 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
75 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
77 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
80 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
87 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
88 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
90 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
92 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
93 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
94 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
97 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
101 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
105 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
106 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
108 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
109 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
110 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
111 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
112 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
113 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
114 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
115 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 33.92 | 76 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 20.3557 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 5.9991 | 9.0151 | 0 | 0 | 0 | 0 | 5.3415 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: |  |  |  |  | 2010-08-11: Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  | 2010-08-11: 3
|  |  | Purchase orders-Noncommercial items |  |  |  | 2010-08-11: 5
|  |  | Subcontracts (non construction) |  |  |  | 2010-08-11: 8
|  |  | Construction subcontracts |  |  |  | 2010-08-11: 9
PF4/5 Radial support consists of 2 existing clamps at locations 180° apart and near the eletrical leads. Function is to control the shape and centering when under thermal expansion and provide strain relief to eletrical leads.
Ron,
This sub-task (1204) will require field work for Mike Viola.

## 1205 Umbrella
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [11 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Contingency % | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [15 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 |  | 1205 Umbrella Support Structure | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | Lower Umbrella | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 |  | Preliminary Design Activities | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
7 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 | × | Input from Analyst Group: Interface Details to Center Stack. |  | Titus | 0 |  |  | 2010-06-01 | 2010-06-01 | 2010-06-01 | 2010-06-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
9 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 30 |  |  | 2010-05-01 | 2010-05-01 | 2010-06-12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 100 |  |  |  |  | 80 | [8 empty] | 32.22% | 2, 4, 9, 11
10 |  |  | Complete Preliminary CAD Models |  | 12 | 8 |  |  | 2010-10-20 08:56 | 2010-11-06 04:08 | 2010-10-20 08:56 | 2010-06-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 20 | [13 empty] | 50% | 2, 4, 9, 11
11 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
12 |  | ME Analysis & CAD Model Iterations (Titus) | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 6 | [8 empty] | 10% | 2, 4, 9
13 |  |  | Stress, EM, Thermal | Titus | 32 |  |  | 2010-05-01 | 2010-05-01 | 2010-06-14 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 46 | [14 empty] | 20% | 2, 3, 4, 10
14 |  |  | Analysis of Preliminary Design Approved | Titus | 0 | 13 |  |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
15 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 |  | PDR |  |  | 0 |  |  | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20%
17 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
18 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 38 | 16 |  |  | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 40 |  |  |  |  | 24 | [8 empty] | 35% | 2, 4, 9, 11
19 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
20 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
21 |  | DOE CD-2 (Lehman) Review |  |  | 0 |  |  | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
22 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
23 |  | Preliminary Design CAD Model Completed |  |  | 0 | 18 |  |  | 2010-12-12 13:44 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
24 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 |  | Final Design Activities | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 |  | Final Design Eng Iterations, Detailed CAD Modeling (15 models) |  |  | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 45 |  |  |  |  | 20.25 | [8 empty] | 37.59% | 2, 4, 9, 11
29 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
30 |  | Final Design Analysis |  | Titus | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 180 | [14 empty] | 10%
31 |  | Design Drawings ( 11 dwg) |  |  | 35 | 30 |  |  | 2011-01-04 | 2011-02-22 | 2010-10-20 08:56 | 2011-01-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 88 |  |  |  |  | 8.25 | [8 empty] | 20% | 2, 4, 9, 10
32 |  | Validation of Design Complete |  | Titus | 10 | 31 |  |  | 2011-02-22 | 2011-03-08 | 2010-10-20 08:56 | 2011-02-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 15 | [14 empty] | 25%
33 |  | Update CAD Models per Validation |  |  | 10 | 32 |  |  | 2011-03-08 | 2011-03-22 | 2010-10-20 08:56 | 2011-03-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 15 | [13 empty] | 50% | 2, 4, 9, 11
34 |  | Revise Fabrication & Assembly Drawings per Validation |  |  | 10 | 33 |  |  | 2011-03-22 | 2011-04-05 | 2010-10-20 08:56 | 2011-03-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 44 | [13 empty] | 50% | 2, 4, 9, 11
35 |  | Review, Check Drawings |  |  | 5 | 34 |  |  | 2011-04-05 | 2011-04-12 | 2010-10-20 08:56 | 2011-04-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 22 |  |  |  |  | 29.7 | [8 empty] | 27.02% | 2, 4, 9, 11
36 |  | Drawings Ready for FDR |  |  | 0 | 35 |  |  | 2011-04-12 | 2011-04-12 | 2010-10-20 08:56 | 2011-04-12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
37 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 |  | FDR |  |  | 0 |  |  | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12%
39 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 |  | Procurement & Fabrication | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 |  | Prep Req & Procurement Package |  |  | 10 |  |  | 2011-05-01 | 2011-05-01 | 2011-05-15 | 2011-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 40 | [8 empty] | 33% | 2, 4, 9
43 |  | Submit Req to Procurement |  |  | 0 | 42 |  |  | 2011-05-15 | 2011-05-15 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
44 |  |  | Procurement Processing | Procurement | 22 | 43 |  |  | 2011-05-15 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
45 |  |  | Submit for Vendor Quotes |  | 0 | 44 |  |  | 2011-06-14 19:12 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
46 |  |  | Eval Quotes | Procurement | 43 | 45 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 10% | 2, 4, 9
47 |  |  | Tech Eval of Vendors |  | 43 | 45 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 10% | 2, 4, 9
48 |  |  | Award / Order Approved |  | 0 | 46 | 47 |  | 2011-08-14 | 2011-08-14 | 2010-10-20 08:56 | 2011-08-14 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
49 |  |  | Vendor Oversight |  | 102 | 48 |  |  | 2011-08-14 | 2012-01-03 19:12 | 2010-10-20 08:56 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 10 | [8 empty] | 10% | 2, 4, 9
50 |  |  | Receipt of Hardware |  | 4 | 48 |  |  | 2011-08-14 | 2011-08-19 14:24 | 2010-10-20 08:56 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
51 |  | QA Inspection |  |  | 10 | 50 |  |  | 2011-08-19 14:24 | 2011-09-02 14:24 | 2010-10-20 08:56 | 2011-08-19 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 12 | 48 | [7 empty] | 42% | 2, 4, 9
52 |  | Resolve Procurement Issues |  |  | 5 | 51 |  |  | 2011-09-02 14:24 | 2011-09-09 14:24 | 2010-10-20 08:56 | 2011-09-02 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 2 | [8 empty] | 10% | 2, 4, 9
53 |  | Documentation: Assembly Procedures |  |  | 10 | 52 |  |  | 2011-09-09 14:24 | 2011-09-23 14:24 | 2010-10-20 08:56 | 2011-09-09 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 4 |  |  |  |  | 16 | [8 empty] | 18% | 2, 4, 9
54 |  | Assembly of Components |  |  | 15 | 53 |  |  | 2011-09-23 14:24 | 2011-10-14 14:24 | 2010-10-20 08:56 | 2011-09-23 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 4 | 32 | [7 empty] | 45.56% | 2, 4, 9
55 |  | Handling / Warehouse / Storage |  |  | 3 | 54 |  |  | 2011-10-14 14:24 | 2011-10-18 19:12 | 2010-10-20 08:56 | 2011-10-14 14:24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [13 empty] | 8 | [7 empty] | 20% | 2, 4, 9
56 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
57 |  |  | Parts ready for installation |  | 0 | 55 |  |  | 2011-10-18 19:12 | 2011-10-18 19:12 | 2010-10-20 08:56 | 2011-10-18 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
58 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 |  | 1205 Umbrella Support Structure | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 |  | Upper Umbrella | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 |  | Preliminary Design Activities | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | × | Input from Analyst Group: Interface Details to Center Stack. |  | Titus | 0 |  |  | 2010-06-01 | 2010-06-01 | 2010-06-01 | 2010-06-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 30 |  |  | 2010-05-01 | 2010-05-01 | 2010-06-12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 100 |  |  |  |  | 80 | [8 empty] | 32.22% | 2, 4, 9, 11
68 |  |  | Complete Preliminary CAD Models |  | 12 | 8 |  |  | 2010-10-20 08:56 | 2010-11-06 04:08 | 2010-10-20 08:56 | 2010-06-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 20 | [13 empty] | 50% | 2, 4, 9, 11
69 |  | Mockups: Real estate issues |  |  | 66 |  |  | 2010-05-01 | 2010-05-01 | 2010-08-01 09:36 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 |  | ME Analysis & CAD Model Iterations (Titus) | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 6 | [8 empty] | 10% | 2, 4, 9
71 |  |  | Stress, EM, Thermal | Titus | 32 |  |  | 2010-05-01 | 2010-05-01 | 2010-06-14 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 46 | [14 empty] | 20% | 2, 3, 4, 10
72 |  |  | Analysis of Preliminary Design Approved | Titus | 0 | 13 |  |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
73 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 |  | PDR |  |  | 0 |  |  | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
75 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 38 | 16 |  |  | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 40 |  |  |  |  | 24 | [8 empty] | 35% | 2, 4, 9, 11
77 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 |  | DOE CD-2 (Lehman) Review |  |  | 0 |  |  | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
80 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 |  | Preliminary Design CAD Model Completed |  |  | 0 | 18 |  |  | 2010-12-12 13:44 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
82 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 |  | Final Design Activities | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 |  | Final Design Eng Iterations, Detailed CAD Modeling (15 models) |  |  | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 45 |  |  |  |  | 20.25 | [8 empty] | 37.59% | 2, 4, 9, 11
87 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
88 |  | Final Design Analysis |  | Titus | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 180 | [14 empty] | 10%
89 |  | Design Drawings ( 11 dwg) |  |  | 35 | 88 |  |  | 2011-01-04 | 2011-02-22 | 2010-10-20 08:56 | 2011-01-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 88 |  |  |  |  | 8.25 | [8 empty] | 20% | 2, 4, 9, 10
90 |  | Validation of Design Complete |  | Titus | 10 | 89 |  |  | 2011-02-22 | 2011-03-08 | 2010-10-20 08:56 | 2011-02-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 15 | [14 empty] | 25%
91 |  | Update CAD Models per Validation |  |  | 10 | 90 |  |  | 2011-03-08 | 2011-03-22 | 2010-10-20 08:56 | 2011-03-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 15 | [13 empty] | 50% | 2, 4, 9, 11
92 |  | Revise Fabrication & Assembly Drawings per Validation |  |  | 10 | 91 |  |  | 2011-03-22 | 2011-04-05 | 2010-10-20 08:56 | 2011-03-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 44 | [13 empty] | 50% | 2, 4, 9, 11
93 |  | Review, Check Drawings |  |  | 5 | 92 |  |  | 2011-04-05 | 2011-04-12 | 2010-10-20 08:56 | 2011-04-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 22 |  |  |  |  | 29.7 | [8 empty] | 27.02% | 2, 4, 9, 11
94 |  | Drawings Ready for FDR |  |  | 0 | 93 |  |  | 2011-04-12 | 2011-04-12 | 2010-10-20 08:56 | 2011-04-12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
95 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 |  | FDR |  |  | 0 |  |  | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
97 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 |  | Procurement & Fabrication | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 |  | Prep Req & Procurement Package |  |  | 10 |  |  | 2011-05-01 | 2011-05-01 | 2011-05-15 | 2011-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 40 | [8 empty] | 33% | 2, 4, 9
101 |  | Submit Req to Procurement |  |  | 0 | 100 |  |  | 2011-05-15 | 2011-05-15 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
102 |  |  | Procurement Processing | Procurement | 22 | 101 |  |  | 2011-05-15 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
103 |  |  | Submit for Vendor Quotes |  | 0 | 102 |  |  | 2011-06-14 19:12 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
104 |  |  | Eval Quotes | Procurement | 43 | 103 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 10% | 2, 4, 9
105 |  |  | Tech Eval of Vendors |  | 43 | 103 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 10% | 2, 4, 9
106 |  |  | Award / Order Approved |  | 0 | 105 |  |  | 2011-08-14 | 2011-08-14 | 2010-10-20 08:56 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
107 |  |  | Vendor Oversight |  | 102 | 106 |  |  | 2011-08-14 | 2012-01-03 19:12 | 2010-10-20 08:56 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 10 | [8 empty] | 10% | 2, 4, 9
108 |  |  | Receipt of Hardware |  | 5 | 107 |  |  | 2012-01-03 19:12 | 2012-01-10 19:12 | 2010-10-20 08:56 | 2012-01-03 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
109 |  | QA Inspection |  |  | 10 | 108 |  |  | 2012-01-10 19:12 | 2012-01-24 19:12 | 2010-10-20 08:56 | 2012-01-10 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 12 | 48 | [7 empty] | 42% | 2, 4, 9
110 |  | Resolve Procurement Issues |  |  | 5 | 109 |  |  | 2012-01-24 19:12 | 2012-01-31 19:12 | 2010-10-20 08:56 | 2012-01-24 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 2 | [8 empty] | 10% | 2, 4, 9
111 |  | Documentation: Assembly Procedures |  |  | 10 | 110 |  |  | 2012-01-31 19:12 | 2012-02-14 19:12 | 2010-10-20 08:56 | 2012-01-31 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 4 |  |  |  |  | 16 | [8 empty] | 18% | 2, 4, 9
112 |  | Assembly of Components |  |  | 15 | 111 |  |  | 2012-02-14 19:12 | 2012-03-06 19:12 | 2010-10-20 08:56 | 2012-02-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 4 | 32 | [7 empty] | 45.56% | 2, 4, 9
113 |  | Handling / Warehouse / Storage |  |  | 3 | 112 |  |  | 2012-03-06 19:12 | 2012-03-11 | 2010-10-20 08:56 | 2012-03-06 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [13 empty] | 8 | [7 empty] | 20% | 2, 4, 9
114 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
115 |  |  | Parts ready for installation |  | 0 | 113 |  |  | 2012-03-11 | 2012-03-11 | 2010-10-20 08:56 | 2012-03-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
116 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[11 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [14 empty] | 0 | 0 | 0 | 0 | 0 | 482 | 756 | 0 | 0 | 0 | 0 | 536.4 | 176 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 271.5352 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 85.2465 | 89.6767 | 0 | 0 | 0 | 0 | 80.9374 | 15.6746 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: | [5 empty] | 2010-04-29: Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  |  | 2010-04-29: 3
|  |  | Purchase orders-Noncommercial items |  |  |  |  | 2010-04-29: 5
|  |  | Subcontracts (non construction) |  |  |  |  | 2010-04-29: 8
|  |  | Construction subcontracts |  |  |  |  | 2010-04-29: 9
Lower Umbrella defined as: lower (lid / spokes, umbrella, legs), and interface to Center Stack, interface to pedestal.
Upper Umbrella defined as: upper( lid, umbrella, legs) and interface to Center Stack.

## 1206 Pedestal
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [11 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Contingency % | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [15 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | 1206 Pedestal Support Structure | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 |  | Preliminary Design Activities | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
7 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 |  | Input from Analyst Group: Interface Details to Center Stack. |  | Titus | 0 |  |  | 2010-06-01 | 2010-06-01 | 2010-06-01 | 2010-06-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
9 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 30 |  |  | 2010-05-01 | 2010-05-01 | 2010-06-12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 80 |  |  |  |  | 60 | [8 empty] | 32.86% | 2, 4, 9, 11
10 |  |  | Complete Preliminary CAD Models |  | 10 | 8 |  |  | 2010-10-20 08:56 | 2010-11-03 08:56 | 2010-10-20 08:56 | 2010-06-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 20 | [13 empty] | 50% | 2, 4, 9, 11
11 |  | Mockups: Real estate issues |  |  | 66 |  |  | 2010-05-01 | 2010-05-01 | 2010-08-01 09:36 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
12 |  | ME Analysis & CAD Model Iterations (Titus) | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
13 |  |  | Stress, EM, Thermal | Titus | 32 |  |  | 2010-05-01 | 2010-05-01 | 2010-06-14 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
14 |  |  | Analysis of Preliminary Design Approved | Titus | 0 | 13 |  |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
15 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 |  | PDR |  |  | 0 |  |  | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20%
17 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
18 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 38 | 16 |  |  | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 24 |  |  |  |  | 12 | [8 empty] | 36.67% | 2, 4, 9, 11
19 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
20 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
21 |  | DOE CD-2 (Lehman) Review |  |  | 0 |  |  | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
22 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
23 |  | Preliminary Design CAD Model Completed |  |  | 0 | 18 |  |  | 2010-12-12 13:44 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
24 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 |  | Final Design Activities | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 |  | Final Design Eng Iterations, Detailed CAD Modeling (19 models) |  |  | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 57 |  |  |  |  | 23 | [8 empty] | 38.5% | 2, 4, 9, 11
29 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
30 |  | Final Design Analysis |  | Titus | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 60
31 |  | Design Drawings (8 dwg) |  |  | 35 | 30 |  |  | 2011-01-04 | 2011-02-22 | 2010-10-20 08:56 | 2011-01-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 64 |  |  |  |  | 6 | [8 empty] | 20% | 2, 4, 9, 10
32 |  | Validation of Design Complete |  | Titus | 10 | 31 |  |  | 2011-02-22 | 2011-03-08 | 2010-10-20 08:56 | 2011-02-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 30 | [14 empty] | 25%
33 |  | Update CAD Models per Validation |  |  | 10 | 32 |  |  | 2011-03-08 | 2011-03-22 | 2010-10-20 08:56 | 2011-03-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 19 | [13 empty] | 50% | 2, 4, 9, 11
34 |  | Revise Fabrication & Assembly Drawings per Validation |  |  | 10 | 33 |  |  | 2011-03-22 | 2011-04-05 | 2010-10-20 08:56 | 2011-03-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 32 | [13 empty] | 50% | 2, 4, 9, 11
35 |  | Review, Check Drawings |  |  | 5 | 34 |  |  | 2011-04-05 | 2011-04-12 | 2010-10-20 08:56 | 2011-04-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 16 |  |  |  |  | 20.8 | [8 empty] | 27.39% | 2, 4, 9, 11
36 |  | Drawings Ready for FDR |  |  | 0 | 35 |  |  | 2011-04-12 | 2011-04-12 | 2010-10-20 08:56 | 2011-04-12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
37 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 |  | FDR |  |  | 0 |  |  | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12%
39 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 |  | Procurement & Fabrication | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 |  | Prep Req & Procurement Package |  |  | 10 |  |  | 2011-05-01 | 2011-05-01 | 2011-05-15 | 2011-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 32 | [8 empty] | 20% | 2, 4, 9
43 |  | Submit Req to Procurement |  |  | 0 | 42 |  |  | 2011-05-15 | 2011-05-15 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
44 |  |  | Procurement Processing | Procurement | 22 | 43 |  |  | 2011-05-15 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
45 |  |  | Submit for Vendor Quotes |  | 0 | 44 |  |  | 2011-06-14 19:12 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
46 |  |  | Eval Quotes | Procurement | 43 | 45 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 10% | 2, 4, 9
47 |  |  | Tech Eval of Vendors |  | 43 | 45 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 10% | 2, 4, 9
48 |  |  | Award / Order Approved |  | 0 | 46 | 47 |  | 2011-08-14 | 2011-08-14 | 2010-10-20 08:56 | 2011-08-14 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
49 |  |  | Vendor Oversight |  | 102 | 48 |  |  | 2011-08-14 | 2012-01-03 19:12 | 2010-10-20 08:56 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 10% | 2, 4, 9
50 |  |  | Receipt of Hardware |  | 5 | 49 |  |  | 2012-01-03 19:12 | 2012-01-10 19:12 | 2010-10-20 08:56 | 2012-01-03 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
51 |  | QA Inspection |  |  | 10 | 50 |  |  | 2012-01-10 19:12 | 2012-01-24 19:12 | 2010-10-20 08:56 | 2012-01-10 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 4 | 16 | [7 empty] | 42% | 2, 4, 9
52 |  | Resolve Procurement Issues |  |  | 5 | 51 |  |  | 2012-01-24 19:12 | 2012-01-31 19:12 | 2010-10-20 08:56 | 2012-01-24 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 2 | [8 empty] | 10% | 2, 4, 9
53 |  | Documentation: Assembly Procedures |  |  | 15 | 52 |  |  | 2012-01-31 19:12 | 2012-02-21 19:12 | 2010-10-20 08:56 | 2012-01-31 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 4 |  |  |  |  | 32 | [8 empty] | 14.44% | 2, 4, 9
54 |  | Assembly of Components |  |  | 20 | 53 |  |  | 2012-02-21 19:12 | 2012-03-20 19:12 | 2010-10-20 08:56 | 2012-02-21 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 4 | 80 | [7 empty] | 48.1% | 2, 4, 9
55 |  |  | Parts ready for installation |  | 0 | 54 |  |  | 2012-03-20 19:12 | 2012-03-20 19:12 | 2010-10-20 08:56 | 2012-03-20 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
56 |  | Handling / Warehouse / Storage |  |  | 5 | 55 |  |  | 2012-03-20 19:12 | 2012-03-27 19:12 | 2010-10-20 08:56 | 2012-03-20 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [13 empty] | 12 | [7 empty] | 50% | 2, 4, 9
57 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
68 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
69 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10% | 2, 4, 10
71 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20% | 2, 3, 4, 10
72 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20% | 2, 4, 10
75 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
77 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0% | 2, 4, 10
80 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
87 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
88 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20% | 3, 9
90 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
92 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
93 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
94 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12% | 2, 4, 10
97 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 33% | 2, 4, 10
101 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
105 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
106 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50%
108 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 11.2% | 2, 4, 10
109 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
110 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5% | 2, 4, 10
111 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
112 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
113 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25% | 2, 4, 10
114 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
115 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[11 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [14 empty] | 0 | 0 | 0 | 0 | 0 | 90 | 316 | 0 | 0 | 0 | 0 | 219.8 | 108 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 96.1854 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 15.9174 | 37.4839 | 0 | 0 | 0 | 0 | 33.1656 | 9.6185 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: | [5 empty] | 2010-04-29: Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  |  | 2010-04-29: 3
|  |  | Purchase orders-Noncommercial items |  |  |  |  | 2010-04-29: 5
|  |  | Subcontracts (non construction) |  |  |  |  | 2010-04-29: 8
|  |  | Construction subcontracts |  |  |  |  | 2010-04-29: 9
The pedestal support consists of: lower & upper pedestal, grout plate, epoxy bonded insert bolts, and interfaces to the lower lid and center stack.
Installation of the clamps requires drilling holes for anchors which is field work for Mike Viola. This will also require alignment, possibly using an alignment fixture.

## 1207 Ves Legs
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Contingency % | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [14 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | 1207 Vessel Leg Support Structure | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 |  | Preliminary Design Activities | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
7 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
9 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
10 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
11 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
12 |  | ME Analysis & CAD Model Iterations (Titus) | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
13 |  |  | Stress, EM, Thermal | Titus | 32 |  | 2010-05-01 | 2010-05-01 | 2010-06-14 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 19.84 | [14 empty] | 20% | 2, 4, 9, 10
14 |  |  | Analysis of Preliminary Design Approved | Titus | 0 | 13 |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
15 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 |  | PDR |  |  | 0 |  | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20%
17 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
18 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
19 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
20 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
21 |  | DOE CD-2 (Lehman) Review |  |  | 0 |  | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
22 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
23 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
24 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 |  | Final Design Activities | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 9, 11
29 |  | Update CAD & Design Drawings ( 3 models, 2 dwg) |  |  | 100 |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 25 |  |  |  |  | 7 | [8 empty] | 41.25% | 2, 4, 9, 11
30 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
31 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20% | 3, 9
32 |  | Validation of Design Complete |  | Titus | 20 | 29 |  | 2011-01-04 | 2011-02-01 | 2010-10-20 08:56 | 2011-01-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 8
33 |  | Update CAD Models per Validation |  |  | 10 | 32 |  | 2011-02-01 | 2011-02-15 | 2010-10-20 08:56 | 2011-02-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 3 | [13 empty] | 50% | 2, 4, 9, 11
34 |  | Revise Fabrication & Assembly Drawings per Validation |  |  | 10 | 33 |  | 2011-02-15 | 2011-03-01 | 2010-10-20 08:56 | 2011-02-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 8 | [13 empty] | 50% | 2, 4, 9, 11
35 |  | Review, Check Drawings |  |  | 10 | 34 |  | 2011-03-01 | 2011-03-15 | 2010-10-20 08:56 | 2011-03-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 4 |  |  |  |  | 6 | [8 empty] | 26% | 2, 4, 9, 11
36 |  | Drawings Ready for FDR |  |  | 0 | 35 |  | 2011-03-15 | 2011-03-15 | 2010-10-20 08:56 | 2011-03-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5%
37 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 |  | FDR |  |  | 0 |  | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12%
39 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 |  | Procurement & Fabrication | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 |  | Prep Req & Procurement Package |  |  | 3 |  | 2011-05-01 | 2011-05-01 | 2011-05-05 04:48 | 2011-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 10% | 2, 4, 9
43 |  | Submit Req to Procurement |  |  | 0 | 42 |  | 2011-05-05 04:48 | 2011-05-05 04:48 | 2010-10-20 08:56 | 2011-05-05 04:48 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
44 |  |  | Procurement Processing | Procurement | 22 | 43 |  | 2011-05-05 04:48 | 2011-06-05 | 2010-10-20 08:56 | 2011-05-05 04:48 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
45 |  |  | Submit for Vendor Quotes |  | 0 | 44 |  | 2011-06-05 | 2011-06-05 | 2010-10-20 08:56 | 2011-06-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
46 |  |  | Eval Quotes | Procurement | 43 | 45 |  | 2011-06-05 | 2011-08-04 04:48 | 2010-10-20 08:56 | 2011-06-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 1 | [8 empty] | 10% | 2, 4, 9
47 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
48 |  |  | Award / Order Approved |  | 0 | 46 |  | 2011-08-04 04:48 | 2011-08-04 04:48 | 2010-10-20 08:56 | 2011-08-04 04:48 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
49 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10% | 2, 4, 9
50 |  |  | Receipt of Hardware |  | 60 | 48 |  | 2011-08-04 04:48 | 2011-10-27 04:48 | 2010-10-20 08:56 | 2011-08-04 04:48 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5%
51 |  | QA Inspection |  |  | 10 | 50 |  | 2011-10-27 04:48 | 2011-11-10 04:48 | 2010-10-20 08:56 | 2011-10-27 04:48 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 1 | 2 | [7 empty] | 36.67% | 2, 4, 9
52 |  | Resolve Procurement Issues |  |  | 5 | 51 |  | 2011-11-10 04:48 | 2011-11-17 04:48 | 2010-10-20 08:56 | 2011-11-10 04:48 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 1
53 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
54 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
55 |  |  | Parts ready for installation |  | 0 | 52 |  | 2011-11-17 04:48 | 2011-11-17 04:48 | 2010-10-20 08:56 | 2011-11-17 04:48 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5%
56 |  | Handling / Warehouse / Storage |  |  | 1 | 55 |  | 2011-11-17 04:48 | 2011-11-18 14:24 | 2010-10-20 08:56 | 2011-11-17 04:48 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [13 empty] | 1 | [7 empty] | 5% | 2, 4, 9
57 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
68 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
69 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10% | 2, 4, 10
71 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20% | 2, 3, 4, 10
72 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20% | 2, 4, 10
75 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
77 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0% | 2, 4, 10
80 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
87 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
88 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20% | 3, 9
90 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
92 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
93 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
94 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12% | 2, 4, 10
97 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 33% | 2, 4, 10
101 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
105 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
106 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50%
108 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 11.2% | 2, 4, 10
109 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
110 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 5% | 2, 4, 10
111 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
112 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | #DIV/0! | 2, 4, 10
113 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25% | 2, 4, 10
114 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 50% | 2, 4, 10
115 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 27.84 | 40 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 13.5571 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 4.9238 | 4.7448 | 0 | 0 | 0 | 0 | 3.6214 | 0.26718 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: |  |  |  |  | 2010-04-29: Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  | 2010-04-29: 3
|  |  | Purchase orders-Noncommercial items |  |  |  | 2010-04-29: 5
|  |  | Subcontracts (non construction) |  |  |  | 2010-04-29: 8
|  |  | Construction subcontracts |  |  |  | 2010-04-29: 9
Vessel leg support upgrades consists of 4 S.S. clamps and 16-0.5 inch epoxy bonded anchor bolts.
Installation of the clamps requires drilling holes for the hilti anchors which is field work for Mike Viola. This will also require alignment, possibly using an alignment fixture.

## 1208 PF4-5 Vert Sup
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [11 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM**TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Contingency % | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [15 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | 1208 PF4 PF5 Verticle Support | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 |  | Preliminary Design Activities | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
7 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
9 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 20 |  |  | 2010-05-01 | 2010-05-01 | 2010-05-29 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 40 |  |  |  |  | 24 | [8 empty] | 35% | 2, 4, 9, 11
10 |  |  | Complete Preliminary CAD Models |  | 5 | 9 |  |  | 2010-10-20 08:56 | 2010-10-27 08:56 | 2010-10-20 08:56 | 2010-05-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 20 |  |  |  |  | 8 | [8 empty] | 38.57% | 2, 4, 9, 11
11 |  | Mockups: Real estate issues & sizing |  |  | 66 |  |  | 2010-05-01 | 2010-05-01 | 2010-08-01 09:36 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 10 | [5 empty] | 4 |  |  |  |  | 2 | 32 | [7 empty] | 47.89% | 2, 4, 9, 11
12 |  | ME Analysis & CAD Model Iterations (Titus) | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
13 |  |  | Stress, EM, Thermal | Titus | 32 |  |  | 2010-05-01 | 2010-05-01 | 2010-06-14 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 49.28 | [14 empty] | 20% | 2, 4, 9, 10
14 |  |  | Analysis of Preliminary Design Approved | Titus | 0 | 10 | 13 |  | 2010-10-27 08:56 | 2010-10-27 08:56 | 2010-10-20 08:56 | 2010-10-27 08:56 | 2010-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
15 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 |  | PDR |  |  | 0 |  |  | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20%
17 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
18 |  | Design Eng & CAD Models: Iterations, Optimization & Updates |  |  | 38 | 16 |  |  | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 24 |  |  |  |  | 4 | [8 empty] | 44.29% | 2, 4, 9, 11
19 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
20 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
21 |  | DOE CD-2 (Lehman) Review |  |  | 0 |  |  | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
22 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
23 |  | Preliminary Design CAD model Completed |  |  | 0 | 18 |  |  | 2010-12-12 13:44 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-12-12 13:44 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
24 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 |  | Final Design Activities | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 |  | Final Design Eng Iterations, Detailed CAD Modeling (42 models) |  |  | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 126 |  |  |  |  | 38 | [8 empty] | 40.73% | 2, 4, 9, 11
29 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
30 |  | Final Design Analysis |  | Titus | 100 |  |  | 2010-08-17 | 2010-08-17 | 2011-01-04 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 200
31 |  | Design Drawings (23 dwg) |  |  | 45 | 30 |  |  | 2011-01-04 | 2011-03-08 | 2010-10-20 08:56 | 2011-01-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 184 |  |  |  |  | 17 | [8 empty] | 20% | 2, 4, 9, 10
32 |  | Validation of Design Complete |  | Titus | 10 | 31 |  |  | 2011-03-08 | 2011-03-22 | 2010-10-20 08:56 | 2011-03-08 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [6 empty] | 30 | [14 empty] | 25%
33 |  | Update CAD Models per Validation |  |  | 10 | 32 |  |  | 2011-03-22 | 2011-04-05 | 2010-10-20 08:56 | 2011-03-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 42 | [13 empty] | 50% | 2, 4, 9, 11
34 |  | Revise Fabrication & Assembly Drawings per Validation |  |  | 10 | 33 |  |  | 2011-04-05 | 2011-04-19 | 2010-10-20 08:56 | 2011-04-05 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 92 | [13 empty] | 50% | 2, 4, 9, 11
35 |  | Review, Check Drawings |  |  | 5 | 34 |  |  | 2011-04-19 | 2011-04-26 | 2010-10-20 08:56 | 2011-04-19 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 46 |  |  |  |  | 46 | [8 empty] | 30% | 2, 4, 9, 11
36 |  | Drawings Ready for FDR |  |  | 0 | 35 |  |  | 2011-04-26 | 2011-04-26 | 2010-10-20 08:56 | 2011-04-26 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
37 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 |  | FDR |  |  | 0 |  |  | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-04-29 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12%
39 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 |  | Procurement & Fabrication | [8 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 |  | Prep Req & Procurement Package |  |  | 10 |  |  | 2011-05-01 | 2011-05-01 | 2011-05-15 | 2011-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 32 | [8 empty] | 50% | 2, 4, 9
43 |  | Submit Req to Procurement |  |  | 0 | 42 |  |  | 2011-05-15 | 2011-05-15 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
44 |  |  | Procurement Processing | Procurement | 22 | 43 |  |  | 2011-05-15 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-05-15 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
45 |  |  | Submit for Vendor Quotes |  | 0 | 44 |  |  | 2011-06-14 19:12 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
46 |  |  | Eval Quotes | Procurement | 43 | 45 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 25% | 2, 4, 10
47 |  |  | Tech Eval of Vendors |  | 43 | 45 |  |  | 2011-06-14 19:12 | 2011-08-14 | 2010-10-20 08:56 | 2011-06-14 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 16 | [8 empty] | 25% | 2, 4, 10
48 |  |  | Award / Order Approved |  | 0 | 46 | 47 |  | 2011-08-14 | 2011-08-14 | 2010-10-20 08:56 | 2011-08-14 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
49 |  |  | Vendor Oversight |  | 101 | 48 |  |  | 2011-08-14 | 2012-01-02 09:36 | 2010-10-20 08:56 | 2011-08-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 40 | [8 empty] | 25% | 2, 4, 10
50 |  |  | Receipt of Hardware |  | 1 | 49 |  |  | 2012-01-02 09:36 | 2012-01-03 19:12 | 2010-10-20 08:56 | 2012-01-02 09:36 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
51 |  | QA Inspection |  |  | 10 | 50 |  |  | 2012-01-03 19:12 | 2012-01-17 19:12 | 2010-10-20 08:56 | 2012-01-03 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 4 | 12 | [7 empty] | 40% | 2, 4, 10
52 |  | Resolve Procurement Issues |  |  | 5 | 51 |  |  | 2012-01-17 19:12 | 2012-01-24 19:12 | 2010-10-20 08:56 | 2012-01-17 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 2 | [8 empty] | 20% | 2, 4, 10
53 |  | Documentation: Assembly Procedures |  |  | 10 | 52 |  |  | 2012-01-24 19:12 | 2012-02-07 19:12 | 2010-10-20 08:56 | 2012-01-24 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 24 | [8 empty] | 33% | 2, 4, 10
54 |  | Assembly of Components |  |  | 15 | 53 |  |  | 2012-02-07 19:12 | 2012-02-28 19:12 | 2010-10-20 08:56 | 2012-02-07 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 4 | 80 | [7 empty] | 48.1% | 2, 4, 10
55 |  |  | Parts ready for installation |  | 0 | 54 |  |  | 2012-02-28 19:12 | 2012-02-28 19:12 | 2010-10-20 08:56 | 2012-02-28 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 25%
56 |  | Handling / Warehouse / Storage |  |  | 5 | 55 |  |  | 2012-02-28 19:12 | 2012-03-06 19:12 | 2010-10-20 08:56 | 2012-02-28 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [13 empty] | 24 | [7 empty] | 50% | 2, 4, 10
57 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
68 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
69 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
71 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
72 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
75 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
77 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
80 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
87 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
88 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
90 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
92 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
93 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
94 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
97 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
101 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
105 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
106 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
108 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
109 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
110 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
111 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
112 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
113 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
114 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
115 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[11 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [14 empty] | 10 | 0 | 0 | 0 | 0 | 279.28 | 578 | 0 | 0 | 0 | 0 | 269 | 148 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 183.4261 | [11 empty] | 11.7 | 0 | 0 | 0 | 0 | 49.3935 | 68.5624 | 0 | 0 | 0 | 0 | 40.5894 | 13.1809 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: | [5 empty] | 2010-04-29: Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  |  | 2010-04-29: 3
|  |  | Purchase orders-Noncommercial items |  |  |  |  | 2010-04-29: 5
|  |  | Subcontracts (non construction) |  |  |  |  | 2010-04-29: 8
|  |  | Construction subcontracts |  |  |  |  | 2010-04-29: 9
PF4-PF5 Verticle Support consists of: columns, column clamps, visco-elastic material shims, and shims at existing support plates.

## 1209 XXX C&S
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM**TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [14 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | 1209 xxx | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
7 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
9 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
10 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
11 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
12 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
13 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
14 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
15 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
17 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
18 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
19 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
20 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
21 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
22 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
23 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
24 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
29 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
30 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
31 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
32 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
33 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
34 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
35 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
36 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
37 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
39 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
43 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
44 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
45 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
46 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
47 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
48 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
49 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
50 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
51 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
52 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
53 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
54 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
55 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
56 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
57 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
68 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
69 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
71 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
72 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
75 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
77 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
80 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
87 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
88 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
90 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
92 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
93 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
94 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
97 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
101 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
105 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
106 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
108 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
109 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
110 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
111 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
112 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
113 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
114 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
115 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: | [6 empty] | Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items | [5 empty] | 3
|  |  | Purchase orders-Noncommercial items | [5 empty] | 5
|  |  | Subcontracts (non construction) | [5 empty] | 8
|  |  | Construction subcontracts | [5 empty] | 9

## 1220 Misc C&S
| Cost Center: |  |  | 9417
| Job Number: |  |  | 1200
| Job Title: |  |  | Vacuum Vessel & Support Structure
| Job Manager: |  |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE**TB (Electr Tech) | EM** EM (FO&M Engr) | EM**TB (FO&M Tech) | FC** AM (P&C Officer) | LP** TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Contingency % | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optional) | [14 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 |  | 1220 Misc | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 |  | Preliminary Design Activities |  |  | 77 |  | 2010-05-01 | 2010-05-01 | 2010-08-16 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 |  | Revise FMEA |  |  | 5 |  | 2010-05-24 | 2010-05-24 | 2010-05-31 | 2010-05-24 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 8 | [8 empty] | 25% | 2, 4
6 |  | Revise SRD |  |  | 5 | 5 |  | 2010-10-20 08:56 | 2010-10-27 08:56 | 2010-10-20 08:56 | 2010-05-31 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 24 | [8 empty] | 33% | 2, 4
7 |  | Project Oversight |  |  | 77 |  | 2010-05-01 | 2010-05-01 | 2010-08-16 19:12 | 2010-05-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 231 | [8 empty] | 25% | 2, 4, 9
8 |  | Update Cost & Schedule |  |  | 2 |  | 2010-06-14 | 2010-06-14 | 2010-06-16 19:12 | 2010-06-14 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 24 | [8 empty] | 33% | 2, 4
9 |  | Prep for PDR |  |  | 5 |  | 2010-06-01 | 2010-06-01 | 2010-06-08 | 2010-06-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 40 | [8 empty] | 20% | 2, 4
10 |  | PDR |  |  | 0 |  | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 20%
11 |  | Disposition of PDR CHITS |  |  | 30 | 10 |  | 2010-10-20 08:56 | 2010-12-01 08:56 | 2010-10-20 08:56 | 2010-06-23 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 40 | [8 empty] | 50% | 2, 4
12 |  | DOE CD-2 (Lehman) Review | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
13 |  |  | Prep for Review |  | 5 |  | 2010-08-04 | 2010-08-04 | 2010-08-11 | 2010-08-04 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 40 | [8 empty] | 20% | 2, 4
14 |  |  | Review |  | 0 | 13 |  | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-08-11 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 0%
15 |  | Final Design Activities |  |  | 162 |  | 2010-08-17 | 2010-08-17 | 2011-03-31 19:12 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
16 |  | Project Oversight |  |  | 162 |  | 2010-08-17 | 2010-08-17 | 2011-03-31 19:12 | 2010-08-17 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 324 | [8 empty] | 50% | 2, 4, 9
17 |  | Preliminary Design Accepted: Design Requirements Frozen |  |  | 0 |  | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 10%
18 |  | Update Cost & Schedule |  |  | 2 |  | 2011-03-22 | 2011-03-22 | 2011-03-24 19:12 | 2011-03-22 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 24 | [8 empty] | 33% | 2, 4
19 |  | Prep for FDR |  |  | 5 | 18 |  | 2011-03-24 19:12 | 2011-03-31 19:12 | 2010-10-20 08:56 | 2011-03-24 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [12 empty] | 40 | [8 empty] | 20% | 2, 4
20 |  | FDR |  |  | 0 | 19 |  | 2011-03-31 19:12 | 2011-03-31 19:12 | 2010-10-20 08:56 | 2011-03-31 19:12 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [21 empty] | 12%
21 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
22 |  | Laboratory Misc / Admin: meetings, training, safety, etc. |  |  | 217 |  | 2010-06-01 | 2010-06-01 | 2011-03-31 19:12 | 2010-06-01 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | [7 empty] | 22 |  |  |  |  | 129 | [8 empty] | 10% | 2, 4, 9
23 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
24 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
29 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
30 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
31 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
32 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
33 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
34 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
35 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
36 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
37 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
39 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
43 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
44 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
45 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
46 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
47 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
48 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
49 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
50 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
51 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
52 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
53 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
54 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
55 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
56 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
57 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
68 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
69 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
71 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
72 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
75 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
77 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
80 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
87 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
88 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
90 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
92 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
93 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
94 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
97 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
101 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
105 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
106 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
108 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
109 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
110 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
111 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
112 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
113 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
114 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
115 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 142.032 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2.6096 | 0 | 0 | 0 | 0 | 139.4224 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
|  | (1) Procurement lead time: |  |  |  |  | 2010-08-31: Weeks
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  | 2010-08-31: 3
|  |  | Purchase orders-Noncommercial items |  |  |  | 2010-08-31: 5
|  |  | Subcontracts (non construction) |  |  |  | 2010-08-31: 8
|  |  | Construction subcontracts |  |  |  | 2010-08-31: 9
Item 22: Non project related activity, but personnel not available for project effort, for example: safety training.

## Total Cost
Cost Center: |  | 9417 |  | 9417
Job Number: |  | 1200 |  | 1200
Job Title: |  | Vacuum Vessel & Support Structure |  | Vacuum Vessel & Support Structure
Job Manager: |  | D. Mangra & M. Smith |  | D. Mangra & M. Smith
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
numb | P3 cross ref (optional) | [14 empty] | 1.17 | 1.17 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 |  | 1200 V.V & SS | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
2 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
3 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
4 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
5 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
6 |  | 1201 TF Outer | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 151824 | 0 | 0 | 5 | 0 | 535.44 | 510 | 0 | 0 | 0 | 0 | 282 | 304 | 0 | 0 | 0 | 0 | 0 | 0
7 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
8 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
9 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
10 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
11 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
12 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
13 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
14 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
15 |  | 1202 PF2 Support | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 13505 | 0 | 0 | 0 | 0 | 43.84 | 154 | 0 | 0 | 0 | 0 | 42 | 3 | 0 | 0 | 0 | 0 | 0 | 0
16 |  | 1203 PF3 Support | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 5280 | 0 | 0 | 0 | 0 | 43.84 | 38 | 0 | 0 | 0 | 0 | 29 | 5 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | 1204 PF4 PF5 Leads & Radial Support | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 0 | 0 | 0 | 0 | 0 | 33.92 | 76 | 0 | 0 | 0 | 0 | 35.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | 1205 Umbrella | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 196170 | 0 | 0 | 0 | 0 | 482 | 756 | 0 | 0 | 0 | 0 | 536.4 | 176 | 0 | 0 | 0 | 0 | 0 | 0
19 |  | 1206 Pedestal | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 27450 | 0 | 0 | 0 | 0 | 90 | 316 | 0 | 0 | 0 | 0 | 219.8 | 108 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | 1207 Ves Legs | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 3860 | 0 | 0 | 0 | 0 | 27.84 | 40 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | 1208 PF4 PF5 Verticle Support | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 86440 | 0 | 0 | 5 | 0 | 279.28 | 578 | 0 | 0 | 0 | 0 | 269 | 148 | 0 | 0 | 0 | 0 | 0 | 0
22 |  | 1209 xxx | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 |  | 1220 Misc | [7 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 |  | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
25 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
26 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
27 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
28 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
29 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
30 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
31 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
32 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
33 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
34 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
35 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
36 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
37 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
38 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
39 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
40 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
41 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
42 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
43 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
44 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
45 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
46 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
47 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
48 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
49 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
50 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
51 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
52 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
53 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
54 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
55 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
56 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
57 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
58 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
59 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
60 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
61 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
62 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
63 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
64 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
65 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
66 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
67 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
68 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
69 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
70 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
71 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
72 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
73 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
74 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
75 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
76 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
77 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
78 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
79 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
80 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
81 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
82 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
83 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
84 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
85 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
86 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
87 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
88 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
89 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
90 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
91 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
92 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
93 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
94 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
95 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
96 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
97 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
98 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
99 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
100 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
101 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
102 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
103 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
104 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
105 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
106 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
107 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
108 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
109 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
110 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
111 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
112 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
113 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
114 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
115 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
116 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
117 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
118 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
119 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
120 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
121 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
122 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
123 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
124 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
125 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
126 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
127 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
128 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
129 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
130 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
131 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
132 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
133 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
134 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
135 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
136 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
137 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
138 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
139 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
140 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
141 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
142 | [9 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
[10 empty] | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56 | 2010-10-20 08:56
|  | TOTALS | [13 empty] | 484529 | 0 | 0 | 10 | 0 | 1536.16 | 2490 | 0 | 0 | 0 | 0 | 2361.6 | 747 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  | 1567.8176 |  | 1567.8176 | [10 empty] | 566.8989 | 0 | 0 | 11 | 0 | 271.6853 | 295.3638 | 0 | 0 | 0 | 0 | 356.3418 | 66.5278 | 0 | 0 | 0 | 0 | 0 | 0

## M&S
Cost Center: |  |  | 9417
Job Number: |  |  | 1200
Job Title: |  |  | Vacuum Vessel & Support Structure
Job Manager: |  |  | D. Mangra & M. Smith
Materials and Subcontracts (M&S)
|  |  |  | 1 Unit, Set, or Group |  | Unit Cost |  | Total # of
WAF # |  |  | Description: | quantity | units | $ | per unit | Units /Sets | Total Cost | Basis Comments | Basis Caterogry | Contingency %
1201 Outer TF | [8 empty] | 0
|  |  | Support ring / Link | 125 | lbf-each | 25 | lbf-each | 24 | 75000 | weight per fabrication cost | 2, 9, 11 | 25
|  |  | Clamps | 25 | lbf-each | 25 | lbf-each | 24 | 15000 | weight per fabrication cost | 2, 9, 11 | 25
|  |  | S.S. Hardware | 1 | bolt | 15 | bolt | 600 | 9000 | McMaster Carr | 2, 6 | 10
|  |  | G10 insulation | 1 | each | 27 | each | 72 | 1944 | McMaster Carr | 2, 6 | 15
|  |  | S.S. Rod Ends | 1 | each | 96 | each | 30 | 2880 | McMaster Carr | 2, 6 | 10
|  |  | Spring Link / Clevis Reinforcement | 1 | each | 800 | each | 50 | 40000 | Direct engineering quote, weight per fabrication cost | 2, 9 | 30
| Total M&S $ | 143824 | [6 empty] | 0
1202 PF2 Support |  |  | Existing Clamp | 85 | lbf-each | 25 | lbf-each | 5 | 10625 | weight per fabrication cost | 2, 9, 11
|  |  | 718 Inconel Bolts | 6 | each | 40 | each | 12 | 2880 | M. S. Aerospace Inc. | 2, 6 | 25
| Total M&S $ | 13505 | [6 empty] | 0
1203 PF3 Support | [8 empty] | 0
|  |  | 718 Inconel Bolts | 6 | each | 40 | each | 22 | 5280 | M. S. Aerospace Inc. | 2, 6 | 25
| Total M&S $ | 5280 | [6 empty] | 0
1204 PF4/5 Leads & Radial Support | [8 empty] | 0
0
0
| Total M&S $ | 0 | [6 empty] | 0
1205 Umbrella | [8 empty] | 0
|  |  | 718 Inconel Bolts | 14 | each | 40 | each | 20 | 11200 | M. S. Aerospace Inc. | 2, 6 | 25
|  |  | S.S. Bolts, washers | 1 | each | 15 | each | 178 | 2670 | McMaster Carr | 2, 6 | 10
[9 empty] | 0 | McMaster Carr | 2, 6 | 10
|  |  | S.S. Gusset | 7 | lbf-each | 25 | lbf-each | 44 | 7700 | weight per fabrication cost | 2, 9, 11 | 25
[9 empty] | 0 |  | 2, 9, 11 | 25
|  |  | Stiffener Ring (Upper) | 240 | lbf-each | 25 | lbf-each | 4 | 24000 | weight per fabrication cost | 2, 9, 11 | 25
|  |  | Stiffener Ring (Lower) | 240 | lbf-each | 25 | lbf-each | 4 | 24000 | weight per fabrication cost | 2, 9, 11 | 25
|  |  | Stiffener Plate | 30 | lbf-each | 25 | lbf-each | 24 | 18000 | weight per fabrication cost | 2, 9, 11 | 25
|  |  | Inconel Feet | 60 | lbf-each | 80 | lbf-each | 20 | 96000 | weight per fabrication cost | 2, 9, 11 | 25
|  |  | Upper Lid | [5 empty] | 5600 | Basis is previous umbrella lid x 1.3 | 2, 4, 9, 11 | 15
|  |  | Lower Lid | [5 empty] | 6000 | Basis is previous umbrella lid x 1.3 | 2, 4, 9, 11 | 15
|  |  | G10 insulation | [5 empty] | 1000 | McMaster Carr | 2, 6 | 15
| Total M&S $ | 196170 | [6 empty] | 0
1206 Pedestal | [8 empty] | 0
|  |  | Epoxy Bonded Bolts & Inserts | 1 | bolt-insert | 15 | bolt-insert | 18 | 270 | Unisorb | 2, 6 | 10
|  |  | SS. Bolts, washers | 1 | bolt | 15 | bolt | 72 | 1080 | McMaster Carr | 2, 6 | 10
|  |  | Shim Stock | [5 empty] | 500
|  |  | Pedestal sub-assembly | [5 empty] | 20000 | Pedestal sub-assembly basis: use previous pedestal: $old x 1.3 = $20k | 2, 4, 9, 11 | 15
|  |  | Grout Plate | [5 empty] | 5600 | Grout plate basis: scaled from umbrella lid. | 2, 4, 9, 11 | 15
| Total M&S $ | 27450 | [6 empty] | 0
1207 Vessel Legs | [8 empty] | 0
|  |  | Foot reinforcements. | 35 | lbf-each | 25 | lbf-each | 4 | 3500 | weight per fabrication cost | 2, 9, 11 | 25
|  |  | Epoxy Bonded Bolts & Inserts | 1 | bolt-insert | 15 | bolt-insert | 24 | 360 | Unisorb | 2, 6 | 10
0
0
0
| Total M&S $ | 3860 | [6 empty] | 0
1208 PF4/5 Verticle Support | [8 empty] | 0
|  |  | S.S. Bolts, washers | 1 | bolt | 15 | bolt | 240 | 3600 | McMaster Carr | 2, 6 | 10
|  |  | Inconel Bolts | 1 | bolt | 40 | bolt | 96 | 3840 | M. S. Aerospace Inc. | 2, 6 | 25
|  |  | Shim Existing Clamp (replacements) | [5 empty] | 1200 | SS shim, McMaster Carr | 2, 6 | 10
|  |  | Shim (new) | 1 | each | 100 | each | 48 | 4800 | Viscoelastic, 3M | 2, 6 | 10
|  |  | Clamps | 150 | lbf-each | 25 | lbf-each | 12 | 45000 | weight per fabrication cost | 2, 9, 11 | 25
| Total M&S $ | 76440 | Verticle Columns | 120 | lbf-each | 25 | lbf-each | 6 | 18000 | weight per fabrication cost | 2, 9, 11 | 25
0
0
0
0
0
0
0
0
0
0
[8 empty] | JOB # 1200 Total M&S | 466529
Inconel Feet: Account for increased material costs of Inconel fabricated parts: from Mcmaster Carr ≈ $55/lbf of Inconel 625.
So, fabrication cost @ $80/lbf-each
NOTES:
Basis for metal components which are fabricated (cuttting, machining, welding etc) is as follows:
Component Weight x ($25/weight) = $Cost

## Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 1200
Job Title: |  | Vacuum Vessel & Support Structure
Job Manager: |  | D. Mangra & M. Smith
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | x |  |  | Design activities for all sub job #'s: 1201-1220 approximately at 80% PDR level.
| Design Complexity |  |  | x |  | Job is well understood, since at 80% PDR level.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1200 | Design / Cog Eng total man-hours > 1 eng |  |  |  | VL | requested resources | 2, 4, 9, 10
1200 | Schedule is fronted loaded for designer, analyst and eng man power resources. |  |  |  | VL | requested resources | 2, 4, 9, 10

## Drawing Basis
| assy | sub assy | description | contents | part | DWG | cad | dwg
1201
tf | 1 | 1 | TF coils/clamps/links | TF coils |  | 1
|  | 1 | spring assembly | Spring | 3 | 2
|  |  |  | clamp around TF | 2 | 2
|  | 1 | link weldment | links | 6 | 3
|  |  |  | rods end | 1
|  |  |  | bolts | 7
|  |  |  | sp washer | 1
|  | 1 | tf rings | insulators | 3 | 3
|  |  |  | links plates | 1 | 1
| 1 |  | main
| 2 | 1 | bumper |  | 1 | 1
total | 4 | 5 |  |  | 25 | 13 | 34 | 13
1202
PF2 | 4 |  |  | pf2 mod | 6 | 4
total | 4 |  |  |  | 6 | 4 | 10 | 4
1203
total | 1 |  |  |  | 1 | 2 | 2 | 2
1204
PF4/5 leads
radial support | 2 |  | radial clamp |  |  | 2
total | 2 | 0 |  |  | 0 | 2 | 2 | 2
1205
Umbrella(U & L) |  |  | ring/gusset weldment
lids |  |  |  | existing sliding
feet |  |  | umbrella assy
rings |  |  | upper lids
interface
lower spokes
umbrella to vessel
total | [6 empty] | 30 | 22
1206
Pedestal |  | 1 | upper pestal weldment |  | 4 | 1
|  | 1 | lower pedetal |  | 5 | 1
|  |  | plate |  | 1 | 1
shims
| 1 |  | pedestal assy |  |  | 1
|  |  | interface |  | 3 | 3
|  | 1 | plate/grout |  | 2 | 1
total | 1 | 3 |  |  | 15 | 8 | 19 | 8
1207
Leg clamp | 1 |  | assy
|  |  | clamps |  | 1 | 1
|  |  | drill anchor holes |  | 1 | 1
total | 1 |  |  |  | 2 | 2 | 3 | 2
1208
pf4/5 | 1 |  | pf4/5 to vessel |  |  | 1
| 1 | 2 | clamp support | clamps | 8 | 3
|  |  | shims to old suport | shims | 4 | 2
|  | 2 | shim assy |  | 6 | 8
|  | 2 |  | clamps weldment | 6 | 2
|  | 1 |  | column weldment | 3 | 1
|  |  |  | clamp plate | 1 | 1
|  | 1 | radial clamps |  | 3 | 4
| 1 |  | pf4/5 assy |  |  | 1
total | 3 | 8 |  |  | 31 | 23 | 42 | 23
Sept 9, 2010: 1202, 1204, 1205, revised per updated input from designer.

## notes
Basis Notes for Estimates: Procurement Activities
Eval quotes: 1d/quote
Tech Eval: 1 day/ vendor
Vendor oversight -
TF 1 week
PF4/5 1 week
Umbr U/L 0.5 wk,
remaining items 1 wk
Key
Preliminary Design = PD, Final Design = FD, Final Design Review = FDR,
Computer Aided Design = CAD, Engineer = Eng,
man-hours = mh, man-day = md = 8 mh, Project Day = pd = 1 md
Project Week = pw = 5pd, man-month = mm,
man-year = my = 1776 mh (includes vac, sick, etc)
Basis Notes for Contingency
NOTE: Main milestones (i.e. PDR) "schedule" contingency accounts for (cumulative) all associated sub tasks.
Also, contingency % for milestones reflects schedule concerns, when man-power is included in a task, % reflects man power concerns.
Milestone Durations
PD Duration 5/1/10 to 8/16/10 77 md
5/1/10 to 6/23 39 md
PDR 6/23/10 to 8/15/10 38 md
FD Duration 8/17/10 to 3/31/11 162 md
Drawings for Validation 8/17 to 11/15 64 md
11/16/10 to 2/15/11 65 md
Received Materials/Parts 4/27/11 - 1/1/12 178 md
Received to Ready Install 1/1/12 - 5/1/12 approx 4 mm
Parts Ready Install 4/27/11 to 5/1/12 263 md
-----------------------------------------------------------------
Milestone / Schedule slippage (non cumulative)
PDR: 3 mw
FDR 4 mw
Parts Ready Install 4 mw
=================================================
Designer Models @ 50%
Designer Drawings @ 50%
Analyst: 8 hrs per week = 20%
Engineer 4 hrs per week = 10%
Tech @ 50%
Normalized when efforts are combined.
==================================================
Procurement Activities
Eng @ 10-50% task dependent.
Basis Notes for Estimates: CAD Models & Drawings
Detail CAD Designer mh @ 3mh/FD model, Eng @ [0.3 to 0.5]*(total Designer mh)
Update FD drawings: Designer @ 8 mh/drawing, Eng @ (0.75mh)/drawing
Validation update CAD: Designer @ 1mh/model
Validation update Drawings: Designer @ 4mh/drw
Check Drawings: Other Designer @ 2 hr/drawing
Check & signoff: Eng @ 2 to 3.0mh/draw : includes 0.5h for oversite
========================================================
Basis Notes for Estimates: tab 1220
For PD efforts:
Eng project management @ 3 mh/pd for various activities.
For FD efforts:
Eng project management @ 2 mh/pd for various activities.
===========================================
Basis for Laboratory Misc (from 6/1/2010 to 4/1/2011 approx 43 mw)
Designer approx 24 mh/my or 2mh/mm (email)
Eng @ 3hr /mw
Basis Notes for Estimates: tab 1206
QA: Pedestal components, approx 3 main heavy parts.
Tech: estimate 2 mh per part, but min 8 hr.
Eng: 2 mh for discussion prior, .25 mh per part, 1 mn admin
Handling & Storage: Pedestal components, approx 3 main heavy parts.
estimate 2 men, 2mh/every move each part.
From start of QA effort to parts ready for installation approx 16 weeks total.
Estimate 3 moves.
Basis Notes for Estimates: tab 1208
QA: approx 6 sets of assembled parts.
from Receipt of parts to parts ready approx 16 weeks.
Tech: estimate 2 mh per part.
Eng: 2 mh for discussion prior, .25 mh per part, 1 mn admin
Handling & Storage: approx 6 sets of assembled parts (heavy parts).
estimate 2 men, 2 mh/mw for each part occuring over approx 17 weeks.
Basis Notes for Estimates: tab 1201
QA: approx 24 sets of assembled outer links (heavy parts)
from Receipt of parts to parts ready approx 16 weeks.
Tech: estimate 2 mh per part.
Eng: 2 mh for discussion prior, .25 mh per part, 1 mn admin
Handling & Storage: 24 sets of assembled outer links (heavy parts)
estimate 2 men, 2mh/mw for each part occuring over approx 17 weeks.
Basis Notes for Estimates: tab 1204
Since design is pending analysis, actual design and components is not known.
Estimate for assembly ( Task 54 ) based on 2 men for 2 weeks.
Basis Notes for Estimates: tab 1205
Project Flow: Descriptions, Logic, Definitions, etc.
Final design, analysis and modeling iterations occur simultaneously., i
When these are completed, the design is "finalized" and start of detailed drawings is acceptable.
Analysis/Calculation tasks entail developing the calculation sheet as the work is in progress.
Design validation is review of the drawings, calculations, and other documentation (approving the evidence) for an acceptable final design.