## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 1301
Job Title: | Outer Toroidal Field Coils
Job Manager: | James H. Chrzanowski
Rev 1 6/16/2010
Description:
This job includes the fabrication of (1) new Outer TF coil (OTF) by OS vendor to replace the existing [leaking] OTF#7 in NSTX. Also procurement of insulations, aluminum castings and supports for new OTF coil. Field Work: Includes drilling of additional holes in each OTF coil lead to accommodate upgrade requirements [288 holes].This estimate does not include costs associated with installation of coils into NSTX.
Schedule:
Refer to the Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost | Work |  | Activity Name | Responsible Cog Engr | Start | End | Duration | Duration | Start | EAEM1 | EAEM2 | EAEM3 | EAEM4 | EAEM5 | EAEM6 | EAEM7 | EAEM | EAEM | EMEM1 | EMEM2 | EMEM3 | EMEM4 | EMEM5 | EEEM | EASB1 | EASB3 | EASB4 | EASB5 | EASB6 | EASB7 | EASB8 | EMSM1 | EMSM2 | EMSM3 | EMTB1 | EMTB2 |  |  | EMTB5 | M&S | OS | Travel | Stkrm. | Subtotal | Basis of Estimate | Category | Contingency
Center | Package | Job # | [6 empty] | Date | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs |  |  | mhrs |  |  |  |  | M&S |  |  | %
[5 empty] | Date | Date | (Weeks) | (Weeks) |  | (Chrzan.) | (Titus) | (Zhang) | (Zolfaghari) | (Avasarala) | (Brooks) | (Raftopoul.) | (general) | (Myatt) | (Mangra) | (Tresmer) | (Willard) | (Prinski) | (Simmons) |  | (Paul) | (Martinelli) | (Upcavage) | (Jariwala) | (Wojtowicz) | (Paluzzi) | (Elect) | (Meighan) | (Jurcz.) |  | (Tech) | (Machinist) |  |  | (General) | K$ | k$ | k$ | k$ | k$
9417 | 1*** | 1301 | OUTER TOROIDAL FIELD COILS | Chrzanowski | [5 empty] | See Job 1300
|  |  | Revise OTF drawings | [5 empty] | 2011-04-25 | [20 empty] | 120 |  | 16 | [13 empty] | 2 | 10%
Purchase & Fabrication
|  |  | Generate Spec & SOW for outside procurement |  |  |  |  | 2 | 2012-05-01 | [36 empty] | 2 | 10%
|  |  | Prep requisition & submit to procurement |  |  |  |  | 1 | 2012-05-15 | [36 empty] | 2 | 10%
|  |  | Bid & award OTF manufacturing |  |  |  |  | 5 | 2012-07-01 | [36 empty] | 2 | 10%
|  |  | Manufacture (1) OTF coils |  |  |  |  | 30 | 2012-07-01 | [31 empty] | 90 | 3 |  | 93 |  | 4 | 30%
Delete
Miscellaneous parts and materials
|  |  | Prep requisition & submit to procurement | [5 empty] | 2012-10-01 | [36 empty] | 2 | 10%
|  |  | Procure aluminum support castings and S.S. support clamps | [5 empty] | 2012-10-15 | [22 empty] | 16 | [7 empty] | 15 |  |  |  | 15 |  | 4 | 25%
|  |  | Procure hardware, epoxy/glass for support blocks, misc | [5 empty] | 2012-10-22 | [22 empty] | 24 | [7 empty] | 15 |  |  |  | 15 |  | 4 | 25%
|  |  | Copper fittings, etc | [5 empty] | 2012-10-22 | [30 empty] | 1.5 |  |  |  | 1.5 |  | 4 | 15%
In-house Fabrication
|  |  | Setup work area for installing supports |  |  |  |  | 2 | 2013-01-07 | [25 empty] | 160 | [8 empty] | 0 |  | 4 | 25%
|  |  | Install alum blocks & SS support clamps |  |  |  |  | 6 | 2013-01-28 | [22 empty] | 120 |  |  | 220 | 60 | [7 empty] | 0 |  | 4 | 25%
OTF Field Work
|  |  | Fabricate drill jig |  |  |  |  | 1 | 2012-10-01 | [26 empty] | 40 |  |  |  | 5 |  |  |  | 5 |  | 2 | 15%
|  |  | Drill (24) additional holes in OTF flags- [12 coils] |  |  |  |  | 10 | TBD | [26 empty] | 400 | [9 empty] | 2 | 25%
[5 empty] | 2009-10-01 | 2013-01-07 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 176 | 0 | 0 | 380 | 500 | 0 | 0 | 0 | 36.5 | 90 | 3 | 0 | 129.5
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NSTX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 1301
Job Title: |  | Outer Toroidal Field Coils
Job Manager: |  | James H. Chrzanowski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | x
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | After press mold operation- numerous dry areas are found |  |  |  | U | Attempt local repair- if unsuccessful, Rebuild coil |  |  |  | X | 50 | Not critical path
2 | Coil does not pass final acceptance tests |  |  |  | U | Attempt local repair- if unsuccessful, Rebuild coil |  |  |  | X | 50 | Not critical path
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9417
Job Number: | 1301
Job Title: | Outer Toroidal Field Coils
Job Manager: | James H. Chrzanowski
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Fabricate (1) OTF coils |  | 90 | 4
Procure Alum castimngs & S.S.supports |  | 15 | 4
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1
|  | 2 - Engineering Judgement/Experience |  | 2
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4
|  | 5 - Prototype Data/Test Results |  | 5
|  | 6 - Catelogue Price/Vendor Quote |  | 6
|  | 7 - Placed Contracts |  | 7
|  | 8 - Actual experience for NCSX Work |  | 8
|  | 9 - Other |  | 9
TOTALS