## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 1302
Job Title: | Centerstack Assembly
Job Manager: | James H. Chrzanowski
Description:
This job includes activities associated with the assembly of the new centerstack. Details include: CAD support for setup of the CS assembly area Generating Assembly and Installation Procedures Setup and Tear down of the assembly area Assembly of the CS Assembly includes the inner TF bundle/ OH Coil assembly, mounting of the OH surface diagnostics, installation of the micro-therm insulation, installation of the casing and inner PF coils and installation of the CS PFCs.
Schedule:
Refer to the Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost | Work |  | Activity Name | Responsible Cog Engr | Start | End | Duration |  | EAEM1 | EAEM2 | EAEM3 | EAEM4 | EAEM5 | EAEM6 | EAEM7 | EAEM | EAEM | EMEM1 | EMEM2 | EMEM3 | EMEM4 | EMEM5 | EEEM | EASB1 | EASB2 | EASB3 | EASB4 | EASB5 | EASB6 | EASB7 | EASB8 | EMSM1 | EMSM2 | EMSM3 | EMTB1 | EMTB2 | EMTB3 | EMTB4 | EMTB5 | M&S | OS | Travel | Stkrm. | Subtotal | Basis of Estimate | Category | Contingency
Center | Package | Job # | [5 empty] | Start | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs |  |  |  |  | M&S |  |  | %
[5 empty] | Date | Date | (Weeks) | Date | (Chrzan.) | (Titus) | (Zhang) | (Zolfaghari) | (Avasarala) | (Brooks) | (Raftopoul.) | (general) | (Myatt) | (Mangra) | (Tresmer) | (Willard) | (Prinski) | (Simmons) |  | (Paul) | (Morris) | (Martinelli) | (Upcavage) | (Jariwala) | (Wojtowicz) | (Paluzzi) | (Elect) | (Meighan) | (Jurcz.) |  | (Technician) | (Machinist) | (Welder) | (electrical) | (General) | K$ | k$ | k$ | k$ | k$
9417 | 1*** | 1302 | CENTERSTACK ASSEMBLY | Chrzanowski |  |  |  |  | See Job 1300
|  |  | Cad support for setup of centerstack assembly area |  |  |  | 5 | 2012-07-20 | [21 empty] | 200 | [15 empty] | 4 | 20%
|  |  | Generate CS Assembly procedure |  | 2011-05-07 | 2012-06-11 | 2 | 2012-06-01 | [37 empty] | 4 | 10%
|  |  | Generate CS Installation procedure |  | 2012-11-05 | 2012-12-17 | 2 | 2013-01-04 | [37 empty] | 4 | 10%
|  |  | Modify CS Assembly Fixture |  |  | 2012-06-11 | 4 | 2012-07-20 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [10 empty] | 160 |  | 120 |  |  | 10 |  |  | 1 | 11 |  | 2 | 25%
|  |  | Setup CS Assembly Area |  |  | 2012-06-11 | 6 | 2012-08-24 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [7 empty] | 24 |  |  | 360 |  |  | 200 |  | 10 |  |  | 2 | 12 |  | 4 | 25%
|  |  | Receive OH/TF Assembly |  |  |  | 1 | 2012-08-17
|  |  | Receive Inner PF coils |  |  |  | 1 | 2012-09-07
|  |  | Perform acceptance electric and hydraulic tests on PF coils |  |  |  |  | 2012-09-14 | [23 empty] | 24 |  |  | 24 | [11 empty] | 10%
|  |  | Wrap PF1A coil with Microtherm insulation |  |  |  |  | 2012-10-26 | [26 empty] | 40 | [11 empty] | 20%
|  |  | Receive CS Vacuum Casing |  |  |  | 1 | 2012-09-07
|  |  | Install inconel weld studs or nuts to casing wall |  |  |  | 4 | 2012-10-05 | [28 empty] | 240 | [5 empty] | 0.5 | 0.5 |  | 2 | 25%
|  |  | Mount upper & lower PF1b coils to CS casing |  |  |  | 2 | 2012-11-09 | [28 empty] | 144 |  | 80 |  |  |  |  | 0 |  | 2 | 25%
|  |  | Assemble Centerstack Components |  | 2012-06-11 | 2012-12-17 | 24 | 2012-12-14 |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [7 empty] | 690 |  |  | 4320 |  |  |  |  | 20 |  |  | 10 | 30 |  | 4 | 30%
Apply groundplane to OH coil bundle
Mount surface diagnostics to OH surface
Wrap OH bundle with Micro-therm insulation
Install Lower PF1A coil to CS Casing
Install CS support structure
Install CS Vacuum Casing
Install upper PF1A coil & support
Mount diagnostics & wiring on surface of CS casing [Diag cost & respons Job 4100]
Mount PFC tiles to surface of casing
In field tile modifications- Responsibility of PFC Job 1001
Terminate organ pipe feed-thru's [Diagnostic cost & respons Job 4100]
|  |  | Deliver CS assembly to the NSTX Test Cell |  |  |  | 1 | 2013-06-07
|  |  | Tear down assembly area |  | 2013-01-07 | 2013-02-04 | 4 | 2013-10-01 | [23 empty] | 24 |  |  | 360 |  |  | 80 | [5 empty] | 0 |  | 8 | 15%
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [5 empty] | 200 |  | 762 |  |  | 5264 |  | 504 | 280 | 0 | 40 |  |  | 13.5 | 53.5
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 1302
Job Title: |  | Centerstack Assembly
Job Manager: |  | James H. Chrzanowski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | x
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Components do not arrive when required |  |  |  | U | If schedule critical- OT or second shift would be required to regain schedule
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9417
Job Number: | 1302
Job Title: | Centerstack Assembly
Job Manager: | James H. Chrzanowski
Materials and Subcontracts (M&S) |  | K$ | Basis of Estimate
Description:
Material for setting up area |  | 10 | 2
Modify assy fixture |  | 10 | 2
Assemble CS- miscellaneous |  | 20 | 2
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1
|  | 2 - Engineering Judgement/Experience |  | 2
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4
|  | 5 - Prototype Data/Test Results |  | 5
|  | 6 - Catelogue Price/Vendor Quote |  | 6
|  | 7 - Placed Contracts |  | 7
|  | 8 - Actual experience for NCSX Work |  | 8
|  | 9 - Other |  | 9
TOTALS

## Tab E Work Sheet
OH Solenoid
Inner TF Bundle
PF-1A
PF-1B
CS Casing