## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 1304
Job Title: | Inner Toroidal Field Bundle
Job Manager: | James H. Chrzanowski
REV 2 10/13/2010
Description:
Includes the design of the TF bundle, TF flex bus and flex bus supports. Includes all analytical & CAD design efforts for these components. Includes the early procurement of the TF conductor [80 lengths]. Also the procurement of the TF flex bus and supports. Does not include the manufacturing of the Inner TF bundle, which is included as part of the OH fabrication in Job 1305.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost | Work |  | Activity Name | Responsible Cog Engr | Start | End | Duration | Start | EAEM1 | EAEM2 | EAEM3 | EAEM4 | EAEM5 | EAEM6 | EAEM7 | EAEM | EAEM | EMEM1 | EMEM2 | EMEM3 | EMEM4 | EMEM5 | EEEM | EASB1 | EASB2 | EASB3 | EASB4 | EASB5 | EMSM | EMTB | EASB7 | EASB8 | EMSM1 | EMSM2 | EMSM3 | EMTB1 | EMTB2 | EMTB3 | EMTB4 | EMTB5 | M&S | OS | Travel | Stkrm. | Subtotal | Basis of Estimate | Category | Contingency
Center | Package | Job # | [5 empty] | Date | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs |  |  |  |  | M&S |  |  | %
[5 empty] | Date | Date | (Weeks) |  | (Chrzan.) | (Titus) | (Zhang) | (Zolfaghari) | (Avasarala) | (Brooks) | (Raftopoul.) | (general) | (Myatt) | (Mangra) | (Tresmer) | (Willard) | (Prinski) | Ali |  | (Paul) | (Morris) | (Martinelli) | (Upcavage) | (Jariwala) | Meighan |  | (Paluzzi) | (Elect) | (Meighan) | (Jurcz.) |  | (Technician) | (Machinist) | (Welder) | (electrical) | (General) | K$ | k$ | k$ | k$ | k$
9417 | 1*** | 1304 | INNER TF BUNDLE- Design & Fabrication | Chrzanowski |  |  |  |  | See Job 1300
|  |  | R&D Activities | [41 empty] | 0
|  |  | Perform additional Friction Stir Weld Trials- Phase II |  |  |  | 15 | 2010-04-22 | [33 empty] | 49 |  |  | 49 |  | 7 | 10%
|  |  | Fabricate Flex bus assy's for testing [2] | [26 empty] | 120 | [11 empty] | 5 |  |  | 5 |  | 2 | 30%
|  |  | New Insulation primer R&D tests |  |  |  |  | 2010-08-16 | [33 empty] | 15 |  |  | 15 |  | 4 | 20%
See job 9417-1***-1303 for R&D jobs and costs
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01 | [38 empty] | 0
|  |  | Design-analyze tension strap |  | 2010-06-01 | 2010-11-01 |  | 2010-06-24 |  |  | 60 | [33 empty] | 0 |  | 4 | 20%
|  |  | Analyze TF bus bar |  | 2010-06-01 | 2010-11-01 |  | 2010-06-24 | [11 empty] | 100 | [24 empty] | 0 |  | 4 | 20%
|  |  | Complete analysis of TF Flex bus |  |  |  |  | 2010-06-24 | [11 empty] | 144
|  |  | Complete and check thermal stresses |  | 2010-06-01 | 2010-11-01 |  | 2010-06-24 |  |  | 60 | [33 empty] | 0 |  | 4 | 20%
|  |  | Maintain input to Willard's Flex model- displacements Temper |  | 2010-06-01 | 2010-11-01 |  | 2010-06-24 |  | 40 | [34 empty] | 0 |  | 4 | 20%
|  |  | Check Willard's calculations |  | 2010-06-01 | 2010-11-01 |  | 2010-06-24 | [13 empty] | 60 | [22 empty] | 0 |  | 4 | 20%
|  |  | Tooling/Fixturing calculations |  | 2010-06-01 | 2010-11-01 |  | 2010-06-24 | [13 empty] | 60 | [22 empty] | 0 |  | 4 | 20%
|  |  | Calculation/Write/check files |  |  |  |  | 2010-06-24 |  | 60 | [36 empty] | 4 | 20%
|  |  | Analyze double row of teeth |  |  |  |  | 2010-06-24 | [13 empty] | 200 | [24 empty] | 4 | 20%
|  |  | Pedestal/Lower skirt/ TF Teeth Analysis |  | 2010-06-01 | 2010-11-01 |  | 2010-06-24 | [13 empty] | 200 | [22 empty] | 0 |  | 4 | 20%
|  |  | Finish torque for upper teeth and covers post processing |  | 2010-06-01 | 2010-11-01 |  | 2010-06-24 |  | 40 | [34 empty] | 0 |  | 4 | 20%
|  |  | DCPS Input |  |  |  |  | 2010-06-24 |  | 100
|  |  | Complete detail and assembly Cad drawings [TF bundle, joint and components] |  | 2010-06-01 | 2010-11-01 | 39 | 2010-06-24 | [15 empty] | 560 | [20 empty] | 0 |  | 2 | 25%
|  |  | Prepare for FDR |  | 2010-09-27 | 2010-11-08 | 2 | 2011-03-11 | [15 empty] | 40 | [20 empty] | 0 |  | 2 | 10%
|  |  | HOLD TF CONDUCTOR PEER REVIEW [to allow early procurement] |  | 2010-01-11 | 2010-01-15 | 1 | 2010-08-13 | [36 empty] | 0
Purchase & Fabrication
TF Conductor
|  |  | Extrusion: Prep requisition/SOW & submit to procurement |  | 2010-02-01 | 2010-02-08 | 1 | 2010-08-20 | [36 empty] | 0 |  | 4 | 10%
|  |  | Bid & Award conductor extrusion order [80 pcs] |  | 2010-02-08 | 2010-03-08 | 5 | 2010-08-27 | [36 empty] | 0 |  | 4 | 10%
|  |  | Manufacture Copper extrusions [80] |  | 2010-03-08 | 2010-07-12 | 18 | 2010-10-01 | [32 empty] | 242 |  |  |  | 242 |  | 6 | 35%
|  |  | Receive TF conductors from extruder |  |  |  |  | 2011-02-04
|  |  | Machining #1: Prep requisition & submit to procurement |  | 2010-06-21 | 2010-06-28 | 1 | 2011-01-07 | [36 empty] | 0 |  | 4 | 10%
|  |  | Bid & Award conductor machining [40 pcs] |  | 2010-06-28 | 2010-07-26 | 4 | 2011-01-14 | [36 empty] | 0 |  | 4 | 10%
|  |  | Machine conductors [finish machine, cooling grooves, lead area]- 40 |  | 2010-07-26 | 2010-10-25 | 13 | 2011-02-11 | [33 empty] | 250 | 5 |  | 255 |  | 6 | 35%
|  |  | Receive first delivery of TF conductors from machinist |  |  |  |  | 2011-04-08
|  |  | Receive balance of TF conductors from machinist |  |  |  |  | 2011-05-13
|  |  | Procure Cu-Cr-Zr ITF lead extensions for FSW] |  |  |  | 20 | 2010-12-17 | [33 empty] | 50 |  |  | 50 |  | 2 | 25%
|  |  | FSW: Prep requisition & submit to procurement |  | 2010-10-04 | 2010-10-11 | 1 | 2011-03-11 | [36 empty] | 0 |  | 4 | 10%
|  |  | Bid & award lead welding [40 pcs] |  | 2010-10-11 | 2010-11-08 | 4 | 2011-03-18 | [36 empty] | 0 |  | 4 | 10%
|  |  | Friction Stir-Weld coil leads to conductors- 40 |  | 2010-11-08 | 2011-01-10 | 12 | 2011-04-15 | [33 empty] | 250 | 3 |  | 253 |  | 6 | 35%
|  |  | Receive First delivery of TF conductors from FSW |  |  |  |  | 2011-06-03
|  |  | Receive balance of TF conductors from FSW |  |  |  |  | 2011-07-08
|  |  | Post FSW Machining #2: Prep requisition & submit to procurement |  |  |  | 1 | 2011-07-08 | [39 empty] | 10%
|  |  | Bid & Award conductor machining [40 pcs] |  |  |  | 4 | 2011-07-15 | [39 empty] | 10%
|  |  | Machine conductors [Final lead area & Inserts]- 40 pcs |  |  |  | 8 | 2011-06-10 | [33 empty] | 100 | 2 |  | 102 |  | 2 | 35%
|  |  | Receive First Delivery of TF conductors from Machinist |  |  |  |  | 2011-07-15
|  |  | Receive balance of TF conductors from machinist |  |  |  |  | 2011-08-19
Flex Bus [Inner to Outer TF]
|  |  | Procure C151 [Cu-Cr] copper material for flex bus |  |  |  | 8 | 2012-09-07 | [33 empty] | 25 |  |  | 25 |  | 6 | 25%
|  |  | Flex bus- Prep requisition & submit to procurement |  |  |  | 1 | 2012-10-05 | [36 empty] | 0 |  | 4 | 10%
|  |  | Bid & award flex bus order [80 assy's] |  |  |  | 4 | 2012-10-12 | [36 empty] | 0 |  | 4 | 10%
|  |  | Fabricate Flex bus |  |  |  | 12 | 2012-11-09 | [33 empty] | 65 | 3 |  | 68 |  | 2 | 35%
|  |  | Receive Flex bus |  |  |  |  | 2013-02-01
|  |  | Procure Cu-Cr-Zr [C1815] for OTF lead extensions |  |  |  | 12 | 2012-07-20 | [20 empty] | 24 | [12 empty] | 78 |  |  | 78 |  | 6 | 25%
|  |  | Procure OTF lead extensions [OTF to flex] |  |  |  | 16 | 2012-10-12 | [33 empty] | 50 |  |  | 50 |  | 2 | 30%
|  |  | Procure supports for OTF jumpers |  |  |  | 12 | 2012-11-09 | [33 empty] | 50 |  |  | 50 |  | 2 | 30%
|  |  | Procure lower TF coil to bus jumpers & supports |  |  |  | 8 | 2012-10-12 | [33 empty] | 24 |  |  | 24 |  | 2 | 30%
|  |  | Miscellaneous parts | [41 empty] | 0
|  |  | Procure super nuts [600] |  |  |  | 20 | 2012-09-14 | [20 empty] | 16 | [11 empty] | 150 |  |  |  | 150 |  | 2 | 25%
|  |  | Procure joint hardware [belleville & flat washers, bolts, nuts] |  |  |  | 6 | 2012-12-21 | [20 empty] | 8 | [11 empty] | 25 |  |  |  | 25 |  | 6 | 25%
|  |  | Procure Copper lead extensions for upper ITF [OFHC] |  |  |  | 12 | 2012-12-07 | [20 empty] | 16 | [12 empty] | 25 |  |  | 25 |  | 2 | 25%
|  |  | Procure upper/lower OH to TF support structures |  |  |  | 12 | 2011-07-15 | [33 empty] | 30 |  |  | 30 |  | 2 | 30%
|  |  | Procure cooling fittings |  |  |  | 4 | 2011-06-03 | [20 empty] | 8 | [11 empty] | 5 |  |  |  | 5 |  | 6 | 15%
|  |  | Tooling for installing flex bus segments |  |  |  | 10 | 2012-10-05 | [15 empty] | 80 | [16 empty] | 25 |  |  |  | 25 |  |  | 25%
|  |  | Procure Upper/Lower teeth interface structues |  |  |  | 12 | 2011-07-15 | [33 empty] | 50 |  |  | 50 |  | 2 | 35%
[9 empty] | 0 | 240 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244 | 0 | 520 | 0 | 680 |  |  |  |  | 72 | 120 | [14 empty] | 1576
Fabrication of the ITF bundle is costed in job 9417-1***-1305
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 1304
Job Title: |  | Inner Toroidal Field Bundle
Job Manager: |  | James H. Chrzanowski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Copper extrusion vendor has difficulty making full length conductors |  |  |  | U | FSW shorter conductors together |  |  |  |  | 100 |  | XX
2 | [12 empty] | XX
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9417
Job Number: | 1304
Job Title: | Inner Toroidal Field Bundle
Job Manager: | James H. Chrzanowski
Materials and Subcontracts (M&S) |  | K$ | Basis of Estimate
Description:
ITF copper extrusions |  | 242 | 6
Machine conductors |  | 250 | 6
Friction Stir Weld coil leads to conductor |  | 250 | 6
Final Machine leads- Post FSW |  | 50 | 2
C1815 copper material for OTF lead extensions |  | 78 | 6
OTF copper lead extensions |  | 50 | 2
C151 copper material for Flex bus |  | 25 | 6
TF flex bus fabrication |  | 65 | 2
Supports for TF jumpers |  | 30 | 2
Lower TF power bus jumpers & supports |  | 12 | 2
CU-Cr-Zr lead extensions [FSW] |  | 50 | 2
Super bolts |  | 310 | 2
Upper lead copper spacers |  | 25 | 2
OH to TF lead support structures |  | 30 | 2
Misc joint hardware |  | 25
2
Tooling for installing TF flexes |  | 20
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1
|  | 2 - Engineering Judgement/Experience |  | 2
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4
|  | 5 - Prototype Data/Test Results |  | 5
|  | 6 - Catelogue Price/Vendor Quote |  | 6
|  | 7 - Placed Contracts |  | 7
|  | 8 - Actual experience for NCSX Work |  | 8
|  | 9 - Other |  | 9
TOTALS

## Tab E Worksheet
UPP TF BUNDLE
Umbrella Lid Interface
G-10/Kapton flash shield between lead areas
Lead extensions [Upper only]
Quick Disconnect cooling tube connections w/ drip containment
Upgraded TF Bundle 15.7 inch diameter