## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 1306
Job Title: | Inner Poloidal Field Coils
Job Manager: | James H. Chrzanowski
Description:
Includes the design and procurement of the Inner poloidal field coils and supports [PF1A and PF1B]. Includes all analytical & CAD design efforts for these components. Includes the early procurement of the PF conductor and Co-wound [Glass/Kapton] insulation. Also includes the procurement of the PF support mandrels that the PF1A and 1B coils will be wound onto plus the fabrication of (3) sets of new inner PF coils (PF1A, 1B and 1C)
Schedule:
Refer to the Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost | Work |  | Activity Name | Responsible Cog Engr | Start | End | Duration | Start | EAEM1 | EAEM2 | EAEM3 | EAEM2 | EAEM5 | EAEM6 | EAEM7 | EAEM | EAEM | EMEM1 | EMEM2 | EMEM3 | EMEM4 | EMEM5 | EEEM | EASB1 | EASB2 | EASB3 | EASB4 | EASB5 | EASB6 | EASB7 | EASB8 | EMSM1 | EMSM2 | EMSM3 | EMTB1 | EMTB2 | EMTB3 | EMTB4 | EMTB5 | M&S | OS | Travel | Stkrm. | Subtotal | Basis of Estimate | Category | Contingency
Center | Package | Job # | [5 empty] | Date | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs |  |  |  |  | M&S |  |  | %
[5 empty] | Date | Date | (Weeks) |  | (Chrzan.) | (Titus) | (Zhang) | Myatt | (Avasarala) | (Brooks) | (Raftopoul.) | (general) | (Myatt) | (Mangra) | (Tresmer) | (Willard) | (Prinski) | (Simmons) |  | (Paul) | (Morris) | (Martinelli) | (Upcavage) | (Jariwala) | (Wojtowicz) | (Paluzzi) | (Elect) | (Meighan) | (Jurcz.) |  | (Technician) | (Machinist) | (Welder) | (electrical) | (General) | K$ | k$ | k$ | k$ | k$
9417 | 1*** | 1306 | INNER POLOIDAL FIELD COILS (Shaping) | Chrzanowski |  |  |  |  | See Job 1300
|  |  | Final Design Activities | [40 empty] | 0
|  |  | Complete Inner PF coil analysis |  |  |  |  | 2010-06-24 |  |  |  | 100 | [31 empty] | 0 |  | 2 | 20%
|  |  | PF lead & flag analysis |  |  |  |  | 2010-06-24 |  |  |  | 60 | [31 empty] | 0 |  | 2 | 20%
|  |  | Fatigue assessment & DCPS |  |  |  |  | 2010-06-24 |  |  |  | 60 | [31 empty] | 0 |  | 2 | 20%
|  |  | Calculation write/Check/File |  |  |  |  | 2010-06-24 |  |  |  | 60 | [33 empty] | 2 | 20%
|  |  | Complete Cad detail and assembly drawings of Inner PF coils & supports |  |  |  |  | 2010-06-24 | [16 empty] | 416 | [18 empty] | 0 |  | 2 | 20%
|  |  | Prepare for FDR |  |  |  | 2 | 2011-03-11 | [16 empty] | 24 | [18 empty] | 0 |  | 2 | 10%
|  |  | Purchase & Fabrication | [40 empty] | 0
Procure Conductor
|  |  | Generate SOW for conductor |  | 2010-11-22 | 2010-12-06 | 2 | 2011-05-27 | [37 empty] | 2 | 10%
|  |  | Prep requisition & submit to procurement |  | 2010-12-06 | 2010-12-13 | 1 | 2011-06-10 | [37 empty] | 2 | 10%
|  |  | Bid & award conductor order [220%] |  | 2010-12-13 | 2011-01-17 | 5 | 2011-06-17 | [37 empty] | 2 | 10%
|  |  | Manufacture Copper conductor [extrusion] |  | 2011-01-17 | 2011-04-25 | 14 | 2011-07-22 | [32 empty] | 46.4144 |  |  | 46.4144 |  | 3 | 25%
Procure Kapton/glass co-wound insulation
|  |  | Prep requisition & submit to procurement [insulation] |  | 2010-11-08 | 2010-11-15 | 1 | 2011-08-26 | [23 empty] | 8 | [13 empty] | 2 | 10%
|  |  | Procure Kapton/glass co-wound insulation |  | 2010-11-15 | 2011-01-10 | 10 | 2011-09-02 | [23 empty] | 18 | [7 empty] | 20 |  |  |  | 20 |  | 6 | 20%
Coil Fabrication- 6 coils
|  |  | Procure Stainless steel supt for PF1A & PF1B coils |  | 2011-05-02 | 2012-02-06 | 16 | 2011-07-29 | [23 empty] | 40 | [8 empty] | 100 | 2 |  | 102 |  | 3 | 25%
|  |  | Generate SOW & Manufacturing SPEC for Inner PF coils |  | 2011-02-21 | 2011-03-14 | 3 | 2011-09-23 | [37 empty] | 2 | 10%
|  |  | Prep requisition & submit to procurement |  | 2011-03-14 | 2011-03-21 | 1 | 2011-10-14 | [37 empty] | 2 | 10%
|  |  | Review bids and award contract |  | 2011-03-21 | 2011-05-02 | 6 | 2011-10-21 | [37 empty] | 2 | 10%
|  |  | Fabricate Inner [6] Inner PF coils |  | 2011-05-02 | 2012-02-06 | 40 | 2011-12-02 | [23 empty] | 120 | [8 empty] | 180 | 6 |  | 186 |  | 3 | 25%
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [13 empty] | 0 | 0 | 0
[5 empty] | 2009-10-01 | 2013-01-07 |  |  | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 326.4144 | 8 | 0 | 354.4144
CATEGORIZATION CODES:
|  |  |  | Sept 7 2012 |  |  |  |  | 1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 1306
Job Title: |  | Inner Poloidal Field Coils
Job Manager: |  | James H. Chrzanowski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | x
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Poor impregnation |  |  |  | U | Local dry areas can be repaired. Extensive areas of poor VPI may require rewinding new coil |  |  |  | 10 | 50 | X
2 | Coil fails final acceptance tests |  |  |  | U | If coil cannot be repaired, a new coil be have to be wound |  |  |  | X | 50 | X
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9417
Job Number: | 1306
Job Title: | Inner Poloidal Field Coils
Job Manager: | James H. Chrzanowski
Materials and Subcontracts (M&S) |  | k$ | Basis of Estimate
Description:
Copper conductor |  | 46.4 | 4
Co-wound insulation [Kapton/glass] |  | 20 | 6
Fabricate inner PF coils |  | 180 | 6
Fabricate PF supports [mandrels- PF1A & 1B] |  | 100 | 2
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS

## Worksheet
|  | width | Height | Hole Dia | Hole Area | Area | Coil R | Turn | Length/Turn | Length/Coil | Length/Coil |  | Wt/coil
PF Conductors |  | in | in | in | in2 | in2 | in |  | in | in | ft | x 2 | lb | x 2
PF1a |  | 0.551 | 1.1 | 0.205 | 0.118 | 0.4881 | 12.571 | 64 | 78.9459 | 5052.5363 | 421.0447 | 842.0894 | 789.1658 | 1578.3315
PF1b |  | 0.633 | 0.392 | 0.126 | 0.0024 | 0.24574 | 15.763 | 32 | 98.9916 | 3167.7325 | 263.9777 | 527.9554 | 249.0963 | 498.1926
PF1c |  | 0.705 | 0.603 | 0.126 | 0.0024 | 0.42271 | 21.674 | 20 | 136.1127 | 2722.2544 | 226.8545 | 453.7091 | 368.2361 | 736.4722
[15 empty] | x 2.2 | 7.5
[14 empty] | 2812.9963 | 6188.5918 | 46.4144 | k
[8 empty] | Pi | 3.14
[7 empty] | Density | 0.32 | #/Cu in
PF-1B and Support mandrel
PF-1A and Support Mandrel
PF-1C and Ceramic Break Assembly