## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 1307
Job Title: | Center Stack Vacuum Casing
Job Manager: | James Chrzanowski
Description:
Includes the design and fabrication of the Centerstack casing and ceramic break assembly for the upgraded centerstack. Scope includes: 1) All analysis and Cad design for these components. 2)Procurement of the centerstack casing from OS 3) Includes the fabrication of CS support legs 4) Includes the procurement/fabrication of a new ceramic break assy 5) Includes the in-house assembly of the casing components. 6) Includes the mounting of the PF1B structure/coils to the casing
Schedule:
Refer to the Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost | Work |  | Activity Name | Responsible Cog Engr | Start | End | Duration | Start | EAEM1 | EAEM2 | EAEM3 | EAEM4 | EAEM5 | EAEM6 | EAEM7 | EAEM | EAEM2 | EAEM3 | EMEM1 | EMEM2 | EMEM4 | EMEM5 | EEEM | EMSM | EASB2 | EASB3 | EASB4 | EASB5 | EASB6 | EASB7 | EASB8 | EMSM1 | EMSM2 | EMSM3 | EMTB1 | EMTB2 | EMTB3 | EMTB4 | EMTB5 | M&S | OS | Travel | Stkrm. | Subtotal | Basis of Estimate | Category | Contingency
Center | Package | Job # | [5 empty] | Date | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs |  |  |  |  | M&S |  |  | %
[5 empty] | Date | Date | (Weeks) |  | (Chrzan.) | (Titus) | (Zhang) | (Zolfaghari) | (Avasarala) | (Brooks) | (Raftopoul.) | (general) | (Brooks) | (Titus) | (Mangra) | (Tresmer) | (Prinski) | (Simmons) |  | Meighan | (Morris) | (Martinelli) | (Upcavage) | (Jariwala) | (Wojtowicz) | (Paluzzi) | (Elect) | (Meighan) | (Jurcz.) |  | (Techs) | (Machinist) | (Welder) | (electrical) | (General) | K$ | k$ | k$ | k$ | k$
9417 | 1*** | 1307 | CS CASING - Design & Fabrication | Chrzanowski |  |  |  |  | See Job 1300
Scope: includes casing, bellows, ceramic break assembly, Bakeout leads on casing,
|  |  | Final Design Activities | [40 empty] | 0
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 |  | 2010-06-24 | [16 empty] | 416 | [18 empty] | 0 |  | 2 | 20%
|  |  | Complete bellow & ceramic break analysis Analysis |  |  |  |  | 2010-06-24 | [9 empty] | 60 | [25 empty] | 0 |  | 2 | 20%
|  |  | Complete Halo loading |  |  |  |  | 2010-06-24 | [8 empty] | 80 | [28 empty] | 2 | 20%
|  |  | Complete- Maintain heat balance cooling calculations |  |  |  |  | 2010-06-24 | [8 empty] | 80 | [28 empty] | 2 | 20%
|  |  | Itegrate thermal, halo, disruption loads into calculations |  |  |  |  | 2010-06-24 | [8 empty] | 80 | [28 empty] | 2 | 20%
|  |  | Fatigue Assessment |  |  |  |  | 2010-06-24 | [8 empty] | 20 | [28 empty] | 2 | 20%
|  |  | Prepare for FDR |  |  |  |  | 2011-03-10 | [16 empty] | 24 | [18 empty] | 0 |  | 2 | 20%
Procurement & Fabrication
CS Casing
|  |  | Prepare CS casing SOW & requisition |  | 2011-01-03 | 2011-02-28 | 4 | 2011-12-02 | [35 empty] | 0 |  | 2 | 10%
|  |  | Submit & evaluate RFQ returns |  | 2011-02-28 | 2011-05-23 | 4 | 2012-01-13 | [33 empty] | 2 |  | 2 |  | 2 | 10%
|  |  | Award CS Casing order |  |  |  | 1 | 2012-02-10 | [35 empty] | 0 |  | 2 | 10%
|  |  | Fabricate CS Casing |  |  |  | 30 | 2012-02-10 | [31 empty] | 230 |  | 5 |  | 235 |  | 4 | 35%
Generate requisitions for CS components
|  |  | Procure Inconel Bellows [PPPL supply to CS casing vendor] |  | 2011-02-28 | 2011-05-23 | 12 | 2011-11-18 | [31 empty] | 35 | 0 |  |  | 35 |  | 2 | 25%
|  |  | Procure Rotatable Flanges |  | 2011-02-28 | 2011-05-23 | 12 | [32 empty] | 0 | 17.1494 |  |  | 17.1494 |  | 4 | 25%
|  |  | Fabricate CHI copper Leads- upper & lower [For vessel bakeout] |  | 2011-02-28 | 2011-05-23 | 12 | [32 empty] | 0 | 16 |  |  | 16 |  | 4 | 20%
|  |  | Procure CS casing support structure |  | 2011-02-28 | 2011-05-23 | 16 | [33 empty] | 30 |  |  | 30 |  | 2 | 25%
|  |  | Procure Weld material |  | 2011-02-28 | 2011-05-23 | 12 | [16 empty] | 8 | [15 empty] | 5 |  |  |  | 5 |  | 2 | 15%
|  |  | Miscellaneous M&S |  | 2011-02-28 | 2011-05-23 | 12 | [16 empty] | 16 | [15 empty] | 5 |  |  |  | 5 |  | 2 | 15%
|  |  | Procure Ceramic Insulators [inc. [1] spare |  |  |  | 12 | [32 empty] | 80 | 0 |  |  | 80 |  | 4 | 35%
|  |  | Fabricate Ceramic break SS structure |  |  |  | 12 | [32 empty] | 0 | 45 |  |  | 45 |  | 2 | 15%
|  |  | Procure Viton "O" rings |  |  |  | 6 | [16 empty] | 8 | [15 empty] | 5 |  |  |  | 5 |  | 4 | 30%
|  |  | Organ pipe adapters& feedthru's |  |  |  | 10 | [16 empty] | 24 | [15 empty] | 35 |  |  |  | 35
In-house Fabrication
|  |  | Design stud installation fixture | [21 empty] | 80 | [18 empty] | 0 |  | 2 | 20%
|  |  | Fabricate Fixture for Stud installation [To be used in Job 1302] | [31 empty] | 80 | 40 |  |  |  | 1 |  |  | 1 | 2 |  | 2 | 20%
|  |  | Assemble and Test Ceramic Breaks inc. PF-1C coil assy |  |  |  | 4 | [16 empty] | 40 | [14 empty] | 200 | 2 | 0 |  |  | 2 |  | 2 | 20%
|  |  | Deliver CS casing to CS Assembly area |  |  |  |  | 2012-09-07 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  |  | 0
[5 empty] | 2009-10-01 | 2013-01-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 96 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 200 | 398 | 108.1494 | 7 | 1 | 514.1494
Costs do not include installation
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 1307
Job Title: |  | Center Stack Vacuum Casing
Job Manager: |  | James Chrzanowski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | x
| Design Complexity |  | x
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Components arrive late for assembly |  |  |  | U | OT required to accommodate schedule |  |  |  | None | None |  | TBD
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9417
Job Number: | 1307
Job Title: | Center Stack Vacuum Casing
Job Manager: | James Chrzanowski
Materials and Subcontracts (M&S) |  | K$ | Basis of Estimate
Description:
CS casing manufacturing [OS] |  | 230 | 4
Inconel bellows |  | 35 | 4
Rotable flanges |  | 17.1 | 4
Inconel weld studs |  | 7 | 6
CS casing support structure |  | 30 | 2
Weld material |  | 5 | 2
Miscellaneous |  | 5 | 9
Bakeout leads |  | 16 | 4
Viton O-rings |  | 5 | 4
Ceramic insulators |  | 55 | 4
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS

## Worksheet
| Orig Costs | Inflation | New Cost
Rotable flanges | 13.2 | 1.2992 | 17.1494
Inconel Forgings | 30.9 | 1.2992 | 40.1453 | 1.5 | 60.2179
| 20 | 1.2992 | 25.984 | 3 | 77.952
•Ceramic Break Assembly
•Bellows Assembly
•CS Inconel Casing
•Organ pipes [diagnostics & gas]
•CHI electrical leads for bakeout
•Plasma Facing Components
•Inner Poloidal Field Coils