## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 2300
Job Title: | Miscellaneous Diagnostic and Antenna Qualification
Job Manager: | P. Titus
Description:
At the beginning of the CDR, this task covered the ECH and other antenna systems, and was expanded to include miscellaneous diagnostics and components attached to the vessel which will be effected by the increases in EM , thermal, nuclear, dynamic loading and space allocation. A data base of antennas and diagnostics was created and elements sensitive to CSU changes were investigated. This included thin sheet metal shutters that may have thermal issues with higher power and eddy current loading.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9417
| Job Number: |  |  | 2300
| Job Title: |  |  | Miscellaneous Diagnostic and Antenna Qualification
| Job Manager: |  |  | P. Titus
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS (priced at FY10 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.178 | 1.178 | 1.617 | 1.232 | 1.859 | 177.11 | 118.8 | 135.2 | 101.48 | 67.89 | 172.42 | 150.61 | 122.43 | 83.52 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
1 |  | Physics Requirements | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
2 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
3 |  | Preliminary Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
4 |  |  | Disposition PDR Chits | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
5 |  |  | Create/Update Diagnostic Database |  |  |  |  | 2010-04-01 | 2010-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [29 empty] | 8 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
6 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
7 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
8 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
9 |  | Final Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
10 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
11 |  |  | Run Other GRD disruptions for the HHFW antenna | Han Zhang |  |  |  | 2010-06-01 | 2010-09-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 100 | [19 empty] | 20% | 20% |  | 8 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
12 |  |  | Updat HHFW Antenna | Han Zhang |  |  |  | 2010-06-01 | 2010-09-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 60 | [19 empty] | 20% | 20% |  | 8 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
13 |  |  | Maintain/Update Diagnostic Database | JBoales |  |  |  | 2010-06-01 | 2010-09-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 200 | [19 empty] | 20% | 20% |  | 8 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
14 |  |  | File Preliminary Database/Study | Jboales |  |  |  | 2010-06-01 | 2010-09-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 100 | [19 empty] | 20% | 20% |  | 8 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
15 |  |  | Check/Complete Disruption and Thermal Analyses |  |  |  |  | 2010-09-01 | 2011-03-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 100 | [19 empty] | 20% | 20% |  | 8 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
16 |  |  | Present/track recommentdations |  |  |  |  | 2010-09-01 | 2011-03-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 100 | [19 empty] | 20% | 20% |  | 8 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
17 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
18 |  |  | FDR Prep |  |  |  |  | 2011-02-01 | 2011-02-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 100 | [19 empty] | 20% | 20% |  | 8 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
19 |  |  | CONDUCT FDR |  |  |  |  | 2011-02-01 | 2011-02-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 20 | [19 empty] | 20% | 20% |  | 8 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
20 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
29 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
53 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
54 |  | OTHER TASKS | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 138.1458 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 138.1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [24 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [6 empty] | Weeks | [16 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [5 empty] | 3 | [16 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [5 empty] | 5 | [16 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [5 empty] | 8 | [16 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [5 empty] | 9 | [16 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 2300
Job Title: |  | Miscellaneous Diagnostic and Antenna Qualification
Job Manager: |  | P. Titus
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | x
| Design Complexity | x
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Diagnostic/waveguide has a present weakness that hasn't been seen in operation |  |  |  | High | Reinforce
2 | Diagnostic/waveguide requires more analysis to qualify |  |  |  | High | Expand Analysis models beyond those used in the scoping study |  |  | Add a Person-Month of Analysis | $25k
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9417
Job Number: | 2300
Job Title: | Miscellaneous Diagnostic and Antenna Qualification
Job Manager: | P. Titus
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
CATEGORIZATION CODES:
|  | 1 - National Standards |  | 1 | 0 | #DIV/0!
|  | 2 - Engineering Judgement/Experience |  | 2 | 0 | #DIV/0!
|  | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | #DIV/0!
|  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | #DIV/0!
|  | 5 - Prototype Data/Test Results |  | 5 | 0 | #DIV/0!
|  | 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | #DIV/0!
|  | 7 - Placed Contracts |  | 7 | 0 | #DIV/0!
|  | 8 - Actual experience for NCSX Work |  | 8 | 0 | #DIV/0!
|  | 9 - Other |  | 9 | 0 | #DIV/0!
|  |  | TOTALS |  | 0 | #DIV/0!

## ESTIMATE
NSTX UPGRADE WAF STATUS
2009-09-01
Cost Center | Work Package | Job # | WBS |  |  |  |  | Responsible Job Manager | WAF Forecast Completion | WAF Received | WAF Input to P3 | Prelim. Estimate ($K) | WAF Reviewed | Analysis Tasks | Engr | Prelim Design Hrs | Final Design Hrs
1.2 Plasma Heating and Current Drive Systems
1180 | 2*** | 2310 |  | 1.2.1 High Harmonic Fast Wave |  |  |  | P. Titus
1180 | 2*** | 2310 |  | 1.2.2 Coaxial Helicity Injection Current Drive |  |  |  | P. Titus
1180 | 2*** | 2310 |  | 1.2.3 Electron Cyclotron Heating |  |  |  | P. Titus
[14 empty] | Disruption analysis of Antenna | Ellis/Zhang | 300 | 300
[14 empty] | Documentation | Simmons | 40 | 40
|  |  |  | 1.2.4 Neutral Beam Injection |  |  |  | T.Stevenson
1180 | 2*** | 2410 |  |  | 1.2.4.1 NBI Project Support & Integration |  |  | T. Stevenson | 2009-08-14 | 2009-08-14
1180 | 2*** | 2420 |  |  | 1.2.4.2 NBI - Sources |  |  | M. Cropper | 2009-08-14 | 2009-08-14
1180 | 2*** | 2430 |  |  | 1.2.4.3 NBI - Decontamination |  |  | T. Stevenson | 2009-08-14 | 2009-08-14
1180 | 2*** | 2440 |  |  | 1.2.4.4 NBI - Beamline Relocation and Refurbishment |  |  | M. Denault | 2009-08-14 | 2009-08-14
1180 | 2*** | 2450 |  |  | 1.2.4.5 NBI - Services |  |  | M. Denault | 2009-08-14 | 2009-08-14
1180 | 2*** | 2460 |  |  | 1.2.4.6 NBI - Armor/Protective Plates |  |  | C Priniski
[5 empty] | 1.2.4.7 NBI - Power & Controls |  |  | Raki
1180 | 2*** | 2470 |  |  |  | 1.2.4.7.1 NBI - Power |  | Raki | 2009-08-14 | 2009-08-14
1180 | 2*** | 2475 |  |  |  | 1.2.4.7.2 NBI - Controls |  | M. Cropper | 2009-08-14 | 2009-08-14
1180 | 2*** | 2480 |  |  | 1.2.4.8 NBI - Nozzle/Duct |  |  | C. Priniski | 2009-08-14 | 2009-08-14
1180 | 2*** | 2490 |  |  | 1.2.4.9 NBI - Equipment Removals & Relocations |  |  | E. Perry | 2009-08-06 | 2009-08-06 | 2009-08-14
|  |  | 1.3 Auxiliary Systems |  |  |  |  | W.Blanchard
1170 | 3*** | ? |  | 1.3.1 Vacuum Pumping Systems |  |  |  | L. Dudek | ?
|  |  |  | 1.3.2 Coolant Systems |  |  |  | M.Denault
1170 | 3*** | 3200 |  |  |  |  | Water Cooling System Mods for CSU - Includes design, analysis, fabrication and installation of a new pump, and hardware upgrade on the cooling water system to permit the OH coil to operate at 600 psig | M. Denault | 2009-09-11
|  |  |  | 1.3.3 Bakeout System |  |  |  | W.Blanchard
1170 | 3*** | 3300 |  |  |  |  | Bakeout System mods for CSU - Includes upgrade to the power supply system to permit ohmic heating of the center stack casing for 350 C bakeout of the CS Tiles | L. Dudek | 2009-09-11
|  |  |  | 1.3.4 Gas Delivery Systems |  |  |  | W.Blanchard
1170 | 3*** | 3400 |  |  |  |  | Gas Delivery System Mods for CSU - Includes the design, fabrication and installation of the Gas Delivery System on the new Centerstack. | W. Blanchard | 2009-09-11
|  | n/a |  | 1.3.5 Glow Discharge Cleaning System |  |  |  | L. Dudek
|  |  | 1.4 Plasma Diagnostics |  |  |  |  | R.Kiata
|  |  |  | 1.4.1 Plasma Diagnostics |  |  |  | R. Kaita
1170 | 4*** | 4100 |  |  |  |  | Center Stack Diagnostics for CSU - Includes design and fabrications of CS magnetics diagnostics to replace units removed with old center stack | R. Kaita | 2009-09-11
[14 empty] | Disruption Loading of diagnostics | Zhang | 40 | 80
|  |  | 1.5 Power Systems |  |  |  |  | Raki
1170 | 5*** | 5100 |  | 1.5.1 AC Power Systems |  |  |  | Raki | 2009-09-11
1170 | 5*** | 5200 |  | 1.5.2 TF Power Conversion Systems |  |  |  | Raki | 2009-09-11
1170 | 5*** | 5300 |  | 1.5.3 PF/OH Power Conversion System |  |  |  | Raki | 2009-09-11
1170 | 5*** | 5400 |  | 1.5.4 CHI Power Conversion System |  |  |  | Raki | 2009-09-11
1170 | 5*** | 5500 |  | 1.5.5 General Power Systems and Integration |  |  |  | Raki | 2009-09-11
1170 | 5*** | 5501 |  |  |  |  | COIL BUS RUNS - Includes design and fabrication of bus runs/supports for theOH/ TF/ Inner PF and CHI Includes bus from coils to air-cooled bus in test cell west side | J. Chrzanowski | 2009-09-11
[14 empty] | Bus Loren tz Forces/Support Stress Analysis | Bryant |  | 60
1170 | 6*** | 6100 | 1.6 Central Instrumentation & Control |  |  |  |  | P. Sichta | ?
|  |  |  | 1.6.1 Control System |  |  |  | P. Sichta
|  |  |  | 1.6.2 Data Acquisition System |  |  |  | P. Sictha
|  |  | 1.7 Project Support & Integration |  |  |  |  | E.Perry
1170 | 7*** | 7100 |  | 1.7.1 Project Management & Integration |  |  |  | L. Dudek | ?
1170 | 7*** | 7200 |  | 1.7.2 Project Physics |  |  |  | J. Menard | ?
1170 | 7*** | 7300 |  | 1.7.3 Integrated Systems Test |  |  |  | C. Gentile | ?
|  |  | 1.8 Site Preparation and Torus Assembly |  |  |  |  | E.Perry
1170 | 8*** | 8100 |  | 1.8.1 Site Preparation |  |  |  | E.Perry | ?
|  |  |  | 1.8.2 Torus Assembly |  |  |  | E.Perry
1170 | 8*** | 8200 |  |  |  |  | Centerstack and Coil structure Installation - Covers the materials and labor to install the centerstack and related hardware and the upgraded coil support structures | E.Perry | ?
[14 empty] | Analysis of Fixtures | Willard |  | 100
[16 empty] | 380 | 580 | Hrs
[16 empty] | 3.1667 | 4.8333 | Man-Months
[14 empty] | Prelim Design Start Date | 2009-10-15
[14 empty] | Preliminary Design End Date | 2010-02-15 | 4 Months
[14 empty] | Final Design Start Date | 2010-02-15
[14 empty] | Final Design End Date | 2010-12-15 |  | 10 Months