## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9418
Job Number: | 2425
Job Title: | NSTX Beamline 2 Relocation
Job Manager: | Martin Denault
Description:
This job includes the efforts to relocate a TFTR neutral beam line and ancillary equipment into the NSTX test cell. This includes the High Voltage Enclosures (HVEs) and the complete beam box.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9418
| Job Number: |  |  | 2425
| Job Title: |  |  | NSTX Beamline 2 Relocation
| Job Manager: |  |  | Martin Denault
Estimate (user input)
[5 empty] | SCHEDULE | [12 empty] | FY10$K |  |  |  |  | HOURS (priced at FY10 rates) | [19 empty] | % | % |  |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Contingency | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [16 empty] | 1.178 | 1.178 | 1.617 | 1.232 | 1.859 | 177.11 | 118.8 | 135.2 | 101.3 | 74.4 | 172.42 | 150.61 | 122.43 | 83.52 | 149.15 | 148.87 | 115.61 | 89.2 | 142.83 | 177 | 208.3 | 156.85 | 1 | 1 | 1
1
2
3 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
4 |  | Preliminary Design |  | Denault | [7 empty] | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
5 |  | PDR Prep |  |  | 5 | 17 |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [12 empty] | 10% |  | 4- Experience
6 |  | CONDUCT PDR |  |  | 2 | 18 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [12 empty] | 10% |  | 4- Experience
7 |  | Lehman Review |  |  | 5 |  |  |  | 2010-12-15 | 2010-12-15 | 2010-12-22 | 2010-12-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [14 empty] | 4- Experience
8 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
9 |  | Final Design |  | Denault | [7 empty] | 2011-01-28 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
10 |  | Disposition PDR Chits |  |  | 2 | 21 |  |  | 2011-01-28 | 2011-01-28 | 2011-01-30 19:12 | 2011-01-28 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [12 empty] | 10% |  | 4- Experience
11 |  | Design Drawings |  |  | 10 | 22 |  |  |  | 2007-11-12 | 2007-11-26 | 2007-10-01 | 2007-11-12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 |  |  |  | 40 |  |  |  | 20 | [12 empty] | 10% |  | 4- Experience
12 |  | Update Analyses |  |  | 5 | 23 |  |  |  | 2007-10-02 09:36 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [8 empty] | 40 | [12 empty] | 10% |  | 4- Experience
13 |  | Update Cost & Schedule Estimate |  |  | 5 | 24 |  |  |  | 2007-11-12 | 2007-11-19 | 2007-10-01 | 2007-11-12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [6 empty] | 40 | [5 empty] | 10% |  | 4- Experience
14 |  | Prep Procurement Specs |  |  | 5 | 25 |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [12 empty] | 10% |  | 4- Experience
15 |  | FDR Prep |  |  | 5 | 26 |  |  |  | 2011-06-12 19:12 | 2011-06-19 19:12 | 2007-10-01 | 2011-06-12 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [12 empty] | 10% |  | 4- Experience
16 |  | CONDUCT FDR |  |  | 2 | 27 |  |  |  | 2007-10-02 09:36 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [12 empty] | 10% |  | 4- Experience
17 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
18 |  | Procurement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
19 |  | Steel and Parts | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [23 empty] | 0
20 |  |  | Prep Requisition and procurement package |  | 1 | 28 |  |  | 2011-06-10 | 2011-06-10 | 2011-06-11 09:36 | 2011-06-10 | 2007-11-12 | 2007-10-01 | 2007-10-01 | 2007-10-01
21 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 32 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
22 |  |  | Procurement lead time (1) |  | 30 | 33 |  |  |  | 2007-10-01 | 2007-11-12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
23 |  |  | AWARD |  | 1 | 34 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
24 |  |  | Fabricate or delivery |  | 30 | 35 |  |  |  | 2007-10-01 | 2007-11-12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
25 |  | Lifting Equip. | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
26 |  |  | Prep Requisition and procurement package |  | 2 | 28 |  |  | 2011-06-10 | 2011-06-10 | 2011-06-12 19:12 | 2011-06-10 | 2007-11-12 | 2007-10-01 | 2007-10-01 | 2007-10-01
27 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 38 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
28 |  |  | Procurement lead time (1) |  | 30 | 39 |  |  |  | 2007-10-01 | 2007-11-12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
29 |  |  | AWARD |  | 1 | 40 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
30 |  |  | Fabricate or delivery |  | 30 | 41 |  |  |  | 2007-10-01 | 2007-11-12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
31 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 |  | Fab/Assembly |  | Denault | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
33 |  | Fab/Assy Procedure | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
34 |  | Shop Fabrication | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
35 |  | Assembly | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
36 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
37 |  | Installation |  | Denault | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
38 |  | Installation Procedure | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
39 |  | Machine Installation | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
40 |  | PTP Testing | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
41 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
42 |  | Engineering 1 Days Per Week title III |  | 1 | 280 |  |  |  | 2011-02-01 | 2011-02-01 | 2012-02-28 | 2011-02-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 160 |  |  |  | 448 | [12 empty] | 10% |  | 4- Experience
43 |  | Engineering Support 1/2 Days Per Week title III |  | 0.5 | 280 |  |  |  | 2011-02-02 | 2011-02-02 | 2012-02-29 | 2011-02-02 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 224 | [12 empty] | 25% |  | 4- Experience
44 |  | Drafting Support 1/2 day/week title III |  | 0.5 | 280 |  |  |  | 2011-02-03 | 2011-02-03 | 2012-03-01 | 2011-02-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 224 | [19 empty] | 10% |  | 4- Experience
45
46 |  | Path | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 15
47 |  |  | Road |  | 5 |  |  |  | 2012-01-01 | 2012-01-01 | 2012-01-08 | 2012-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 40 | 160 | [10 empty] | 25% |  | 4- Experience
48 |  |  | Duct Removal |  | 2 | 59 |  |  | 2012-01-01 | 2012-01-01 | 2012-01-03 19:12 | 2012-01-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 25% |  | 4- Experience
49 |  |  | Lintel Removal |  | 3 | 60 |  |  |  | 2010-06-29 | 2010-07-03 04:48 | 2007-10-01 | 2010-06-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 16 | 8 | 24 | 96 | [10 empty] | 25% |  | 4- Experience
50 |  |  | Lintel Install |  | 2 | 107 |  |  |  | 2007-10-09 09:36 | 2007-10-12 04:48 | 2007-10-01 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 16 | 8 | 16 | 64 | [10 empty] | 25% |  | 4- Experience
51 |  |  | Duct Install |  | 2 | 62 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 0 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 25% |  | 4- Experience
|  |  | Suits | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 4
52 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
54 |  | Metrology | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 3
55 |  |  | Setup |  | 5 |  |  |  | 2009-10-01 | 2009-10-01 | 2009-10-08 | 2009-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 |  | 80 | [10 empty] | 10% |  | 4- Experience
56 |  |  | Measure |  | 15 | 67 |  |  |  | 2007-10-01 | 2007-10-22 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 240 |  | 240 | [10 empty] | 10% |  | 4- Experience
57 |  |  | Model |  | 5 | 68 |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 | [7 empty] | 80 | [12 empty] | 10% |  | 4- Experience
58 |  |  | Lay out |  | 5 | 69 |  |  |  | 2012-01-02 09:36 | 2012-01-09 09:36 | 2007-10-01 | 2012-01-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 |  | 80 | [10 empty] | 10% |  | 4- Experience
|  |  | Suits | [14 empty] | 5
59 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
60 |  | Labyrinth Removal |  |  | 20 |  |  |  | 2010-06-01 | 2010-06-01 | 2010-06-29 | 2010-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 20 | [12 empty] | 32 |  | 160 | 480 | [10 empty] | 20% |  | 4- Experience
61 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
62 |  | Lift Fixtures | [15 empty] | 20
63 |  |  | Construction |  | 20 |  |  |  | 2010-01-10 | 2010-01-10 | 2010-02-07 | 2010-01-10 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [17 empty] | 480 | [10 empty] | 10% |  | 4- Experience
64 |  |  | Load Test |  | 5 | 75 |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | 40 | 120 | [10 empty] | 10% |  | 4- Experience
65 |  |  | Move |  | 1 | 76 |  |  |  | 2010-01-02 09:36 | 2010-01-03 19:12 | 2007-10-01 | 2010-01-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [17 empty] | 24 | [10 empty] | 10% |  | 4- Experience
66 |  |  | Trial Runs |  | 5 | 77 |  |  |  | 2007-10-06 14:24 | 2007-10-13 14:24 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | 40 | 120 | [10 empty] | 10% |  | 4- Experience
67 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
68 |  | Box Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2
69 |  |  | Lift onto Rollers |  | 1 | 95 | 155 | 19 | 2012-01-01 | 2012-01-01 | 2012-01-02 09:36 | 2012-01-01 | 2007-10-05 04:48 |  |  | 2007-10-01 | [15 empty] | 152 | 8 | 48 | [10 empty] | 20% |  | 4- Experience
70 |  |  | Move IN |  | 1 | 88 |  |  |  | 2007-10-06 14:24 | 2007-10-08 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [10 empty] | 20% |  | 4- Experience
71 |  |  | Over Wall |  | 1 | 89 |  |  |  | 2007-10-10 19:12 | 2007-10-12 04:48 | 2007-10-01 | 2007-10-10 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [10 empty] | 20% |  | 4- Experience
72 |  |  | Placement |  | 10 | 90 |  |  |  | 2007-10-01 | 2007-10-15 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | 80 | 480 | [10 empty] | 20% |  | 4- Experience
73 |  |  | Metrology |  | 10 | 91 |  |  |  | 2007-10-01 | 2007-10-15 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | 80 | 160 | [10 empty] | 20% |  | 4- Experience
|  |  | Suits | [14 empty] | 10
74 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
75 |  | Source Platform | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
76 |  |  | Off |  | 1 |  |  |  | 2010-01-01 | 2010-01-01 | 2010-01-02 09:36 | 2010-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 24 | [10 empty] | 10% |  | 4- Experience
77 |  |  | Move |  | 1 | 95 |  |  |  | 2007-10-05 04:48 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 16 | [10 empty] | 10% |  | 4- Experience
78 |  |  | Lift |  | 1 | 96 |  |  |  | 2007-10-05 04:48 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [10 empty] | 10% |  | 4- Experience
79 |  |  | On |  | 1 | 97 |  |  |  | 2007-10-06 14:24 | 2007-10-08 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [10 empty] | 10% |  | 4- Experience
80 |  |  | Metrology |  | 10 | 98 |  |  |  | 2007-10-06 14:24 | 2007-10-20 14:24 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 160 | 80 | 320 | [10 empty] | 10% |  | 4- Experience
81 |  |  | Suits | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 4
82 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
83 |  | Lid Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 5
84 |  |  | Stabilize |  | 3 | 99 |  |  |  | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 24 | 24 | 120 | [10 empty] | 20% |  | 4- Experience
85 |  |  | Lift onto Rollers |  | 1 | 103 |  |  |  | 2007-10-09 09:36 | 2007-10-10 19:12 | 2007-10-01 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [10 empty] | 20% |  | 4- Experience
86 |  |  | Move IN |  | 1 | 104 |  |  |  | 2007-10-06 14:24 | 2007-10-08 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [10 empty] | 20% |  | 4- Experience
87 |  |  | Over Wall |  | 1 | 105 |  |  |  | 2007-10-08 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [10 empty] | 20% |  | 4- Experience
88 |  |  | Placement |  | 1 | 106 |  |  |  | 2007-10-05 04:48 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 16 | [10 empty] | 20% |  | 4- Experience
89 |  |  | Metrology |  | 1 | 107 |  |  |  | 2007-10-09 09:36 | 2007-10-10 19:12 | 2007-10-01 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | 8 | 48 | [10 empty] | 20% |  | 4- Experience
90 |  |  | Suits | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2
91 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
92 |  | Component Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2
93 |  |  | 90in Flange |  | 2 | 108 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
94 |  |  | Magnet |  | 2 | 112 |  |  |  | 2007-10-03 19:12 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [10 empty] | 10% |  | 4- Experience
95 |  |  | Ion Dump |  | 2 | 113 |  |  |  | 2007-10-02 09:36 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [10 empty] | 10% |  | 4- Experience
96 |  |  | Exit Spool |  | 2 | 114 |  |  |  | 2007-10-02 09:36 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
97 |  |  | TIV |  | 2 | 115 |  |  |  | 2007-10-03 19:12 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
98 |  |  | Calorimeter |  | 2 | 116 |  |  |  | 2007-10-03 19:12 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [10 empty] | 10% |  | 4- Experience
99 |  |  | Suits | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 4
100 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
101 |  | Source Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
102 |  |  | Move 1 |  | 2 | 99 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
103 |  |  | Align 1 |  | 4 | 121 |  |  |  | 2007-10-03 19:12 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 64 | 32 | 128 | [10 empty] | 10% |  | 4- Experience
104 |  |  | Move 2 |  | 2 | 122 |  |  |  | 2007-10-03 19:12 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
105 |  |  | Align 2 |  | 4 | 123 |  |  |  | 2007-10-02 09:36 | 2007-10-08 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 64 | 32 | 128 | [10 empty] | 10% |  | 4- Experience
106 |  |  | Move 3 |  | 2 | 124 |  |  |  | 2007-10-02 09:36 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
107 |  |  | Align 3 |  | 4 | 125 |  |  |  | 2007-10-03 19:12 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 64 | 32 | 128 | [10 empty] | 10% |  | 4- Experience
|  |  | Suits | [14 empty] | 4
108 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
109 |  | HVE 1 Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
110 |  |  | Move |  | 2 |  | 19 |  | 2011-06-01 | 2011-06-01 | 2011-06-03 19:12 | 2011-06-01 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [10 empty] | 10% |  | 4- Experience
111 |  |  | Disassemble |  | 2 | 129 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
112 |  |  | Move to Crain Access |  | 2 | 130 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
113 |  |  | Lift into TFTR |  | 1 | 131 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [10 empty] | 10% |  | 4- Experience
114 |  |  | Move In |  | 1 | 132 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [10 empty] | 10% |  | 4- Experience
115 |  |  | Over Wall |  | 2 | 133 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 80 | [10 empty] | 10% |  | 4- Experience
116 |  |  | Reassemble |  | 2 | 134 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
117 |  |  | Placement |  | 3 | 135 |  |  |  | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 24 | 96 | [10 empty] | 10% |  | 4- Experience
118 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
119 |  | HVE 2 Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
120 |  |  | Move |  | 2 |  |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [10 empty] | 10% |  | 4- Experience
121 |  |  | Disassemble |  | 2 | 139 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
122 |  |  | Move to Crain Access |  | 2 | 140 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
123 |  |  | Lift into TFTR |  | 1 | 141 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [10 empty] | 10% |  | 4- Experience
124 |  |  | Move In |  | 1 | 142 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [10 empty] | 10% |  | 4- Experience
125 |  |  | Over Wall |  | 2 | 143 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 80 | [10 empty] | 10% |  | 4- Experience
126 |  |  | Reassemble |  | 2 | 144 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
127 |  |  | Placement |  | 3 | 145 |  |  |  | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 24 | 96 | [10 empty] | 10% |  | 4- Experience
128 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
129 |  | HVE 3 Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
130 |  |  | Move |  | 2 |  |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [10 empty] | 10% |  | 4- Experience
131 |  |  | Disassemble |  | 2 | 149 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
132 |  |  | Move to Crain Access |  | 2 | 150 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
133 |  |  | Lift into TFTR |  | 1 | 151 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [10 empty] | 10% |  | 4- Experience
134 |  |  | Move In |  | 1 | 152 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [10 empty] | 10% |  | 4- Experience
135 |  |  | Over Wall |  | 2 | 153 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 80 | [10 empty] | 10% |  | 4- Experience
136 |  |  | Reassemble |  | 2 | 154 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [10 empty] | 10% |  | 4- Experience
137 |  |  | Placement |  | 3 | 155 |  |  |  | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 24 | 96 | [10 empty] | 10% |  | 4- Experience
|  |  | HVE Hilti | [14 empty] | 1 | [15 empty] | 40 | [10 empty] | 10%
|  |  | Floor Plug | [14 empty] | 3 | [15 empty] | 200 | [10 empty] | 10%
[12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [15 empty] | 108 | 0 | 0 | 0 | 0 | 80 | 160 | 224 | 0 | 0 | 200 | 0 | 0 | 64 | 2356 | 1312 | 6296 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1511.3843 | [12 empty] | 127.224 | 0 | 0 | 0 | 0 | 14.1688 | 19.008 | 30.2848 | 0 | 0 | 34.484 | 0 | 0 | 5.3453 | 351.3974 | 195.3174 | 727.8806 | 0 | 0 | 0 | 0 | 6.274 |  | 0 | 0
| Notes: | [19 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  |  | Weeks | [14 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  |  |  | 3 | [14 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  |  |  | 5 | [14 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  |  |  | 8 | [14 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  |  |  | 9 | [14 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
118732

## Tab C Risk and Uncertainty
Cost Center: |  | 9418
Job Number: |  | 2425
Job Title: |  | NSTX Beamline 2 Relocation
Job Manager: |  | Martin Denault
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9418
Job Number: | 2425
Job Title: | NSTX Beamline 2 Relocation
Job Manager: | Martin Denault
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Pipe |  |  | Vendor Pricing
Parts |  |  | Vendor Pricing
MISC |  |  | Experience
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS