## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9418
Job Number: | 2430
Job Title: | NSTX Beamline 2 Decontamination
Job Manager: | Tim Stevenson
Description:
This job includes disassembly and decontamination activities of a TFTR Neutral Beam beamline in preparation for beamline refurbishment and reuse as an NSTX upgrade. Job includes a Peer Review to assess results. (Held 4/21/10). Job also includes post- Peer Review decon on targeted areas of box, lid, dump, and calorimeter. Dump, source platform and calorimeter will be disassembled such that obscurred areas can receive decon attention. Primary Decon slated to conclude end of June 2010.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9418
| Job Number: |  |  | 2430
| Job Title: |  |  | NSTX Beamline 2 Decontamination
| Job Manager: |  |  | Tim Stevenson
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS (priced at FY10 rates) | [19 empty] | % | % |  |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Resp | Duration in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Cont | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.178 | 1.178 | 1.617 | 1.232 | 1.859 | 177.11 | 118.8 | 135.2 | 101.48 | 67.89 | 172.42 | 150.61 | 122.43 | 83.52 | 149.15 | 148.87 | 115.61 | 89.2 | 120.76 | 177 | 208.3 | 150.77 | 1 | 1 | 1 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
1 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
2 |  |  | Decon Calorimeter |  | 30 |  | 2009-10-01 | 2009-10-01 | 2009-11-12 | 2009-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 240 |  | 1200 | [13 empty] | 10-15% | Crew of 5 NB Techs with Supervisor | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
3 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
4 |  |  | Decon Ion Dump |  | 30 |  |  | 2009-12-01 | 2010-01-12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 240 |  | 1200 | [13 empty] | 10-15% | Crew of 5 NB Techs with Supervisor | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
5 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
6 |  |  | Decon Bending Magnet |  | 30 |  |  | 2010-01-04 | 2010-02-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 240 |  | 1200 | [13 empty] | 10-15% | Crew of 5 NB Techs with Supervisor | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
7 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
8 |  |  | Decon 90 inch flange and neutralizer |  | 30 |  |  | 2010-02-15 | 2010-03-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 240 |  | 1200 | [13 empty] | 10-15% | Crew of 5 NB Techs with Supervisor | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
9 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
10 |  |  | Decon exit spool piece |  | 20 |  |  | 2010-04-01 | 2010-04-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 160 |  | 800 | [13 empty] | 10-15% | Crew of 5 NB Techs with Supervisor | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
11 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
12 |  |  | Decon BL Lid |  | 45 |  |  | 2010-04-15 | 2010-06-17 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 360 |  | 1800 | [13 empty] | 10-15% | Crew of 5 NB Techs with Supervisor | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
13 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
14 |  |  | Decon BL Box |  | 45 |  |  | 2010-06-10 | 2010-08-12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 360 |  | 1800 | [13 empty] | 10-15% | Crew of 5 NB Techs with Supervisor | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
15 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
16 |  |  | Decon BL exterior and accoutrements |  | 15 |  |  | 2010-09-01 | 2010-09-22 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 120 |  | 600 | [13 empty] | 10-15% | Crew of 5 NB Techs with Supervisor | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
17 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
18 |  |  | Decon Program Evaluation / Operation Impact Report |  | 10 |  |  | 2007-10-01 | 2007-10-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 240 | [12 empty] | 10-15% |  | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
19 |  |  | Hardware and tools | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  |  | 12 | [25 empty] | 10-15% | See Tab-D | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
20 |  |  | Radiation PCs, boots, gloves, masks, etc. | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 25 | [26 empty] | 10-15% | See Tab-D | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
21 |  |  | B-25 special sizes | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 25 | [26 empty] | 10-15% | See Tab-D | 2-Engineering Judgement | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
22 |  |  | Decon supplies & consumables | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  |  | 12 | [25 empty] | 10-15% | See Tab-D | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
23 | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
24 |  |  | Post-Peer Review Decon (Box, Lid, Dump, Cal) |  | 50 |  | 2010-04-21 | 2010-04-21 | 2010-06-30 | 2010-04-21 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 320 |  | 640 | [13 empty] | 10-15% |  | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
25 |  |  | Area maintenance |  | 100 |  | 2010-04-21 | 2010-04-21 | 2010-09-08 | 2010-04-21 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2 | 2 | [11 empty] | 25 | [13 empty] | 10-15% |  | 2-Experience | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
26 |  |  | Note: HP & ERWM coverage not included in this job. | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
|  | TOTALS | [13 empty] | 52 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2280 | 0 | 10465 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1345.1076 | [10 empty] | 61.256 | 30.628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343.3908 | 0 | 874.0368 | 35.796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [17 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: |  |  |  |  | Weeks | [11 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  | 3 | [11 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items |  |  |  | 5 | [11 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) |  |  |  | 8 | [8 empty] | 78 |  |  | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts |  |  |  | 9 | [11 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9418
Job Number: |  | 2430
Job Title: |  | NSTX Beamline 2 Decontamination
Job Manager: |  | Tim Stevenson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | x
| Design Complexity |  |  | x
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9418
Job Number: | 2430
Job Title: | NSTX Beamline 2 Decontamination
Job Manager: | Tim Stevenson
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Radiation PCs, boots, gloves masks, etc… | 26 | Cost estimate for FY2010 was based on costs incurred in FY2010 ytd pro-rated for a full year of decon activities | 2-Experience
Hardware/Tools, Decon Supplies & Consumables | 27 | Cost estimate for FY2010 was based on costs incurred in FY2010 ytd pro-rated for a full year of decon activities | 2-Experience
* Double the cost of PCard and StockRoom costs incurred in FY2009 and distributed evenly between "Hardaware & Tools" and "Decon Suppies & Consumables"
B-25 Container Special Size | $25K | Assumed we could incur costs as much as $25K if we had to fabricate Special Size B-25 container | 2- Engineering Judgement
53
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS