## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9418
Job Number: | 2450
Job Title: | NSTX Beamline 2 Services
Job Manager: | Martin Denault
Rev 3 10/14/2010
Description:
This job includes the efforts to provide services to the new neutral beamline and ancillary equipment in the NSTX test cell. These services include water, cryogenic systems, gas supplies, and vacuum lines.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9418
| Job Number: |  |  | 2450
| Job Title: |  |  | NSTX Beamline 2 Services
| Job Manager: |  |  | Martin Denault
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | Duration in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (opt) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Contingency | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1
2
3 |  | Conceptual Design |  | Denault | [5 empty] | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
4 |  | PREPARE WORK PLANNING FORM |  |  | 1 |  | 2009-09-24 | 2009-09-24 | 2009-09-25 09:36 | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | [14 empty] | 4-Experience
5 |  | Prep System Description |  |  | 2 | 4 |  | 2009-09-25 09:36 | 2009-09-28 04:48 | 2007-10-01 | 2009-09-25 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [14 empty] | 4-Experience
6 |  | Prep System Requirements |  |  | 3 | 5 |  | 2009-09-28 04:48 | 2009-10-02 09:36 | 2007-10-01 | 2009-09-28 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 24 | [14 empty] | 4-Experience
7 |  | R&D |  |  | 10 | 6 |  | 2009-10-02 09:36 | 2009-10-16 09:36 | 2007-10-01 | 2009-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [14 empty] | 4-Experience
8 |  | Analysis |  |  | 20 | 7 |  | 2009-10-16 09:36 | 2009-11-13 09:36 | 2007-10-01 | 2009-10-16 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 |  |  |  |  | 80 |  |  |  | 160 | [14 empty] | 4-Experience
9 |  | CDR |  |  | 2 | 8 | 2009-01-11 | 2009-11-13 09:36 | 2009-11-16 04:48 | 2009-01-11 | 2009-11-13 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [14 empty] | 4-Experience
10 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
11 |  | Preliminary Design |  | Denault | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
12 |  | Thermal Analysis |  |  | 10 | 9 |  | 2009-11-16 04:48 | 2009-11-30 04:48 | 2007-10-01 | 2009-11-16 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 80 | [14 empty] | 4-Experience
13 |  | Seismic Analysis |  |  | 10 | 12 |  | 2009-11-30 04:48 | 2009-12-14 04:48 | 2007-10-01 | 2009-11-30 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 80 | [14 empty] | 4-Experience
14 |  | FMEA Analysis |  |  | 5 | 13 |  | 2009-12-14 04:48 | 2009-12-21 04:48 | 2007-10-01 | 2009-12-14 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 40 | [14 empty] | 4-Experience
15 |  | Prepare NEPA Form |  |  | 2 | 14 |  | 2009-12-21 04:48 | 2009-12-24 | 2007-10-01 | 2009-12-21 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [14 empty] | 4-Experience
16 |  | Update Cost & Schedule Estimate |  |  | 10 | 15 |  | 2009-12-24 | 2010-01-07 | 2007-10-01 | 2009-12-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [6 empty] | 80 | [7 empty] | 4-Experience
17 |  | Design Drawings |  |  | 60 | 16 |  | 2010-01-07 | 2010-04-01 | 2007-10-01 | 2010-01-07 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 480 |  |  |  | 160 |  |  |  | 240 | [14 empty] | 4-Experience
18 |  | PDR Prep |  |  | 10 | 17 |  | 2010-04-01 | 2010-04-15 | 2007-10-01 | 2010-04-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [12 empty] | 10% |  | 4-Experience
19 |  | CONDUCT PDR |  |  | 2 | 18 | 2010-05-01 | 2010-05-01 | 2010-05-03 19:12 | 2010-05-01 | 2010-04-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [12 empty] | 10% |  | 4-Experience
20 |  | Lehman Review |  |  | 5 | 19 |  | 2010-05-03 19:12 | 2010-05-10 19:12 | 2007-10-01 | 2010-05-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [12 empty] | 10% |  | 4-Experience
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
21 |  | Final Design |  | Denault | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
22 |  | Disposition PDR Chits |  |  | 2 | 20 |  | 2010-05-10 19:12 | 2010-05-13 14:24 | 2007-10-01 | 2010-05-10 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [12 empty] | 10% |  | 4-Experience
23 |  | Design Drawings |  |  | 10 | 22 |  | 2010-05-13 14:24 | 2010-05-27 14:24 | 2007-10-01 | 2010-05-13 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 |  |  |  | 80 |  |  |  | 20 | [12 empty] | 10% |  | 4-Experience
24 |  | Update Analyses |  |  | 5 | 23 |  | 2010-05-27 14:24 | 2010-06-03 14:24 | 2007-10-01 | 2010-05-27 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [8 empty] | 40 | [12 empty] | 10% |  | 4-Experience
25 |  | Update Cost & Schedule Estimate |  |  | 10 | 24 |  | 2010-06-03 14:24 | 2010-06-17 14:24 | 2007-10-01 | 2010-06-03 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [6 empty] | 80 | [5 empty] | 10% |  | 4-Experience
26 |  | Prep Procurement Specs |  |  | 10 | 25 |  | 2010-06-17 14:24 | 2010-07-01 14:24 | 2007-10-01 | 2010-06-17 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [12 empty] | 10% |  | 4-Experience
27 |  | FDR Prep |  |  | 10 | 26 |  | 2010-07-01 14:24 | 2010-07-15 14:24 | 2007-10-01 | 2010-07-01 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [12 empty] | 10% |  | 4-Experience
28 |  | CONDUCT FDR |  |  | 2 |  | 2010-10-01 | 2010-10-01 | 2010-10-03 19:12 | 2010-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [12 empty] | 10% |  | 4-Experience
29 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
30 |  | Procurement | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
31 |  | Cryo parts | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 |  |  | Prep Requisition and procurement package |  | 1 | 28 | 2011-01-01 | 2011-01-01 | 2011-01-02 09:36 | 2011-01-01 | 2010-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
33 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 32 |  | 2011-01-02 09:36 | 2011-01-03 19:12 | 2007-10-01 | 2011-01-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01
34 |  |  | Procurement lead time (1) |  | 30 | 33 |  | 2011-01-03 19:12 | 2011-02-14 19:12 | 2007-10-01 | 2011-01-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
35 |  |  | AWARD |  | 1 | 34 |  | 2011-02-14 19:12 | 2011-02-16 04:48 | 2007-10-01 | 2011-02-14 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
36 |  |  | Fabricate or delivery |  | 90 | 35 |  | 2011-02-16 04:48 | 2011-06-22 04:48 | 2007-10-01 | 2011-02-16 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01
37 |  | Pipe and misc. | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
38 |  |  | Prep Requisition and procurement package |  | 2 | 28 | 2011-01-01 | 2011-01-01 | 2011-01-03 19:12 | 2011-01-01 | 2010-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
39 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 38 |  | 2011-01-03 19:12 | 2011-01-05 04:48 | 2007-10-01 | 2011-01-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
40 |  |  | Procurement lead time (1) |  | 30 | 39 |  | 2011-01-05 04:48 | 2011-02-16 04:48 | 2007-10-01 | 2011-01-05 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01
41 |  |  | AWARD |  | 1 | 40 |  | 2011-02-16 04:48 | 2011-02-17 14:24 | 2007-10-01 | 2011-02-16 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01
42 |  |  | Fabricate or delivery |  | 30 | 41 |  | 2011-02-17 14:24 | 2011-03-31 14:24 | 2007-10-01 | 2011-02-17 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01
43 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
44 |  | Fab/Assembly |  | Denault | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
45 |  | Fab/Assy Procedure | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
46 |  | Shop Fabrication | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
47 |  | Assembly | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
48 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
49 |  | Installation |  | Denault | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
50 |  | Installation Procedure | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
51 |  | Machine Installation | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
52 |  | PTP Testing | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  |  | Engineering |  | 500 |  | 2011-01-01 | 2011-01-01 | 2012-12-01 | 2011-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 120 |  |  |  | 2400 | [12 empty] | 10% |  | 4-Experience
|  |  | Engineering Support | 800 Hours | 500 |  | 2011-01-01 | 2011-01-01 | 2012-12-01 | 2011-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 80 | [26 empty] | 25% |  | 4-Experience
|  |  | Drafting Support |  | 500 |  | 2011-01-01 | 2011-01-01 | 2012-12-01 | 2011-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 800 | [20 empty] | 10% |  | 4-Experience
54 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
56 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
57 |  |  | Helium Transfer Lines |  | 160 |  | 2011-10-01 | 2011-10-01 | 2012-05-12 | 2011-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 120 | [12 empty] | 450 |  |  | 3000 | [10 empty] | 50% |  | See Tab E for SB breakdown
58 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 0
59 |  |  | Nitrogen Transfer Lines |  | 120 |  | 2011-11-15 | 2011-11-15 | 2012-05-01 | 2011-11-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 80 | [12 empty] | 180 |  |  | 1200 | [10 empty] | 20% |  | See Tab E for SB breakdown
60 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
61 |  |  | SF6 Transfer Lines |  | 30 |  | 2012-04-01 | 2012-04-01 | 2012-05-13 | 2012-04-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10 | [12 empty] | 67.5 |  |  | 450 | [10 empty] | 15% |  | See Tab E for SB breakdown
62 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
63 |  |  | HVE Water Lines |  | 65 |  | 2011-11-15 | 2011-11-15 | 2012-02-14 | 2011-11-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 100 | [12 empty] | 180 |  |  | 1200 | [10 empty] | 25% |  | See Tab E for SB breakdown
64 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
65 |  |  | Ion Dump Water Lines |  | 100 |  | 2011-07-01 | 2011-07-01 | 2011-11-18 | 2011-07-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 135 | [12 empty] | 420 |  |  | 2800 | [10 empty] | 25% |  | See Tab E for SB breakdown
66 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
67 |  |  | Ion Source Water Lines |  | 80 |  | 2011-09-01 | 2011-09-01 | 2011-12-22 | 2011-09-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 90 | [12 empty] | 300 |  |  | 2000 | [10 empty] | 25% |  | See Tab E for SB breakdown
72 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
73 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
74 |  |  | Vacuum Lines |  | 30 |  | 2012-05-01 | 2012-05-01 | 2012-06-12 | 2012-05-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 85 | [12 empty] | 86.25 |  |  | 575 | [10 empty] | 15% |  | See Tab E for SB breakdown
84 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
85 |  |  | Stack 8 Vacuum Lines |  | 30 |  | 2011-06-01 | 2011-06-01 | 2011-07-13 | 2011-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 50 | [12 empty] | 52.5 |  |  | 350 | [10 empty] | 15% |  | See Tab E for SB breakdown
92 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
93 |  |  | Gas System |  | 25 |  | 2010-06-01 | 2010-06-01 | 2010-07-06 | 2010-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 15 | [12 empty] | 48.75 |  |  | 325 | [10 empty] | 15% |  | See Tab E for SB breakdown
97 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
98 |  |  | Legs |  | 12 |  | 2011-06-01 | 2011-06-01 | 2011-06-17 19:12 | 2011-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 15 | [12 empty] | 37.5 |  |  | 250 | [10 empty] | 15% |  | See Tab E for SB breakdown
|  |  | Penetrations | [28 empty] | 900
|  |  | HVAC | [12 empty] | 15 | [5 empty] | 80
102 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  |  | Platform mods | [12 empty] | 75 | [5 empty] | 200 |  |  |  | 40 |  |  | 230 | 200 |  | 2300 | [10 empty] | 15%
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [13 empty] | 870 | 0 | 0 | 0 | 0 | 280 | 1640 | 0 | 0 | 0 | 480 | 0 | 0 | 2052.5 | 3908 | 0 | 15350 | 0 | 0 | 0 | 0 | 160 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 4059.4594 | [10 empty] | 1066.62 | 0 | 0 | 0 | 0 | 52.808 | 204.836 | 0 | 0 | 0 | 83.232 | 0 | 0 | 173.231 | 624.8892 | 0 | 1829.72 | 0 | 0 | 0 | 0 | 24.1232 | 0 | 0
Notes:
| (1) Procurement lead time: |  |  |  | Weeks | [12 empty] | CATEGORIZATION CODES:
| Purchase orders-Commercial, off-the-shelf items |  |  |  | 3 | [12 empty] | 1 - National Standards
| Purchase orders-Noncommercial items |  |  |  | 5 | [12 empty] | 2 - Engineering Judgement/Experience
| Subcontracts (non construction) |  |  |  | 8 | [12 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
| Construction subcontracts |  |  |  | 9 | [12 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and Uncertainty
Cost Center: |  | 9418
Job Number: |  | 2450
Job Title: |  | NSTX Beamline 2 Services
Job Manager: |  | Martin Denault
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Heat Load may be too high, remake He lines | [8 empty] | 50 | 50 | 10 | 55
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9418
Job Number: | 2450
Job Title: | NSTX Beamline 2 Services
Job Manager: | Martin Denault
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Pipe |  |  | Vendor Pricing
Parts |  |  | Vendor Pricing
MISC |  |  | Experience
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS