## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9418
Job Number: | 2475
Job Title: | NBI-Controls & Instrumentation
Job Manager: | Mark Cropper
REV 1 10/11/2010
Description:
This work covers the controls and instrumentation for the NB2. The work covers PLC, programming, control racks, new thermocouples, TC scanner, miscellaneous controls, and control cabling. The work also includes the gradient grid upgrade. System integration and testing will be performed
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9418
| Job Number: |  |  | 2475
| Job Title: |  |  | NBI-Controls & Instrumentation
| Job Manager: |  |  | Mark Cropper
Estimate (user input)
[5 empty] | SCHEDULE | [12 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | Subcontact labor | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Contingency | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [16 empty] | 1.226 | 1.226 | 1.23 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1 | bar: 2008-10-01 to 2008-11-01
1 |  | Control System Layout | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
2 |  | PLC |  |  | 15 |  |  |  | 2010-01-04 | 2010-01-04 | 2010-01-25 | 2010-01-04 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 120 | [15 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
3 |  | Remote LCC |  |  | 5 |  |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [15 empty] | 10% | cropper | NBL-1 Design
4 |  | TC Scanners- Beamline & P.P. |  |  | 10 |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 80 | [15 empty] | 10% | cropper | based on previous jobs
5 |  | NBOS Station |  |  | 5 |  |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [15 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
6 |  | Drawings - CWD's & Cable diagrams |  |  | 120 |  |  |  |  | 2007-10-01 | 2008-03-17 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 320 |  |  |  |  | 640 | [15 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
7 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
8 |  | Final Design | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
9 |  | Disposition PDR Chits |  |  | 2 |  |  |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
10 |  | Design Drawings |  |  | 20 | 11 |  |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 160 | [15 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
11 |  | FDR |  |  | 1 |  |  |  |  | #REF! | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 8 | [15 empty] | 10% | cropper | based on previous jobs
12 |  | Update Cost & Schedule Estimate |  |  | 5 |  |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [15 empty] | 10% | cropper | based on previous jobs
13 | [9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2008-10-01 to 2008-11-01
14 |  | Procurement | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2008-10-01 to 2008-11-01
15 |  | Item 1: | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [29 empty] | cropper | based on previous jobs
16 |  |  | Prep Requisition and procurement package |  | 5 |  |  |  | 2011-01-01 |  |  |  | #REF! | #REF! | #REF! | #REF! | [12 empty] | 40 | [7 empty] | cropper | based on previous jobs | [6 empty] | 10% | cropper | based on previous jobs
17 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 11 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 431 | [10 empty] | 8 | [7 empty] | cropper | based on previous jobs | [6 empty] | 10%
18 |  |  | Procurement lead time (1) |  | 15 | [7 empty] | 2007-10-01 | #REF! | #REF! | #REF!
19 |  |  | AWARD | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 |  |  | Fabricate or delivery |  | 40 | 17 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2007-10-01 | [28 empty] | 15%
21 | [9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A
22 |  | Fab/Assembly | [7 empty] | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | #N/A | 2007-10-01
23 |  | Fab/Assy Procedure |  |  | 5 |  |  |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | #REF! | 2007-10-01 | [28 empty] | 10% | cropper | based on previous jobs
24 |  | Shop Fabrication | [7 empty] | #REF! | #REF! | 2007-10-01 | #REF! | #REF! | #REF! | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
25 |  | Cable Tray |  |  | 40 |  |  |  | 2011-06-01 |  |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [5 empty] | 640 | [9 empty] | 15% |  | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
26 |  | Gradient Grid divider |  |  | 20 | 20 | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 |  | 640 | [13 empty] | 10% | cropper,rossi,gilton,lasky,halerson | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
27 |  | Control Rack Cage |  |  | 5 | 20 |  |  |  | #N/A | #N/A | 2011-01-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 8 | [5 empty] | 80 | [9 empty] | 10% | cropper | based on previous jobs
28 |  | Rack relocation |  |  | 25 | 11 |  |  | 2011-06-01 | #REF! | #REF! | 2007-10-01 | #REF! | #N/A | #N/A | #N/A | [12 empty] | 40 |  | 240 |  |  |  | 400 | [9 empty] | 10% | cropper | NBL-1 Design
29 |  | Penetrations |  |  | 5 | 11 |  |  | 2011-06-01 | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 |  |  |  | 40 | [8 empty] | 8 | [5 empty] | 80 | [9 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
30 |  | Disconnect remote control |  |  | 20 | 20 | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 8 | 24 | 104 |  |  |  | 68 | [9 empty] | 10% | Cropper,rossi,gilton,lasky,Halverson | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
31 | [9 empty] | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
32 |  | Installation | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2008-10-01 to 2008-11-01
33 |  | Installation Procedures |  |  | 10 | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 |  |  |  |  | 80 | [15 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
34 |  | Beam Line Cabling |  |  | 80 | 20 | 25 | 28 |  | 2007-10-01 | 2007-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  |  |  | 80 | [8 empty] | 320 |  | 1280 |  |  |  | 16 | [9 empty] | 10% | cropper | NBL-1 Design
35 |  | Aux Cabling |  |  | 20 | 34 | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 80 |  | 700 | [13 empty] | 10% | cropper | NBL-1 Design
36 |  | Protective Plate Interlocks - (I/P & Pyrometer/IR Camara) |  |  | 20 | 11 | 20 | 28 |  | #N/A | #N/A | 2011-06-01 | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | [12 empty] | 40 |  | 320 | [13 empty] | 20% | Cropper | NBL-1 Design
37 |  | TC Scanners - beamline & Protective Plates |  |  | 40 | 11 | 20 | 28 |  | #REF! | #REF! | 2007-10-01 | #REF! | #REF! | #REF! | #REF! | [12 empty] | 40 |  | 400 | [13 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
38 |  | NBOS Station |  |  | 10 | 11 | 20 |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 80 |  | 160 | [13 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
39 |  | LCC Remote |  |  | 40 | 11 | 20 |  |  | #REF! | #REF! | 2011-06-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | 640 | 640 | [13 empty] | 10% | cropper,rossi | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
40 |  | Power Supply Upgrade |  |  | 23 | 11 | 20 |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | 160 | 368 | [13 empty] | 10% | cropper,rossi | NBL-1 Design
41 |  | Protective Plate TC's |  |  | 10 | 11 | 20 | 28 |  |  |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 |  | 80 | [13 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
42 | [9 empty] | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
43 | [9 empty] | #REF! | #REF! | 2007-10-01 | #REF! |  | #REF! | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
44 |  | PLC & RSView Programing |  |  | 40 | 11 | 20 |  |  | #REF! | #REF! | 2011-06-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 320 | [15 empty] | 10% | cropper | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
45 |  | Beamline TC Scanner Programing |  |  | 20 | 11 | 20 |  |  | #N/A | #N/A | 2007-10-01 | 2007-10-08 | #N/A | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | 160 | [14 empty] | 10% | cropper,rossi | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
46 |  | Protective Plate TC Scanner Programing |  |  | 20 | 11 | 20 |  |  | #REF! | #REF! | 2007-10-01 | #REF! | #REF! | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | 160 | [14 empty] | 10% | cropper,rossi | NBL-1 Design
47 |  | LCC Remote LabView Programing |  |  | 40 | 11 | 20 |  |  | #REF! | #REF! |  | #REF! | #REF! | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | 320 | [14 empty] | 10% | cropper,rossi | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
48 | [9 empty] | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
49 |  | Control System PTP Testing |  |  | 20 | 47 |  |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 160 | 160 | 160 | [13 empty] | 25% | cropper,rossi,lasky | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
50 | [9 empty] | 2007-10-01 | 2007-10-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
51 | [12 empty] | #REF! | #REF! | #REF! | 2007-10-01
52 | [9 empty] | #REF! | #REF! |  | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
53 | [9 empty] | #REF! | #REF! | 2007-10-01 | #REF! | #REF! | #REF! | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
54 |  | Commissioning & testing of 4A power system |  |  | 20 | 49 |  |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 320 | 160 | 480 | [13 empty] | 25% | Cropper,rossi,gilton,lasky,Halverson,edwards | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
55 |  | Commissioning & testing of 4B power system |  |  | 20 | 54 |  |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 320 | 160 | 480 | [13 empty] | 25% | Cropper,rossi,gilton,lasky,Halverson,edwards | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
56 |  | Commissioning & testing of 4C power system |  |  | 20 | 55 |  |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 320 | 160 | 480 | [13 empty] | 25% | Cropper,rossi,gilton,lasky,Halverson,edwards | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
57 |  | 40 KV beam Operation |  |  | 20 | 56 |  |  |  | #REF! | #REF! | 2007-10-01 | #REF! | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 160 | 160 | 480 | [13 empty] | 25% | Cropper,rossi,gilton,lasky,Halverson | NBL-1 Design | bar: 2008-10-01 to 2008-11-01
[12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2008-11-01
|  | TOTALS | [15 empty] | 431 | 0 | 120 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 3720 | 2264 | 7012 | 0 | 0 | 0 | 1284 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 2264.86 | [12 empty] | 528.406 | 0 | 147.6 | 0 | 0 | 0 | 49.96 | 0 | 0 | 0 | 0 | 561.72 | 269.416 | 591.8128 | 0 | 0 | 0 | 115.9452 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [19 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  | Weeks | [15 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  |  | 3 | [15 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  |  | 5 | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  |  | 8 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  |  | 9 | [15 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9418
Job Number: |  | 2475
Job Title: |  | NBI-Controls & Instrumentation
Job Manager: |  | Mark Cropper
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9418
Job Number: | 2475
Job Title: | NBI-Controls & Instrumentation
Job Manager: | Mark Cropper
Materials and Subcontracts (M&S) |  |  |  | Basis of Estimate
Description:
NBOS Stations - 138' & Test cell |  | 14380 |  | catalog prices (see Tab E for breakdown)
PLC equipment |  | 96000 |  | catalog prices (see Tab E for breakdown)
LCC remote NI equipment |  | 56000 |  | catalog prices (see Tab E for breakdown)
Thermocouple Scanner Protive Plate |  | 17000 |  | catalog prices (see Tab E for breakdown)
Thermocouple Scanners Beamline (one per beamline) |  | 34000 |  | catalog prices (see Tab E for breakdown)
Vacuum system equipment |  | 23840 |  | catalog prices (see Tab E for breakdown)
Power supply control upgrade |  | 51040 |  | catalog prices (see Tab E for breakdown)
cryo System |  | 8000 |  | catalog prices (see Tab E for breakdown)
Water System equipment |  | 5000 |  | catalog prices (see Tab E for breakdown)
cable |  | 60000 |  | based on previous jobs
Cable Tray ? |  | 2000 |  | based on previous jobs
Cage & Kirk Locks |  | 5000 |  | based on previous jobs
fiber optic cable |  | 2000 |  | catalog price 1000' @ $2.00/ft
Thermocouples for Duct & Protective Plates |  | 2500 |  | catalog price 1000' @ $2.50/ft
Protective Plate Interlocks |  | 10000 |  | based on previous jobs
miss |  | 5000 |  | based on previous jobs
Pyrometers - 3 |  | 30000 |  | catalog prices (see Tab E for breakdown)
Disconnect remote control |  | 10000 |  | catalog prices (see Tab E for breakdown)
| Total | 431760
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS

## Tab E M&S Backup
Detailed M&S Estimates
Cost Center: | 9418
Job Number: | 2475
Job Title: | NBI-Controls & Instrumentation
Job Manager: | Mark Cropper
TFT5EA00003 | 5 Pair Feed Through | 401.75 | 10 | 4017.5
626B11TCE | 10 Torr Baratron | 952 | 6 | 5712
626B13TCE | 1000 Torr Baratron | 952 | 6 | 5712
RGA 100 | Residual Gas Analyzer | 4000 | 2 | 8000
PX219-200G10V | Pressure Transmitter 0-200 psi | 195 | 2 | 390
| Vacuum hardware | Total |  | 23831.5
RSView Station 138' Level
| Dell T3400 Computer & 2 Monitors | 2200 | 1 | 2200
| 1784-PKTX Data Hiway Card | 1835 | 1 | 1835
|  | 0 | 1 | 0
|  |  | Total | 4035
RGA Station 138' Level
| Dell T3400 Computer & 2 Monitors | 2200 | 1 | 2200
| Four Port Serial Card | 102.99 | 1 | 102.99
|  |  | Total | 2302.99
Calorimeter Monitor Station
| Dell T3400 Computer & Monitor | 2000 | 1 | 2000
|  |  | Total | 2200
RSView/RGA Station Test Cell
| Dell T3400 Computer | 1800 | 1 | 1800
| Four Port Serial Card | 102.99 | 1 | 102.99
| 1784-PKTX Data Hiway Card | 1835 | 1 | 1835
| RS-232 Data Switch | 30 | 2 | 60
3797.99
Calorimeter Camera
| Axis 214PTZ network camera | 1300 | 1 | 1300
|  |  | Total | 1300
Network
| 8 Port Gigabit Switch | 120 | 2 | 240
| Cables | 500 | 1 | 500
740
| NBOS Control Stations |  | Total | 14375.98
| Description | cost ea. | # required | Total
| Description | cost ea. | # required | Total
Racks
1771-A3B | 12 Slot Rack- 19" rack mount | 958 | 3 | 2874
1771-ASB | Remote I/O Com | 1813 | 3 | 5439
1771-AF1 | Fiber optic module | 2182 | 2 | 4364
|  |  | Total | 12677
I/O Modules
1771-IBD | 24 VDC Input Module- 16 | 568 | 13 | 7384
1771-OBD | 24 VDC Output Module- 16 | 812 | 3 | 2436
1771-IGD | TTL Input Module | 668 | 2 | 1336
1771-OW | Contact Output | 1375 | 5 | 6875
1771-IFE | Analog Input | 2469 | 5 | 12345
1771-OFE2 | Analog Output | 2399 | 2 | 4798
1771-NT1 | Thermocouple Input | 4217 | 5 | 21085
1771-OAD | AC Output - 16 | 904 | 10 | 9040
|  |  | Total | 65299
Cables
1492-ACABLE025E | IFE Cable | 199 | 11 | 2189
1492-ACABLE025G | OFE Cable | 157 | 4 | 628
1492-ACABLE025J | IR Cable | 234 | 2 | 468
1492-CABLE025F | 16 point I/O cable | 128 | 40 | 5120
1492-CABLE025T | 8 point I/O cable | 128 | 10 | 1280
|  | 0 | 0 | 0
|  |  | Total | 9685
Terminal Strips
1492-AIFM8-3 | IFE Terminal strip | 130 | 11 | 1430
1492-AIFM4-3 | OFE Terminal strip | 104 | 4 | 416
1492-AIFM6S-3 | IR Terminal strip | 116 | 2 | 232
1492-AIF20F-2 | 16 point I/O Terminal strip | 123 | 50 | 6150
|  | 0 | 0 | 0
|  |  | Total | 8228
|  | Total |  | 95889
Chassis
779218-01 | 14 Slot Chassis with power supply | 3599 | 1 | 3599
763000-01 | Power Cord | 9 | 1 | 9
778644-01 | Rack Mount Kit | 159 | 1 | 159
|  |  | Total | 3767
Processor
780343-33 | PXI-8183 850MHZ Processor | 1999 | 1 | 1999
778469-512 | 512 MB Ram upgrade | 199 | 1 | 199
2198
I/O
779547-01 | PIX-6255 80 channel Analog Input | 2299 | 1 | 2299
779632-01 | PIX-6259 32 Channel Analog Input | 1599 | 1 | 1599
778998-01 | PIX 6723 32 Channel Analog Output | 1400 | 1 | 1400
192061-02 | SHC68-68-EPM Shielded Cable | 129 | 3 | 387
191945-02 | SCH68-68 Twisted Pair Cable | 89 | 3 | 267
777141-01 | TBX-68 Connector Block | 159 | 6 | 954
778967-01 | PIX-6511 64 Channel Digital Input | 459 | 3 | 1377
778543-01 | PIX-6528 48 Channel Digital Input/Output | 677 | 3 | 2031
777812-01 | CB-100 Kit (connecter block & cable) | 259 | 3 | 777
182762-02 | 2 meter cable | 86 | 3 | 258
776164-90 | CB-50 I/O Connector block | 115 | 3 | 345
11694
|  | Total per source |  | 17659
|  | Total for three systems |  | 52977
Network
RSV4000 | Linksys Router | 120.99 | 1 | 120.99
SLM2008 | Linksys 8 port Switch | 119.99 | 1 | 119.99
| Cable & connectors | 500 | 1 | 500
740.98
Display Computer
| Dell T3400 with dual 20" monitors | 2200 | 1 | 2200
2200
| LCC Remote equipment | Grand Total |  | 55917.98
Chassis
778636-01 | 8 Slot Chassis with power supply | 2099 | 1 | 2099
763000-01 | Power Cord | 9 | 1 | 9
778643-01 | Rack Mount Kit | 159 | 1 | 159
|  |  | Total | 2267
Processor
780343-33 | PXI-8183 850MHZ Processor | 1999 | 1 | 1999
778469-512 | 512 MB Ram upgrade | 199 | 1 | 199
2198
I/O
779296-01 | PIX-6225 80 channel Analog Input | 1399 | 5 | 6995
192061-02 | SHC68-68-EPM Shielded Cable | 129 | 5 | 645
191945-02 | SCH68-68 Twisted Pair Cable | 89 | 5 | 445
779313-01 | PIX-6521 8 Channel Relay Output | 529 | 1 | 529
778621-02 | SH37F-37M | 29 | 1 | 29
779491-01 | CB-37F-HVD | 169 | 1 | 169
| Connecters & cable | 1000 | 1 | 1000
9812
| Thermocouple Scanner | Total ea. |  | 14277
Upgrade Parts
| Gradient Grid parts | 14000 | 3 | 42000
| HVST Filament Control Parts | 350 | 4 | 1400
| Decel Control Grid Parts | 350 | 4 | 1400
| Crowbar Parts | 60 | 24 | 1440
| Vac Ion Pump Power Supply | 1200 | 4 | 4800
| Power Supplies |  | Total | 51040
211S | Temperature Monitor | 647 | 1 | 647
2308-12 | VME rack & power supply | 1176 | 1 | 1176
231 | Temperature transmitter | 583 | 7 | 4081
2308-BP | blank panel | 21 | 5 | 105
DT-470-CU-13 | Diode sensor | 254 | 7 | 1778
| Cryo Hardware |  | Total | 7787
M41E1 | 4 Way Solenoid Valve | 150 | 12 | 1800
MM6 | Solenoid Manifold - 6 Station | 60 | 2 | 120
51025K374 | 1/4" tube to 1/8" MPT fitting | 2.79 | 60 | 167.4
6763K11 | Regulator | 35.47 | 2 | 70.94
3844K1 | Gauge | 10.7 | 2 | 21.4
4264k21 | 1/2" ball valve | 7.66 | 2 | 15.32
5078K65 | hex bushing | 2.88 | 4 | 11.52
9151K56 | 1/8" MPT tube | 2.2 | 4 | 8.8
| 1/4" tubing | 0.2 | 1000 | 200
| pneumatic Actuators | 500 | 4 | 2000
| Water System |  | Total | 4415.38
MI18 | Pyrometer with lens & 30 m fiber | 10000 | 3 | 30000
| Pyrometer | Total. |  | 30000
Motorize Disconnect Control Parts List
Main Control Box
Item No. | Qty | Designator | Description | Manufacturer | Vender | Part Number | Cost Ea. | Total
1 | 1 | Main Box | Non-metallic JIC series 14 x 12 x 6 inch (HxWxD) NEMA 4X enclosure | Hubbell | Automation Direct | HW-J141206SC | 68 | 68
2 | 1 | Main Box | Sub Panel | Hubbell | Automation Direct | HW-MP1412A | 12.25 | 12.25
3 | 1 | Motor Starter Protector | Manual starter protector with thermal overload release, setting range from 2.5 to 4 amps |  | Automation Direct | MS25-400 | 35 | 35
4 | 4 | K1 - K4 | Cube relay, 120 VAC coil voltage, 4PDT, 15A contact rating, with LED indicator and push-to-test button |  | Automation Direct | 784-4C-120A | 7.5 | 30
5 | 4 | K1 - K4 Sockets | DIN-rail socket for 784 series cube relays |  | Automation Direct | 784-4C-SKT-1 | 4.75 | 19
6 | 2 | TB-1 , TB2 | Direct mount terminal strip, 12 pole, 150V, 15A/20A, 18-14 AWG, nylon, with wire protector. | WECO | Automation Direct | BMM093CS | 54 | 54
7 | 1 | J1 Flange | CONN RCPT MALE 28POS WALL MT | Souriau | Digikey | SOU1115-ND | 10.47 | 10.47
8 | 1 | J1 Plug | CONN PLUG CABLE FEMALE 28POS | Souriau | Digikey | SOU1091-ND | 15.12 | 15.12
9 | 1 | J2 Flange | CONN RCPT FEMALE 28POS WALL MT | Souriau | Digikey | SOU1114-ND | 10.47 | 10.47
10 | 1 | J2 Plug | CONN PLUG CABLE MALE 28POS | Souriau | Digikey | SOU1092-ND | 15.12 | 15.12
11 | 2 | J1, J2 Strain Reliefs | CABLECLAMP W/STR RELIEF IP65 #20 | Souriau | Digikey | SOU1136-ND | 10.47 | 20.94
12 | 2 | J3, J4 Flange | CONN RCPT FEMALE 12POS WALL MT | Souriau | Digikey | SOU1108-ND | 6.73 | 13.46
13 | 2 | J3, J4 Plug | CONN PLUG CABLE MALE 12POS | Souriau | Digikey | SOU1087-ND | 11.55 | 23.1
14 | 2 | J3, J4 Strain Reliefs | CABLECLAMP W/STR RELIEF IP65 #14 | Souriau | Digikey | SOU1133-ND
15 | 100 | J1, J2 Pins | CONN PIN 16-18AWG CRIMP GOLD | Souriau | Digikey | SOU1252-ND | 0.76 | 76
16 | 100 | J1, J2 Sockets | CONN SOCKET 16-18AWG CRIMP GOLD | Souriau | Digikey | SOU1248-ND | 0.93 | 93
17 | 1 | CB1 | CIRCUIT BREAKER THERM 5A ILLUM | Tyco | Digikey | PB528-ND | 3.43 | 3.43
18 | 2 | S1,S2 | SWITCH TOGGLE DPST 20A .250" QC | E-Switch | Digikey | EG4820-ND | 4.06 | 8.12
19 | 2 | CNT-V & CNT-F | Resettable AC Counters |  | McMaster Carr | 8686T27 | 44.42 | 44.42
20 | 2 | C1,C2 | Capacitor Clamp | Mallory | Mouser | 539-VR6A | 2.92 | 5.84
Push Button Switch Box
Item No. | Qty | Designator | Description | Manufacturer | Vender | Part Number | Cost Ea. | Total
1 | 1 | Outer Weather Box | Fiberglass Encl. (NEMA 6P/12)Padlockable Latch, 9.6" H X 7.5" W X 4.8" D |  | McMaster Carr | 7740K13 | 69.33 | 69.33
2 | 1 | Outer Weather Box Panel | Aluminum Mounting Panel |  | McMaster Carr | 6917K13 | 8.35 | 8.35
3 | 1 | Push Button switch Box | Four-hole plastic enclosure for 22mm devices |  | Automation Direct | SA110-40SL | 13.5 | 13.5
4 | 2 | S1 open, S2 open | PB, 22mm, PLASTIC, GRN, LED ILLUM, 120V, FLUSH, 1 N.O. |  | Automation Direct | GCX3202-120L | 16.75 | 33.5
5 | 2 | S1 Closed, S2 Closed | PB, 22mm, PLASTIC, RED, LED ILLUM, 120V, FLUSH, 1 N.C. |  | Automation Direct | GCX3201-120L | 14.75 | 29.5
6 | 1 | S1 Closed, S2 Closed | CONTACT BLOCK, 22mm, 2/PK, N.O. |  | Automation Direct | ECX1040-2 | 6.25
7 | 4 | S1,S2 Open/Close Failed | INDICATOR 110V 8MM PROMINENT RED |  | Digikey | 679-1495-ND | 9.89 | 39.56
8 | 1 | Wire Feedthru | Thick-Wall Dark Gray PVC Threaded Pipe Nipple 3/4" Pipe X 2" Length, Threaded Ends |  | McMaster Carr | 4882K29 | 0.84 | 0.84
Motor Assy
Item No. | Qty | Designator | Description | Manufacturer | Vender | Part Number | Cost Ea. | Total
1 | 2 | M1, M2 | FLEXTORQ 762 SERIES 1 PHASE 115/230V | Bison |  | 016-762-0267 | 574 | 1148
2 | 2 | M1, M2 Shaft | SINGLE SHAFT | Bison |  | P108-762-1250 | 30.95 | 61.9
3 | 2 | M1,M2 coupling Hub | Flexible Spider Shaft Coupling Hub 3/4" Bore, 3-21/64" OD, with Keyway |  | McMaster Carr | 6408K183 | 25.19 | 50.38
4 | 2 | M1,M2 coupling Hub | Flexible Spider Shaft Coupling Hub 1-1/4" Bore, 3-21/64" OD, with Keyway |  | McMaster Carr | 6408K291 | 25.19 | 50.38
5 | 2 | M1,M2 coupling Hub | Hytrel Spider for 3-21/64" Outside Diameter Flexible Spider Shaft Coupling Hub |  | McMaster Carr | 6408K97 | 41.44 | 82.88
6 | 4 | M1,M2 Open/Closed limit switch | LSMTL1 WAYNPT SS PLNGR+ROLL | IEC | Automation Direct | ABM2E13Z11 | 40 | 160
7 | 2 | Cord Grip | Liquid-Tight Straight Cord Grip Aluminum, 1/2" NPT Trade Size, .50"-.63" Cord Dia |  | McMaster Carr | 8302K151 | 11.15 | 22.3
8 | 4 | Liquid Tight Fittings | Liquid-Tight Metal Conduit Fitting 90 Deg Elbow, Die Cast Zinc, 3/8" Trade Size |  | McMaster Carr | 7119K81 | 4.08 | 16.32
9 | 4 ft | Liquid Tight Flexible Conduit | Liquid-Tight Flexible Steel Conduit 3/8" Trade Size, 0.49" ID, 0.7" OD |  | McMaster Carr | 7127K66 | 1.99/ft | 7.96
Cable/Wire
Item No. | Qty | Designator | Description | Manufacturer | Vender | Part Number | Cost Ea. | Total
1 | 7 ft | Cable 692A | Oil Resistant Continuous-Flex Cable Unshielded, 16/4 Awg, .30" OD, 300 VAC, Gray |  | McMaster Carr | 8082K65 | 2.39/ft | 16.73
2 | 10 ft | Cable 692B | Oil Resistant Continuous-Flex Cable Unshielded, 16/7 Awg, .39" OD, 300 VAC, Gray |  | McMaster Carr | 8082K66 | 3.70/ft | 37
3 | 8 ft | Cable 692C | Heavy Duty Continuous-Flex Cable Unshielded, 16/18 Awg, .56" OD, 300 VAC, Gray |  | McMaster Carr | 9221K59 | 24.33/ft | 194.64
4 | 40 ft | Cable 692D,E,F | Oil Resistant Continuous-Flex Cable Unshielded, 16/12 Awg, .55" OD, 300 VAC, Gray |  | McMaster Carr | 8082K67 | 5.57/ft | 222.8
5 | 200 ft | 16 AWG wire | Stranded Single-Conductor Wire UL 1015, 16 Awg, 600 VAC, Gray |  | McMaster Carr | 7587K029 | 22.93/100ft | 45.86
Metal Supplies
Item No. | Qty | Designator | Description | Manufacturer | Vender | Part Number | Cost Ea. | Total
1 | 20 ft | Unistrut | Steel Strut Channel Slotted, 1-5/8" X 1-5/8", Galvanized, 10' Length |  | McMaster Carr | 3310T661 | 54.48/10ft | 108.96
2 | 8 ft | Angle | 2 1/2 X 2 1/2 X 1/4 Aluminum Angle |  |  | 8982K33 | 48.93 | 48.93
3 | 16 Ft | Angle | 2 X 3 X 1/4 Aluminum Angle |  |  | 8982K572 | 46.00/8ft | 92
4 | 1 | Aluminum Sheet | 24 X 24 X 1/4 Aluminum Sheet |  |  | 89155K26 |  | 138.09
5 | 1 | Aluminum Sheet | 3/8 X 12 X 12 Aluminum Sheet |  |  | 89155K34‡ |  | 48.89
6 | 1 | Aluminum Bar | 3/4 X 3/4 X 12" |  |  | 86895K13 |  | 15.39
[5 empty] | TOTAL COST 1 SWITCHGEAR W/ TWO MOTOR ASSY. |  |  | 3321.73