## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 5501
Job Title: | Coil Bus Runs
Job Manager: | Mark Smith
Description:
This job includes design and fabrication of bus runs/supports between the NSTX coils and the FCPC cable terminations located in the NSTX test cell west side. Includes new air-cooled TF bus; relocation of OH cable bus from top to bottom of machine; new CHI ring bus and bus links to lower VV and new bus for the inner PF coils.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head
Busbar System Includes: TF air-cooled [From TC water fall to bottom of machine] OH Coax [Inside umbrella] Inner PF coils [U/L PF1a, 1b and 1c] CHI/bakeout [Lower ring bus & ring to VV bus NOTE: Installation costs are included.

## Tab B Cost & Schedule Est
| Cost Center: |  |  | 9417
| Job Number: |  |  | 5501
| Job Title: |  |  | Coil Bus Runs
| Job Manager: |  |  | Mark Smith
Estimate (user input)
[5 empty] | SCHEDULE | [32 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [6 empty] | ` | [5 empty] | % |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT | [15 empty] | Calculated Starts | [16 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79
task | TASK DESCRIPTION |  |  | Responsible | Total | 0-30% | 30-50% | 50-70% | 70-80% | 80-90% | 90-100% | Start Date |  |  | 30% | 50% | 70% | 80% | 90% | User Input Start Date (optional) | START DATE | 30% | 50% | 70% | 80% | 90% | FINISH DATE |  |  |  |  | 0.3 | 0.5 | 0.7 | 0.8 | 0.9 | actual= A | M&S (41) | CREDIT CARD (43) | Stk Room | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) MEIGHAN | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | RESA Machinist |  |  | CONTINGENCY % | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
# | P3 cross ref (optional) | [36 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 95.31 | 1 | 1
1 |  | Physics Requirements | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
2 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
3 |  | PREPARE WORK PLANNING FORM | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
4 |  | Cost & Schedule Estimate | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
5 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
6 |  | Preliminary Design |  | M. Smith | 38 | 11.4 | 7.6 | 7.6 | 3.8 | 3.8 | 3.8 | [8 empty] | 2010-05-01 | 2010-05-01 | 2010-05-16 23:02 | 2010-05-27 14:24 | 2010-06-07 05:46 | 2010-06-12 13:26 | 2010-06-17 21:07 | 2010-06-23 04:48 | 2010-05-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 38 | [6 empty] | 10% | 2, 4, ,9
7 |  | FMEA |  | M. Smith | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | [8 empty] | 2010-06-01 | 2010-06-01 | 2010-06-03 02:24 | 2010-06-04 12:00 | 2010-06-05 21:36 | 2010-06-06 14:24 | 2010-06-07 07:12 | 2010-06-08 | 2010-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [6 empty] | 10% | 2, 4, 9
8 |  | OH Coaxial Bus |  | M. Smith | 13 | 3.9 | 2.6 | 2.6 | 1.3 | 1.3 | 1.3 | [8 empty] | 2010-05-01 | 2010-05-01 | 2010-05-06 11:02 | 2010-05-10 02:24 | 2010-05-13 17:46 | 2010-05-15 13:26 | 2010-05-17 09:07 | 2010-05-30 02:24 | 2010-05-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
9 |  |  | Eng Design: electrical, thermal, EM & stress | M.Smith & EE | 4 | 1.2 | 0.8 | 0.8 | 0.4 | 0.4 | 0.4 | [8 empty] | 2010-05-21 | 2010-05-21 | 2010-05-22 16:19 | 2010-05-23 19:12 | 2010-05-24 22:05 | 2010-05-25 11:31 | 2010-05-26 00:58 | 2010-05-26 14:24 | 2010-05-21 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 8 |  |  |  | 32 | [6 empty] | 20% | 2, 4, 9
10 |  |  | CAD: Coaxial bus design, bus routing, supports | G. Paluzzi | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | [7 empty] | 9 | 2010-05-01 | 2010-05-01 | 2010-05-03 02:24 | 2010-05-04 12:00 | 2010-05-05 21:36 | 2010-05-06 14:24 | 2010-05-26 14:24 | 2010-05-27 07:12 | 2010-05-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2010-05-26 14:24 | [7 empty] | 40 |  |  |  |  | 2 | [6 empty] | 20% | 2, 4, 9, 11
11 |  |  | Analysis Mech: thermal, EM & stress | EAEM | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 10 | [8 empty] | 2010-05-27 07:12 | 2010-05-28 03:22 | 2010-05-28 16:48 | 2010-05-29 06:14 | 2010-05-29 12:58 | 2010-05-29 19:41 | 2010-05-30 02:24 | 2007-10-01 | 2010-05-27 07:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 12 | [12 empty] | 20% | 2, 4, 9
12 |  |  | Analysis Elec: electrical | EE | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 10 | [8 empty] | 2010-05-27 07:12 | 2010-05-28 03:22 | 2010-05-28 16:48 | 2010-05-29 06:14 | 2010-05-29 12:58 | 2010-05-29 19:41 | 2010-05-30 02:24 | 2007-10-01 | 2010-05-27 07:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 4 | [10 empty] | 20% | 2, 4, 9
13 |  | PF Bus |  | M. Smith | 13 | 3.9 | 2.6 | 2.6 | 1.3 | 1.3 | 1.3 | [8 empty] | 2010-05-07 07:12 | 2010-05-07 07:12 | 2010-05-12 18:14 | 2010-05-16 09:36 | 2010-05-20 00:58 | 2010-05-21 20:38 | 2010-05-23 16:19 | 2010-06-04 16:48 | 2010-05-07 07:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
14 |  |  | Eng Design: electrical, thermal, EM & stress | M.Smith & EE | 4 | 1.2 | 0.8 | 0.8 | 0.4 | 0.4 | 0.4 | 9 | [8 empty] | 2010-05-26 14:24 | 2010-05-28 06:43 | 2010-05-29 09:36 | 2010-05-30 12:29 | 2010-05-31 01:55 | 2010-05-31 15:22 | 2010-06-01 04:48 | 2007-10-01 | 2010-05-26 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 8 |  |  |  | 32 | [6 empty] | 20% | 2, 4, 9
15 |  |  | CAD: bus routing, supports | G. Paluzzi | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | [7 empty] | 14 | 2010-05-07 07:12 | 2010-05-07 07:12 | 2010-05-09 09:36 | 2010-05-10 19:12 | 2010-05-12 04:48 | 2010-05-12 21:36 | 2010-06-01 04:48 | 2010-06-01 21:36 | 2010-05-07 07:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2010-06-01 04:48 | [7 empty] | 40 |  |  |  |  | 2 | [6 empty] | 20% | 2, 4, 9, 11
16 |  |  | Analysis Mech: thermal, EM & stress | EAEM | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 11 | 15 | [7 empty] | 2010-06-01 21:36 | 2010-06-02 17:46 | 2010-06-03 07:12 | 2010-06-03 20:38 | 2010-06-04 03:22 | 2010-06-04 10:05 | 2010-06-04 16:48 | 2007-10-01 | 2010-05-30 02:24 | 2010-06-01 21:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 12 | [12 empty] | 20% | 2, 4, 9
17 |  |  | Analysis Elec: electrical | EE | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 12 | 15 | [7 empty] | 2010-06-01 21:36 | 2010-06-02 17:46 | 2010-06-03 07:12 | 2010-06-03 20:38 | 2010-06-04 03:22 | 2010-06-04 10:05 | 2010-06-04 16:48 | 2007-10-01 | 2010-05-30 02:24 | 2010-06-01 21:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 4 | [10 empty] | 20% | 2, 4, 9
18 |  | TF Bus |  | M. Smith | 18 | 5.4 | 3.6 | 3.6 | 1.8 | 1.8 | 1.8 | [8 empty] | 2010-05-13 14:24 | 2010-05-13 14:24 | 2010-05-21 03:50 | 2010-05-26 04:48 | 2010-05-31 05:46 | 2010-06-02 18:14 | 2010-06-05 06:43 | 2010-06-11 | 2010-05-13 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
19 |  |  | Eng Design: electrical, thermal, EM & stress | M.Smith & EE | 4 | 1.2 | 0.8 | 0.8 | 0.4 | 0.4 | 0.4 | 14 | [8 empty] | 2010-06-01 04:48 | 2010-06-02 21:07 | 2010-06-04 | 2010-06-05 02:53 | 2010-06-05 16:19 | 2010-06-06 05:46 | 2010-06-06 19:12 | 2007-10-01 | 2010-06-01 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 8 |  |  |  | 32 | [6 empty] | 20% | 2, 4, 9
20 |  |  | CAD: bus routing, supports | G. Paluzzi | 10 | 3 | 2 | 2 | 1 | 1 | 1 | [7 empty] | 19 | 2010-05-13 14:24 | 2010-05-13 14:24 | 2010-05-17 19:12 | 2010-05-20 14:24 | 2010-05-23 09:36 | 2010-05-24 19:12 | 2010-06-06 19:12 | 2010-06-08 04:48 | 2010-05-13 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2010-06-06 19:12 | [7 empty] | 80 |  |  |  |  | 4 | [6 empty] | 20% | 2, 4, 9, 11
21 |  |  | Analysis Mech: thermal, EM & stress | EAEM | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 16 | 20 | [7 empty] | 2010-06-08 04:48 | 2010-06-09 00:58 | 2010-06-09 14:24 | 2010-06-10 03:50 | 2010-06-10 10:34 | 2010-06-10 17:17 | 2010-06-11 | 2007-10-01 | 2010-06-04 16:48 | 2010-06-08 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 12 | [12 empty] | 20% | 2, 4, 9
22 |  |  | Analysis Elec: electrical | EE | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 17 | 20 | [7 empty] | 2010-06-08 04:48 | 2010-06-09 00:58 | 2010-06-09 14:24 | 2010-06-10 03:50 | 2010-06-10 10:34 | 2010-06-10 17:17 | 2010-06-11 | 2007-10-01 | 2010-06-04 16:48 | 2010-06-08 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 4 | [10 empty] | 20% | 2, 4, 9
23 |  | CHI Bus |  | M. Smith | 28 | 8.4 | 5.6 | 5.6 | 2.8 | 2.8 | 2.8 | [8 empty] | 2010-05-26 04:48 | 2010-05-26 04:48 | 2010-06-06 23:02 | 2010-06-14 19:12 | 2010-06-22 15:22 | 2010-06-26 13:26 | 2010-06-30 11:31 | 2010-06-26 | 2010-05-26 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
24 |  |  | Eng Design: electrical, thermal, EM & stress | M.Smith & EE | 4 | 1.2 | 0.8 | 0.8 | 0.4 | 0.4 | 0.4 | 19 | [8 empty] | 2010-06-06 19:12 | 2010-06-08 11:31 | 2010-06-09 14:24 | 2010-06-10 17:17 | 2010-06-11 06:43 | 2010-06-11 20:10 | 2010-06-12 09:36 | 2007-10-01 | 2010-06-06 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 8 |  |  |  | 32 | [6 empty] | 20% | 2, 4, 9
25 |  |  | CAD: ring bus design, bus routing, supports | G. Paluzzi | 20 | 6 | 4 | 4 | 2 | 2 | 2 | [7 empty] | 24 | 2010-05-26 04:48 | 2010-05-26 04:48 | 2010-06-03 14:24 | 2010-06-09 04:48 | 2010-06-14 19:12 | 2010-06-17 14:24 | 2010-06-20 09:36 | 2010-06-23 04:48 | 2010-05-26 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2010-06-12 09:36 | [7 empty] | 160 |  |  |  |  | 2 | [6 empty] | 20% | 2, 4, 9, 11
26 |  |  | Analysis Mech: thermal, EM & stress | EAEM | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 21 | 25 | [7 empty] | 2010-06-23 04:48 | 2010-06-24 00:58 | 2010-06-24 14:24 | 2010-06-25 03:50 | 2010-06-25 10:34 | 2010-06-25 17:17 | 2010-06-26 | 2007-10-01 | 2010-06-11 | 2010-06-23 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 12 | [12 empty] | 20% | 2, 4, 9
27 |  |  | Analysis Elec: electrical | EE | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 22 | 25 | [7 empty] | 2010-06-23 04:48 | 2010-06-24 00:58 | 2010-06-24 14:24 | 2010-06-25 03:50 | 2010-06-25 10:34 | 2010-06-25 17:17 | 2010-06-26 | 2007-10-01 | 2010-06-11 | 2010-06-23 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 4 | [10 empty] | 20% | 2, 4, 9
28 |  | Update Cost & Schedule Estimate |  | M. Smith | 3 | 0.9 | 0.6 | 0.6 | 0.3 | 0.3 | 0.3 | [8 empty] | 2010-06-11 | 2010-06-11 | 2010-06-12 06:14 | 2010-06-13 02:24 | 2010-06-13 22:34 | 2010-06-14 08:38 | 2010-06-14 18:43 | 2010-06-15 04:48 | 2010-06-11 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [6 empty] | 10% | 2, 4
29 |  | PDR Prep & PDR |  | M. Smith | 6 | 1.8 | 1.2 | 1.2 | 0.6 | 0.6 | 0.6 | 28 |  |  | 8 | 13 | 18 | 24 |  |  | 2010-06-15 04:48 | 2010-06-17 17:17 | 2010-06-19 09:36 | 2010-06-21 01:55 | 2010-06-21 22:05 | 2010-06-22 18:14 | 2010-06-23 14:24 | 2007-10-01 | 2010-06-15 04:48 | 2007-10-01 | 2007-10-01 | 2010-05-30 02:24 | 2010-06-04 16:48 | 2010-06-11 | 2010-06-12 09:36 | 2007-10-01 | [12 empty] | 48 | [6 empty] | 10% | 2, 4
30 |  | Disposition of PDR CHITS |  |  | 30 | 9 | 6 | 6 | 3 | 3 | 3 | 29 | [8 empty] | 2010-06-23 14:24 | 2010-07-06 04:48 | 2010-07-14 14:24 | 2010-07-23 | 2010-07-27 04:48 | 2010-07-31 09:36 | 2010-08-04 14:24 | 2007-10-01 | 2010-06-23 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | [6 empty] | 25% | 2, 4, 9
31 |  | Eng Design & CAD Model Updates: Design Optimization |  |  | 38 | 11.4 | 7.6 | 7.6 | 3.8 | 3.8 | 3.8 | 29 | [8 empty] | 2010-06-23 14:24 | 2010-07-09 13:26 | 2010-07-20 04:48 | 2010-07-30 20:10 | 2010-08-05 03:50 | 2010-08-10 11:31 | 2010-08-15 19:12 | 2007-10-01 | 2010-06-23 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 38 | [6 empty] | 25% | 2, 4, 9, 11
32 |  |  | OH Coaxial Bus Preliminary Design Updates & Optimization Completed |  | 8 | 2.4 | 1.6 | 1.6 | 0.8 | 0.8 | 0.8 | 29 | [8 empty] | 2010-06-23 14:24 | 2010-06-26 23:02 | 2010-06-29 04:48 | 2010-07-01 10:34 | 2010-07-02 13:26 | 2010-07-03 16:19 | 2010-07-04 19:12 | 2007-10-01 | 2010-06-23 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 40 | [11 empty] | 25% | 2, 4, 9, 11
33 |  |  | PF Bus Preliminary Design Updates & Optimization Completed |  | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 32 | [8 empty] | 2010-07-04 19:12 | 2010-07-09 | 2010-07-11 19:12 | 2010-07-14 14:24 | 2010-07-16 | 2010-07-17 09:36 | 2010-07-18 19:12 | 2007-10-01 | 2010-07-04 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 40 | [11 empty] | 25% | 2, 4, 9, 11
34 |  |  | TF Bus Preliminary Design Updates & Optimization Completed |  | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 33 | [8 empty] | 2010-07-18 19:12 | 2010-07-23 | 2010-07-25 19:12 | 2010-07-28 14:24 | 2010-07-30 | 2010-07-31 09:36 | 2010-08-01 19:12 | 2007-10-01 | 2010-07-18 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 40 | [11 empty] | 25% | 2, 4, 9, 11
35 |  |  | CHI Bus Preliminary Design Updates & Optimization Completed |  | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 34 | [8 empty] | 2010-08-01 19:12 | 2010-08-06 | 2010-08-08 19:12 | 2010-08-11 14:24 | 2010-08-13 | 2010-08-14 09:36 | 2010-08-15 19:12 | 2007-10-01 | 2010-08-01 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 40 | [11 empty] | 25% | 2, 4, 9, 11
36 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
37 |  | DOE CD-2 (Lehman) Review | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
38 |  |  | - |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | [8 empty] | 2010-08-04 | 2010-08-04 | 2010-08-06 02:24 | 2010-08-07 12:00 | 2010-08-08 21:36 | 2010-08-09 14:24 | 2010-08-10 07:12 | 2010-08-11 | 2010-08-04 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 16 |  |  |  |  | 40 | [6 empty] | 10% | 2, 4
39 |  |  | Review |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | [8 empty] | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2010-08-11 | 2007-10-01 | 2010-08-11 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 8 | [6 empty] | 5% | 2, 4
40 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
41 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
42 |  | Final Design |  | M. Smith | 162 | 48.6 | 32.4 | 32.4 | 16.2 | 16.2 | 16.2 | [9 empty] | 2010-08-17 | 2010-10-24 00:58 | 2010-12-08 09:36 | 2011-01-22 18:14 | 2011-02-14 10:34 | 2011-03-09 02:53 | 2011-03-31 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 162 | [6 empty] | 20% | 2, 4, 9
43 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
44 |  | OH Coaxial Bus |  | M. Smith | 38 | 11.4 | 7.6 | 7.6 | 3.8 | 3.8 | 3.8 | [8 empty] | 2010-08-17 | 2010-08-17 | 2010-09-01 23:02 | 2010-09-12 14:24 | 2010-09-23 05:46 | 2010-09-28 13:26 | 2010-10-03 21:07 | 2010-10-09 04:48 | 2010-08-17 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
45 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
46 |  |  | Complete Busbar System Design | M. Smith & EE | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | [8 empty] | 2010-08-17 | 2010-08-17 | 2010-08-19 02:24 | 2010-08-20 12:00 | 2010-08-21 21:36 | 2010-08-22 14:24 | 2010-08-23 07:12 | 2010-08-24 | 2010-08-17 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 4 |  |  |  | 16 | [6 empty] | 20% | 2, 4, 9
47 |  |  | Update CAD: Develop Drawings for Validation | G. Paluzzi | 6 | 1.8 | 1.2 | 1.2 | 0.6 | 0.6 | 0.6 | 46 | [8 empty] | 2010-08-24 | 2010-08-26 12:29 | 2010-08-28 04:48 | 2010-08-29 21:07 | 2010-08-30 17:17 | 2010-08-31 13:26 | 2010-09-01 09:36 | 2007-10-01 | 2010-08-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 39 |  |  |  |  | 10 | [6 empty] | 20% | 2, 4, 9, 11
48 | [11 empty] | 47 | [15 empty] | 2007-10-01 | 2010-09-01 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
49 |  |  | Update / Validate Analysis: EM, Stress, Thermal | Titus | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 47 | [8 empty] | 2010-09-01 09:36 | 2010-09-03 12:00 | 2010-09-04 21:36 | 2010-09-06 07:12 | 2010-09-07 | 2010-09-07 16:48 | 2010-09-08 09:36 | 2007-10-01 | 2010-09-01 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 16 | [12 empty] | 25% | 2, 4, 9
50 |  |  | Update / Validate Electrical Analysis | EE | 3 | 0.9 | 0.6 | 0.6 | 0.3 | 0.3 | 0.3 | 47 | [8 empty] | 2010-09-01 09:36 | 2010-09-02 15:50 | 2010-09-03 12:00 | 2010-09-04 08:10 | 2010-09-04 18:14 | 2010-09-05 04:19 | 2010-09-05 14:24 | 2007-10-01 | 2010-09-01 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 12 | [10 empty] | 25% | 2, 4, 9
51 |  |  | Update Models & Drawings: Drawings Checked & Ready for Signoff | G. Paluzzi | 3 | 0.9 | 0.6 | 0.6 | 0.3 | 0.3 | 0.3 | 48 | 49 | 50 | [6 empty] | 2010-09-08 09:36 | 2010-09-09 15:50 | 2010-09-10 12:00 | 2010-09-11 08:10 | 2010-09-11 18:14 | 2010-09-12 04:19 | 2010-09-12 14:24 | 2007-10-01 |  | 2010-09-08 09:36 | 2010-09-05 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 23 |  |  |  |  | 9 | [6 empty] | 20% | 2, 4, 9, 11
52 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 |  | PF Bus |  | M. Smith | 38 | 11.4 | 7.6 | 7.6 | 3.8 | 3.8 | 3.8 | 44 | [8 empty] | 2010-10-09 04:48 | 2010-10-25 03:50 | 2010-11-04 19:12 | 2010-11-15 10:34 | 2010-11-20 18:14 | 2010-11-26 01:55 | 2010-12-01 09:36 | 2007-10-01 | 2010-10-09 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
54 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
55 |  |  | Complete Busbar System Design | M. Smith & EE | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 46 | [8 empty] | 2010-08-24 | 2010-08-26 02:24 | 2010-08-27 12:00 | 2010-08-28 21:36 | 2010-08-29 14:24 | 2010-08-30 07:12 | 2010-08-31 | 2007-10-01 | 2010-08-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 4 |  |  |  | 16 | [6 empty] | 20% | 2, 4, 9
56 |  |  | Update CAD: Develop Drawings for Validation | G. Paluzzi | 23 | 6.9 | 4.6 | 4.6 | 2.3 | 2.3 | 2.3 | 47 | 55 |  |  |  |  | 51 |  |  | 2010-09-01 09:36 | 2010-09-11 01:26 | 2010-09-17 12:00 | 2010-09-23 22:34 | 2010-09-27 03:50 | 2010-09-30 09:07 | 2010-10-03 14:24 | 2007-10-01 | 2010-09-01 09:36 | 2010-08-31 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2010-09-12 14:24 | 2007-10-01 | [7 empty] | 159 |  |  |  |  | 28 | [6 empty] | 20% | 2, 4, 9, 11
57 | [11 empty] | 56 | [15 empty] | 2007-10-01 | 2010-10-03 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
58 |  |  | Update / Validate Analysis: EM, Stress, Thermal | Titus | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 56 | [8 empty] | 2010-10-03 14:24 | 2010-10-05 16:48 | 2010-10-07 02:24 | 2010-10-08 12:00 | 2010-10-09 04:48 | 2010-10-09 21:36 | 2010-10-10 14:24 | 2007-10-01 | 2010-10-03 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 24 | [12 empty] | 25% | 2, 4, 9
59 |  |  | Update / Validate Electrical Analysis | EE | 3 | 0.9 | 0.6 | 0.6 | 0.3 | 0.3 | 0.3 | 56 | [8 empty] | 2010-10-03 14:24 | 2010-10-04 20:38 | 2010-10-05 16:48 | 2010-10-06 12:58 | 2010-10-06 23:02 | 2010-10-07 09:07 | 2010-10-07 19:12 | 2007-10-01 | 2010-10-03 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 12 | [10 empty] | 25% | 2, 4, 9
60 |  |  | Update Models & Drawings: Drawings Checked & Ready for Signoff | G. Paluzzi | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 57 | 58 | 59 | [6 empty] | 2010-10-10 14:24 | 2010-10-14 19:12 | 2010-10-17 14:24 | 2010-10-20 09:36 | 2010-10-21 19:12 | 2010-10-23 04:48 | 2010-10-24 14:24 | 2007-10-01 |  | 2010-10-10 14:24 | 2010-10-07 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 93 |  |  |  |  | 24 | [6 empty] | 20% | 2, 4, 9, 11
61 |  | TF Bus |  | M. Smith | 38 | 11.4 | 7.6 | 7.6 | 3.8 | 3.8 | 3.8 | 53 | [8 empty] | 2010-12-01 09:36 | 2010-12-17 08:38 | 2010-12-28 | 2011-01-07 15:22 | 2011-01-12 23:02 | 2011-01-18 06:43 | 2011-01-23 14:24 | 2007-10-01 | 2010-12-01 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
62 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
63 |  |  | Complete Busbar System Design | M. Smith & EE | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 55 | [8 empty] | 2010-08-31 | 2010-09-02 02:24 | 2010-09-03 12:00 | 2010-09-04 21:36 | 2010-09-05 14:24 | 2010-09-06 07:12 | 2010-09-07 | 2007-10-01 | 2010-08-31 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 4 |  |  |  | 16 | [6 empty] | 20% | 2, 4, 9
64 |  |  | Update CAD: Develop Drawings for Validation | G. Paluzzi | 21 | 6.3 | 4.2 | 4.2 | 2.1 | 2.1 | 2.1 | 56 | 63 |  |  |  |  | 60 |  |  | 2010-10-03 14:24 | 2010-10-12 10:05 | 2010-10-18 07:12 | 2010-10-24 04:19 | 2010-10-27 02:53 | 2010-10-30 01:26 | 2010-11-02 | 2007-10-01 | 2010-10-03 14:24 | 2010-09-07 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2010-10-24 14:24 | 2007-10-01 | [7 empty] | 152 |  |  |  |  | 34 | [6 empty] | 20% | 2, 4, 9, 11
65 | [11 empty] | 64 | [15 empty] | 2007-10-01 | 2010-11-02 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
66 |  |  | Update / Validate Analysis: EM, Stress, Thermal | Titus | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 64 | [8 empty] | 2010-11-02 | 2010-11-04 02:24 | 2010-11-05 12:00 | 2010-11-06 21:36 | 2010-11-07 14:24 | 2010-11-08 07:12 | 2010-11-09 | 2007-10-01 | 2010-11-02 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 16 | [12 empty] | 25% | 2, 4, 9
67 |  |  | Update / Validate Electrical Analysis | EE | 3 | 0.9 | 0.6 | 0.6 | 0.3 | 0.3 | 0.3 | 64 | [8 empty] | 2010-11-02 | 2010-11-03 06:14 | 2010-11-04 02:24 | 2010-11-04 22:34 | 2010-11-05 08:38 | 2010-11-05 18:43 | 2010-11-06 04:48 | 2007-10-01 | 2010-11-02 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 12 | [10 empty] | 25% | 2, 4, 9
68 |  |  | Update Models & Drawings: Drawings Checked & Ready for Signoff | G. Paluzzi | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 65 | 66 | 67 | [6 empty] | 2010-11-09 | 2010-11-13 04:48 | 2010-11-16 | 2010-11-18 19:12 | 2010-11-20 04:48 | 2010-11-21 14:24 | 2010-11-23 | 2007-10-01 |  | 2010-11-09 | 2010-11-06 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 74 |  |  |  |  | 18 | [6 empty] | 20% | 2, 4, 9, 11
69 |  | CHI Bus |  | M. Smith | 38 | 11.4 | 7.6 | 7.6 | 3.8 | 3.8 | 3.8 | 61 | [8 empty] | 2011-01-23 14:24 | 2011-02-08 13:26 | 2011-02-19 04:48 | 2011-03-01 20:10 | 2011-03-07 03:50 | 2011-03-12 11:31 | 2011-03-17 19:12 | 2007-10-01 | 2011-01-23 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
70 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
71 |  |  | Complete Busbar System Design | M. Smith & EE | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 63 | [8 empty] | 2010-09-07 | 2010-09-09 02:24 | 2010-09-10 12:00 | 2010-09-11 21:36 | 2010-09-12 14:24 | 2010-09-13 07:12 | 2010-09-14 | 2007-10-01 | 2010-09-07 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 4 |  |  |  | 16 | [6 empty] | 20% | 2, 4, 9
72 |  |  | Update CAD: Develop Drawings for Validation | G. Paluzzi | 29 | 8.7 | 5.8 | 5.8 | 2.9 | 2.9 | 2.9 | 64 | 71 |  |  |  |  | 68 |  |  | 2010-11-02 | 2010-11-14 04:19 | 2010-11-22 07:12 | 2010-11-30 10:05 | 2010-12-04 11:31 | 2010-12-08 12:58 | 2010-12-12 14:24 | 2007-10-01 | 2010-11-02 | 2010-09-14 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2010-11-23 | 2007-10-01 | [7 empty] | 202 |  |  |  |  | 38 | [6 empty] | 20% | 2, 4, 9, 11
73 | [11 empty] | 72 | [15 empty] | 2007-10-01 | 2010-12-12 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
74 |  |  | Update / Validate Analysis: EM, Stress, Thermal | Titus | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 72 | [8 empty] | 2010-12-12 14:24 | 2010-12-14 16:48 | 2010-12-16 02:24 | 2010-12-17 12:00 | 2010-12-18 04:48 | 2010-12-18 21:36 | 2010-12-19 14:24 | 2007-10-01 | 2010-12-12 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 24 | [12 empty] | 25% | 2, 4, 9
75 |  |  | Update / Validate Electrical Analysis | EE | 3 | 0.9 | 0.6 | 0.6 | 0.3 | 0.3 | 0.3 | 72 | [8 empty] | 2010-12-12 14:24 | 2010-12-13 20:38 | 2010-12-14 16:48 | 2010-12-15 12:58 | 2010-12-15 23:02 | 2010-12-16 09:07 | 2010-12-16 19:12 | 2007-10-01 | 2010-12-12 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 12 | [10 empty] | 25% | 2, 4, 9
76 |  |  | Update Models & Drawings: Drawings Checked & Ready for Signoff | G. Paluzzi | 11 | 3.3 | 2.2 | 2.2 | 1.1 | 1.1 | 1.1 | 73 | 74 | 75 | [6 empty] | 2010-12-19 14:24 | 2010-12-24 05:17 | 2010-12-27 07:12 | 2010-12-30 09:07 | 2010-12-31 22:05 | 2011-01-02 11:02 | 2011-01-04 | 2007-10-01 |  | 2010-12-19 14:24 | 2010-12-16 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 114 |  |  |  |  | 28 | [6 empty] | 20% | 2, 4, 9, 11
77 |  | Update Cost & Schedule Estimate |  | M. Smith | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 76 | [8 empty] | 2011-01-04 | 2011-01-04 20:10 | 2011-01-05 09:36 | 2011-01-05 23:02 | 2011-01-06 05:46 | 2011-01-06 12:29 | 2011-01-06 19:12 | 2007-10-01 | 2011-01-04 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 8 | [6 empty] | 10% | 2, 4
78 |  | FDR Prep |  | M. Smith | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 |  |  |  | 51 | 60 | 68 | 76 | 77 | 2010-08-17 | 2010-08-17 | 2010-09-12 14:24 | 2010-10-24 14:24 | 2010-11-23 | 2011-01-04 | 2011-01-06 19:12 | 2011-01-07 12:00 | 2010-08-17 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2010-09-12 14:24 | 2010-10-24 14:24 | 2010-11-23 | 2011-01-04 | 2011-01-06 19:12 | [12 empty] | 40 | [6 empty] | 10% | 2, 4
79 |  | FDR |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | [7 empty] | 2011-03-31 | 2011-03-31 | 2011-03-31 | 2011-03-31 | 2011-03-31 | 2011-03-31 | 2011-03-31 | 2011-03-31 | 2011-03-31 | 2011-01-07 12:00 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 8 | [6 empty] | 5% | 2, 4
80 |  | Procurement |  |  | 263 | 78.9 | 52.6 | 52.6 | 26.3 | 26.3 | 26.3 | [8 empty] | 2011-04-27 | 2011-04-27 | 2011-08-15 11:02 | 2011-10-28 02:24 | 2012-01-09 17:46 | 2012-02-15 13:26 | 2012-03-23 09:07 | 2012-04-29 04:48 | 2011-04-27 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 65.75 | [6 empty] | 30% | 2, 4, 9
81 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
82 |  | Prep Req & Procurement Package |  |  | 10 | 3 | 2 | 2 | 1 | 1 | 1 | [8 empty] | 2011-04-27 | 2011-04-27 | 2011-05-01 04:48 | 2011-05-04 | 2011-05-06 19:12 | 2011-05-08 04:48 | 2011-05-09 14:24 | 2011-05-11 | 2011-04-27 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 80 | [6 empty] | 20% | 2, 4
83 |  | Submit Req to Procurement |  |  | 1 | 0.3 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 82 | [8 empty] | 2011-05-11 | 2011-05-11 10:05 | 2011-05-11 16:48 | 2011-05-11 23:31 | 2011-05-12 02:53 | 2011-05-12 06:14 | 2011-05-12 09:36 | 2007-10-01 | 2011-05-11 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
84 |  | Procurement Lead Time |  |  | 30 | 9 | 6 | 6 | 3 | 3 | 3 | 83 | [8 empty] | 2011-05-12 09:36 | 2011-05-25 | 2011-06-02 09:36 | 2011-06-10 19:12 | 2011-06-15 | 2011-06-19 04:48 | 2011-06-23 09:36 | 2007-10-01 | 2011-05-12 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
85 |  |  | Award: Coil Bus Runs |  | 1 | 0.3 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 84 | [8 empty] | 2011-06-23 09:36 | 2011-06-23 19:41 | 2011-06-24 02:24 | 2011-06-24 09:07 | 2011-06-24 12:29 | 2011-06-24 15:50 | 2011-06-24 19:12 | 2007-10-01 | 2011-06-23 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
86 |  | Copper Total |  |  | 80 | 24 | 16 | 16 | 8 | 8 | 8 | 85 | [8 empty] | 2011-06-24 19:12 | 2011-07-28 09:36 | 2011-08-19 19:12 | 2011-09-11 04:48 | 2011-09-22 09:36 | 2011-10-03 14:24 | 2011-10-14 19:12 | 2007-10-01 | 2011-06-24 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 15.2494 | [10 empty] | 2 | 8 |  | 8 |  |  |  | 20% | 2, 4, 6, 9, 11
87 |  | Insulation & Protection Total | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 9.323 | [10 empty] | 2 | 8 |  | 8 |  |  |  | 20% | 2, 4, 6, 9, 11
88 |  | SS Hardware, Fittings, Materials Total | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 16.4126 | [10 empty] | 2 | 8 |  | 8 |  |  |  | 20% | 2, 4, 6, 9, 11
89 |  | G10 FR4 Total | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 6.825 | [10 empty] | 2 | 8 |  | 8 |  |  |  | 25% | 2, 4, 6, 9, 11
90 |  | Fab & Safety Comsumables Total | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 5 | [10 empty] | 2 | 8 |  | 8 |  |  |  | 20% | 2, 4, 6, 9, 11
91 |  | Struc Support Material Total | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 3 | [10 empty] | 2 | 8 |  | 8 |  |  |  | 25% | 2, 4, 6, 9, 11
92 |  | Misc Total | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 9.781 | [10 empty] | 2 | 8 |  | 8 |  |  |  | 25% | 2, 4, 6, 9, 11
93 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
94 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
95 |  |  | All Hardware & Materials Received |  | 0 | [14 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
96 |  | Fab/Assembly |  | M. Smith | 140 | 42 | 28 | 28 | 14 | 14 | 14 | 95 | [8 empty] | 2011-10-01 | 2011-11-28 19:12 | 2012-01-07 | 2012-02-15 04:48 | 2012-03-05 19:12 | 2012-03-25 09:36 | 2012-04-14 | 2007-10-01 | 2011-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 4 |  | 4 |  |  |  |  | 16 |  |  |  | 210 | [6 empty] | 20% | 2, 4, 9
97 |  | OH Coaxial Bus | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
98 |  |  | Documentation: Fab/Assy Procedure |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 95 | [8 empty] | 2011-10-01 | 2011-10-03 02:24 | 2011-10-04 12:00 | 2011-10-05 21:36 | 2011-10-06 14:24 | 2011-10-07 07:12 | 2011-10-08 | 2007-10-01 | 2011-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 8 |  |  |  |  | 30 | 12 | [5 empty] | 25% | 2, 4, 9
99 |  |  | Fabrication: pre-installation components |  | 20 | 6 | 4 | 4 | 2 | 2 | 2 | 98 | [8 empty] | 2011-10-08 | 2011-10-16 09:36 | 2011-10-22 | 2011-10-27 14:24 | 2011-10-30 09:36 | 2011-11-02 04:48 | 2011-11-05 | 2007-10-01 | 2011-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 12 |  |  | 320 | 180 |  |  | 35% | 2, 9
100 |  |  | Assembly: pre-installation components |  | 20 | 6 | 4 | 4 | 2 | 2 | 2 | 99 | [8 empty] | 2011-11-05 | 2011-11-13 09:36 | 2011-11-19 | 2011-11-24 14:24 | 2011-11-27 09:36 | 2011-11-30 04:48 | 2011-12-03 | 2007-10-01 | 2011-11-05 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 160 |  |  |  | 35% | 2, 9
101 |  |  | Insulation & Protective Layer |  | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 100 | [8 empty] | 2011-12-03 | 2011-12-07 04:48 | 2011-12-10 | 2011-12-12 19:12 | 2011-12-14 04:48 | 2011-12-15 14:24 | 2011-12-17 | 2007-10-01 | 2011-12-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 160 |  |  |  | 35% | 2, 9
102 |  |  | Electrical Testing |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 101 | [8 empty] | 2011-12-17 | 2011-12-19 02:24 | 2011-12-20 12:00 | 2011-12-21 21:36 | 2011-12-22 14:24 | 2011-12-23 07:12 | 2011-12-24 | 2007-10-01 | 2011-12-17 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [10 empty] | 16 |  |  | 8 |  | 16 |  |  |  | 35% | 2, 9
103 |  |  | Parts Ready for Field fit up & Installation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | [8 empty] | 2011-12-24 | 2011-12-24 | 2011-12-24 | 2011-12-24 | 2011-12-24 | 2011-12-24 | 2011-12-24 | 2007-10-01 | 2011-12-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
104 |  | PF Bus | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
105 |  |  | Documentation: Fab/Assy Procedure |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 98 | [8 empty] | 2011-10-08 | 2011-10-10 02:24 | 2011-10-11 12:00 | 2011-10-12 21:36 | 2011-10-13 14:24 | 2011-10-14 07:12 | 2011-10-15 | 2007-10-01 | 2011-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 8 |  |  |  |  | 24 | 10 | [5 empty] | 25% | 2, 9
106 |  |  | Fabrication: pre-installation components |  | 20 | 6 | 4 | 4 | 2 | 2 | 2 | 105 | 103 | [7 empty] | 2011-12-24 | 2012-01-01 09:36 | 2012-01-07 | 2012-01-12 14:24 | 2012-01-15 09:36 | 2012-01-18 04:48 | 2012-01-21 | 2007-10-01 | 2011-10-15 | 2011-12-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 12 |  |  | 160 | 160 |  |  | 35% | 2, 9
107 |  |  | Parts Ready for Field fit up & Installation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | [8 empty] | 2012-01-21 | 2012-01-21 | 2012-01-21 | 2012-01-21 | 2012-01-21 | 2012-01-21 | 2012-01-21 | 2007-10-01 | 2012-01-21 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
108 |  | TF Bus | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
109 |  |  | Documentation: Fab/Assy Procedure |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 105 | [8 empty] | 2011-10-15 | 2011-10-17 02:24 | 2011-10-18 12:00 | 2011-10-19 21:36 | 2011-10-20 14:24 | 2011-10-21 07:12 | 2011-10-22 | 2007-10-01 | 2011-10-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 8 |  |  |  |  | 24 | 10 | [5 empty] | 25% | 2, 9
110 |  |  | Fabrication: pre-installation components |  | 20 | 6 | 4 | 4 | 2 | 2 | 2 | 106 | 109 | [7 empty] | 2012-01-21 | 2012-01-29 09:36 | 2012-02-04 | 2012-02-09 14:24 | 2012-02-12 09:36 | 2012-02-15 04:48 | 2012-02-18 | 2007-10-01 | 2012-01-21 | 2011-10-22 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 12 |  |  | 160 | 160 |  |  | 35% | 2, 9
111 |  |  | Parts Ready for Field fit up & Installation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | [8 empty] | 2012-02-18 | 2012-02-18 | 2012-02-18 | 2012-02-18 | 2012-02-18 | 2012-02-18 | 2012-02-18 | 2007-10-01 | 2012-02-18 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
112 |  | CHI Bus | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
113 |  |  | Documentation: Fab/Assy Procedure |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 109 | [8 empty] | 2011-10-22 | 2011-10-24 02:24 | 2011-10-25 12:00 | 2011-10-26 21:36 | 2011-10-27 14:24 | 2011-10-28 07:12 | 2011-10-29 | 2007-10-01 | 2011-10-22 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 8 |  |  |  |  | 24 | 10 | [5 empty] | 25% | 2, 9
114 |  |  | Fabrication: pre-installation components |  | 20 | 6 | 4 | 4 | 2 | 2 | 2 | 111 | 113 | [7 empty] | 2012-02-18 | 2012-02-26 09:36 | 2012-03-03 | 2012-03-08 14:24 | 2012-03-11 09:36 | 2012-03-14 04:48 | 2012-03-17 | 2007-10-01 | 2012-02-18 | 2011-10-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 12 |  |  | 160 | 160 |  |  | 35% | 2, 9
115 |  |  | Parts Ready for Field fit up & Installation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | [8 empty] | 2012-03-17 | 2012-03-17 | 2012-03-17 | 2012-03-17 | 2012-03-17 | 2012-03-17 | 2012-03-17 | 2007-10-01 | 2012-03-17 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
116 |  | Installation |  | Mike Viola | [23 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10.962 | [17 empty] | 25% | 2, 9
117 |  | OH Coaxial Bus | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
118 |  |  | Documentation: Installation Procedure |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | [8 empty] | 2012-08-01 | 2012-08-01 | 2012-08-03 02:24 | 2012-08-04 12:00 | 2012-08-05 21:36 | 2012-08-06 14:24 | 2012-08-07 07:12 | 2012-08-08 | 2012-08-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | [6 empty] | 25% | 2, 4, 9
119 |  |  | Field Fit Up, Fabrication, Installation |  | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 118 | [8 empty] | 2012-08-08 | 2012-08-12 04:48 | 2012-08-15 | 2012-08-17 19:12 | 2012-08-19 04:48 | 2012-08-20 14:24 | 2012-08-22 | 2007-10-01 | 2012-08-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 5 | 4 |  |  |  | 20 |  |  | 160 | 20 |  |  | 35% | 2, 9
120 |  |  | Testing |  | 1 | 0.3 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 119 | [8 empty] | 2012-08-22 | 2012-08-22 10:05 | 2012-08-22 16:48 | 2012-08-22 23:31 | 2012-08-23 02:53 | 2012-08-23 06:14 | 2012-08-23 09:36 | 2007-10-01 | 2012-08-22 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [10 empty] | 8 |  |  | 8 | [5 empty] | 35% | 2, 9
121 |  |  | Bus Installation Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | [8 empty] | 2012-08-23 09:36 | 2012-08-23 09:36 | 2012-08-23 09:36 | 2012-08-23 09:36 | 2012-08-23 09:36 | 2012-08-23 09:36 | 2012-08-23 09:36 | 2007-10-01 | 2012-08-23 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
122 |  | PF Bus | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
123 |  |  | Documentation: Installation Procedure |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 118 | [8 empty] | 2012-08-08 | 2012-08-10 02:24 | 2012-08-11 12:00 | 2012-08-12 21:36 | 2012-08-13 14:24 | 2012-08-14 07:12 | 2012-08-15 | 2007-10-01 | 2012-08-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | [6 empty] | 25% | 2, 4, 9
124 |  |  | Field Fit Up, Fabrication, Installation |  | 60 | 18 | 12 | 12 | 6 | 6 | 6 | 121 | 123 | [7 empty] | 2012-08-23 09:36 | 2012-09-17 14:24 | 2012-10-04 09:36 | 2012-10-21 04:48 | 2012-10-29 14:24 | 2012-11-07 | 2012-11-15 09:36 | 2007-10-01 | 2012-08-23 09:36 | 2012-08-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 42 | 4 |  |  |  | 90 |  |  | 1200 | 120 |  |  | 35% | 2, 9
125 |  |  | Testing |  | 6 | 1.8 | 1.2 | 1.2 | 0.6 | 0.6 | 0.6 | 124 | [8 empty] | 2012-11-15 09:36 | 2012-11-17 22:05 | 2012-11-19 14:24 | 2012-11-21 06:43 | 2012-11-22 02:53 | 2012-11-22 23:02 | 2012-11-23 19:12 | 2007-10-01 | 2012-11-15 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [10 empty] | 48 |  |  | 48 | [5 empty] | 35% | 2, 9
126 |  |  | Bus Installation Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | [8 empty] | 2012-11-23 19:12 | 2012-11-23 19:12 | 2012-11-23 19:12 | 2012-11-23 19:12 | 2012-11-23 19:12 | 2012-11-23 19:12 | 2012-11-23 19:12 | 2007-10-01 | 2012-11-23 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
127 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
128 |  | TF Bus | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
129 |  |  | Documentation: Installation Procedure |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 123 | [8 empty] | 2012-08-15 | 2012-08-17 02:24 | 2012-08-18 12:00 | 2012-08-19 21:36 | 2012-08-20 14:24 | 2012-08-21 07:12 | 2012-08-22 | 2007-10-01 | 2012-08-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | [6 empty] | 25% | 2, 4, 9
130 |  |  | Field Fit Up, Fabrication, Installation |  | 20 | 6 | 4 | 4 | 2 | 2 | 2 | 125 | 129 | [7 empty] | 2012-11-23 19:12 | 2012-12-02 04:48 | 2012-12-07 19:12 | 2012-12-13 09:36 | 2012-12-16 04:48 | 2012-12-19 | 2012-12-21 19:12 | 2007-10-01 | 2012-11-23 19:12 | 2012-08-22 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 9 | 4 |  |  |  | 20 |  |  | 400 | 40 |  |  | 35% | 2, 9
131 |  |  | Testing |  | 2 | 0.6 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 130 | [8 empty] | 2012-12-21 19:12 | 2012-12-22 15:22 | 2012-12-23 04:48 | 2012-12-23 18:14 | 2012-12-24 00:58 | 2012-12-24 07:41 | 2012-12-24 14:24 | 2007-10-01 | 2012-12-21 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [10 empty] | 16 |  |  | 16 | [5 empty] | 35% | 2, 9
132 |  |  | Bus Installation Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | [8 empty] | 2012-12-24 14:24 | 2012-12-24 14:24 | 2012-12-24 14:24 | 2012-12-24 14:24 | 2012-12-24 14:24 | 2012-12-24 14:24 | 2012-12-24 14:24 | 2007-10-01 | 2012-12-24 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
133 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
134 |  | CHI Bus | [25 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
135 |  |  | Documentation: Installation Procedure |  | 5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 129 | [8 empty] | 2012-08-22 | 2012-08-24 02:24 | 2012-08-25 12:00 | 2012-08-26 21:36 | 2012-08-27 14:24 | 2012-08-28 07:12 | 2012-08-29 | 2007-10-01 | 2012-08-22 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | [6 empty] | 25% | 2, 4, 9
136 |  |  | Field Fit Up, Fabrication, Installation |  | 40 | 12 | 8 | 8 | 4 | 4 | 4 | 130 | 135 | [7 empty] | 2012-12-21 19:12 | 2013-01-07 14:24 | 2013-01-18 19:12 | 2013-01-30 | 2013-02-04 14:24 | 2013-02-10 04:48 | 2013-02-15 19:12 | 2007-10-01 | 2012-12-21 19:12 | 2012-08-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 27 | 4 |  |  |  | 40 |  |  | 640 | 80 |  |  | 35% | 2, 9
137 |  |  | Testing |  | 3 | 0.9 | 0.6 | 0.6 | 0.3 | 0.3 | 0.3 | 136 | [8 empty] | 2013-02-15 19:12 | 2013-02-17 01:26 | 2013-02-17 21:36 | 2013-02-18 17:46 | 2013-02-19 03:50 | 2013-02-19 13:55 | 2013-02-20 | 2007-10-01 | 2013-02-15 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [10 empty] | 24 |  |  | 24 | [5 empty] | 35% | 2, 9
138 |  |  | Bus Installation Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | [8 empty] | 2013-02-20 | 2013-02-20 | 2013-02-20 | 2013-02-20 | 2013-02-20 | 2013-02-20 | 2013-02-20 | 2007-10-01 | 2013-02-20 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
139 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
140 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [19 empty] | 40% | 2, 9
141 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
142 | [27 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[28 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [35 empty] | 80.553 | 0 | 4 | 0 | 0 | 128 | 1467 | 144 | 0 | 112 | 0 | 1622.75 | 202 | 0 | 3592 | 920 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1053.275 | [32 empty] | 98.7579 | 0 | 6.848 | 0 | 0 | 24.1408 | 183.2283 | 24.9696 | 0 | 13.328 | 0 | 259.4777 | 30.4818 | 0 | 324.3576 | 87.6852 | 0
Notes:
Logical Pre-requisites
Duration in Work Days
Completion %
NOTE: Since the bus runs require field fit up and fabrication, the cost for installation was included in this WAF. Mike Viola is cog for the installation.
Approx: 5 CAD models & 3 drawings
Approx: 21 CAD models & 12 drawings
Approx: 32 CAD models & 7 drawings
Approx: 30 CAD models & 14 drawings
NOTE: Bus bar installation begins when the installations of the CS, Umbrellas, and the PF and TF support structures are completed.

## M&S
Cost Center: | 9417
Job Number: | 5501
Job Title: | Coil Bus Runs
Job Manager: | Mark Smith
Materials and Subcontracts (M&S)
| 1 Unit, Set, or Group |  | Unit Cost |  | Total # of
Description: | quantity | units | $ | per unit | Units /Sets | Total Cost | Basis Comments | Basis Caterogry | Contingency %
Copper
CHI main ring | 1 | lbf | 2.9 | lbf | 194.0248 | 562.6718 |  | 2, 4, 6, 9, 11 | 20
CHI busbar | 1 | lbf | 2.9 | lbf | 270.2 | 783.58 |  | 2, 4, 6, 9, 11 | 20
PF1 | 1 | lbf | 2.9 | lbf | 1351 | 3917.9 |  | 2, 4, 6, 9, 11 | 20
TF | 1 | lbf | 2.9 | lbf | 3340.8 | 9688.32 |  | 2, 4, 6, 9, 11 | 20
OH Inner | 1 | lbf | 2.9 | lbf | 30.4 | 88.16 |  | 2, 4, 6, 9, 11 | 20
OH Outer | 1 | lbf | 2.6 | lbf | 80.3 | 208.78 |  | 2, 4, 6, 9, 11 | 20
Insulation & Protection
Kapton | 1 | 1 roll | 80 | 1 roll | 41 | 3280 |  | 2, 4, 6, 9, 11 | 20
Fiberglass | 1 | 1 roll | 7 | 1 roll | 149 | 1043 |  | 2, 4, 6, 9, 11 | 20
Epoxy | 1 | 1 | 1000 | 1 | 5 | 5000 |  | 2, 4, 6, 9, 11 | 20
SS Hardware | [7 empty] | 2, 4, 6, 9, 11
Bolts | 1 | each | 3.45 | each | 820 | 2829 |  | 2, 4, 6, 9, 11 | 20
Flatwasher | 1 | 25/pack | 9.7 | 1 pack | 32.8 | 318.16 |  | 2, 4, 6, 9, 11 | 20
Belleville Washer | 1 | 5/pack | 7.1 | 1 pack | 164 | 1164.4 |  | 2, 4, 6, 9, 11 | 20
Nut | 1 | 10/pack | 5.5 | 1 pack | 82 | 451 |  | 2, 4, 6, 9, 11 | 20
SS Water Fittings | 1 | per fitting | 125 | per fitting | 74 | 9250 |  | 2, 4, 6, 9, 11 | 20
316 SS Tube (Cooling tube OH) | 1 | each | 300 | each | 8 | 2400 |  | 2, 4, 6, 9, 11 | 20
G10 FR4 @ 1.5in thickness (36 in x 48 in) | 1 | sheet | 1500 | sheet | 3 | 4500 |  | 2, 4, 6, 9, 11 | 25
G10 FR4 @ 0.75in thickness (36 in x 48 in) | 1 | sheet | 565 | sheet | 3 | 1695 |  | 2, 4, 6, 9, 11 | 25
G10 FR4 @ 0.25in thickness (36 in x 48 in) | 1 | sheet | 210 | sheet | 3 | 630 |  | 2, 4, 6, 9, 11 | 25
Fabrication Items (consumable) | [5 empty] | 4000 |  | 2, 4, 6, 9 | 20
Safety Items (consumable) | [5 empty] | 1000 |  | 2, 4, 6, 9 | 20
Structural Support Materials | [5 empty] | 3000 |  | 2, 4, 6, 9 | 20
Miscellaneous: rework & additional materials, unforeseen items | [5 empty] | 9780.9972 | 10% rework & additional materials, $5k | 2, 4, 6, 9 | 25
Misc During Fabrication | [5 empty] | 4000 |  | 2, 4, 6, 9 | 25
Misc During Field Fit up & Installation | [5 empty] | 10961.9944 | 20% more materials and unforeseen items | 2, 4, 6, 9 | 25
0
[5 empty] | Total M&S | 80552.9634
Copper Total | 15.2494
Insulation & Protection Total | 9.323
SS Hardware, Fittings, Materials Total | 16.4126
G10 FR4 Total | 6.825
Fab & Safety Comsumables Total | 5
Struc Support Material Total | 3
Misc Total | 9.781
Misc During Fabrication | 4
Misc During Field Fit up & Installation | 10.962
Notes: Fabrication items (consumable) are items such as: materials for prototypes and fixtures; machine bits; epoxy buckets and mixers; rags; etc. Safety Items (consumable) are items such as: Tyvek suits, gloves, clean up supplies etc.

## Risk & Uncertainty
Cost Center: |  | 9417
Job Number: |  | 5501
Job Title: |  | Coil Bus Runs
Job Manager: |  | Mark Smith
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | x
| Design Complexity |  |  | x
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate |  | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
Design of Bus Routes
[8 empty] | 2, 4, 9 |  |  | 0 | 0
Installation is Field Fit Up | [7 empty] | 2, 4, 9 |  |  | 0 | 0
Final design (including optimization) is contingent upon the designs of the center stack, pedestal, umbrellas and umbrella lids being frozen / completed. This could impact Designer, Eng, Analyst man hours along with schedule.
Uncertainty during installation of the required modifcations from the designed bus routes. Could impact estimates for man power, duration of tasks, and M&S.

## notes M&S
| # Complete |  | Total Hardware Sets | 820
| Circuits |  | Bolt | 3.45 | each | 2829
CHI main ring | 1 |  | Flat Washer | 9.7 | pack 25 | 318.16
CHI busbar | 3 |  | Bevel Washer | 7.1 | pack 5 | 1164.4 | [5 empty] | Installation Support
PF1 | 6 |  | Nut | 5.5 | pack 10 | 451 | [6 empty] | # Complete | # Busbars | # Elec Joints | Designer Hrs (as-built revisions) |  | Techs
TF | 2 |  |  |  |  | 4762.56 | [6 empty] | Circuits |  |  | complex
OH | 1 | [10 empty] | CHI main ring | 1 | 2 | 4 | 2.5 | 5.8 | 160
[12 empty] | CHI busbar | 3 | 6 | 4 | 3 | 20.88 | 480
| # Busbars | Busbar Dims (inches) |  |  | CrossSectional |  | Total |  | Cost | Cooling | Total Fittings | PF1 | 6 | 12 | 4 | 3 | 41.76 | 960
|  | L1 | L2 | Radius | Area | Length (in) | Length (in) | lbf/ft | @ $2.9/lbf | # fittings |  | TF | 2 | 4 | 11 | 2 | 9.28 | 320
CHI main ring | 2 | 1 | 1 | 48 | 1 | 301.5929 | 603.1858 | 3.86 | 562.6718 | 8 | 16 | OH | 1 | 1 | 6 | 2 | 4.64 | 160
CHI busbar | 6 | 1 | 1 | - | 1 | 140 | 840 | 3.86 | 783.58 | 8 | 48
PF1 | 12 | 2 | 1 | - | 2 | 175 | 2100 | 7.72 | 3917.9 | 0 | 0
TF | 4 | 6 | 1 | - | 6 | 432 | 1728 | 23.2 | 9688.32 | 0 | 0
OH | 1 |  |  | 0.5 | 0.7854 | 120 | 120 | 3.04 | 88.16 | 10 | 10
| 1 |  | 0.175 | 0.625 | 0.78343 | 120 | 120 | 8.03 | 232.87 |  | 9250
| # Busbars | Electrical Joints |  | # of HW | Total |  |  |  | 15273.5018
|  | # | Bolt Size | Sets /busbar | # HW Sets1
CHI main ring | 2 | 4 | 0.375 | 16 | 32
CHI busbar | 6 | 4 | 0.375 | 16 | 96
PF1 | 12 | 4 | 0.375 | 16 | 192
TF | 4 | 11 | 0.5 | 44 | 176
OH | 1 | 6 | 0.375 | 24 | 24
| # Complete | Brackets | # of HW | Total | G10 1.5 inch thick |  |  | Total G10
| Circuits | # of | Sets / Bracket | # HW Sets2 | L1 | L2 | Area / Bracket | Area
CHI main ring | 1 | 10.3776 | 22 | 22 | 4 | 3 | 12 | 124.531
CHI busbar | 3 | 5.8889 | 12 | 36 | 4 | 3 | 12 | 212
PF1 | 6 | 6.8611 | 14 | 84 | 6 | 3 | 18 | 741
TF | 2 | 17.5 | 36 | 144 | 9 | 4 | 36 | 2520 | G10 FR4 @ 1.5in thickness (36 in x 48 in)
OH | 1 | 6.3333 | 14 | 14 | 6 | 6 | 36 | 228 | 1500 | per sheet
|  | Adjusted |  | required |  | epoxy | Sum | 3825.531 | 1728 | in^2 / sheet
|  | length | surface area | Kapton 2 mil | Fiberglass | cubic inches |  | 4781.9137 | 2.7673
| CHI main ring | 753.9822 | 3015.9289 | 6031.8579 | 3015.9289 | 60.3186 |  |  | 4150.9668
| CHI busbar | 1050 | 4200 | 8400 | 4200 | 84
| PF1 | 2625 | 15750 | 31500 | 15750 | 315
| TF | 2160 | 30240 | 60480 | 30240 | 604.8
| OH | 150 | 471.2389 | 942.4778 | 471.2389 | 9.4248
|  |  | Totals | 107354.3357 | 107354.3357 | 1073.5434
|  |  | rolls | 41.2901 | 149.1032 | 4.6474
|  |  | cost | 3303.2103 | 1043.7227 | 4647.3738 | 8994.3069
1.5 lap kapton
2 wraps 2 inch Fiberglass
Account for waste / scrap: add 25%

## notes
Basis Notes for Estimates: CAD Models & Drawings Detail CAD Designer mh @ 3mh/FD model, Eng @ [0.3 to 0.5]*(total Designer mh) Update FD drawings: Designer @ 8 mh/drawing, Eng @ (0.75mh)/drawing Validation update CAD: Designer @ 1mh/model Validation update Drawings: Designer @ 4mh/drw Check Drawings: Other Designer @ 2 hr/drawing Check & signoff: Eng @ 2 to 3.0mh/draw : includes 0.5h for oversite ======================================================== Designer man hr during installation, function of: bus complexity, # of circuits, # of joints. complexitty (subjective): use simple @ 2 mh/ circuit, complex @ 3mh. mh needed = (complex*# of cir)+(complex*# of cir)*(.33*# of jnts)
Basis Notes for Estimates: For PD, and FD Activities: Eng project management @ 1 mh/md for various activities. For Procurement Activities: Eng project management @ 0.25 mh/md for various activities. For Fab Activities: Eng project management @ 1.5 mh/md for various activities. Eng support @ 1-2mh/md of installation Tech support during installation: 2m for 2mw/each circuit. During installation Need rigging crew (2m) @ 25% of duration time for heavy lifting (TF, PF only) Need RESA machinist @ 25% time for each bus. Electrical testing is 1md/circuit.