## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 6100
Job Title: | Central I&C and Data Acquisition
Job Manager: | Paul Sichta
Rev 1 7/2/2010
Description:
This upgrade will be capable of producing plasmas on the order of 6.5 seconds; to-date they are less than two seconds. Some CAMAC and PC-based data acquisition systems will require an upgrade and in some cases replacement. The Test Cell network will need more drops to accomodate new data acquisition systems. The real-time plasma control system will require a software upgrade to accommodate additional input/output signals, control loops, and a longer control period. Some test cell racks will be relocated; there will be a modest effort required to route the control, timing, and communication cabling and qualify the systems. There are numerous other IT improvements required; these will be funded by NSTX Operations since they would occur regardless of the upgrade effort.
Schedule:
Approvals:
__________________________________________________________
| Job Manager | Job Manager
__________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9417
| Job Number: |  |  | 6100
| Job Title: |  |  | Central I&C and Data Acquisition
| Job Manager: |  |  | Paul Sichta
Estimate (user input)
[5 empty] | SCHEDULE | [13 empty] | FY10$K |  |  |  |  | HOURS (priced at FY10 rates) | [19 empty] | % | % |  |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT | [5 empty] | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Resp | Duration in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Contingency | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [17 empty] | 1.178 | 1.178 | 1.617 | 1.232 | 1.859 | 177.11 | 118.8 | 135.2 | 101.48 | 67.89 | 172.42 | 150.61 | 122.43 | 83.52 | 149.15 | 148.87 | 115.61 | 89.2 | 142.83 | 177 | 208.3 | 156.85 | 1 | 1 | 1
1 | This upgrade will be capable of producing plasmas on the order of 10 seconds; to-date they are less than two seconds. For dozens of CAMAC and PC-based data acquisition systems this will require an upgrade, and in some cases replacement. The real-time plasma control system may require an upgrade to accommodate additional input/output signals, control loops, and a longer control period. The networks, back-end compute servers, and data storage systems will need be upgraded to achieve reasonable performance for time-sensitive functions. Some test cell racks will be relocated; there will be a modest effort required to route the control, timing, and communication cabling and qualify the systems. | Project Integration | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
2 |  |  | WBS Mgmnt & Interfaces Coordination | Sichta | 700 |  |  |  |  | 2009-09-23 | 2009-09-23 | 2012-05-30 | 2009-09-23 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 200 | [19 empty] | 10% |  | 4
3 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
28 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
29 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
30 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
31 |  | Final Design | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 |  |  | Disposition PDR Chits | Sichta | 30 | 27 |  |  |  |  | 2007-10-01 | 2007-11-12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 10 | [19 empty] | 10% |  | 4
33 |  |  | Assess workscope changes | Sichta | 10 | 32 |  |  |  |  | 2007-11-12 | 2007-11-26 | 2007-10-01 | 2007-11-12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 32 | [19 empty] | 10% |  | 4
34 |  |  | Delay design for NSTX run support | Sichta | 1 |  |  |  |  | 2010-08-01 | 2010-08-01 | 2010-08-02 09:36 | 2010-08-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 1 | [19 empty] | 10% |  | 4
35b |  |  | PCS Software design analysis | Mastrov | 30 | 34 |  |  |  |  | 2010-08-02 09:36 | 2010-09-13 09:36 | 2007-10-01 | 2010-08-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 80 | [19 empty] | 10% |  | 4
36 |  |  | CAMAC Memory PCB design | Wertenb | 30 | 34 |  |  |  |  | 2010-08-02 09:36 | 2010-09-13 09:36 | 2007-10-01 | 2010-08-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 10 | 60 | [18 empty] | 10% |  | 4
37 |  |  | CAMAC Replacement selection | Tchilin | 60 | 34 |  |  |  |  | 2010-08-02 09:36 | 2010-10-25 09:36 | 2007-10-01 | 2010-08-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 0 | 0 | [5 empty] | 32 | [19 empty] | 10% |  | 4
38 |  |  | Cntr Stk diags data acq design | Sichta | 10 | 34 |  |  |  |  | 2010-08-02 09:36 | 2010-08-16 09:36 | 2007-10-01 | 2010-08-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 24 | 24 | [19 empty] | 10% |  | 4
39 |  |  | DAS upgrade for NSTX diagnostics | Tchilin | 30 | 34 |  |  |  |  | 2010-08-02 09:36 | 2010-09-13 09:36 | 2007-10-01 | 2010-08-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 24 | [19 empty] | 10% |  | 4
40 |  |  | I&C effort due to NTC GIS rack move | Massry | 30 | 34 | 25 |  |  |  | 2010-08-02 09:36 | 2010-09-13 09:36 | 2007-10-01 | 2010-08-02 09:36 |  | 2007-10-01 | 2007-10-01 | [8 empty] | 40 | 24 | [18 empty] | 10% |  | 4
41 |  |  | ECN & new drawings | Massry | 40 | 40 | 39 | 38 |  |  | 2010-09-13 09:36 | 2010-11-08 09:36 | 2007-10-01 | 2010-09-13 09:36 | 2010-09-13 09:36 | 2010-08-16 09:36 | 2007-10-01 | [7 empty] | 160 | 160 | 80 | [18 empty] | 10% |  | 4
42 |  |  | Update System documents | Sichta | 10 | 41 |  |  |  |  | 2010-11-08 09:36 | 2010-11-22 09:36 | 2007-10-01 | 2010-11-08 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 60 | [19 empty] | 10% |  | 4
43 |  |  | FDR Prep | Sichta | 5 |  |  |  |  | 2011-01-02 | 2011-01-02 | 2011-01-09 | 2011-01-02 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 80 | [19 empty] | 10% |  | 4
44 |  |  | Disposition FDR Chits | Sichta | 30 | 43 |  |  |  |  | 2011-01-09 | 2011-02-20 | 2007-10-01 | 2011-01-09 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 16 | [19 empty] | 10% |  | 4
45 |  |  | Network Design | Henders | 30 | 40 |  |  |  |  | 2010-09-13 09:36 | 2010-10-25 09:36 | 2007-10-01 | 2010-09-13 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 16 | 40 | [18 empty] | 10% |  | 4
46 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
47 |  | Procurement | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
48 |  |  | Wait for I&C Procurement Start | Sichta | 1 |  |  |  |  | 2012-03-01 | 2012-03-01 | 2012-03-02 09:36 | 2012-03-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 1 | [19 empty] | 10% |  | 4
49c |  |  | CAMAC Replacement proto | Tchilin | 60 | 48 | [12 empty] | 16 | 8 | [5 empty] | 32 | [19 empty] | 10% |  | 4
49d |  |  | CAMAC Replacement equipment | Tchilin | 60 | 37 | 48 | 49c |  |  | #N/A | #N/A | 2007-10-01 | 2010-10-25 09:36 | 2012-03-02 09:36 | #N/A | 2007-10-01 |  | 120 | 20 | [5 empty] | 40 | [19 empty] | 10% |  | 4
50 |  |  | CAMAC Memory module | Wertenb | 90 | 36 | 48 |  |  |  | 2012-03-02 09:36 | 2012-07-06 09:36 | 2007-10-01 | 2010-09-13 09:36 | 2012-03-02 09:36 | 2007-10-01 | 2007-10-01 |  | 11 | 5 | [5 empty] | 8 | 24 | [18 empty] | 10% |  | 4
51 |  |  | Networking equipment & fiber optics | Henders | 40 | 44 | 48 |  |  |  | 2012-03-02 09:36 | 2012-04-27 09:36 | 2007-10-01 | 2011-02-20 | 2012-03-02 09:36 | 2007-10-01 | 2007-10-01 |  | 26 | 8 | [5 empty] | 16 | 24 | [18 empty] | 10% |  | 4
52 |  |  | GIS rack-move I&C fiber optics & equip. | Massry | 30 | 40 | 48 | 44 |  |  | 2012-03-02 09:36 | 2012-04-13 09:36 | 2007-10-01 | 2010-09-13 09:36 | 2012-03-02 09:36 | 2011-02-20 | 2007-10-01 |  | 8 | 4 | [5 empty] | 32 | 16 | [18 empty] | 10% |  | 4
53 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
54 |  | Fabrication/Programming | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
55 |  |  | Wait for I&C Fabrication Start (per NSTX ops) | Sichta | 1 |  |  |  |  | 2012-06-01 | 2012-06-01 | 2012-06-02 09:36 | 2012-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 1 | [19 empty] | 10% |  | 4
56 |  |  | I&C Peer Review | Mastrov | 5 | 55 |  |  |  |  | 2012-06-02 09:36 | 2012-06-09 09:36 | 2007-10-01 | 2012-06-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 40 | 12 | [18 empty] | 10% |  | 4
57c |  |  | PCS Infrastructure code & debug | Mastrov | 60 | 56 |  |  |  |  | 2012-06-09 09:36 | 2012-09-01 09:36 | 2007-10-01 | 2012-06-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 40 | [19 empty] | 10% |  | 4
58 |  |  | PSRTC code & debug | Mastrov | 60 | 57b |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 160 | [19 empty] | 10% |  | 4
59 |  |  | Update PSRTC Simulation models | Hatcher | 30 | 56 |  |  |  |  | 2012-06-09 09:36 | 2012-07-21 09:36 | 2007-10-01 | 2012-06-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 |  | 32 |  | 16 | [17 empty] | 10% |  | 4
60 |  |  | PCS code & debug | Mastrov | 60 | 57b |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 60 | [19 empty] | 10% |  | 4
61a |  |  | CAMAC replacement proto | Tchilin | 120 | [20 empty] | 120 | [19 empty] | 10% |  | 4
61b |  |  | CAMAC replacement - local software | Tchilin | 120 | 55 | 49d | 61a |  |  | #N/A | #N/A | 2007-10-01 | 2012-06-02 09:36 | #N/A | 0 | 2007-10-01 | [8 empty] | 300 | [19 empty] | 10% |  | 4
62 |  |  | CAMAC replacement - MDSplus changes | Tchilin | 20 | 61b |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 100 | [19 empty] | 10% |  | 4
63 |  |  | Cntr Stk diags data acq changes | Sichta | 10 | 55 |  |  |  |  | 2012-06-02 09:36 | 2012-06-16 09:36 | 2007-10-01 | 2012-06-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 16 | [19 empty] | 10% |  | 4
64 |  |  | CAMAC Replacement systems fab. | Wertenb | 90 | 55 | 49d |  |  |  | #N/A | #N/A | 2007-10-01 | 2012-06-02 09:36 | #N/A | 2007-10-01 | 2007-10-01 | [8 empty] | 120 | 240 | [18 empty] | 10% |  | 4
65 |  |  | CAMAC Memory module fab. | Wertenb | 60 | 55 | 50 |  |  |  | 2012-07-06 09:36 | 2012-09-28 09:36 | 2007-10-01 | 2012-06-02 09:36 | 2012-07-06 09:36 | 2007-10-01 | 2007-10-01 |  | 5 | [6 empty] | 16 | 40 |  | 40 | [16 empty] | 10% |  | 4
66 |  |  | PCS – Support Transrex Firing Generator | Mastrov | 30 | 58 |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 80 | [19 empty] | 10% |  | 4
67 |  |  | DAS programming for NSTX diags upgd | Tchilin | 60 | 62 |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 24 | [19 empty] | 10% |  | 4
68 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
69 |  | Installation | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
70 |  |  | Wait for I&C Installation Start (per NSTX ops) | Sichta | 1 |  |  |  |  | 2012-07-01 | 2012-07-01 | 2012-07-02 09:36 | 2012-07-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 1 | [19 empty] | 10% |  | 4
71 |  |  | CAMAC Replacement systems install | Tchilin | 90 | 70 | 65 |  |  |  | 2012-09-28 09:36 | 2013-02-01 09:36 | 2007-10-01 | 2012-07-02 09:36 | 2012-09-28 09:36 | 2007-10-01 | 2007-10-01 | [8 empty] | 80 | 120 | 40 | 60 | [16 empty] | 10% |  | 4
72 |  |  | CAMAC Memory install | Wertenb | 10 | 70 | 87 |  |  |  | 2012-10-05 09:36 | 2012-10-19 09:36 | 2007-10-01 | 2012-07-02 09:36 | 2012-10-05 09:36 | 2007-10-01 | 2007-10-01 | [8 empty] | 8 | 12 | [18 empty] | 10% |  | 4
73a |  |  | NTC/DARM fiber & network install | Henders | 30 | 70 | 50 | [17 empty] | 32 | 40 |  |  |  |  | 80 | [14 empty] | 10% |  | 4
74 |  |  | install I&C Thermocouple equipment | Wertenb | 5 | 70 |  |  |  |  | 2012-07-02 09:36 | 2012-07-09 09:36 | 2007-10-01 | 2012-07-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 8 | 16 | [18 empty] | 10% |  | 4
75 |  |  | Install I&C due to NTC GIS rack relocation | Massry | 60 | 70 |  |  |  |  | 2012-07-02 09:36 | 2012-09-24 09:36 | 2007-10-01 | 2012-07-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 40 | 48 | 60 |  |  |  | 120 | [14 empty] | 10% |  | 4
76 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
77 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
78 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
79 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
80 |  | Testing | [10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
81 |  |  | CS Infrastructure tests | Mastrov | 30 | 57 |  |  |  |  | 2012-06-09 09:36 | 2012-07-21 09:36 | 2007-10-01 | 2012-06-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 40 | 8 | 24 | 24 | [16 empty] | 10% |  | 4
82 |  |  | PSRTC Simulation PTP-034 | Mastrov | 5 | 81 |  |  |  |  | 2012-07-21 09:36 | 2012-07-28 09:36 | 2007-10-01 | 2012-07-21 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 |  | 32 | [19 empty] | 10% |  | 4
83 |  |  | PSRTC PTP-035 | Mastrov | 5 | 81 |  |  |  |  | 2012-07-21 09:36 | 2012-07-28 09:36 | 2007-10-01 | 2012-07-21 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 24 |  | 40 |  | 24 | [17 empty] | 10% |  | 4
84b |  |  | PCS tesing | Hatcher | 10 | 83 |  |  |  |  | 2012-07-28 09:36 | 2012-08-11 09:36 | 2007-10-01 | 2012-07-28 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 40 | [19 empty] | 10% |  | 4
85 |  |  | Support ISTP-001 | Mastrov | 5 | 84b | 75 | 90 |  |  | 2012-10-01 09:36 | 2012-10-08 09:36 | 2007-10-01 | 2012-08-11 09:36 | 2012-09-24 09:36 | 2012-10-01 09:36 | 2007-10-01 | [6 empty] | 24 |  | 24 |  | 24 | [17 empty] | 10% |  | 4
86 |  |  | CAMAC Replacement system tests | Tchilin | 60 | 71 | 61 | 62 | 73 |  | #N/A | #N/A | 2007-10-01 | 2013-02-01 09:36 | #N/A | #N/A | 2012-10-19 09:36 | [8 empty] | 160 | 80 | [18 empty] | 10% |  | 4
87 |  |  | CAMAC Memory bench tests | Wertenb | 5 | 65 |  |  |  |  | 2012-09-28 09:36 | 2012-10-05 09:36 | 2007-10-01 | 2012-09-28 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 8 | 40 | [18 empty] | 10% |  | 4
88 |  |  | CAMAC Memory field tests | Wertenb | 5 | 87 | 72 |  |  |  | 2012-10-19 09:36 | 2012-10-26 09:36 | 2007-10-01 | 2012-10-05 09:36 | 2012-10-19 09:36 | 2007-10-01 | 2007-10-01 | [8 empty] | 8 | 20 | [18 empty] | 10% |  | 4
89 |  |  | Cntr Stk diags testing | Sichta | 5 | 74 |  |  |  |  | 2012-07-09 09:36 | 2012-07-16 09:36 | 2007-10-01 | 2012-07-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 24 | 16 | [18 empty] | 10% |  | 4
90 |  |  | test relocated I&C GIS rack systems | Massry | 5 | 75 |  |  |  |  | 2012-09-24 09:36 | 2012-10-01 09:36 | 2007-10-01 | 2012-09-24 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 60 | 40 | [18 empty] | 10% |  | 4
91 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [28 empty] | 10%
92 |  |  | Project Ready for ISTP Target | Sichta | 1 |  |  |  |  | 2013-02-01 | 2013-02-01 | 2013-02-02 09:36 | 2013-02-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 1 | [19 empty] | 10% |  | 4
93 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
94 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
95 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
96 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
97 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
98 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
99 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
142 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[13 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [16 empty] | 186 | 45 | 0 | 0 | 0 | 128 | 256 | 2645 | 972 | 128 | 124 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 835.9994 | [13 empty] | 219.108 | 53.01 | 0 | 0 | 0 | 22.6701 | 30.4128 | 357.604 | 98.6386 | 8.6899 | 21.3801 | 0 | 24.486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [27 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  | Weeks | [23 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  |  | 3 | [23 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  |  | 5 | [23 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  |  | 8 | [23 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  |  | 9 | [23 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
Note on D49: incl force calcs

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 6100
Job Title: |  | Central I&C and Data Acquisition
Job Manager: |  | Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
-15% / +25%
| Design Complexity |  |  | X
8
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Loss of key personnel |  |  |  | U | hire replacement and assess schedule impact |  |  | Estimated impact is < 1 months on the critical path. Impact on cost because untrained personnel will be less effective. | 10 | 50 | 0 | 4
2 | Data acquisition takes too long |  |  |  | VU | Upgrade additional data acq systems and/or networks, revise software |  |  | Estimated impact is 0 months on the critical path. Costs will be due to upgrading additional CAMAC systems. | 5 | 25 | 0 | 2
3 | NSTX operations does not fund workscope as listed in WBS6100 PDR |  |  |  | U | Additional workscope for upgrade |  |  | Estimated impact is < 1 months on the critical path. Impact on cost due to additional workscope. | 50 | 300 | 0 | 4
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9417
Job Number: | 6100
Job Title: | Central I&C and Data Acquisition
Job Manager: | Paul Sichta
Materials and Subcontracts (M&S) | QTY | Cost Each ($K) | Total($K) | Basis of Estimate
Description:
CAMAC replacement Transient Digitizers (for proto) | 2 | 12 | 24 | 4
LabVIEW software , PC, & Adnaco | 4 | 5 | 20 | 4
CAMAC replacement systems & spares | 8 | 15 | 120 | 4
CAMAC memory board (Lawson unit assembled) | 10 | 1 | 10 | 4
CAMAC memory Carrier board PCB | 1 | 2 | 2 | 4
CAMAC memory Carrier board parts | 10 | 0.4 | 4 | 4
Memory Module off-site fabrication | 1 | 5 | 5 | 4
NTC/DARM Fiber & Conduit | 1 | 16 | 16 | 4
NTC/DARM Network Equip. | 1 | 18 | 18 | 4
Fiber Optic Cable set for GIS rack move | 1 | 10 | 10 | 4
Cables/conn/jbox set for GIS rack move | 1 | 2 | 2 | 4
231
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
Note on A12: assumption that some CAMAC replacements might be a PC-based system
Note on A13: D-Tacq price range, incl. LEMO transition panels
Note on A18: used Sep2009 NSTX NTC networking upgrade Henderson CDR info as a basis. Since we need ~16 new NTC network drops, NTC patch fibers, (2) 18-ckt trunk lines, cassettes, (2) cassettes boxes.
Note on A19: used Sep2009 NSTX NTC networking upgrade Henderson CDR info as a basis. Since we need ~16 new NTC network drops, buy a new switch (assume existing at capacity), 24 SFP 100 Mbit optic ports, 16 media convertors.
Note on A20: systran, PCS sample clock, lawson/dymec, CAMAC, facclk, LDGIS, piezo valve driver,
Note on A22: Something like DL385, and PCIexpress adapter for Vmetro