## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9418
Job Number: | 7400
Job Title: | Health Physics Technical Support
Job Manager: | Tim Stevenson
REV 1 10/15/2010
Description:
Decon, BL refurbishment, BL relocation require continuous HP support. This job covers time for two HPs, overtime, and minor sundries for HP ops for FY 10,11,12. Two HPs are required to cover surveys, regulatory compliance documentation, procedures, and RWPs. Two HPs are required during every decon evolution where one individual is suited up in PCs inside the RWP area and one is outside providing support and running smears. HP is also required to process cleaned items for release. FY09 Decon Ops experience has demonstrated the need for 2 HPs. Equipment Removal/Relocation (Job 2490) requires one HP support during the removal of equipment.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9418
| Job Number: |  |  | 7400
| 9418 |  |  | Health Physics Technical Support
| Job Manager: |  |  | Tim Stevenson
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | Duration in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Contingency | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
1 |  |  | Decon HP Support (2) FY 2010 |  | 260 |  | 2009-10-01 | 2009-10-01 | 2010-09-30 | 2009-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10 | 10 | [16 empty] | 3452 | [8 empty] | 13% |  | 2 Full-Time HP Techs each year | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
2 |  |  | Decon HP Overtime 2010 | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [5 empty] | 100 | [22 empty] | 13% | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
3 |  |  | Decon HP Support (2) FY 2011 |  | 260 |  | 2010-10-01 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10 | 10 | [16 empty] | 800 | [8 empty] | 13% |  | 2 Full-Time HP Techs each year | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
4 |  |  | Decon HP Overtime 2011 | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [5 empty] | 100 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
4A |  |  | EQ Rem/Rel HP Support (1) FY 2011 |  | 120 |  | 442310 | 2011-01-03 | 2011-07-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [19 empty] | 2720 | [8 empty] | 13% |  | Estimated @ 340 days of HP support during planned removals/relocations | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
5 |  |  | Decon HP Support (2) FY 2012 |  | 260 |  | 2011-10-01 | 2011-10-01 | 2012-09-29 | 2011-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10 | 10 | [16 empty] | 2800 | [8 empty] | 13% |  | 2 Full-Time HP Techs each year | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
6 |  |  | Decon HP Overtime 2012 | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [5 empty] | 100 | [22 empty] | 13% | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
7 |  |  | Decon HP Support (2) FY 2013 |  | 260 |  | 2011-10-01 | 2012-10-01 | 2013-09-30 | 2011-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 5 | 5 | [16 empty] | 2400 | [8 empty] | 13% |  | 1 Full-Time HP Tech each year | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
8 |  |  | Decon HP Overtime 2013 | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [5 empty] | 50 | [22 empty] | 13% | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
9 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
10 |  |  | Decon HP Support (2) FY 2014 |  | 195 |  |  | 2007-10-01 | 2008-06-30 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 3.75 | 3.75 | [16 empty] | 1295 | [8 empty] | 13% | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
11 |  |  | Decon HP Overtime 2014 | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [5 empty] | 37.5 | [22 empty] | 13% | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
12 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
13 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
14 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
|  | TOTALS | [13 empty] | 38.75 | 38.75 | 0 | 0 | 387.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13467 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 2751.6566 | [10 empty] | 47.5075 | 47.5075 | 0 | 0 | 733.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1923.4916 | 0 | 0 | 0 | 0 | 0
Notes:
| (1) Procurement lead time: |  |  |  | Weeks | [14 empty] | CATEGORIZATION CODES:
| Purchase orders-Commercial, off-the-shelf items |  |  |  | 3 | [14 empty] | 1 - National Standards
| Purchase orders-Noncommercial items |  |  |  | 5 | [14 empty] | 2 - Engineering Judgement/Experience
| Subcontracts (non construction) |  |  |  | 8 | [14 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
| Construction subcontracts |  |  |  | 9 | [14 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9418
Job Number: |  | 7400
9418 | 9418 | Health Physics Technical Support
Job Manager: |  | Tim Stevenson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X
| Design Complexity |  |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | unplanned overtime | [7 empty] | add'l 10% |  | 35
2
3 | [5 empty] | strykowsky estimates
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9418
Job Number: | 7400
9418 | 9418
Job Manager: | Tim Stevenson
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
NOT APPLICABLE
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS