## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 8200
Job Title: | Installation of Coil Support System
Job Manager: | Mike Viola
Project Start Date: | 2011-10-01
Rev 4 7/21/2010
Description:
The scope of this job includes the PF and TF support upgrade. This involves removing some equipment and cable tray for clearance and accessibility, welding stiffeners to PF2 and PF3 supports and installing new PF5 columns, replace bad TF coil. NSTX is an operating machine complete with a full complement of diagnostics in every bay. In order to reach the existing structure for modification, some equipment relocation is required. After work is compelte, a significant metrology effort will be needed to verify alignements. Finally, the equipemnt and cable tray previously removed must be reinstalled, tested and recommissioned.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9417
| Job Number: |  |  | 8200
| Job Title: |  |  | Installation of Coil Support System
| Job Manager: |  |  | Mike Viola
| Project Start Date: |  |  | 2011-10-01
Estimate (user input)
[5 empty] | SCHEDULE | [12 empty] | FY10$K |  |  |  |  | HOURS (priced at FY10 rates) | [16 empty] | % | % |  |  | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  |  | Calculated
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WorkDays | CREW SIZE | Logical Pre-requisites (one task numbers in each column ,any order) |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01
numb | P3 cross ref (optinal) | [16 empty] | 1.178 | 1.178 | 1.714 | 1.271 | 1.971 | 193.33 | 128.05 | 143.2 | 101.3 | 184.89 | 160.46 | 127.23 | 90.78 | 165.2 | 155.15 | 123.17 | 95.5 | 130.28 | 173.91 | 1 | 1 | 1
1 |  | Milestone dates | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
2 | 8200-0002 |  | Designs complete | Mangra | 1 |  |  |  |  | 2011-10-01 | 2011-10-02 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
3 | 8200-0003 |  | Assembly Sequence complete | Mangra | 1 |  |  |  |  | 2011-10-01 | 2011-10-02 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
4 | 8200-0004 |  | Parts arrived | Mark Smith | 1 |  |  |  | 2012-04-01 | 2012-04-01 | 2012-04-02 09:36 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
5 | 8200-0005 |  | Start procedural development | Mark Smith | 1 |  |  |  | 2012-01-01 | 2012-01-01 | 2012-01-02 09:36 | 2012-01-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
6 | 8200-0006 |  | Mobilize crews | Viola | 1 |  |  |  | 2012-04-01 | 2012-04-01 | 2012-04-02 09:36 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
7 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
8 |  | Management | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
8a |  |  | FY10/FY11 oversight (@ 3 md /month) 5/1/10-9/30/11 | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 408
9 |  |  | Opening Duration | Viola | 300 |  |  |  | 2012-04-01 | 2012-04-01 | 2013-05-26 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 0
10 | 8200-0010 |  | Shop Fabrication oversight 20% FTE for duration | Langish | 300 | 0.2 |  |  | 2012-04-01 | 2012-04-01 | 2013-05-26 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 480 | [8 empty] | 10
11 | 8200-0011 |  | Shop Fabrication support 1.5 FTE for duration | Langish | 300 | 1.5 |  |  | 2012-04-01 | 2012-04-01 | 2013-05-26 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 3600 | [6 empty] | 20
12 | 8200-0012 |  | Assembly oversight .8 FTE | Viola | 300 | 0.8 |  |  | 2012-04-01 | 2012-04-01 | 2013-05-26 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 1920 | [8 empty] | 10
13 | 8200-0013 |  | Assembly oversight 1 FTE | Winston | 300 | 1 |  |  | 2012-04-01 | 2012-04-01 | 2013-05-26 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [15 empty] | 2400 | [7 empty] | 10
14 | 8200-0014 |  | Title 3 Support Engineer | Mark Smith | 300 | 0.4 |  |  | 2012-04-01 | 2012-04-01 | 2013-05-26 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 960 | [8 empty] | 10
15 | 8200-0015 |  | Title 3 Support Drafting | Designer | 300 | 0.2 |  |  | 2012-04-01 | 2012-04-01 | 2013-05-26 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [7 empty] | 480 | [15 empty] | 10
16 | 8200-0016 |  | OT for efficiency (2 crews 1 weekend a month) | Techs | 300 | 0.2 |  |  | 2012-04-01 | 2012-04-01 | 2013-05-26 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 480 | [6 empty] | 20
17 | 8200-0017 |  | MISC M&S $250 per day* 2 crews | Techs | 300 | 2 |  |  | 2012-04-01 | 2012-04-01 | 2013-05-26 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 |  | 150 | [21 empty] | 10
18 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
19 |  | Documentation | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
20 | 8200-0020 |  | PREPARE WORK PLANNING FORM | Viola | 3 | 1 |  |  | 2012-01-01 | 2012-01-01 | 2012-01-05 04:48 | 2012-01-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 24 | [8 empty] | 50
21 | 8200-0021 |  | Fab/AssyInstallation Procedure | Mark Smith | 20 | 1 |  |  | 2012-01-01 | 2012-01-01 | 2012-01-29 | 2012-01-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 160 | [8 empty] | 50
22 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
23 |  | UPGRADE | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
24 |  | BAY BY BAY DIAGNOSTIC CATALOGUE | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
25 |  | Assume 8 lower 8 midplane and 4 upper bays | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
26 | 8200-0026 |  | Perform bay by bay catalogue and label Elect | SM | 12 | 1 |  |  | 2012-01-01 | 2012-01-01 | 2012-01-17 19:12 | 2012-01-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [15 empty] | 96 | [7 empty] | 40
27 | 8200-0027 |  | Perform bay by bay catalogue and label Mech | SM | 12 | 1 |  |  | 2012-01-01 | 2012-01-01 | 2012-01-17 19:12 | 2012-01-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [15 empty] | 96 | [7 empty] | 40
28 | 8200-0028 |  | Write removal procedures | SM | 60 | 1 | 27 |  |  | 2012-01-17 19:12 | 2012-04-10 19:12 | 2011-10-01 | 2012-01-17 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [15 empty] | 480 | [7 empty] | 40
29 | 8200-0029 |  | Remove RF pipes | RF EE/SB/TB | 20 | 2.5 |  |  | 2012-04-01 | 2012-04-01 | 2012-04-29 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [6 empty] | 60 | 120 |  |  |  |  | 260 |  |  |  | 800 | [6 empty] | 10
30 | 8200-0030 |  | Write Electrical Removal & Installation Procedures | SM | 20 | 2 |  |  | 2012-01-01 | 2012-01-01 | 2012-01-29 | 2012-01-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [15 empty] | 80 | [7 empty] | 40
31 | 8200-0031 |  | Safe, remove and store Elect | Techs E | 15 | 2.5 |  |  | 2012-04-01 | 2012-04-01 | 2012-04-22 | 2012-04-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 300 | [6 empty] | 40
32 | 8200-0032 |  | Upper Tray remove and store Elect | Techs E | 20 | 2.5 | 31 |  |  | 2012-04-22 | 2012-05-20 | 2011-10-01 | 2012-04-22 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 400 | [6 empty] | 40
33 | 8200-0033 |  | Remove and store Mech | Techs M1 | 10 | 5 | 31 |  |  | 2012-04-22 | 2012-05-06 | 2011-10-01 | 2012-04-22 | 2011-10-01 | 2011-10-01 | 2011-10-01 |  | 10 | [14 empty] | 400 | [6 empty] | 40
34 | 8200-0034 |  | Remove and store Upper and lower port eqpt | Techs M1 | 18 | 2.5 | 33 |  |  | 2012-05-06 | 2012-05-31 04:48 | 2011-10-01 | 2012-05-06 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 360 | [6 empty] | 40
35 | 8200-0035 |  | Remove section of platform | Techs M2 | 10 | 5 | 34 |  |  | 2012-05-31 04:48 | 2012-06-14 04:48 | 2011-10-01 | 2012-05-31 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 400 | [6 empty] | 40
36 | 8200-0036 |  | Fiducialize Coil and Vacuum vessel | Priniski+Tech | 20 | 1 | 35 |  |  | 2012-06-14 04:48 | 2012-07-12 04:48 | 2011-10-01 | 2012-06-14 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 160 |  | 160 | [6 empty] | 40
37 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
38 |  | EQUIPMENT REMOVALS | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
39 | 8200-0039 |  | Remove insulation | Techs M1 | 15 | 2.5 | 33 |  |  | 2012-05-06 | 2012-05-27 | 2011-10-01 | 2012-05-06 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 300 | [6 empty] | 30
40 | 8200-0040 |  | Gas Injection System | Techs M1 | 15 | 2.5 | 39 |  |  | 2012-05-27 | 2012-06-17 | 2011-10-01 | 2012-05-27 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 300 | [6 empty] | 30
41 | 8200-0041 |  | Disconnect trim coil and lock mode coil | Techs M1 | 2 | 2.5 | 40 |  |  | 2012-06-17 | 2012-06-19 19:12 | 2011-10-01 | 2012-06-17 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 40 | [6 empty] | 30
42 | 8200-0042 |  | Remove trim coil and lock mode coil | Techs M1 | 4 | 2.5 | 41 |  |  | 2012-06-19 19:12 | 2012-06-25 09:36 | 2011-10-01 | 2012-06-19 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 80 | [6 empty] | 30
43 | 8200-0043 |  | Clear platform and area to remove bad TF | Techs M2 | 10 | 2.5 | 35 |  |  | 2012-06-14 04:48 | 2012-06-28 04:48 | 2011-10-01 | 2012-06-14 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 200 | [6 empty] | 30
44 | 8200-0044 |  | Remove bad TF | Techs M2 | 5 | 5 | 43 |  |  | 2012-06-28 04:48 | 2012-07-05 04:48 | 2011-10-01 | 2012-06-28 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 200 | [6 empty] | 30
| 8200-1001 |  | Remove LLD | Machine Techs | 20 | 2.5 | 44 |  |  | 2012-07-05 04:48 | 2012-08-02 04:48 | 2011-10-01 | 2012-07-05 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 400 | [6 empty] | 30
45 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
46 |  | UPPER HALF | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
47 |  |  | 2 week delay contingency for rework |  | 10 |  | 31 |  |  | 2012-04-22 | 2012-05-06 | 2011-10-01 | 2012-04-22 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 0
48 | 8200-0048 |  | Umbrella Lid Remove existing | Rigger Techs | 1 | 5 | 44 |  |  | 2012-07-05 04:48 | 2012-07-06 14:24 | 2011-10-01 | 2012-07-05 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 |  | 2 | [14 empty] | 40 | [6 empty] | 35
49 | 8200-0049 |  | VV Umbrella legs Weld reinforcement plates | Techs W1 | 8 | 2.5 | 48 |  |  | 2012-07-06 14:24 | 2012-07-17 19:12 | 2011-10-01 | 2012-07-06 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
50 | 8200-0050 |  | Remove exisitng hardware | Techs M1 | 5 | 2.5 | 49 |  |  | 2012-07-17 19:12 | 2012-07-24 19:12 | 2011-10-01 | 2012-07-17 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 100 | [6 empty] | 35
51 | 8200-0051 |  | Umbrella legs add reinforcement plate | Techs M1 | 5 | 2.5 | 50 |  |  | 2012-07-24 19:12 | 2012-07-31 19:12 | 2011-10-01 | 2012-07-24 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 100 | [6 empty] | 35
52 | 8200-0052 |  | TF Install datums and remove turnbuckles | Techs M2 | 8 | 2.5 | 48 |  |  | 2012-07-06 14:24 | 2012-07-17 19:12 | 2011-10-01 | 2012-07-06 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
53 | 8200-0053 |  | TF Install new clamps | Techs M2 | 12 | 2.5 | 52 |  |  | 2012-07-17 19:12 | 2012-08-03 14:24 | 2011-10-01 | 2012-07-17 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 240 | [6 empty] | 35
54 | 8200-0054 |  | TF Install Vessel ties and align | Techs M2 | 18 | 2.5 | 53 |  |  | 2012-08-03 14:24 | 2012-08-28 19:12 | 2011-10-01 | 2012-08-03 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 360 | [6 empty] | 35
55 | 8200-0055 |  | TF Install new hoop brace | Techs M2 | 12 | 2.5 | 54 |  |  | 2012-08-28 19:12 | 2012-09-14 14:24 | 2011-10-01 | 2012-08-28 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 240 | [6 empty] | 35
56 | 8200-0056 |  | TF Align and match drill new hoop brace | Techs M2 | 18 | 2.5 | 55 |  |  | 2012-09-14 14:24 | 2012-10-09 19:12 | 2011-10-01 | 2012-09-14 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 360 | [6 empty] | 35
57 | 8200-0057 |  | TF Install and torque all bolts | Techs M2 | 8 | 2.5 | 56 |  |  | 2012-10-09 19:12 | 2012-10-21 | 2011-10-01 | 2012-10-09 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
58 | 8200-0058 |  | Design & build lifting method | Mark Smith | 16 | 3 |  |  |  | 2011-10-01 | 2011-10-23 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 |  | 10 | [5 empty] | 256 | [6 empty] | 128 |  | 384 | [6 empty] | 35
59 | 8200-0059 |  | PF2 Mark Location; lift and support | Rigger Techs | 2 | 2.5 | 48 |  |  | 2012-07-06 14:24 | 2012-07-09 09:36 | 2011-10-01 | 2012-07-06 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 40 | [6 empty] | 35
60 | 8200-0060 |  | PF2 Replace existing hardware (bolted) | Techs M1 | 1 | 2.5 | 59 | 51 |  | 2012-07-31 19:12 | 2012-08-02 04:48 | 2011-10-01 | 2012-07-09 09:36 | 2012-07-31 19:12 | 2011-10-01 | 2011-10-01 | [16 empty] | 20 | [6 empty] | 35
61 | 8200-0061 |  | PF2 Install New plates (bolted) | Techs M1 | 4 | 2.5 | 60 |  |  | 2012-08-02 04:48 | 2012-08-07 19:12 | 2011-10-01 | 2012-08-02 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 80 | [6 empty] | 35
62 | 8200-0062 |  | PF2 weld reinforcement | Techs W1 | 8 | 2.5 | 61 |  |  | 2012-08-07 19:12 | 2012-08-19 | 2011-10-01 | 2012-08-07 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
63 | 8200-0063 |  | PF2 Reinstall | Rigger Techs | 2 | 2.5 | 62 |  |  | 2012-08-19 | 2012-08-21 19:12 | 2011-10-01 | 2012-08-19 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 40 | [6 empty] | 35
64 | 8200-0064 |  | PF3 lift and support | Rigger Techs | 2 | 2.5 | 63 |  |  | 2012-08-21 19:12 | 2012-08-24 14:24 | 2011-10-01 | 2012-08-21 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 40 | [6 empty] | 35
65 | 8200-0065 |  | PF3 remove bolted support | Techs M1 | 1 | 2.5 | 64 |  |  | 2012-08-24 14:24 | 2012-08-26 | 2011-10-01 | 2012-08-24 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 20 | [6 empty] | 35
66 | 8200-0066 |  | PF3 Install new bolted support | Techs M1 | 8 | 2.5 | 65 |  |  | 2012-08-26 | 2012-09-06 04:48 | 2011-10-01 | 2012-08-26 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
67 | 8200-0067 |  | PF3 weld reinforcement | Techs W1 | 18 | 2.5 | 66 |  |  | 2012-09-06 04:48 | 2012-10-01 09:36 | 2011-10-01 | 2012-09-06 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 360 | [6 empty] | 35
68 | 8200-0068 |  | PF3 Reinstall and align | Rigger Techs | 3 | 2.5 | 67 |  |  | 2012-10-01 09:36 | 2012-10-05 14:24 | 2011-10-01 | 2012-10-01 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 60 | [6 empty] | 35
69 | 8200-0069 |  | PF5 U&L Disconnect existing midplane columns | Techs M1 | 4 | 2.5 |  | 66 |  | 2012-09-06 04:48 | 2012-09-11 19:12 | 2011-10-01 | 2011-10-01 | 2012-09-06 04:48 | 2011-10-01 | 2011-10-01 | [16 empty] | 80 | [6 empty] | 35
70 | 8200-0070 |  | PF4, 5 lift and install 1/4" plate | Techs M1 | 8 | 5 | 69 |  |  | 2012-09-11 19:12 | 2012-09-23 | 2011-10-01 | 2012-09-11 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 320 | [6 empty] | 35
71 | 8200-0071 |  | PF4, 5 Install newbolts and torque | Techs M1 | 6 | 2.5 | 70 |  |  | 2012-09-23 | 2012-10-01 09:36 | 2011-10-01 | 2012-09-23 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 120 | [6 empty] | 35
72 | 8200-0072 |  | Prefit & match drill New Umbrella Lid |  | 10 | 5 |  |  |  | 2011-10-01 | 2011-10-15 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [23 empty] | 35
73 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
74 |  | LOWER HALF | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
75 |  |  | 2 week delay contingency for rework |  | 10 |  | 59 |  |  | 2012-07-09 09:36 | 2012-07-23 09:36 | 2011-10-01 | 2012-07-09 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 0
76 | 8200-0076 |  | Umbrella Lid Remove existing | Rigger Techs | 1 | 5 | 60 |  |  | 2012-08-02 04:48 | 2012-08-03 14:24 | 2011-10-01 | 2012-08-02 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 40 | [6 empty] | 35
77 | 8200-0077 |  | TF Install new clamps | Techs M2 | 12 | 2.5 |  | 57 |  | 2012-10-21 | 2012-11-06 19:12 | 2011-10-01 | 2011-10-01 | 2012-10-21 | 2011-10-01 | 2011-10-01 | [16 empty] | 240 | [6 empty] | 35
78 | 8200-0078 |  | TF Install Vessel ties and align | Techs M2 | 18 | 2.5 | 77 |  |  | 2012-11-06 19:12 | 2012-12-02 | 2011-10-01 | 2012-11-06 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 360 | [6 empty] | 35
79 | 8200-0079 |  | TF Install new hoop brace | Techs M2 | 12 | 2.5 | 78 |  |  | 2012-12-02 | 2012-12-18 19:12 | 2011-10-01 | 2012-12-02 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 240 | [6 empty] | 35
80 | 8200-0080 |  | TF Align and match drill new hoop brace | Techs M2 | 18 | 2.5 | 79 |  |  | 2012-12-18 19:12 | 2013-01-13 | 2011-10-01 | 2012-12-18 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 360 | [6 empty] | 35
81 | 8200-0081 |  | TF Install and torque all bolts | Techs M2 | 8 | 2.5 | 80 |  |  | 2013-01-13 | 2013-01-24 04:48 | 2011-10-01 | 2013-01-13 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
82 | 8200-0082 |  | PF2 Mark Location; lower and support | Rigger Techs | 2 | 2.5 | 75 |  |  | 2012-07-23 09:36 | 2012-07-26 04:48 | 2011-10-01 | 2012-07-23 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 40 | [6 empty] | 35
83 | 8200-0083 |  | PF2 Replace existing hardware (bolted) | Techs M1 | 1 | 2.5 |  | 71 |  | 2012-10-01 09:36 | 2012-10-02 19:12 | 2011-10-01 | 2011-10-01 | 2012-10-01 09:36 | 2011-10-01 | 2011-10-01 | [16 empty] | 20 | [6 empty] | 35
84 | 8200-0084 |  | PF2 Install New plates (bolted) | Techs M1 | 4 | 2.5 | 83 |  |  | 2012-10-02 19:12 | 2012-10-08 09:36 | 2011-10-01 | 2012-10-02 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 80 | [6 empty] | 35
85 | 8200-0085 |  | PF2 weld reinforcement | Techs W1 | 8 | 2.5 | 84 |  |  | 2012-10-08 09:36 | 2012-10-19 14:24 | 2011-10-01 | 2012-10-08 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
86 | 8200-0086 |  | PF2 Reinstall | Rigger Techs | 2 | 2.5 | 85 |  |  | 2012-10-19 14:24 | 2012-10-22 09:36 | 2011-10-01 | 2012-10-19 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 40 | [6 empty] | 35
87 | 8200-0087 |  | PF3 lower and support | Rigger Techs | 2 | 2.5 | 86 |  |  | 2012-10-22 09:36 | 2012-10-25 04:48 | 2011-10-01 | 2012-10-22 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 40 | [6 empty] | 35
88 | 8200-0088 |  | PF3 remove bolted support | Techs M1 | 1 | 2.5 | 87 |  |  | 2012-10-25 04:48 | 2012-10-26 14:24 | 2011-10-01 | 2012-10-25 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 20 | [6 empty] | 35
89 | 8200-0089 |  | PF3 Install new bolted support | Techs M1 | 8 | 2.5 | 88 |  |  | 2012-10-26 14:24 | 2012-11-06 19:12 | 2011-10-01 | 2012-10-26 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
90 | 8200-0090 |  | PF3 weld reinforcement | Techs W1 | 18 | 2.5 | 89 |  |  | 2012-11-06 19:12 | 2012-12-02 | 2011-10-01 | 2012-11-06 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 360 | [6 empty] | 35
91 | 8200-0091 |  | PF3 Reinstall and align | Rigger Techs | 3 | 2.5 | 90 |  |  | 2012-12-02 | 2012-12-06 04:48 | 2011-10-01 | 2012-12-02 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 60 | [6 empty] | 35
92 | 8200-0092 |  | PF4, 5 lower and install 1/4" plate | Techs M1 | 12 | 2.5 | 91 |  |  | 2012-12-06 04:48 | 2012-12-23 | 2011-10-01 | 2012-12-06 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 240 | [6 empty] | 35
93 | 8200-0093 |  | PF4, 5 Install newbolts and torque | Techs M1 | 10 | 2.5 | 92 |  |  | 2012-12-23 | 2013-01-06 | 2011-10-01 | 2012-12-23 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 200 | [6 empty] | 35
94 | 8200-0094 |  | PF4 Install new clamps | Techs M1 | 12 | 2.5 | 93 |  |  | 2013-01-06 | 2013-01-22 19:12 | 2011-10-01 | 2013-01-06 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 240 | [6 empty] | 35
95 | 8200-0095 |  | PF5 U&L reconnect and Install new intersticial columns | Techs M1 | 6 | 2.5 | 94 |  |  | 2013-01-22 19:12 | 2013-01-31 04:48 | 2011-10-01 | 2013-01-22 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 120 | [6 empty] | 35
96 | 8200-0096 |  | VV Umbrella legs Weld reinforcement plates | Techs W1 | 8 | 2.5 | 95 |  |  | 2013-01-31 04:48 | 2013-02-11 09:36 | 2011-10-01 | 2013-01-31 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
97 | 8200-0097 |  | Remove exisitng hardware | Techs M1 | 5 | 2.5 | 96 |  |  | 2013-02-11 09:36 | 2013-02-18 09:36 | 2011-10-01 | 2013-02-11 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 100 | [6 empty] | 35
98 | 8200-0098 |  | Umbrella legs add reinforcement plate | Techs M1 | 8 | 2.5 | 97 |  |  | 2013-02-18 09:36 | 2013-03-01 14:24 | 2011-10-01 | 2013-02-18 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
99 | 8200-0099 |  | TF Install New Coil | Techs M1 | 5 | 5 | 98 |  |  | 2013-03-01 14:24 | 2013-03-08 14:24 | 2011-10-01 | 2013-03-01 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 |  | 50 | [14 empty] | 200 | [6 empty] | 35
100 | 8200-0100 |  | Prefit & match drill New Umbrella Lid | Techs M1 | 10 | 5 | 99 |  |  | 2013-03-08 14:24 | 2013-03-22 14:24 | 2011-10-01 | 2013-03-08 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 400 | [6 empty] | 35
101 | 8200-0101 |  | VV legs reinforcement plates | Techs M1 | 8 | 2.5 | 100 |  |  | 2013-03-22 14:24 | 2013-04-02 19:12 | 2011-10-01 | 2013-03-22 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 35
102 | 8200-0102 |  | Reinstall platform sections | Techs M1 | 8 | 5 | 101 |  |  | 2013-04-02 19:12 | 2013-04-14 | 2011-10-01 | 2013-04-02 19:12 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 320 | [6 empty] | 35
103 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
104 |  | ALIGNMENT VERIFICATION COIL AND VACUUM VESSEL | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
105 | 8200-0105 |  | Map internal targets to external | Priniski+Techs | 10 | 2.5 | 99 |  |  | 2013-03-08 14:24 | 2013-03-22 14:24 | 2011-10-01 | 2013-03-08 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 80 |  | 200 | [6 empty] | 30
106 | 8200-0106 |  | Verify Vessel Alignemnt targets | Priniski+Techs | 10 | 2.5 | 105 |  |  | 2013-03-22 14:24 | 2013-04-05 14:24 | 2011-10-01 | 2013-03-22 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 80 |  | 200 | [6 empty] | 30
107 | 8200-0107 |  | Verify Coil Alignment Targets | Priniski+Techs | 20 | 2.5 | 106 |  |  | 2013-04-05 14:24 | 2013-05-03 14:24 | 2011-10-01 | 2013-04-05 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 160 |  | 400 | [6 empty] | 30
108 | 8200-0108 |  | Adjust vessel Internals | Priniski+Techs | 30 | 2.5 | 107 |  |  | 2013-05-03 14:24 | 2013-06-14 14:24 | 2011-10-01 | 2013-05-03 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 240 |  | 600 | [6 empty] | 30
109 | 8200-0109 |  | Adjust TF Coils | Priniski+Techs | 4 | 2.5 | 108 |  |  | 2013-06-14 14:24 | 2013-06-20 04:48 | 2011-10-01 | 2013-06-14 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 32 |  | 80 | [6 empty] | 30
110 | 8200-0110 |  | Adjust PF Coils | Priniski+Techs | 6 | 2.5 | 109 |  |  | 2013-06-20 04:48 | 2013-06-28 14:24 | 2011-10-01 | 2013-06-20 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [14 empty] | 48 |  | 120 | [6 empty] | 30
111 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
112 | 8200-0112 |  | Fit and Install PF 1a, 1b, 1c U&L buswork | Techs M2 | 15 | 2.5 |  | 81 |  | 2013-01-24 04:48 | 2013-02-14 04:48 | 2011-10-01 | 2011-10-01 | 2013-01-24 04:48 | 2011-10-01 | 2011-10-01 | [16 empty] | 300 | [6 empty] | 30
113 | 8200-0113 |  | Fit and Install OH U&L buswork | Techs M2 | 15 | 2.5 | 112 |  |  | 2013-02-14 04:48 | 2013-03-07 04:48 | 2011-10-01 | 2013-02-14 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 300 | [6 empty] | 30
114 | 8200-0114 |  | Install CHI & Ring bus | Techs M2 | 8 | 2.5 | 113 |  |  | 2013-03-07 04:48 | 2013-03-18 09:36 | 2011-10-01 | 2013-03-07 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 160 | [6 empty] | 30
115 | 8200-0115 |  | Install TF coil cooling system (72) | Techs M2 | 3 | 2.5 | 114 |  |  | 2013-03-18 09:36 | 2013-03-22 14:24 | 2011-10-01 | 2013-03-18 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 60 | [6 empty] | 30
116 | 8200-0116 |  | Install Inboard Divertor heating/cooling system | Techs M2 | 15 | 2.5 | 115 |  |  | 2013-03-22 14:24 | 2013-04-12 14:24 | 2011-10-01 | 2013-03-22 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 300 | [6 empty] | 30
117 | 8200-0117 |  | New TF air cooled bus and support system | Techs M2 | 25 | 2.5 | 116 |  |  | 2013-04-12 14:24 | 2013-05-17 14:24 | 2011-10-01 | 2013-04-12 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 500 | [6 empty] | 30
118 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
119 |  | REINSTALL EQUIPMENT | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
120 | 8200-0120 |  | Gas Injection System | Techs M1 | 15 | 5 |  | 102 |  | 2013-04-14 | 2013-05-05 | 2011-10-01 | 2011-10-01 | 2013-04-14 | 2011-10-01 | 2011-10-01 | [16 empty] | 600
121 | 8200-0121 |  | Reinstall insulation | Techs M1 | 10 | 2.5 | 120 |  |  | 2013-05-05 | 2013-05-19 | 2011-10-01 | 2013-05-05 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 200 | [6 empty] | 30
122 | 8200-0122 |  | Platform areas reinstall | Techs M1 | 10 | 5 | 121 |  |  | 2013-05-19 | 2013-06-02 | 2011-10-01 | 2013-05-19 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 400 | [6 empty] | 30
123 | 8200-0123 |  | Heating Manifold Reconfigure | Techs M2 | 10 | 2.5 |  | 117 |  | 2013-05-17 14:24 | 2013-05-31 14:24 | 2011-10-01 | 2011-10-01 | 2013-05-17 14:24 | 2011-10-01 | 2011-10-01 |  | 25 | [14 empty] | 200 | [6 empty] | 30
124 | 8200-0124 |  | Reinstall RF pipes | Techs RF | 30 | 2.5 | 121 |  |  | 2013-05-19 | 2013-06-30 | 2011-10-01 | 2013-05-19 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [6 empty] | 80 | 60 |  |  |  |  | 400 |  |  |  | 1200 | [6 empty] | 10
125 | 8200-0125 |  | Reinstall electrical Tray | Techs E | 40 | 2.5 | 122 |  |  | 2013-06-02 | 2013-07-28 | 2011-10-01 | 2013-06-02 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 800 | [6 empty] | 30
126 | 8200-1004 |  | Machine original OD tiles for Diag sensors | Machine Techs | 10 | 1 | 125 |  |  | 2013-07-28 | 2013-08-11 | 2011-10-01 | 2013-07-28 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 80 | [6 empty] | 30
127 | 8200-1008 |  | Re-install Diag sensors into original OD tiles | Machine Techs | 10 | 2.5 | 126 |  |  | 2013-08-11 | 2013-08-25 | 2011-10-01 | 2013-08-11 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 200 | [6 empty] | 30
128 | 8200-1012 |  | Install original OD tiles and supports | Machine Techs | 20 | 2.5 | 126 |  |  | 2013-08-11 | 2013-09-08 | 2011-10-01 | 2013-08-11 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 400 | [6 empty] | 30
129 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
[12 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
|  | BAY BY BAY DIAGNOSTICS | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
|  | Assume 8 lower 8 midplane and 4 upper bays | [9 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
130 | 8200-0130 |  | Perform bay by bay review Elect | SM | 2 | 2.5 | 110 |  |  | 2013-06-28 14:24 | 2013-07-01 09:36 | 2011-10-01 | 2013-06-28 14:24 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [15 empty] | 40 | [7 empty] | 40
131 | 8200-0131 |  | Perform bay by bay review Mech | SM | 2 | 2.5 | 130 |  |  | 2013-07-01 09:36 | 2013-07-04 04:48 | 2011-10-01 | 2013-07-01 09:36 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [15 empty] | 40 | [7 empty] | 40
132 | 8200-0132 |  | Revise reinstallation procedures | SM | 5 | 2.5 | 131 |  |  | 2013-07-04 04:48 | 2013-07-11 04:48 | 2011-10-01 | 2013-07-04 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [15 empty] | 100 | [7 empty] | 40
133 | 8200-0133 |  | Reinstall Mech | Techs DIAG | 10 | 4 | 132 |  |  | 2013-07-11 04:48 | 2013-07-25 04:48 | 2011-10-01 | 2013-07-11 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 |  | 10 | [14 empty] | 320 | [6 empty] | 40
134 | 8200-0134 |  | Reinstall Upper and lower port Eqpt | Techs DIAG | 18 | 4 | 133 |  |  | 2013-07-25 04:48 | 2013-08-19 09:36 | 2011-10-01 | 2013-07-25 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 576 | [6 empty] | 40
135 | 8200-0135 |  | Reinstall Elect | Techs E | 10 | 2.5 | 133 |  |  | 2013-07-25 04:48 | 2013-08-08 04:48 | 2011-10-01 | 2013-07-25 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 200 | [6 empty] | 40
136 | 8200-0136 |  | Testing | Techs E | 10 | 2.5 | 135 |  |  | 2013-08-08 04:48 | 2013-08-22 04:48 | 2011-10-01 | 2013-08-08 04:48 | 2011-10-01 | 2011-10-01 | 2011-10-01 | [16 empty] | 200 | [6 empty] | 40
137 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
138 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
139 | [11 empty] | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01 | 2011-10-01
|  | TOTALS | [15 empty] | 257 | 0 | 0 | 0 | 0 | 140 | 916 | 0 | 0 | 0 | 0 | 660 | 0 | 4880 | 3332 | 25500 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 4995.0486 | [12 empty] | 302.746 | 0 | 0 | 0 | 0 | 27.0662 | 117.2938 | 0 | 0 | 0 | 0 | 83.9718 | 0 | 806.176 | 516.9598 | 3140.835 | 0 | 0 | 0 | 0 | 0
| Notes: | [25 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [8 empty] | Weeks | [15 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [7 empty] | 3 | [15 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [7 empty] | 5 | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [7 empty] | 8 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [7 empty] | 9 | [15 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
Formulas:
Calculated = IF([SCHEDULE]="","",MAX(O44:S44))

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 8200
Job Title: |  | Installation of Coil Support System
Job Manager: |  | Mike Viola
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Damage to coil insulation during removal - This is in case we accidentally nick or gouge the outer insulation. |  |  |  | VU | repair coil |  |  | Estimate based on conference with Jim Chrzanowski (coil expert) | 10 | 40 | 2 | 4
2 | Realign vacuum vessel - This is in case the vessel springs or changes shape after cutting the new port opening. This could affect the algnment of all the vessel internals mounted to the vessel wall. |  |  |  | L | Metrology |  |  | Based on the time it takes to remove and reinstall existing wall hardware during maintenance weeks | 10 | 40 | 2 | 4
3 | Realign Coils - This is in case the coils spring or change shape after releasing them from their existing clamps. This could afect the algnment of all any coil mounted to the vessel wall/ribs. |  |  |  | U | Metrology - new clamps |  |  | Based on the 6 weeks it took to align the existing coils | 10 | 40 | 2 | 4
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9417
Job Number: | 8200
Job Title: | Installation of Coil Support System
Job Manager: | Mike Viola
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS