## pivot table
Sum of FY11 estimate | Column Labels
| Labor hours | [65 empty] | Non Labor $ | [5 empty] | Grand Total
| E* | EA Designer | [13 empty] | EA Engr | [9 empty] | EC Engr |  |  |  |  | EE Engr | [10 empty] | EE Tech |  |  |  | EM Engr | [13 empty] | EM Tech |  | HP Tech | P&CO |  | Researcher |  | (blank)
Row Labels | STRYKOWSKY | **unassigned | CLARK | JARIWALA | JONES | KHODAK | MARTINELLI | MEDVED | MITCHELL | MORRIS | PALUZZI | PAUL | UPCAVAGE | VANKIRK | WINKELMAN | **unassigned | BROOKS | BRYANT | CHRZANOWSK | MYATT | PRININSKI | SIMMONS | TITUS | ZHANG | ZOLFAGHARI | HENDERS | MASSRY | MASTROV | SICHTA | TCHILIN | **unassigned | HATCHER | LAWSON | MARSALA | MOZULAY | NEUMEYER | RAKI | STEVENSON | VONHALLE | WOOLLEY | ZHAO | CROPPER | EDWARDS | TB **unassigned | WERTENB | **unassigned | BLANCHARD | DENAULT | DODSON | DUDEK | GENTILE | KOZUB | LABIK | PERRY | PRINISKI | SMITH | TRESEMER | VIOLA | WILLARD | **unassigned | NBI TECH | HP TECH | EGEBO | GUZMAN | KAITA | LEBLANC | 31 overtime | 35 travel | 39 other | 41 M&S | 41 S/C | 54 allocations
Job: 1000 - CSU Analytical Support-TITUS (LOE) | [22 empty] | 687 | [49 empty] | 687
Job: 1001 - CS Plasma Facing Components-TRESEMER |  |  |  | 2024.5 | [12 empty] | 350 | [5 empty] | 16 | [33 empty] | 675.6 |  |  | 800.9 | [9 empty] | 15601.7 |  |  | 19468.7
Job: 1002 -Passive Plate Analysis &Upgrade-TITUS | [22 empty] | 352 | [46 empty] | 919.9 |  |  | 1271.9
Job: 1201 - Outer TF Structures-SMITH | [6 empty] | 320.4 | [16 empty] | 406.8 | [31 empty] | 126.6 | [16 empty] | 853.8
Job: 1202 - Outer PF2 Coil Structures-SMITH | [6 empty] | 67.6 | [15 empty] | 24 | [32 empty] | 15 | [16 empty] | 106.6
Job: 1203 - PF3 Support.-SMITH | [6 empty] | 27.4 | [15 empty] | 23.9 | [32 empty] | 8.6 | [16 empty] | 59.9
Job: 1204 - PF4/5 Leads & Radial Supports-SMITH | [6 empty] | 26 | [15 empty] | 24 | [32 empty] | 8.3 | [16 empty] | 58.3
Job: 1205 - Umbrella-SMITH | [6 empty] | 512.5 | [15 empty] | 30 | 294.4 | [31 empty] | 254.2 | [16 empty] | 1091.1
Job: 1206 - Pedestal -SMITH | [6 empty] | 198.7 | [15 empty] | 30 | [32 empty] | 130.9 | [16 empty] | 359.6
Job: 1207 - Vessel Legs -SMITH | [6 empty] | 29.4 | [15 empty] | 8.2 | [32 empty] | 10 | [16 empty] | 47.6
Job: 1208 - PF4&5 Verticle Support-SMITH | [6 empty] | 443.8 | [15 empty] | 169 | [32 empty] | 87.1 | [16 empty] | 699.9
Job: 1220 - Misc Structural Design-SMITH | [33 empty] | 25.9 | [21 empty] | 644.1 |  |  | 320 | [13 empty] | 990
Job: 1300 - Center Stack-CHRZANOWSKI | [11 empty] | 172.3 | [6 empty] | 1278.5 | [53 empty] | 1450.8
Job: 1303 - R&D for TF Joint -KOZUB | [11 empty] | 159.9 | [31 empty] | 58.5 | [7 empty] | 811.1 | [7 empty] | 234.6 | [9 empty] | 80000 |  |  | 81264.1
Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | [11 empty] | 385.3 | [10 empty] | 182 |  | 264.3 | [34 empty] | 60 | [7 empty] | 5000 |  | 578368 |  |  | 584259.6
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI |  |  |  |  | 240 | [6 empty] | 40 | 1894.4 | [9 empty] | 40.2 |  | 166.5 | [34 empty] | 944.2 | [9 empty] | 357 |  |  | 3682.3
Job: 1306 - Inner PF Coils-CHRZANOWSKI |  | 60 | [7 empty] | 356.7 | [9 empty] | 199.6 | [52 empty] | 616.3
Job: 1307 - CS Casing Assembly -CHRZANOWSKI | [9 empty] | 260 | [6 empty] | 168.6 | [5 empty] | 37 | [49 empty] | 465.6
Job: 2300 - ECH Analysis-TITUS | [17 empty] | 99.9 |  |  |  |  | 210 | [49 empty] | 309.9
Job: 2420 - 2nd NBI Sources-CROPPER | [41 empty] | 24 | [30 empty] | 24
Job: 2425 - BL Relocation-DENAULT | [8 empty] | 80 | [13 empty] | 80 | [7 empty] | 39.9 | [16 empty] | 196 | [24 empty] | 395.9
Job: 2440 - 2nd NBI Beamline-DENAULT | [8 empty] | 233.4 | [33 empty] | 381.4 | 68.3 |  |  |  | 432.4 | [11 empty] | 751.2 | 1365.2 | [8 empty] | 102107.8 |  |  | 105339.7
Job: 2450 - 2nd NBI Services-DENAULT | [8 empty] | 80.1 | [13 empty] | 80 | [7 empty] | 80.1 | [16 empty] | 315.9 | [24 empty] | 556.1
Job: 2460 - 2nd NBI Armor-PRINISKI | [14 empty] | 171.9 | [5 empty] | 20 |  | 188 | [31 empty] | 360.5 | [12 empty] | 6000 |  |  |  |  | 6740.4
Job: 2470 - 2nd NBI Power-RAKI |  |  | 112.6 | [33 empty] | 134.7 | [35 empty] | 247.3
Job: 2475 - 2nd NBI Controls-CROPPER |  | 319.9 | [39 empty] | 1266.4 | [30 empty] | 1586.3
Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | [14 empty] | 357.1 | [5 empty] | 56 |  | 40 | [31 empty] | 263.2 |  |  |  |  | 99.9 | [7 empty] | 10533.2 |  | 4999.9 |  |  | 16349.3
Job: 2485 - Vacuum Pumping System-PRINISKI | [14 empty] | 177.7 | [5 empty] | 80 |  | 45.4 | [31 empty] | 67.4 | [17 empty] | 370.5
Job: 2490 - NTC Equipt Relocations-PERRY |  | 16 | [67 empty] | 235.3 |  |  | 251.3
Job: 3200 - Water Cooling System Mods-DENAULT | [8 empty] | 80 | [13 empty] | 40.1 | [7 empty] | 20 | [16 empty] | 236 | [24 empty] | 376.1
Job: 3300 - Bakeout System Mods for CSU-RAKI | [13 empty] | 16 | [22 empty] | 16 | [35 empty] | 32
Job: 3400 - Gas Delivery System Mods-BLANCHARD | [11 empty] | 79.9 | [34 empty] | 178 | [25 empty] | 257.9
Job: 4100 - Center Stack Diagnostics-KAITA | [7 empty] | 120 | [22 empty] | 244 | [12 empty] | 20 |  |  |  |  | 164 | [10 empty] | 20 |  |  |  |  | 20 | [7 empty] | 588
Job: 4500 - MPTS VV Modification-Labik | [7 empty] | 1362.5 | [14 empty] | 180 | [29 empty] | 811.5 | [5 empty] | 712 | 540 | [5 empty] | 207.4 | [6 empty] | 3813.4
Job: 5000 - CSU Power Systems-RAKI | [13 empty] | 1245.3 | [19 empty] | 64 |  |  | 574.3 |  |  |  | 123 | [29 empty] | 10244.9 |  | 12251.5
Job: 5200 - Digital Coil Protection-HATCHER | [15 empty] | 8 | [6 empty] | 240 | [5 empty] | 78 |  |  | 880.4 | 328 |  | 338 |  |  |  |  | 186.1 | [32 empty] | 2058.5
Job: 5501 - Coil Bus Runs-SMITH | [5 empty] | 86.7 |  |  |  |  | 837.7 | [11 empty] | 120 | [7 empty] | 54.9 | [24 empty] | 340.8 | [16 empty] | 1440.1
Job: 6100 - Control Sys Data Acquisition -SICHTA |  | 24 | [11 empty] | 160 | [11 empty] | 16 | 200 | 80.1 | 270.6 | 56 | [14 empty] | 204.1 | [27 empty] | 1010.8
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | 1726.2 | [7 empty] | 862.9 | [12 empty] | 517.1 | [31 empty] | 517.1 | [8 empty] | 690.2 | 862.9 |  |  |  | 6000 |  | 30000 | 20000 |  | 61176.4
Job: 7200 - Center Stack Management-DUDEK | [35 empty] | 431.1 | [9 empty] | 621.1 |  |  |  | 777.3 | [17 empty] | 5000 | 10900 |  |  |  | 17729.5
Job: 7300 - NB2 Management-STEVENSON | [30 empty] | 960 | [6 empty] | 568.9 | 84.8 | [33 empty] | 1613.7
Job: 7400 - Health Physics Support-STEVENSON | [61 empty] | 2400 |  |  |  |  | 100000 |  |  | 20000 |  |  | 122400
JOB: 7700 - NSTX-U HP Allocations-STRYKOWSKY | [71 empty] | 214000 | 214000
Job: 7710 - Upgrade Allocations-STRYKOWSKY | [71 empty] | 18000 | 18000
Job: 7900 - Integrated System Test-GENTILE | [50 empty] | 10.9 | [21 empty] | 10.9
Job; 8200 - CS & Coil Sprt Struc Install- VIOLA | [57 empty] | 270.3 | [14 empty] | 270.3
Grand Total | 1726.2 | 419.9 | 112.6 | 2024.5 | 240 | 86.7 | 1625.8 | 1482.5 | 1336.4 | 616.7 | 837.7 | 837.4 | 1894.4 | 1421.3 | 706.7 | 8 | 518.6 | 99.9 | 1278.5 | 199.6 | 156 | 517.1 | 2846.8 | 701.2 | 430.8 | 16 | 200 | 80.1 | 348.6 | 56 | 1398.9 | 880.4 | 328 | 89.9 | 338 | 431.1 | 725 | 568.9 | 84.8 | 186.1 | 123 | 1290.4 | 381.4 | 146.8 | 204.1 | 621.1 | 178 | 1180.3 | 164 | 777.3 | 10.9 | 811.1 | 811.5 | 517.1 | 691.1 | 1625.6 | 675.6 | 270.3 | 1032 | 3450.8 | 1365.2 | 2400 | 690.2 | 862.9 | 20 | 207.4 | 100000 | 32533.2 | 10900 | 832589.6 | 30244.9 | 232000 | 1286632.9

## detail by month
Job | ACC | resource | division | ACT ID | name | FY11 estimate | OCT FY11 | NOV FY11 | DEC FY11 | JAN FY11 | FEB FY11 | MAR FY11 | APR FY11 | MAY FY11 | JUN FY11 | JUL FY11 | AUG FY11 | SEP FY11 | OCT FY12 | NOV FY12
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | STRYKOWSKY - | Labor hours | E* | STRYKOWSKY | STRYKOWSKY | 1726.2 | 145 | 138.1 | 117.4 | 145 | 138.1 | 158.8 | 145 | 145 | 151.9 | 138.1 | 158.8 | 145 | 145.6 | 138.6
Job: 2475 - 2nd NBI Controls-CROPPER | DESIGNER - designer | Labor hours | EA Designer | DESIGNER | **unassigned | 319.9 | 16 | 43.7 | 37.2 | 45.9 | 43.7 | 50.3 | 45.9 | 37.2
Job: 2490 - NTC Equipt Relocations-PERRY | EA//SB - Designer TBD | Labor hours | EA Designer | EA//SB | **unassigned | 16 | [11 empty] | 16 | 168 | 160
Job: 6100 - Control Sys Data Acquisition -SICHTA | EA//SB - Designer TBD | Labor hours | EA Designer | EA//SB | **unassigned | 24 |  |  | 7.2 | 16.8
Job: 1306 - Inner PF Coils-CHRZANOWSKI | EA//EC - EA Engr TBD | Labor hours | EA Designer | EA//EC | **unassigned | 60 |  |  |  |  | 60
Job: 2470 - 2nd NBI Power-RAKI | CLARK - Designer Elect | Labor hours | EA Designer | CLARK | CLARK | 112.6 | 6.1 | 5.8 | 4.9 | 13.4 | 12.8 | 14.7 | 13.4 | 13.4 | 9.5 | 5.8 | 6.7 | 6.1 | 6.1 | 5.8
Job: 1001 - CS Plasma Facing Components-TRESEMER | JARIWALA - Designer ProE | Labor hours | EA Designer | JARIWALA | JARIWALA | 2024.5 | 55.6 | 125 | 100.4 | 211.3 | 190.9 | 253.9 | 98.9 | 291.3 | 345.7 | 148.9 | 105.9 | 96.7 | 96.7 | 92.1
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | JONES - Designer Elect | Labor hours | EA Designer | JONES | JONES | 240 |  |  |  | 126 | 114
Job: 5501 - Coil Bus Runs-SMITH | KHODAK - | Labor hours | EA Designer | KHODAK | KHODAK | 86.7 | 11.4 | 38.6 | 32.8 | 3.9
Job: 1204 - PF4/5 Leads & Radial Supports-SMITH | MARTINELLI - Designer ProE | Labor hours | EA Designer | MARTINELLI | MARTINELLI | 26 | 6.5 | 1.4 | 1.2 | 1.5 | 1.4 | 0.1 | 1.3 | 8.9 | 3.7
Job: 1203 - PF3 Support.-SMITH | MARTINELLI - Designer ProE | Labor hours | EA Designer | MARTINELLI | MARTINELLI | 27.4 | 7.2 | 1.7 | 1.5 | 1.8 | 0.6 | 0.3 | 0.3 | 10.4 | 3.6
Job: 1207 - Vessel Legs -SMITH | MARTINELLI - Designer ProE | Labor hours | EA Designer | MARTINELLI | MARTINELLI | 29.4 | 6.9 | 1.9 | 1.6 | 2 | 1.9 | 0.1 |  | 11.4 | 3.6
Job: 1202 - Outer PF2 Coil Structures-SMITH | MARTINELLI - Designer ProE | Labor hours | EA Designer | MARTINELLI | MARTINELLI | 67.6 | 19.5 | 4.5 | 3.8 | 4.7 | 0.5 | 0.3 | 3.3 | 26.2 | 4.8
Job: 1206 - Pedestal -SMITH | MARTINELLI - Designer ProE | Labor hours | EA Designer | MARTINELLI | MARTINELLI | 198.7 | 19.2 | 11.8 | 10.1 | 12.4 | 11.8 | 37.1 | 29.3 | 38.2 | 28.8
Job: 1201 - Outer TF Structures-SMITH | MARTINELLI - Designer ProE | Labor hours | EA Designer | MARTINELLI | MARTINELLI | 320.4 | 64 | 10.9 | 9.3 | 11.5 | 20.6 | 68.3 | 34 | 101.8
Job: 1208 - PF4&5 Verticle Support-SMITH | MARTINELLI - Designer ProE | Labor hours | EA Designer | MARTINELLI | MARTINELLI | 443.8 | 29.4 | 15.8 | 13.4 | 16.5 | 47.7 | 70.5 | 64.4 | 43.9 | 142.2
Job: 1205 - Umbrella-SMITH | MARTINELLI - Designer ProE | Labor hours | EA Designer | MARTINELLI | MARTINELLI | 512.5 | 49.5 | 33.8 | 28.7 | 35.5 | 47.1 | 115.7 | 49.2 | 153
Job: 4100 - Center Stack Diagnostics-KAITA | MEDVED - Designer ProE | Labor hours | EA Designer | MEDVED | MEDVED | 120 | [5 empty] | 72.6 | 47.4
Job: 4500 - MPTS VV Modification-Labik | MEDVED - Designer ProE | Labor hours | EA Designer | MEDVED | MEDVED | 1362.5 | 163.5 | 34.5 | 40.5 | 220.5 | 224 | 162.4 | 125.9 | 93.8 | 161.4 | 116 | 2.2 | 17.8
Job: 2425 - BL Relocation-DENAULT | MITCHELL - Designer ProE | Labor hours | EA Designer | MITCHELL | MITCHELL | 80 | 12 | 17.2 | 14.6 | 18.1 | 17.2 | 0.9
Job: 3200 - Water Cooling System Mods-DENAULT | MITCHELL - Designer ProE | Labor hours | EA Designer | MITCHELL | MITCHELL | 80 |  |  | 45.3 | 34.7
Job: 2450 - 2nd NBI Services-DENAULT | MITCHELL - Designer ProE | Labor hours | EA Designer | MITCHELL | MITCHELL | 80.1 | 16 | 19.4 | 16.5 | 20.4 | 7.8
Job: 2440 - 2nd NBI Beamline-DENAULT | MITCHELL - Designer ProE | Labor hours | EA Designer | MITCHELL | MITCHELL | 233.4 | 72 | 14.1 | 12 | 14.8 | 14.1 | 16.2 | 14.8 | 14.8 | 15.5 | 14.1 | 16.2 | 14.8 | 14.8 | 14.1
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | MITCHELL - Designer ProE | Labor hours | EA Designer | MITCHELL | MITCHELL | 862.9 | 72.5 | 69 | 58.7 | 72.5 | 69 | 79.4 | 72.5 | 72.5 | 75.9 | 69 | 79.4 | 72.5 | 72.8 | 69.3
Job: 1307 - CS Casing Assembly -CHRZANOWSKI | MORRIS - Designer ProE | Labor hours | EA Designer | MORRIS | MORRIS | 260 |  |  |  |  | 98.3 | 113.1 | 48.6
Job: 1306 - Inner PF Coils-CHRZANOWSKI | MORRIS - Designer ProE | Labor hours | EA Designer | MORRIS | MORRIS | 356.7 | 62.4 | 69.3 | 58.9 | 72.8 | 69.3 | 24
Job: 5501 - Coil Bus Runs-SMITH | PALUZZI - Designer ProE | Labor hours | EA Designer | PALUZZI | PALUZZI | 837.7 | 106.7 | 88.9 | 75.6 | 92.8 | 58.7 | 108.9 | 177.6 | 128.5
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | PAUL - Designer ProE | Labor hours | EA Designer | PAUL | PAUL | 40 | [7 empty] | 12 | 28
Job: 3400 - Gas Delivery System Mods-BLANCHARD | PAUL - Designer ProE | Labor hours | EA Designer | PAUL | PAUL | 79.9 |  |  |  | 27.5 | 26.2 | 26.2
Job: 1303 - R&D for TF Joint -KOZUB | PAUL - Designer ProE | Labor hours | EA Designer | PAUL | PAUL | 159.9 | 64 | 13.8 | 11.7 | 14.5 | 13.8 | 15.9 | 14.5 | 11.7
Job: 1300 - Center Stack-CHRZANOWSKI | PAUL - Designer ProE | Labor hours | EA Designer | PAUL | PAUL | 172.3 | 25.3 | 24.1 | 20.5 | 25.3 | 24.1 | 27.7 | 25.3
Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | PAUL - Designer ProE | Labor hours | EA Designer | PAUL | PAUL | 385.3 | 65.3 | 39.2 | 33.3 | 41.1 | 39.2 | 45 | 41.1 | 41.1 | 40
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | UPCAVAGE - Designer ProE | Labor hours | EA Designer | UPCAVAGE | UPCAVAGE | 1894.4 | 181.3 | 83 | 63.8 | 320.8 | 361 | 315.6 | 274.8 | 220.8 | 73.3
Job: 3300 - Bakeout System Mods for CSU-RAKI | VANKIRK - Designer Elect | Labor hours | EA Designer | VANKIRK | VANKIRK | 16 |  |  |  |  | 4.3 | 4.9 | 4.5 | 2.3
Job: 6100 - Control Sys Data Acquisition -SICHTA | VANKIRK - Designer Elect | Labor hours | EA Designer | VANKIRK | VANKIRK | 160 |  |  |  |  | 76 | 84
Job: 5000 - CSU Power Systems-RAKI | VANKIRK - Designer Elect | Labor hours | EA Designer | VANKIRK | VANKIRK | 1245.3 | 15.3 | 14.6 | 145.8 | 199.6 | 190.1 | 215 | 116.6 | 97.8 | 91.6 | 49.7 | 57.1 | 52.1 | 93.3 | 90.9
Job: 2460 - 2nd NBI Armor-PRINISKI | WINKELMAN - Designer ProE | Labor hours | EA Designer | WINKELMAN | WINKELMAN | 171.9 | 29.8 | 5.9 | 11.6 | 12.3 | 5.7 | 4.9 | 1.7 |  | 24 | 76
Job: 2485 - Vacuum Pumping System-PRINISKI | WINKELMAN - Designer ProE | Labor hours | EA Designer | WINKELMAN | WINKELMAN | 177.7 | 21.1 | 6.6 | 5.6 | 7 | 6.6 | 39.6 | 5.6 | 5.6 | 20 | 60
Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | WINKELMAN - Designer ProE | Labor hours | EA Designer | WINKELMAN | WINKELMAN | 357.1 | 108.7 | 28.7 | 24.4 | 30.1 | 28.7 | 21.7 | 14.8 |  | 6.1 | 60.6 | 33.3
Job: 5200 - Digital Coil Protection-HATCHER | EA//EM - EA Engr TBD | Labor hours | EA Engr | EA//EM | **unassigned | 8 |  |  |  | 8
Job: 1307 - CS Casing Assembly -CHRZANOWSKI | BROOKS - EA Engr | Labor hours | EA Engr | BROOKS | BROOKS | 168.6 | 52.6 | 80.3 | 27 | 8.7
Job: 1001 - CS Plasma Facing Components-TRESEMER | BROOKS - EA Engr | Labor hours | EA Engr | BROOKS | BROOKS | 350 | 78 | 64 | 58.7 | 112 | 37.3
Job: 2300 - ECH Analysis-TITUS | BRYANT - EA Engr | Labor hours | EA Engr | BRYANT | BRYANT | 99.9 | [5 empty] | 32.8 | 31.3 | 31.3 | 4.5
Job: 1300 - Center Stack-CHRZANOWSKI | CHRZANOWSKI - EA Engr | Labor hours | EA Engr | CHRZANOWSK | CHRZANOWSK | 1278.5 | 108.3 | 103.1 | 87.7 | 108.3 | 103.1 | 118.6 | 108.3 | 106.2 | 111.3 | 101.1 | 116.3 | 106.2 | 106.2 | 101.1
Job: 1306 - Inner PF Coils-CHRZANOWSKI | MYATT - EA Engr | Labor hours | EA Engr | MYATT | MYATT | 199.6 | 19.7 | 53.3 | 45.3 | 73.3 | 8
Job: 2460 - 2nd NBI Armor-PRINISKI | PRININSKI - | Labor hours | EA Engr | PRININSKI | PRININSKI | 20 | [8 empty] | 20
Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | PRININSKI - | Labor hours | EA Engr | PRININSKI | PRININSKI | 56 | [7 empty] | 2.8 | 53.2
Job: 2485 - Vacuum Pumping System-PRINISKI | PRININSKI - | Labor hours | EA Engr | PRININSKI | PRININSKI | 80 | [8 empty] | 20 | 60
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | SIMMONS - EA Engr | Labor hours | EA Engr | SIMMONS | SIMMONS | 517.1 | 43.4 | 41.4 | 35.2 | 43.4 | 41.4 | 47.6 | 43.4 | 43.4 | 45.5 | 41.4 | 47.6 | 43.4 | 29.1 | 27.7
Job: 1207 - Vessel Legs -SMITH | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 8.2 | 4 | 0.7 | 0.6 | 0.7 | 0.7 | 0.8 | 0.7
Job: 1001 - CS Plasma Facing Components-TRESEMER | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 16 | [8 empty] | 16
Job: 1203 - PF3 Support.-SMITH | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 23.9 | 2.4 | 3.5 | 3 | 3.7 | 3.5 | 4.1 | 3.7
Job: 1202 - Outer PF2 Coil Structures-SMITH | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 24 | 2.4 | 3.6 | 3.1 | 3.8 | 3.6 | 4.2 | 3.3
Job: 1204 - PF4/5 Leads & Radial Supports-SMITH | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 24 | 12 | 2.1 | 1.8 | 2.3 | 2.1 | 2.5 | 1.2
Job: 1205 - Umbrella-SMITH | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 30 | [6 empty] | 30
Job: 1206 - Pedestal -SMITH | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 30 | [6 empty] | 15 | 15
Job: 1307 - CS Casing Assembly -CHRZANOWSKI | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 37 | 7 | 10.3 | 8.8 | 10.9
Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 40 | [6 empty] | 8 | 32
Job: 3200 - Water Cooling System Mods-DENAULT | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 40.1 |  |  |  | 4 | 9.9 | 11.4 | 10.4 | 4.4
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 40.2 | 20 | 4 | 3.4 | 4.2 | 4 | 4.6
Job: 2485 - Vacuum Pumping System-PRINISKI | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 45.4 | 19.5 | 5.1 | 4.4 | 5.4 | 5.1 | 5.9
Job: 2425 - BL Relocation-DENAULT | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 80 | 12 | 17.2 | 14.6 | 18.1 | 17.2 | 0.9
Job: 2450 - 2nd NBI Services-DENAULT | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 80 |  |  |  |  | 80
Job: 5501 - Coil Bus Runs-SMITH | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 120 |  |  |  | 91.2 | 28.8
Job: 1208 - PF4&5 Verticle Support-SMITH | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 169 | 38.9 | 31.3 | 26.6 | 32.8 | 9.4 |  |  | 30
Job: 4500 - MPTS VV Modification-Labik | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 180 | [5 empty] | 60 |  |  |  | 80 | 4.4 | 35.6
Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 182 | 20.1 | 26.6 | 22.6 | 53.2 | 48.8 | 10.7
Job: 2460 - 2nd NBI Armor-PRINISKI | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 188 | [5 empty] | 25.6 | 67.2 | 67.2 | 9 | 19
Job: 2300 - ECH Analysis-TITUS | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 210 | 10 | 45.6 | 38.7 | 47.8 | 45.6 | 2.3 |  |  | 20
Job: 5200 - Digital Coil Protection-HATCHER | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 240 |  | 24 | 40.8 | 50.4 | 48 | 55.2 | 21.6 | [5 empty] | 56 | 53.3
Job: 1002 -Passive Plate Analysis &Upgrade-TITUS | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 352 | 58.1 | 78.4 | 66.6 | 61.2 | 56.4 | 31.3
Job: 1000 - CSU Analytical Support-TITUS (LOE) | TITUS - EA Engr | Labor hours | EA Engr | TITUS | TITUS | 687 | 68.2 | 87.5 | 74.4 | 91.9 | 84.9 | 40.9 | 31.9 | 71.5 | 65.4 | 22 | 25.3 | 23.1 | 23.1 | 22
Job: 1205 - Umbrella-SMITH | ZHANG - EA Engr | Labor hours | EA Engr | ZHANG | ZHANG | 294.4 | 42.4 | 68.1 | 57.9 | 71.5 | 54.5
Job: 1201 - Outer TF Structures-SMITH | ZHANG - EA Engr | Labor hours | EA Engr | ZHANG | ZHANG | 406.8 | 114.2 | 71 | 60.3 | 74.5 | 56.8 |  | 30
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | ZOLFAGHARI - EA Engr | Labor hours | EA Engr | ZOLFAGHARI | ZOLFAGHARI | 166.5 | 36.5 | 68.3 | 40.6 | 8.4 | 5.9 | 6.8
Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | ZOLFAGHARI - EA Engr | Labor hours | EA Engr | ZOLFAGHARI | ZOLFAGHARI | 264.3 | 74.4 | 76.2 | 22.3 | 59 | 32.4
Job: 6100 - Control Sys Data Acquisition -SICHTA | HENDERS - EC Engr | Labor hours | EC Engr | HENDERS | HENDERS | 16 | [5 empty] | 1.1 | 11.2 | 3.7
Job: 6100 - Control Sys Data Acquisition -SICHTA | MASSRY - EC Engr | Labor hours | EC Engr | MASSRY | MASSRY | 200 |  |  | 4.8 | 33.6 | 77.6 | 84
Job: 6100 - Control Sys Data Acquisition -SICHTA | MASTROV - EC Engr | Labor hours | EC Engr | MASTROV | MASTROV | 80.1 |  |  |  | 7.5 | 25 | 28.8 | 18.8
Job: 5200 - Digital Coil Protection-HATCHER | SICHTA - EC Engr | Labor hours | EC Engr | SICHTA | SICHTA | 78 |  | 8 | 13.6 | 10.4 | 7.2 | 8.8 | 30
Job: 6100 - Control Sys Data Acquisition -SICHTA | SICHTA - EC Engr | Labor hours | EC Engr | SICHTA | SICHTA | 270.6 | 5 | 3.8 | 43.4 | 27.8 | 5.8 | 4.4 | 17 | 49.4 | 92.2 | 13.4 | 4.4 | 4 | 4 | 3.8
Job: 6100 - Control Sys Data Acquisition -SICHTA | TCHILIN - EC Engr | Labor hours | EC Engr | TCHILIN | TCHILIN | 56 |  |  | 4.5 | 31.4 | 11.6 | 8.5
Job: 2425 - BL Relocation-DENAULT | EE//EM - EE Engr TBD | Labor hours | EE Engr | EE//EM | **unassigned | 39.9 | 6 | 8.6 | 7.3 | 9 | 8.6 | 0.4
Job: 5501 - Coil Bus Runs-SMITH | EE//EM - EE Engr TBD | Labor hours | EE Engr | EE//EM | **unassigned | 54.9 | 3.3 | 1.8 | 1.6 | 36.7 | 11.5
Job: 3200 - Water Cooling System Mods-DENAULT | ELECT ENG - | Labor hours | EE Engr | ELECT ENG | **unassigned | 20 |  |  | 11.3 | 8.7
Job: 2450 - 2nd NBI Services-DENAULT | ELECT ENG - | Labor hours | EE Engr | ELECT ENG | **unassigned | 80.1 | 16 | 19.4 | 16.5 | 20.4 | 7.8
Job: 4100 - Center Stack Diagnostics-KAITA | ELECT ENG - | Labor hours | EE Engr | ELECT ENG | **unassigned | 244 | [5 empty] | 48.4 | 31.6 | 122.1 | 41.9
Job: 7300 - NB2 Management-STEVENSON | RLM'S - | Labor hours | EE Engr | RLM'S | **unassigned | 960 |  |  |  | 480 |  |  |  |  | 480
Job: 5200 - Digital Coil Protection-HATCHER | HATCHER - EE Engr | Labor hours | EE Engr | HATCHER | HATCHER | 880.4 |  | 116.2 | 70.5 | 122.3 | 71.5 | 63.9 | 137.5 | 106 | 53.2 | 43.5 | 50.1 | 45.7 | 101.7 | 96.9
Job: 5200 - Digital Coil Protection-HATCHER | LAWSON - EE Engr | Labor hours | EE Engr | LAWSON | LAWSON | 328 |  | 27 | 45.9 | 35.1 | 99 | 121
Job: 1220 - Misc Structural Design-SMITH | MARSALA - EE Engr | Labor hours | EE Engr | MARSALA | MARSALA | 25.9 |  | 3.2 | 2.7 | 3.3 | 3.2 | 3.7 | 3.3 | 3.3 | 3.2
Job: 5000 - CSU Power Systems-RAKI | MARSALA - EE Engr | Labor hours | EE Engr | MARSALA | MARSALA | 64 | [8 empty] | 4.6 | 18.6 | 21.3 | 19.5 | 19.5 | 18.6
Job: 5200 - Digital Coil Protection-HATCHER | MOZULAY - | Labor hours | EE Engr | MOZULAY | MOZULAY | 338 |  | 27 | 45.9 | 35.1 | 92 | 117.6 | 20.4
Job: 7200 - Center Stack Management-DUDEK | NEUMEYER - EE Engr | Labor hours | EE Engr | NEUMEYER | NEUMEYER | 431.1 | 36.2 | 34.5 | 29.3 | 36.2 | 34.5 | 39.7 | 36.2 | 36.2 | 37.9 | 34.5 | 39.7 | 36.2 | 36.9 | 35.2
Job: 3300 - Bakeout System Mods for CSU-RAKI | RAKI - EE Engr | Labor hours | EE Engr | RAKI | RAKI | 16 |  |  |  |  | 4.3 | 4.9 | 4.5 | 2.3
Job: 2470 - 2nd NBI Power-RAKI | RAKI - EE Engr | Labor hours | EE Engr | RAKI | RAKI | 134.7 | 4.6 | 4.4 | 3.7 | 19.2 | 18.3 | 21 | 19.2 | 19.2 | 11.1 | 4.4 | 5 | 4.6 | 4.6 | 4.4
Job: 5000 - CSU Power Systems-RAKI | RAKI - EE Engr | Labor hours | EE Engr | RAKI | RAKI | 574.3 | 25.3 | 24 | 56.7 | 89.5 | 85.2 | 98 | 33.1 | 25.2 | 28.9 | 33.9 | 38.9 | 35.6 | 84.8 | 83.1
Job: 7300 - NB2 Management-STEVENSON | STEVENSON - EE Engr | Labor hours | EE Engr | STEVENSON | STEVENSON | 568.9 | 47.8 | 45.5 | 38.7 | 47.8 | 45.5 | 52.3 | 47.8 | 47.8 | 50.1 | 45.5 | 52.3 | 47.8 | 48.8 | 46.4
Job: 7300 - NB2 Management-STEVENSON | VONHALLE - EE Engr | Labor hours | EE Engr | VONHALLE | VONHALLE | 84.8 | 7.1 | 6.8 | 5.8 | 7.1 | 6.8 | 7.8 | 7.1 | 7.1 | 7.5 | 6.8 | 7.8 | 7.1 | 7.3 | 6.9
Job: 5200 - Digital Coil Protection-HATCHER | WOOLLEY - EE Engr | Labor hours | EE Engr | WOOLLEY | WOOLLEY | 186.1 |  | 52.7 | 22.7 | 28 | 26.7 | 30.7 | 25.3 | [5 empty] | 35 | 33.3
Job: 5000 - CSU Power Systems-RAKI | ZHAO - EE Engr | Labor hours | EE Engr | ZHAO | ZHAO | 123 | [8 empty] | 8.9 | 35.7 | 41 | 37.4 | 37.4 | 35.7
Job: 2420 - 2nd NBI Sources-CROPPER | CROPPER - EE SM | Labor hours | EE Tech | CROPPER | CROPPER | 24 | [7 empty] | 8.8 | 15.2
Job: 2475 - 2nd NBI Controls-CROPPER | CROPPER - EE SM | Labor hours | EE Tech | CROPPER | CROPPER | 1266.4 | 60.4 | 119.1 | 101.2 | 177.6 | 169.1 | 287.9 | 161.2 | 93 | 96.9
Job: 2440 - 2nd NBI Beamline-DENAULT | EDWARDS - EE Tech | Labor hours | EE Tech | EDWARDS | EDWARDS | 381.4 | 10 | 10.2 | 8.6 | 41.1 | 29.5 | 33.4 | 30.5 | 30.5 | 31.9 | 29 | 57.4 | 69.3 | 69.3 | 66
Job: 4100 - Center Stack Diagnostics-KAITA | EE TECH - | Labor hours | EE Tech | EE TECH | TB **unassigned | 20 | [5 empty] | 12.1 | 7.9
Job: 2440 - 2nd NBI Beamline-DENAULT | EE TECH - | Labor hours | EE Tech | EE TECH | TB **unassigned | 68.3 | [10 empty] | 35.7 | 32.6 | 32.6 | 54.7
Job: 1303 - R&D for TF Joint -KOZUB | EE//TB - EE Tech TBD | Labor hours | EE Tech | EE//TB | TB **unassigned | 58.5 | 10.6 | 8.1 | 6.9 | 8.5 | 8.1 | 9.4 | 6.9
Job: 6100 - Control Sys Data Acquisition -SICHTA | WERTENB - | Labor hours | EE Tech | WERTENB | WERTENB | 204.1 |  |  | 8.9 | 62.2 | 51 | 44.7 | 28 | 9.3
Job: 7200 - Center Stack Management-DUDEK | RLM'S - | Labor hours | EM Engr | RLM'S | **unassigned | 621.1 | 52.2 | 49.7 | 42.2 | 52.2 | 49.7 | 57.1 | 52.2 | 52.2 | 54.6 | 49.7 | 57.1 | 52.2 | 53.2 | 50.7
Job: 3400 - Gas Delivery System Mods-BLANCHARD | BLANCHARD - EM Engr | Labor hours | EM Engr | BLANCHARD | BLANCHARD | 178 | [5 empty] | 14.4 | 64.4 | 60.6 | 38.6
Job: 2425 - BL Relocation-DENAULT | DENAULT - EM Engr | Labor hours | EM Engr | DENAULT | DENAULT | 196 | 9 | 12.9 | 11 | 13.6 | 12.9 | 30 | 28 | 29.6 | 49
Job: 3200 - Water Cooling System Mods-DENAULT | DENAULT - EM Engr | Labor hours | EM Engr | DENAULT | DENAULT | 236 |  |  | 11.3 | 12.6 | 9.9 | 11.4 | 10.4 | 92.4 | 88
Job: 2450 - 2nd NBI Services-DENAULT | DENAULT - EM Engr | Labor hours | EM Engr | DENAULT | DENAULT | 315.9 | 4 | 4.8 | 4.1 | 5.1 | 121.9 | 80 |  |  | 96
Job: 2440 - 2nd NBI Beamline-DENAULT | DENAULT - EM Engr | Labor hours | EM Engr | DENAULT | DENAULT | 432.4 | 33.6 | 32.1 | 27.2 | 33.7 | 32.1 | 36.9 | 33.7 | 33.7 | 35.3 | 32.1 | 48.9 | 53.1 | 53.1 | 50.6
Job: 4100 - Center Stack Diagnostics-KAITA | DODSON - | Labor hours | EM Engr | DODSON | DODSON | 164 | [5 empty] | 24.2 | 15.8 | 44.2 | 79.8
Job: 7200 - Center Stack Management-DUDEK | DUDEK - EM Engr | Labor hours | EM Engr | DUDEK | DUDEK | 777.3 | 65.3 | 62.2 | 52.8 | 65.3 | 62.2 | 71.5 | 65.3 | 65.3 | 68.4 | 62.2 | 71.5 | 65.3 | 59.1 | 56.3
Job: 7900 - Integrated System Test-GENTILE | GENTILE - EM Engr | Labor hours | EM Engr | GENTILE | GENTILE | 10.9 | 0.9 | 0.9 | 0.7 | 0.9 | 0.9 | 1 | 0.9 | 0.9 | 1 | 0.9 | 1 | 0.9 | 0.9 | 0.9
Job: 1303 - R&D for TF Joint -KOZUB | KOZUB - EM Engr | Labor hours | EM Engr | KOZUB | KOZUB | 811.1 | 254.3 | 85.5 | 72.7 | 89.8 | 85.5 | 98.3 | 82.6 | 42.4
Job: 4500 - MPTS VV Modification-Labik | LABIK - | Labor hours | EM Engr | LABIK | LABIK | 811.5 | 105.1 | 31.8 | 30.7 | 108.4 | 105.6 | 104.2 | 56.8 | 99 | 96 | 46.9 | 5.9 | 21.1 | 4.8 | 4.6
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | PERRY - EM Engr | Labor hours | EM Engr | PERRY | PERRY | 517.1 | 43.4 | 41.4 | 35.2 | 43.4 | 41.4 | 47.6 | 43.4 | 43.4 | 45.5 | 41.4 | 47.6 | 43.4 | 72.8 | 69.3
Job: 2485 - Vacuum Pumping System-PRINISKI | PRINISKI - EM Engr | Labor hours | EM Engr | PRINISKI | PRINISKI | 67.4 | 6.5 | 2 | 1.7 | 2.1 | 2 | 10.3 | 1.4 | 1.4 | 40
Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | PRINISKI - EM Engr | Labor hours | EM Engr | PRINISKI | PRINISKI | 263.2 | 31.9 | 21 | 17.9 | 22.1 | 21 | 4.3 | 5.8 | 31.2 | 14.1 | 60.6 | 33.3
Job: 2460 - 2nd NBI Armor-PRINISKI | PRINISKI - EM Engr | Labor hours | EM Engr | PRINISKI | PRINISKI | 360.5 | 8.6 | 18.7 | 44.6 | 50.1 | 32.5 | 29.3 | 13.1 | 12.6 | 75 | 76
Job: 1204 - PF4/5 Leads & Radial Supports-SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 8.3 | 1.8 | 0.4 | 0.3 | 0.4 | 0.4 | 0 |  | 0.3 | 4.7
Job: 1203 - PF3 Support.-SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 8.6 | 1.6 | 0.3 | 0.3 | 0.3 | 0.1 |  |  | 0.6 | 5.4 |  |  |  | 12 | 0.3
Job: 1207 - Vessel Legs -SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 10 | 1.9 | 0.5 | 0.5 | 0.6 | 0.5 | 0 |  | 0.6 | 5.4
Job: 1202 - Outer PF2 Coil Structures-SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 15 | 1.9 | 0.4 | 0.3 | 0.4 | 0 |  |  | 4.8 | 7.2
Job: 1208 - PF4&5 Verticle Support-SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 87.1 | 8.9 | 4.8 | 4 | 5 | 5.4 | 6.5 | 5.9 | 0.6 | 46
Job: 1201 - Outer TF Structures-SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 126.6 | 32.4 | 15.7 | 13.4 | 16.5 | 13.7 | 6.6 | 2.3 | 26
Job: 1206 - Pedestal -SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 130.9 | 12.5 | 22.3 | 19 | 23.4 | 22.3 | 7.7 | 2.7 |  | 21
Job: 1205 - Umbrella-SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 254.2 | 37.6 | 38 | 32.3 | 39.9 | 32.2 | 10.5 | 3.7 | 60
Job: 5501 - Coil Bus Runs-SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 340.8 | 85.6 | 39 | 33.1 | 31.6 | 16.5 | 11.9 | 38.8 | 46.7 | 37.6
Job: 1220 - Misc Structural Design-SMITH | SMITH - | Labor hours | EM Engr | SMITH | SMITH | 644.1 | 81.3 | 69.9 | 59.4 | 73.4 | 63.4 | 72.6 | 66.3 | 66.3 | 91.5
Job: 1001 - CS Plasma Facing Components-TRESEMER | TRESEMER - EM Engr | Labor hours | EM Engr | TRESEMER | TRESEMER | 675.6 | 43.7 | 24.2 | 16.4 | 85.3 | 109.2 | 46.4 | 23.4 | 127.4 | 144 | 49.6 | 6 |  | 52 | 16
Job; 8200 - CS & Coil Sprt Struc Install- VIOLA | VIOLA - EM Engr | Labor hours | EM Engr | VIOLA | VIOLA | 270.3 | 22.7 | 21.6 | 18.4 | 22.7 | 21.6 | 24.9 | 22.7 | 22.7 | 23.8 | 21.6 | 24.9 | 22.7 | 22.7 | 24
Job: 1220 - Misc Structural Design-SMITH | WILLARD - EM Engr | Labor hours | EM Engr | WILLARD | WILLARD | 320 | 32 | 108.7 | 92.4 | 86.9
Job: 4500 - MPTS VV Modification-Labik | WILLARD - EM Engr | Labor hours | EM Engr | WILLARD | WILLARD | 712 | 232.1 | 86.8 | 71.6 | 88.4 | 67.9 | 18.3 | 16.7 | 26.7 | 54.2 | 49.3
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | MEIGHAN - EM Tech | Labor hours | EM Tech | MEIGHAN | **unassigned | 57.1 | 25.1 | 32
Job: 4100 - Center Stack Diagnostics-KAITA | TECH SHOP - | Labor hours | EM Tech | TECH SHOP | **unassigned | 20 | [5 empty] | 12.1 | 7.9
Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | TECH SHOP - | Labor hours | EM Tech | TECH SHOP | **unassigned | 60 | 60
Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | TECH SHOP - | Labor hours | EM Tech | TECH SHOP | **unassigned | 99.9 | 20 | 20.5 | 17.4 | 21.5 | 20.5
Job: 1303 - R&D for TF Joint -KOZUB | TECH SHOP - | Labor hours | EM Tech | TECH SHOP | **unassigned | 234.6 | 42.6 | 32.5 | 27.7 | 34.2 | 32.5 | 37.4 | 27.7
Job: 4500 - MPTS VV Modification-Labik | TECH SHOP - | Labor hours | EM Tech | TECH SHOP | **unassigned | 540 | [7 empty] | 257.1 | 282.9
Job: 2440 - 2nd NBI Beamline-DENAULT | TECH SHOP - | Labor hours | EM Tech | TECH SHOP | **unassigned | 751.2 |  | 40 | 34 | 62.3 | 59.3 | 68.2 | 62.3 | 62.3 | 65.3 | 59.3 | 119 | 119.2 | 119.2 | 137.2
Job: 1001 - CS Plasma Facing Components-TRESEMER | TECH SHOP - | Labor hours | EM Tech | TECH SHOP | **unassigned | 800.9 | 146.5 | 102.4 | 53.2 | 252.9 | 50.4 | 57.9 | 101.6 | 36
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | TECH SHOP - | Labor hours | EM Tech | TECH SHOP | **unassigned | 887.1 | 38.3 | 48.8 | [6 empty] | 230 | 300 | 270 |  | 332 | 328
Job: 2440 - 2nd NBI Beamline-DENAULT | NBI TECH - | Labor hours | EM Tech | NBI TECH | NBI TECH | 1365.2 |  |  |  | 121.8 | 116 | 133.4 | 121.8 | 121.8 | 127.6 | 116 | 229.6 | 277.2 | 277.2 | 264
Job: 7400 - Health Physics Support-STEVENSON | HP TECH - | Labor hours | HP Tech | HP TECH | HP TECH | 2400 | 201.6 | 192 | 163.2 | 201.6 | 192 | 220.8 | 201.6 | 201.6 | 211.2 | 192 | 220.8 | 201.6 | 202.4 | 192.8
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | EGEBO - | Labor hours | P&CO | EGEBO | EGEBO | 690.2 | 58 | 55.2 | 46.9 | 58 | 55.2 | 63.5 | 58 | 58 | 60.7 | 55.2 | 63.5 | 58 | 14.6 | 13.9
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | GUZMAN - | Labor hours | P&CO | GUZMAN | GUZMAN | 862.9 | 72.5 | 69 | 58.7 | 72.5 | 69 | 79.4 | 72.5 | 72.5 | 75.9 | 69 | 79.4 | 72.5 | 72.8 | 69.3
Job: 4100 - Center Stack Diagnostics-KAITA | KAITA - | Labor hours | Researcher | KAITA | KAITA | 20 | [7 empty] | 20
Job: 4500 - MPTS VV Modification-Labik | LEBLANC - | Labor hours | Researcher | LEBLANC | LEBLANC | 207.4 | 19.1 | 7.5 | 10.1 | 37.5 | 35.6 | 28.7 | 14.1 | 21 | 19.1 | 11.2 | 1.8 | 1.7
Job: 7400 - Health Physics Support-STEVENSON | 31 - | Non Labor $ |  | 31 | 31 overtime | 100000 | 8400 | 8000 | 6800 | 8400 | 8000 | 9200 | 8400 | 8400 | 8800 | 8000 | 9200 | 8400 | 8433.7 | 8032.1
Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | TRAVEL - | Non Labor $ |  | TRAVEL | 35 travel | 5000 | [7 empty] | 1461.5 | 1692.3 | 1538.5 | 307.7 |  | 1666.7 | 1666.7
Job: 2460 - 2nd NBI Armor-PRINISKI | TRAVEL - | Non Labor $ |  | TRAVEL | 35 travel | 6000 | [5 empty] | 960 | 2520 | 2520
Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | TRAVEL - | Non Labor $ |  | TRAVEL | 35 travel | 10533.2 | 933.3 | 2461.5 | 2092.3 | 2584.6 | 2461.5
Job: 7200 - Center Stack Management-DUDEK | 35 - | Non Labor $ |  | 35 | 35 travel | 5000 | 420 | 400 | 340 | 420 | 400 | 460 | 420 | 420 | 440 | 400 | 460 | 420 | 428.6 | 408.2
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | 35 - | Non Labor $ |  | 35 | 35 travel | 6000 | 504 | 480 | 408 | 504 | 480 | 552 | 504 | 504 | 528 | 480 | 552 | 504 | 506 | 481.9
Job: 7200 - Center Stack Management-DUDEK | 39 - | Non Labor $ |  | 39 | 39 other | 10900 | 915.6 | 872 | 741.2 | 915.6 | 872 | 1002.8 | 915.6 | 915.6 | 959.2 | 872 | 1002.8 | 915.6 | 934.3 | 889.8
Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | 41 - | Non Labor $ |  | 41 | 41 M&S | 4999.9 | 1000 | 1025.6 | 871.8 | 1076.9 | 1025.6
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | 41 - | Non Labor $ |  | 41 | 41 M&S | 30000 | 2520 | 2400 | 2040 | 2520 | 2400 | 2760 | 2520 | 2520 | 2640 | 2400 | 2760 | 2520 | 421.7 | 401.6
Job: 1303 - R&D for TF Joint -KOZUB | 41 - | Non Labor $ |  | 41 | 41 M&S | 80000 | 32000 | 6906.5 | 5870.5 | 7251.8 | 6906.5 | 7942.4 | 7251.8 | 5870.5
Job: 7400 - Health Physics Support-STEVENSON | CC - Credit Card | Non Labor $ |  | CC | 41 M&S | 10000 | 840 | 800 | 680 | 840 | 800 | 920 | 840 | 840 | 880 | 800 | 920 | 840 | 843.4 | 803.2
Job: 2490 - NTC Equipt Relocations-PERRY | M&S - | Non Labor $ |  | M&S | 41 M&S | 235.3 | [11 empty] | 235.3 | 2431.4 | 4444.4
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | M&S - | Non Labor $ |  | M&S | 41 M&S | 357 | 157 | 200 | [10 empty] | 2400 | 11800
Job: 1002 -Passive Plate Analysis &Upgrade-TITUS | M&S - | Non Labor $ |  | M&S | 41 M&S | 919.9 | 19.8 | 191.5 | 162.8 | 201.1 | 191.5 | 153.2
Job: 7400 - Health Physics Support-STEVENSON | M&S - | Non Labor $ |  | M&S | 41 M&S | 10000 | 840 | 800 | 680 | 840 | 800 | 920 | 840 | 840 | 880 | 800 | 920 | 840 | 843.4 | 803.2
Job: 1001 - CS Plasma Facing Components-TRESEMER | M&S - | Non Labor $ |  | M&S | 41 M&S | 15601.7 | 3251.7 | 5341.1 | 4214.9 | 826.4 | 787 | 905.1 | 275.5
Job: 2440 - 2nd NBI Beamline-DENAULT | M&S - | Non Labor $ |  | M&S | 41 M&S | 102107.8 |  | 7994 | 6794.9 | 8457.2 | 8054.4 | 9262.6 | 8457.2 | 8457.2 | 8859.9 | 8054.4 | 13384 | 14332 | 14798 | 15572
Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | M&S - | Non Labor $ |  | M&S | 41 M&S | 578368 | 13241 | 6532 | 13166 | 62766 | 59477 | 61844 | 56466 | 84954 | 95615 | 86923 | 26884 | 10500 | 83833 | 83333
Job: 5000 - CSU Power Systems-RAKI | S/C - | Non Labor $ |  | S/C | 41 S/C | 10244.9 | 863.1 | 819.4 | 696.5 | 860.3 | 819.4 | 942.3 | 860.3 | 860.3 | 901.3 | 819.4 | 942.3 | 860.3 | 860.3 | 819.4
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | REVIEWERS - | Non Labor $ |  | REVIEWERS | 41 S/C | 20000 | 1680 | 1600 | 1360 | 1680 | 1600 | 1840 | 1680 | 1680 | 1760 | 1600 | 1840 | 1680 | 1686.7 | 1606.4
Job: 7710 - Upgrade Allocations-STRYKOWSKY | 54X - | Non Labor $ |  | 54X | 54 allocations | 18000 | 1512 | 1440 | 1224 | 1512 | 1440 | 1656 | 1512 | 1512 | 1584 | 1440 | 1656 | 1512 | 168.7 | 160.6
JOB: 7700 - NSTX-U HP Allocations-STRYKOWSKY | 54X - | Non Labor $ |  | 54X | 54 allocations | 214000 | 17976 | 17120 | 14552 | 17976 | 17120 | 19688 | 17976 | 17976 | 18832 | 17120 | 19688 | 17976 | 25638 | 24417

## summary
FY11 Estimate
|  |  | Labor hours | [65 empty] | Non Labor $
|  |  | E* | EA Designer | [13 empty] | EA Engr | [9 empty] | EC Engr |  |  |  |  | EE Engr | [10 empty] | EE Tech |  |  |  | EM Engr | [13 empty] | EM Tech |  | HP Tech | P&CO |  | Researcher
|  | Row Labels | STRYKOWSKY | **unassigned | CLARK | JARIWALA | JONES | KHODAK | MARTINELLI | MEDVED | MITCHELL | MORRIS | PALUZZI | PAUL | UPCAVAGE | VANKIRK | WINKELMAN | **unassigned | BROOKS | BRYANT | CHRZANOWSK | MYATT | PRININSKI | SIMMONS | TITUS | ZHANG | ZOLFAGHARI | HENDERS | MASSRY | MASTROV | SICHTA | TCHILIN | **unassigned | HATCHER | LAWSON | MARSALA | MOZULAY | NEUMEYER | RAKI | STEVENSON | VONHALLE | WOOLLEY | ZHAO | CROPPER | EDWARDS | TB **unassigned | WERTENB | **unassigned | BLANCHARD | DENAULT | DODSON | DUDEK | GENTILE | KOZUB | LABIK | PERRY | PRINISKI | SMITH | TRESEMER | VIOLA | WILLARD | **unassigned | NBI TECH | HP TECH | EGEBO | GUZMAN | KAITA | LEBLANC | 31 overtime | 35 travel | 39 other | 41 M&S | 41 S/C | 54 allocations
Center Stack | Blanchard | Job: 3400 - Gas Delivery System Mods-BLANCHARD | [11 empty] | 79.9 | [34 empty] | 178
Center Stack | Chrzanowski | Job: 1300 - Center Stack-CHRZANOWSKI | [11 empty] | 172.3 | [6 empty] | 1278.5
Center Stack | Chrzanowski | Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | [11 empty] | 385.3 | [10 empty] | 182 |  | 264.3 | [34 empty] | 60 | [7 empty] | 5000 |  | 578368
Center Stack | Chrzanowski | Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI |  |  |  |  | 240 | [6 empty] | 40 | 1894.4 | [9 empty] | 40.2 |  | 166.5 | [34 empty] | 944.2 | [9 empty] | 357
Center Stack | Chrzanowski | Job: 1306 - Inner PF Coils-CHRZANOWSKI |  | 60 | [7 empty] | 356.7 | [9 empty] | 199.6
Center Stack | Chrzanowski | Job: 1307 - CS Casing Assembly -CHRZANOWSKI | [9 empty] | 260 | [6 empty] | 168.6 | [5 empty] | 37
Neutral Beam | Cropper | Job: 2420 - 2nd NBI Sources-CROPPER | [41 empty] | 24
Neutral Beam | Cropper | Job: 2475 - 2nd NBI Controls-CROPPER |  | 319.9 | [39 empty] | 1266.4
Neutral Beam | Denault | Job: 2425 - BL Relocation-DENAULT | [8 empty] | 80 | [13 empty] | 80 | [7 empty] | 39.9 | [16 empty] | 196
Neutral Beam | Denault | Job: 2440 - 2nd NBI Beamline-DENAULT | [8 empty] | 233.4 | [33 empty] | 381.4 | 68.3 |  |  |  | 432.4 | [11 empty] | 751.2 | 1365.2 | [8 empty] | 102107.8
Neutral Beam | Denault | Job: 2450 - 2nd NBI Services-DENAULT | [8 empty] | 80.1 | [13 empty] | 80 | [7 empty] | 80.1 | [16 empty] | 315.9
Center Stack | Denault | Job: 3200 - Water Cooling System Mods-DENAULT | [8 empty] | 80 | [13 empty] | 40.1 | [7 empty] | 20 | [16 empty] | 236
Management | Dudek | Job: 7200 - Center Stack Management-DUDEK | [35 empty] | 431.1 | [9 empty] | 621.1 |  |  |  | 777.3 | [17 empty] | 5000 | 10900
Center Stack | Gentile | Job: 7900 - Integrated System Test-GENTILE | [50 empty] | 10.9
Center Stack | Hatcher | Job: 5200 - Digital Coil Protection-HATCHER | [15 empty] | 8 | [6 empty] | 240 | [5 empty] | 78 |  |  | 880.4 | 328 |  | 338 |  |  |  |  | 186.1
Center Stack | Kaita | Job: 4100 - Center Stack Diagnostics-KAITA | [7 empty] | 120 | [22 empty] | 244 | [12 empty] | 20 |  |  |  |  | 164 | [10 empty] | 20 |  |  |  |  | 20
Center Stack | Kozub | Job: 1303 - R&D for TF Joint -KOZUB | [11 empty] | 159.9 | [31 empty] | 58.5 | [7 empty] | 811.1 | [7 empty] | 234.6 | [9 empty] | 80000
Center Stack | Labik | Job: 4500 - MPTS VV Modification-Labik | [7 empty] | 1362.5 | [14 empty] | 180 | [29 empty] | 811.5 | [5 empty] | 712 | 540 | [5 empty] | 207.4
Neutral Beam | Perry | Job: 2490 - NTC Equipt Relocations-PERRY |  | 16 | [67 empty] | 235.3
Neutral Beam | Priniski | Job: 2460 - 2nd NBI Armor-PRINISKI | [14 empty] | 171.9 | [5 empty] | 20 |  | 188 | [31 empty] | 360.5 | [12 empty] | 6000
Neutral Beam | Priniski | Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | [14 empty] | 357.1 | [5 empty] | 56 |  | 40 | [31 empty] | 263.2 |  |  |  |  | 99.9 | [7 empty] | 10533.2 |  | 4999.9
Neutral Beam | Priniski | Job: 2485 - Vacuum Pumping System-PRINISKI | [14 empty] | 177.7 | [5 empty] | 80 |  | 45.4 | [31 empty] | 67.4
Neutral Beam | Raki | Job: 2470 - 2nd NBI Power-RAKI |  |  | 112.6 | [33 empty] | 134.7
Center Stack | Raki | Job: 3300 - Bakeout System Mods for CSU-RAKI | [13 empty] | 16 | [22 empty] | 16
Center Stack | Raki | Job: 5000 - CSU Power Systems-RAKI | [13 empty] | 1245.3 | [19 empty] | 64 |  |  | 574.3 |  |  |  | 123 | [29 empty] | 10244.9
Center Stack | Sichta | Job: 6100 - Control Sys Data Acquisition -SICHTA |  | 24 | [11 empty] | 160 | [11 empty] | 16 | 200 | 80.1 | 270.6 | 56 | [14 empty] | 204.1
Center Stack | Smith | Job: 1201 - Outer TF Structures-SMITH | [6 empty] | 320.4 | [16 empty] | 406.8 | [31 empty] | 126.6
Center Stack | Smith | Job: 1202 - Outer PF2 Coil Structures-SMITH | [6 empty] | 67.6 | [15 empty] | 24 | [32 empty] | 15
Center Stack | Smith | Job: 1203 - PF3 Support.-SMITH | [6 empty] | 27.4 | [15 empty] | 23.9 | [32 empty] | 8.6
Center Stack | Smith | Job: 1204 - PF4/5 Leads & Radial Supports-SMITH | [6 empty] | 26 | [15 empty] | 24 | [32 empty] | 8.3
Center Stack | Smith | Job: 1205 - Umbrella-SMITH | [6 empty] | 512.5 | [15 empty] | 30 | 294.4 | [31 empty] | 254.2
Center Stack | Smith | Job: 1206 - Pedestal -SMITH | [6 empty] | 198.7 | [15 empty] | 30 | [32 empty] | 130.9
Center Stack | Smith | Job: 1207 - Vessel Legs -SMITH | [6 empty] | 29.4 | [15 empty] | 8.2 | [32 empty] | 10
Center Stack | Smith | Job: 1208 - PF4&5 Verticle Support-SMITH | [6 empty] | 443.8 | [15 empty] | 169 | [32 empty] | 87.1
Center Stack | Smith | Job: 1220 - Misc Structural Design-SMITH | [33 empty] | 25.9 | [21 empty] | 644.1 |  |  | 320
Center Stack | Smith | Job: 5501 - Coil Bus Runs-SMITH | [5 empty] | 86.7 |  |  |  |  | 837.7 | [11 empty] | 120 | [7 empty] | 54.9 | [24 empty] | 340.8
Management | Stevenson | Job: 7300 - NB2 Management-STEVENSON | [30 empty] | 960 | [6 empty] | 568.9 | 84.8
Management | Stevenson | Job: 7400 - Health Physics Support-STEVENSON | [61 empty] | 2400 |  |  |  |  | 100000 |  |  | 20000
Management | Strykowsky | Job: 7100 - Project Mgt & Integration-STRYKOWSKY | 1726.2 | [7 empty] | 862.9 | [12 empty] | 517.1 | [31 empty] | 517.1 | [8 empty] | 690.2 | 862.9 |  |  |  | 6000 |  | 30000 | 20000
Management | Strykowsky | JOB: 7700 - NSTX-U HP Allocations-STRYKOWSKY | [71 empty] | 214000
Management | Strykowsky | Job: 7710 - Upgrade Allocations-STRYKOWSKY | [71 empty] | 18000
Center Stack | Titus | Job: 1000 - CSU Analytical Support-TITUS (LOE) | [22 empty] | 687
Center Stack | Titus | Job: 1002 -Passive Plate Analysis &Upgrade-TITUS | [22 empty] | 352 | [46 empty] | 919.9
Center Stack | Titus | Job: 2300 - ECH Analysis-TITUS | [17 empty] | 99.9 |  |  |  |  | 210
Center Stack | Tresemer | Job: 1001 - CS Plasma Facing Components-TRESEMER |  |  |  | 2024.5 | [12 empty] | 350 | [5 empty] | 16 | [33 empty] | 675.6 |  |  | 800.9 | [9 empty] | 15601.7
Center Stack | Viola | Job; 8200 - CS & Coil Sprt Struc Install- VIOLA | [57 empty] | 270.3
|  | Grand Total | 1726.2 | 419.9 | 112.6 | 2024.5 | 240 | 86.7 | 1625.8 | 1482.5 | 1336.4 | 616.7 | 837.7 | 837.4 | 1894.4 | 1421.3 | 706.7 | 8 | 518.6 | 99.9 | 1278.5 | 199.6 | 156 | 517.1 | 2846.8 | 701.2 | 430.8 | 16 | 200 | 80.1 | 348.6 | 56 | 1398.9 | 880.4 | 328 | 89.9 | 338 | 431.1 | 725 | 568.9 | 84.8 | 186.1 | 123 | 1290.4 | 381.4 | 146.8 | 204.1 | 621.1 | 178 | 1180.3 | 164 | 777.3 | 10.9 | 811.1 | 811.5 | 517.1 | 691.1 | 1625.6 | 675.6 | 270.3 | 1032 | 3450.8 | 1365.2 | 2400 | 690.2 | 862.9 | 20 | 207.4 | 100000 | 32533.2 | 10900 | 832589.6 | 30244.9 | 232000