NSTX Upgrade Project

Acquisition Strategy

Draft 2

October 26, 2009

Change Log

Rev. 	Date		Change Description				Pages

SUMMARY PROJECT INFORMATION

Project Title:  NSTX Upgrade Project at PPPL

Total Project Cost (TPC) Range:  $75M to $91M

CD-0 Mission Need Approved:  February 23, 2009

CD-0 Approving Official:  Dr. Patricia Dehmer,

Deputy Director of Science Program of the Office of Science

CD-0 Material Change:  None

- Desired Outcome, Requirements, and Major Applicable Conditions

  - Project Description

The purpose of this project is to design, build and install a new Centerstack for NSTX and install a second Neutral Beamline on NSTX.

  - Performance Parameters Required to Obtain Desired Outcome

Required performance parameters are covered in the General Requirements Document for the Centerstack Upgrade and in the General Requirements Document of installing a second Neutral Beam on NSTX.

  - Environmental, Regulatory, and Technology Development

No environmental, regulatory or technology development issues have been identified.

- Cost and Schedule Range

  - Total Project Cost Range

The preliminary total project cost (TPC) range is $75M - $91M.

  - Funding Profile

Table 1. NSTX Upgrade Project Preliminary Funding Profile

| Fiscal Year | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| --- | --- | --- | --- | --- | --- | --- |
| ROM (Lower Range) | $ 5.1M | $11.0M | $14.5M | $30.3M | $12.1M | $ 1.9M |
| ROM (Upper Range) | $ 5.1M | $11.8M | $17.7M | $35.1M | $15.3M | $ 5.9M |

  - Key Milestones

CDR							October 2009

Submit CD-1 Request					December 2009

PDR							June 2010

Submit CD-2 Request					July 2010

FDR							April 2011

Submit CD-3 Request					May 2011

Begin Upgrade Outage				September 2011

Submit CD-4 Request					June 2014

- Alternatives and Risk Analysis

  - Technical Alternatives Analysis

Alternatives that cover the range of available technical approaches are as follows:

Alternative 1:  Do nothing

Alternative 2:  Upgrade Centerstack and add second Neutral Beamline

Alternative 3:  Upgrade Centerstack only

Alternative 4:  Upgrade Centerstack and later add a Neutral Beamline

The advantages and disadvantages for each of these three alternatives are summarized below:

Alternative		Advantage			Disadvantage

#1			None				No new science

#2			Maximum new science	Higher project cost

#3			Lower project cost		Lower new science

#4			Project cost spread out	No operations for 4 years

  - Location Alternative Analysis

There are no location alternatives available for consideration.

  - Total Lifecycle Costs

The analysis of future maintenance and repair costs is not applicable to this project.

The cost of performing the centerstack upgrade separately from the installation of a second neutral beamline would be significant.

  - Recommended Alternative

Alternate 1 was deemed unacceptable due to

Alternate 2 was deemed unacceptable due to

Alternate 3 is recommended as the preferred alternate because it is the most efficient use of capital funds and it maximizes the operations time for NSTX.

Other Acquisition Alternatives Considerations

Various alternatives have been considered with respect to this project.  One was to evaluate whether to build the new Centerstack at PPPL or to award a contract to a vendor to perform the fabrication.  The other was to evaluate whether to decontaminate existing components of Neutral Beam #4 or to fabricate new ones.

It has been determined that  the Centerstack should be fabricated at PPPL due to the fact that any issues with the fabrication process or design could be handled most efficiently in a setting where the engineers and designers who prepared the design are available for immediate consultation if problems arise.

The decontamination of the neutral beam is being pursued to determine which components can be returned to a condition that is acceptable for use on NSTX, thereby saving the cost of making new components.

3.5 Risk Analysis

An essential part of the project planning will be to ensure the risks associated with the project have been identified, analyzed, and determined to either be avoidable or manageable.  Risk identification and analyses will be continued throughout the planning process.  Each of the identified risks will be monitored at each critical decisions and review point to ensure that they have been satisfactorily addressed, eliminated, or managed.  The risk assessment process was started before CD-0.  Risk analysis process and conclusions were reviewed and revised during the preparation for CD-1.

A formal risk management plan will be included in the Project Execution Plan and it will include how the Risk Registry will be used and strategies for mitigating risks.  Risks will be monitored and managed throughout the project.

- Business and Acquisition Approach

  - Contract Alternatives

Various alternatives have been considered with respect to this project.  Due to the fact that a substantial amount of the work has been performed before at PPPL, it is recommended that the design and fabrication of non-off-the-shelf components be done by PPPL.

  - Major Contracts Contemplated

PPPL will award contracts for the copper required to build the coils and center bundle, the Plasma Facing Components, cabling, and cable installations outside the Test Cell.  Competitive selections will be based on demonstrated technical abilities, qualifications, capabilities and resource availability to meet the schedule requirements, as appropriate.  Firm fixed price contracts are expected.

  - Special Acquisition Procedures

No special acquisition procedures will be used.

  - Performance Incentives / Small Business Approach

Solicitation will be made with consideration for small business, veteran owned small business, service disabled veteran-owned small business, HUB Zone small business, and small disadvantaged business and women-owned small business concerns.  Awards will be based on the best value determined from an evaluation of the technical criteria such as technical qualifications, past performance and experience, as well as cost considerations.

- Management Structure

  - Project Organization

  - Integrated Project Team Members

Jeff Makiel

Lief Dietrich

Barry Sullivan

Mike Williams

Erik Perry

Larry Dudek

Tim Stevenson

Ron Strykowsky

Tom Egebo

Masa Ono

Jon Menard

Jerry Levine

Judy Malsbury

Rod Templon

  - Approach to Performance Evaluation and Validation

DOE O 413.3A, Program and Project Management for the Acquisition of Capital Assets, will be used as the primary management tool and guideline to execute the project.

PPPL is implementing a certifiable EVMS that is compliant with ANSI/EIA-748-A-1998.  This EVMS will be certified prior to CD-3, and will be implement and used to monitor and evaluate project progress and performance for the duration of the project.

A Primavera database, including estimated costs and resources, will be utilized to manage this project.  Throughout the phases of this project, the Primavera database will be updated and refined to reflect the sequence of activities required to be accomplished within specific milestone completion dates and planned costs.  The database will be updated monthly to document progress with respect to the performance durations and cost.  The DOE site office will coordinate the preparation and submittal of any status reports required by DOE Headquarters.

Change Control

The Project Execution Plan specifies a change control process which has been used before at PPPL.  This process will be utilized to manage any required changes to cost, scope, or schedule.

Project Reporting

Monthly reporting will be accomplished through the DOE Project Assessment and Reporting System (PARS).

Project Meetings

PPPL will conduct regularly scheduled meetings and reviews to discuss project technical scope, schedule and cost status, and any emerging issues that may have an adverse impact on technical scope, schedule, or cost.  Participants will include integrated project team representatives as deemed appropriate.

SIGNATURES

This report accurately represents the best thinking and efforts of the NSYX Upgrade Project and the IPT to understand the full range of project risks and alternatives available to accomplish the project mission.

All reasonable risks and mitigations to executing the acquisition strategy have been included at this time, and the IPT believes the recommended acquisition strategy is in the best interest of DOE.

If new information or facts arise that could have a significant impact on the project’s cost, schedule, or performance,  the NSTX Upgrades Project Manager will make the IPT aware of this in a timely manner.

This acquisition strategy may be revised when it makes good business sense to do so.  Any changes must be justified and documented.  Material changes to the acquisition strategy, such as changes in recommended alternative(s), risk profile, contract or competition approach, or major milestones, must be adequately documented and approved at the same approval level as the original document.

APPROVALS

Submitted for Approval:

NSTX Upgrade Project Manager						date

Recommended for Approval:

Contracting Officer								date

Approval:

Approving Officer								date