National Spherical Torus Experiment (NSTX) Upgrade

Preliminary Project Execution Plan

Revision 0

October 26 2009

Concurrences:

| E. Perry NSTX Upgrade Project Manager | M. Williams Head, Engineering and Infrastructure, PPPL |
| --- | --- |
| S. Prager Director, PPPL | J. Makiel NSTX Upgrade Project Federal Project Director, SC-PSO |
| J. Faul Manager, SC-PSO | B. Sullivan NSTX Upgrade Project Program Manager, SC-OFES |
| Approved: |  |
| E. Synakowksi Associate Director for Fusion Energy Sciences Office of Science |

Record of Revisions

| Revision | Date | Description of Changes |
| --- | --- | --- |
| 0 | 10/26/09 | Initial Issue. |

Table of Contents

1	INTRODUCTION AND SCOPE OF THIS DOCUMENT	1

2	MISSION NEED JUSTIFICATION/PROJECT OBJECTIVES	2

3	PROJECT DESCRIPTION	5

4	MANAGEMENT STRUCTURE AND RESPONSIBILITIES	5

5	WORK BREAKDOWN STRUCTURE (WBS)	12

6	RESOURCE PLAN	12

7	PROJECT BASELINES	13

8	Control of Project Baselines	15

9	Project Management and Control Systems	19

10	Funds Management	21

11	RISK MANAGEMENT	22

12	ACQUISITION STRATEGY	22

13	DATA MANAGEMENT SYSTEM	23

14	SYSTEMS ENGINEERING AND TECHNICAL MANAGEMENT	23

15	INTEGRATED SAFETY MANAGEMENT	24

16	SAFEGUARDS AND SECURITY…….............................................................24

17	REVISIONS TO THE PROJECT EXECUTION PLAN	25

# INTRODUCTION AND SCOPE OF THIS DOCUMENT

The National Spherical Torus Experiment (NSTX) is an experimental research facility funded by the Office of Fusion Energy Sciences (OFES) that is operating at the Department of Energy’s Princeton Plasma Physics Laboratory (PPPL).

This Preliminary Project Execution Plan (PEP) covers the NSTX Upgrade Project from Title I design, through fabrication, to integrated system testing for the systems affected by the project. The Department of Energy has identified the NSTX Upgrade Project as a Major Item of Equipment (MIE) Project vs. as a Line Item construction project.  The differentiating factor between capital equipment and line item construction designation is that the equipment can be installed with little or no significant civil construction activities required (i.e., <$5M or <20% of total project cost (TPC)).  The device will be sited within existing experimental facilities at PPPL.  No major building additions are required to accommodate the device; while there may be some minor interior changes in configuration, these changes will not affect the structural integrity of the existing facility.  In addition, the existing facility is currently served by most of the utilities necessary to support the NSTX Upgrade Project device, with only minor additional ancillary equipment needed. Although a MIE Project, the same overall management concepts applicable to line item projects will be applied to the degree appropriate for a project the size and cost of the NSTX Upgrade Project.  DOE Order 413.3A will provide the basis for the overall management of the Project.

Key documents and plans that describe the NSTX Upgrade Project and how it will be managed are listed below.

### DOE-approved project documents:

- Acquisition Strategy (AS)

The Acquisition Strategy describes how the project as defined is consistent with the DOE’s strategic goals, plans, and objectives, and how it meets those goals, plans, and objectives cost effectively and efficiently.

- Project Execution Plan (PEP)

The Project Execution Plan (PEP) is a required baseline project document that establishes roles and responsibilities, and describes in detail the manner in which a project is to be managed and executed.  The PEP serves as the primary agreement on project planning and objectives between OFES, the Federal Project Director, and PPPL.

DOE certified institutional systems or plans:

- PPPL Project Control System Description (PCSD)

Describes PPPL’s system for planning, authorizing, and tracking project work.

- PPPL Integrated Safety Management Plan (ISMP)

Describes the structure and implementation of Integrated Safety Management at PPPL, consistent with DOE policy, requirements, and guidance.

NSTX Upgrade Project approved documents:

- General Requirements Documents (GRDs)

Top-level (i.e., system-level) specification for the NSTX Upgrade Project.

# MISSION NEED JUSTIFICATION/PROJECT OBJECTIVES

## Mission Need

The NSTX Upgrade Project mission need (Critical Decision 0) was approved by the acting Director of the Office of Science (acting SC-1) in February 2009.

2.2     Project Objectives

The key technical objectives of the NSTX Upgrade Project are the fabrication and installation of a new centerstack and the addition of a second neutral beamline.

### Performance Baseline Parameters

The NSTX Upgrade Project’s Performance Baseline is defined by key performance, scope, cost, and schedule parameters:

- Performance - The system performance levels to be demonstrated at project completion.  These include ISTPs for the centerstack and Neutral Beamline #2, as well as certain subsystem functional tests.

- Scope - A quantitative description of the equipment to be provided.

- Cost - The total estimated cost (TEC) and total project cost (TPC) of the project.

- Schedule - The estimated project completion date.

The Project’s cost and schedule baseline will be supported by bottom-up estimates of costs, task durations, and risk-based contingencies, whose technical basis is consistent with the performance and scope parameters.  The implementation of changes in the baseline will be made in accordance with the change control procedures and approval thresholds specified in the final Project Execution Plan at CD-2.

### Fabrication Project Performance at Project Completion

The NSTX Upgrade Project will initially support operation with a magnetic field strength of 1.0T and a plasma current of 1.0+ MA.  Testing of equipment for 10MW of Neutral Beam Injection (NBI) heating with a second beamline and demonstration of 2MA plasma current will be done as part of NSTX Operations.

The milestone marking the transition from a fabrication project to an operating facility is the DOE Critical Decision 4 (CD-4) milestone.

As required by DOE, a Project Close-out Report will be prepared and submitted to the Federal Project Director within six months of completion of the Project.  This report will provide the following information:

- Scope, cost and schedule baseline accomplishments;

- Financial closeout, including a final cost report;

- he technical performance of the systems at project completion;

- Itemized changes in cost, schedule, and technical parameters as compared to the initial baseline  (baseline change control log); and

- Subcontract closeout status.

### Fabrication Project Scope

The NSTX Upgrade Project scope includes all the equipment required at the start of operations.  The scope includes Title I through Title III engineering, fabrication, assembly and installation, integrated systems testing, and project management associated with producing the in-scope equipment.

### Fabrication Project Cost

As indicated in Section ‎1 of this PEP, the NSTX Upgrade Project has been designated as a Major Item of Equipment (MIE) by the Department of Energy and will be built using Capital Equipment Funds.  At CD-1 request, a baseline total estimated cost (TEC) range of $75M - $91M for the project was established.

### Fabrication Project Schedule

The Project’s schedule objective is to complete the project by June 2014.  The DOE level schedule milestone (Level 1 and 2) definitions and their criteria for completion are included in the NSTX Upgrade Project Milestone Dictionary.  These DOE level milestones are summarized below.

Milestone						Date                  .

CDR							October 2009

Submit CD-1 Request					December 2009

PDR							June 2010

Submit CD-2 Request					July 2010

FDR							April 2011

Submit CD-3 Request					May 2011

Begin Upgrade Outage				September 2011

Submit CD-4 Request					June 2014

# PROJECT DESCRIPTION

The NSTX Upgrade Project involves the design, fabrication and installation of a new centerstack and the refurbishment and installation of a TFTR neutral beamline on NSTX.

# MANAGEMENT STRUCTURE AND RESPONSIBILITIES

## NSTX Upgrade Project Organization

The NSTX Upgrade Project is led by the Princeton Plasma Physics Laboratory (PPPL).  Figure ‎4-1 depicts the details of the NSTX Upgrade Project organization structure and the key management responsibilities.

Figure ‎4-1 NSTX Upgrade Project Organization Structure

The following subsections describe the relationships between the elements of the organization and their responsibilities.

### U.S. Department of Energy (DOE)

Within the DOE, the responsibility for the NSTX Upgrade Project resides in the Office of Fusion Energy Sciences (OFES). OFES will also maintain executive level awareness of project progress, and an OFES NSTX Upgrade Project Program Manager has been assigned.  The management responsibility, authority, and accountability for the day-to-day execution of the NSTX Upgrade Project within the DOE are the responsibility of the Manager of the Princeton Site Office (SC-PSO), who has designated a DOE Federal Project Director for the NSTX Upgrade Project.

The Associate Director for Fusion Energy Sciences has been designated as the Acquisition Executive (AE) for the NSTX Upgrade Project.

The OFES NSTX Upgrade Project Program Manager (SC-OFES) is:

- Responsible for programmatic guidance, including defining project objectives, scope, schedule and cost;

- Responsible for allocating project funding;

- Responsible for coordinating the organization and implementation of major project reviews;

- Responsible for project oversight at an executive level.

The NSTX Upgrade Project Federal Project Director (SC-PSO) is responsible to the Acquisition Executive/Program Secretarial Office for executing the project.  The Federal Project Director is responsible for:

- Planning and implementing, and completing the project using a systems engineering approach.

- Organizing and directing the Integrated Project Team (IPT) that is comprised of both DOE and NSTX Upgrade Project team personnel to implement and achieve the overall project objectives and goals.

- Overseeing implementation of the project objectives, scope, schedule and cost, including:

  - Overseeing the design, fabrication, environmental, safety, and health efforts, including risk management, performed by the PPPL team and their subcontractors, and other functions enumerated in the Project Execution Plan, in accordance with public law, regulations, and Executive orders.

  - Serving as the point of contact between federal and contractor staff for all matters relating to the NSTX Upgrade Project and its execution.

  - Performing all required project status reporting to DOE HQ organizations and database management systems.

  - Evaluates and verifies reported progress; makes projections of progress and indentifies trends.

  - Serving as the Contracting Officer’s technical representative.

### Performing Organizations

#### Princeton Plasma Physics Laboratory (PPPL)

PPPL has overall responsibility for NSTX Upgrade Project execution, reporting to DOE through the Laboratory Director. The NSTX Upgrade Project reports directly to the PPPL Associate Laboratory Director for Engineering and Infrastructure.  Project support in the areas of Quality Assurance and Environment, Safety and Health (ES&H) are provided by PPPL. Major hardware procurements will be placed through PPPL’s procurement organization.

4.1.2.2	Other Organizations

All other participants (i.e., industrial or university organizations) are subcontractors to PPPL.

## 4.2	NSTX Upgrade Project Management Team

Key project positions and responsibilities are as follows:

### Senior Laboratory Managers

#### PPPL Director

The PPPL Director has overall responsibility to DOE for the execution of the NSTX Upgrade Project.  The PPPL Director is supported by the Deputy Director for Operations and the Associate Laboratory Director for Engineering and Infrastructure.

#### NSTX Upgrade Project Office

The NSTX Upgrade Project Office is headed by the NSTX Upgrade Project Manager, who reports to the Associate Laboratory Director for Engineering and Infrastructure.

### NSTX Upgrade Project Management Team

#### NSTX Upgrade Project Manager

The NSTX Upgrade Project Manager is responsible for the day-to-day execution of the NSTX Upgrade Project in a safe and cost-effective manner, in accordance with requirements, procedures and standards, as set forth in the PPPL contract with DOE.  This includes executing the technical, cost, schedule, project control, risk management, ES&H, and quality assurance aspects of the project within approved cost, schedule, and scope baselines, as defined in the Project Execution Plan and the contract. The Project Manager will instill a culture of personal accountability within the project team, focusing on driving schedule, without compromising safety and quality. The Project Manager is the Project’s primary point of contact with DOE and with the Program Advisory Committee. The Project Manager reports to the Associate Director for Engineering and Infrastructure.

#### 4.2.2.2	   Centerstack Upgrade Engineering Manager

The Centerstack Upgrade Engineering Manager is responsible for carrying out the centerstack upgrade engineering, design and fabrication to meet requirements specified in the General Requirements Document for the Centerstack Upgrade and the requirements called out in the Project Execution Plan.  The Centerstack Upgrade Engineering Manager reports to the Project Manager.

4.2.2.3	   Second Neutral Beam Engineering Manager

The Second Neutral Beam Engineering Manager is responsible for carrying out the second neutral beam upgrade engineering, design, decontamination, rework and fabrication to meet requirements specified in the General Requirements Document for the Second Neutral Beam and the requirements called out in the Project Execution Plan.  The Second Neutral Beam Engineering Manager reports to the Project Manager.

#### Responsible Line Managers Is this term necessary? It may be confused with our standard definition of RLM.

The Responsible Line Managers (RLMs) are responsible for carrying out NSTX Upgrade Project engineering design and fabrication activities in their respective disciplines.  The Responsible Line Managers (RLMs) report to the Centerstack Upgrade Engineering Manager and/or the Second Neutral Beam Engineering Manager.

#### WBS Managers

The project engineering work organization is structured according to the work breakdown structure (WBS).  A WBS Manager is assigned at the optimal WBS level according to a risk based graded approach.  In some instances, this “optimal” level may be at WBS Level 2 and sometimes at a lower level (job managers or cost account managers).  A WBS Manager is responsible for the execution of the work scope consistent with technical, cost, and schedule objectives.  The WBS managers report to Responsible Line Managers.

#### NSTX Upgrade Project Control Manager

The Project Control Manager reports to the NSTX Upgrade Project Manager and is responsible for all project control and administrative functions necessary to support NSTX Upgrade Project activities.

The NSTX Upgrade Project Control Manager’s responsibilities include:

- Coordinating the development of project plans and administering the centralized Work Authorization system;

- Maintaining up-to-date NSTX Upgrade Project cost and schedule baselines that are consistent with the technical baseline;

- Coordinating the preparation of statements of work, sole source justifications (as appropriate), the processing of requisitions, and tracking of procurements and subcontracts supporting the project;

Establishing, maintaining, and monitoring project budgets and schedules to ensure consistency with project control milestones and funding;

- Operating the PPPL Project Control System (PCS) as the Project Control System for the NSTX Upgrade Project.

- Assisting the Project Engineering Managers in administering the operation of the NSTX Upgrade Project documentation, configuration management, requirements definition, and design description systems;

- Serving as the primary point-of-contact to the PPPL Business Operations Department; and

- Performing administrative functions such as space planning, facility maintenance coordination, travel approvals and vouchers, and overall personnel planning.

#### Engineering Support Team

The Engineering Support Team reports to the NSTX Upgrade Engineering Managers and is responsible for engineering support activities, including:

- Systems Engineering;

- Design Integration;

- Systems Analyses and Technical Assurance; and

- Metrology Coordination.

#### Quality Assurance (QA)

A NSTX Upgrade Project QA Manager will be assigned to support the NSTX Upgrade Project Manager.  The NSTX Upgrade Project QA Manager, with the support of the entire QA Division, will assist the project in meeting quality assurance/control objectives.  Support tasks include:

- Preparing a project QA plan;

- Assisting in the development of project procedures, policies, and other plans, as requested by project management;

- Providing quality related services such as inspections and support of procurements; and

- Performing both compliance-based and performance-based audits of the project and its associated plans and procedures.

- Coordinate DCMA inspections on project industrial subcontracts.  Provide assurance to DOE-PSO of DCMA activity and deliverables.

##### 4.2.2.9	  ES&H

A NSTX Upgrade Project ES&H Manager will be assigned to support the NSTX Upgrade Project Manager.  This ES&H Manager will assist the project in meeting ES&H objectives. These include safe execution of the project and producing a facility that will be safe to operate.  The NSTX Upgrade Project ES&H Manager will assist in implementing PPPL ES&H policies and procedures.  The ES&H Manager will also prepare any required National Environmental Policy Act (NEPA) documentation and necessary revisions to the NSTX Safety Assessment Document (SAD).

While their normal reporting relationship is to the NSTX Upgrade Project Manager, both individuals have separate lines of reporting to the PPPL’s Deputy Director for Operations for items involving overall QA and ES&H impact.

## 4.3	Program Advisory Committee

Advice by the U.S. fusion community on the NSTX Upgrade Project scientific and technical issues is being obtained through the NSTX Program Advisory Committee (PAC).  The NSTX PAC is composed of a broad spectrum of technical experts from the U.S. fusion community.  The PAC provides this advice to the PPPL Director.  It meets periodically at the request of the PPPL Director.

## Integrated Project Team

The NSTX Upgrade Project Integrated Project Team (IPT) is made up of key DOE and NSTX Upgrade Project Team personnel.  The IPT is led by the NSTX Upgrade Project Federal Project Director.  While the makeup of the IPT will evolve as the project matures, the initial makeup of this cross-functional team for CD-3 activities includes the following personnel:

- The NSTX Upgrade Project Federal Project Director

- The OFES NSTX Upgrade Project Program Manager

- The PPPL Associate Laboratory Director for Engineering and Infrastructure

- The NSTX Project Director

- The NSTX Program Director

- The NSTX Upgrade Project Laboratory Project Manager

- The PPPL Procurement Manager

- The NSTX Upgrade Project Quality Assurance Manager

- The NSTX Upgrade Project ES&H Manager

- The NSTX Upgrade Project Control Manager

- The NSTX Control Manager

- The NSTX Centerstack Upgrade Engineering Manager

- The NSTX Second Neutral Beam Engineering Manager

Other DOE and NSTX Upgrade Project Team and PPPL personnel may be added as the need arises in order to accomplish the NSTX Upgrade Project objectives.  For example, as the NSTX Upgrade Project nears operation, personnel with operational experience will be added to the team.  Additionally, as the need arises, DOE or PPPL personnel with expertise, fiscal, technical, and legal areas may be included in the IPT.

5     	WORK BREAKDOWN STRUCTURE (WBS)

The WBS organizes the NSTX Upgrade Project work scope and provides the logical structure that will be used to control the project.  The WBS is composed of as few levels as required for work definition and control.  All the WBS elements are expanded and completely defined in a separately issued and approved WBS dictionary.  The WBS Dictionary entry for each WBS element contains a brief description of the work scope for each element.  A summary-level Work Breakdown Structure listing is provided in Annex I, while the full WBS listing and WBS dictionary can be found on the NSTX Upgrade Project Engineering Web page.

# RESOURCE PLAN

## NSTX Upgrade Project Costs

As indicated in Section ‎1 of this PEP, the NSTX Upgrade Project has been designated by the Department of Energy as a Major Item of Equipment (MIE) and will be funded entirely with Capital Equipment Funds.  As a result of this decision, the overall cost objective that encompasses all project work scope as defined in Annex I is measured in terms of the Total Estimated Cost (TEC).  These TEC cost activities will be used to measure the performance of the NSTX Upgrade Project against its technical, cost, and schedule baselines.

## Funding Profiles

Table 1. NSTX Upgrade Project Preliminary Funding Profile

| Fiscal Year | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| --- | --- | --- | --- | --- | --- | --- |
| ROM (Lower Range) | $ 5.1M | $11.0M | $14.5M | $30.3M | $12.1M | $ 1.9M |
| ROM (Upper Range) | $ 5.1M | $11.8M | $17.7M | $35.1M | $15.3M | $ 5.9M |

## Life Cycle Costs

The elements of the NSTX Upgrade Project life-cycle cost are as follows:

- Planning, including conceptual design (included in the Total Project Cost or TPC, but not in the TEC) as specified in Section ‎2.2.4.

- Major Item of Equipment fabrication: the TEC as specified in Section ‎2.2.4

- Decommissioning and disposal:  $2M.

Note on Research Operations:  Operations costs for NSTX are only expected to increase modestly because of the upgrades (minor additional costs for operating a second neutral beam).

Note on Decommissioning and Disposal:  The decommissioning and disposal cost for NSTX is not expected to be changed as a result of the NSTX Upgrade Project.  At the end of NSTX’s operating life, the remaining equipment will be removed and it is expected that these activities should be routine and relatively inexpensive, although a small amount of radioactive activation and/or contamination of the structures is expected.  The decommissioning and disposal cost estimate is based on the actual costs of removing the Princeton Large Torus (PLT) and Princeton Beta Experiment-Modified (PBX-M) devices in recent years.

# PROJECT BASELINES

The initial NSTX Upgrade Project configuration, schedule, and cost baselines were developed in the conceptual design phase of the project.  Section ‎7.1, which follows, addresses the management and control of the configuration (sometimes also called the technical) baseline.  The project baselines come under the configuration control processes that are outlined later in this PEP.

## Configuration Baseline

The configuration or technical baseline is the configuration/technical documentation formally designated at a specific time during the Project.  Configuration baselines, plus approved changes to those baselines, constitute the current configuration documentation.  Establishment of configuration baselines will follow the industry standard for systems engineering, EIA/IS-632 Systems Engineering.  There are three formally designated configuration baselines, namely the functional, allocated, and product baselines.

The functional baseline is the initially approved documentation describing the system’s functional, performance, and interface requirements and the verification required to demonstrate the achievement of those requirements.  The functional baseline is established when the system (top-level) specification, the General Requirements Document, is approved.

The product baseline is the initially approved documentation describing all of the necessary functional, performance, and physical requirements of the subsystem; and the functional and physical requirements designated for production acceptance testing.  Product or “build to” specifications (CSPECS and PRLs) and engineering drawings are part of the product baseline.  Generally, there is a product baseline for each subsystem, component, and part.  The product baseline is typically established late in final design or early in the fabrication phase with the validation of the product specification and supporting documentation.

## Cost and Schedule Baselines

The DOE schedule baseline is documented in this PEP as indicated in Section ‎2.2.5.

The DOE cost baseline consists of the TEC and the included contingency, as indicated in Section 2.2.5. The supporting budget estimates by WBS are tabulated in Table 7-2 (Cost by WBS).

Table ‎7-2 Budget Estimate by WBS

The NSTX Upgrade Project resource-loaded schedule provides the schedule and cost details for the Project’s performance measurement baseline.  The Primavera Project Planner (P3) commercial scheduling module will be the standard software used for the NSTX Upgrade Project.  There will be a minimum of four levels of detail starting with the Project Summary Schedule (Level 1).  This summary level schedule will identify significant DOE and project milestones and summary logic for the entire project.

The other three levels of schedule are as follows and provide increasingly greater level of detail:

- Level II or Intermediate Schedules – will show major milestones and key tasks summarized by WBS, including key interrelationships.

- Level III or Job Level Schedules – are the detailed schedules prepared by the job manager.  This schedule is established as part of the Work Authorization process and will span at least the current fiscal year.  Since this schedule is the basis for each approved job or task, it is the heart of the cost and schedule baseline.  These schedules will be resource loaded at the activity level and will form the basis for the NSTX Upgrade Project Control System described in Section 10.0 of this PEP.  Progress against established technical, cost, and schedule targets will be measured and evaluated monthly using the information contained in the Level III schedules.  The activity detail that provides basis for these resource loaded schedules are documented in a separate Cost and Schedule Document.  Subsystem-specific contingencies are included and detailed resource-loaded schedules are available.  These schedules clearly demonstrate the critical path activities and major milestones at both the summary and detailed levels.

- Level IV or Working Level Schedules – Depending on the needs of the project, detailed working level schedules are prepared as needed.  As critical tasks occur (e.g., complex fabrication and installation tasks), activities that are covered in the Level III job schedules may be broken down into additional detail to allow for coordination of work by the responsible manager.  Level IV schedules may also be developed by cognizant job managers to aid in the performance and control of their jobs.  This level of schedule detail is normally not controlled at the same rigor as higher level schedules, but efforts are made to ensure continuity to established project milestones and Level III schedules.

# Control of Project Baselines

## Configuration Management Approach

Changes to the NSTX Upgrade Project configuration, cost, and schedule baselines are controlled using a disciplined, yet flexible configuration management approach.  Changes to the baseline are carefully considered and evaluated for impact before proceeding.  Processes for effecting changes to the configuration, cost, and schedule baselines are described in the Configuration Management Plan.

## Change Control Process

The NSTX Upgrade Project change control process ensures that changes to the NSTX Upgrade Project design and requirements are properly identified, screened, evaluated, implemented, and documented.  A formal procedure has been established to implement the process of change classification and submittal of supporting documentation.

Once an Engineering Change Proposal (ECP) has been prepared, and the impacts fully documented, the ECP will come before a project Change Control Board (CCB) that is comprised of senior members of the NSTX Upgrade Project management team.  The NSTX Upgrade Project Manager or his designee will chair the CCB.  The NSTX Upgrade Project Systems Engineering Support Manager will serve as the CCB Secretary.  Other members of the CCB will be assigned as appropriate, but may include the following:

- NSTX Upgrade Project Control Manager

- NSTX Upgrade Project Engineering Managers

- WBS Managers

- ES&H representative

- QA representative

- Other cognizant job managers impacted by the proposed change

The chairperson shall have the ultimate authority to recommend changes for the final approval; other board members act solely as advisors.

Once a proposed change is approved, the project will implement the change in a timely manner.  An updated list of approved, disapproved, and pending changes will be maintained electronically by Project Engineering on the NSTX Upgrade Project web site.

## Change Control Levels

Changes to the NSTX Upgrade Project configuration, cost, or schedule baselines will be classified according to their impact on the project.  The change approval levels are established consistent with the technical, cost, and schedule risk and are intended to feed into the higher level DOE configuration change system.  Program directed changes will be approved at an appropriate level as determined within the Office of Science.  For project baseline deviations, Table ‎8-1 summarizes the performance baseline change authority for the Deputy Secretary of Energy (Level 0), the Associate Director for Fusion Energy Sciences - Office of Science  (Level 1), the NSTX Upgrade Project Federal Project Director ( Level 2), and the NSTX Upgrade Project Laboratory Project Manager (Level 3).

Table ‎8-1 NSTX Upgrade Project Change Classification Matrix

| Change Level | Approval Level | Technical Scope | Schedule | Cost |
| --- | --- | --- | --- | --- |
| 0 | Deputy Secretary of Energy | Any change in scope and/or performance that affects mission need requirements or is not in conformance with the current approved OMB-300. | 6 month or greater increase (cumulative) in the original project completion date. | Increase in excess of 25% (cumulative) of the original cost baseline. |
| 1 | Associate Director for FES | Changes to technical requirements and parameters that affect safety basis and operation function, but do not affect mission need objectives. | Less than a 6 month increase (cumulative) in the original project completion date. | Increase of the original cost baseline. |
| 2 | NSTX Upgrade Project Federal Project Director | Changes with ES&H impacts significant enough to affect the approved NEPA/EA documentation. | <3 month increase (cumulative) in the original project completion date OR Change in DOE level 2 milestone. | Changes requiring the use of contingency funds |
| 3 | NSTX Upgrade Project Manager | Changes not requiring DOE approval. | All other changes to the performance measurement baseline schedules not requiring DOE approval. | All other changes to the performance measurement baseline costs not requiring DOE approval. |

## Contingency Management Plan

The amount of contingency is established at the beginning of the project based on a risk assessment performed as part of the cost estimating process. A formal risk-assessment methodology that considers technical, cost, and schedule risks at the subsystem level, is performed, using a high-medium-low risk classification.  This methodology is outlined in Annex II to this plan.  The initial project contingency level will be approved by the Associate Director for Fusion Energy Sciences as the Acquisition Executive for NSTX Upgrade Project at CD-2 as part of establishing the overall cost and schedule baselines.

Based on experience with similar projects, changes in scope of work and schedule, requiring the application of contingency, typically arise as a project proceeds.  Changes involving the application of contingency must be approved by the NSTX Upgrade Project DOE Federal Project Manager via the configuration control process.  Cost and schedule baselines and remaining contingency will be adjusted upon approval of change proposals.

Each fiscal year, not later than the middle of the year, the NSTX Upgrade Project Manager will assess the status of authorized work, achieved milestones, and current and future risks, to determine how to apply remaining management reserve (See Section ‎10.2) funds under the Project Manager’s control.  They can be used to authorize as yet un-funded work planned for the current or future years, to fund approved changes, or a combination of these.  This decision will occur early enough in the fiscal year to permit effective use of these funds, and will be presented as part of the annual mid-year project review meeting with DOE.

## Value Engineering

Value Engineering (VE) is the systematic application of recognized techniques by a multi-disciplinary team to identify the function of a product or service, establish a worth for that function, generate alternatives through the use of creative thinking, and provide the needed functions to accomplish the original purpose of the project at the lowest life-cycle cost without sacrificing safety, necessary quality, and or environmental attributes of the project.  The NSTX Upgrade Project will apply VE methodologies following a tailored approach to the formal elements of VE.  The NSTX Upgrade Project approach will include:

- Using a multi-disciplinary team to identify and assess alternates;

- Following a systematic job plan;

- Identifying and evaluating function, cost and worth;

- Developing and evaluating new alternatives for required functions; and

- Developing and implementing recommendations.

The NSTX Upgrade Project has applied value engineering methods from early in the design process, starting with the pre-conceptual design phase.  Numerous design studies have been conducted that have significantly shaped and guided the development of the current design.

  - Prior to CD-2, a dedicated value engineering task force will review and assess numerous design and installation alternatives with each WBS Manager during Preliminary Design Review preparation.

# Project Management and Control Systems

## Project Management Systems Approach

The NSTX Upgrade Project Manager will ensure that all project activities are properly controlled using PPPL’s Project Control System (PCS).  This system will be used as a management aid in planning and executing the project work scope and for evaluation of schedule and budget performance.  The status of progress and variance in the WBS elements will be reported monthly to the NSTX Upgrade Project Manager.

The NSTX Upgrade Project Manager will work to ensure early detection of technical, schedule or cost problems.

## Project Control System Overview

The NSTX Upgrade Project will use the existing PPPL Project Control System (PCS) as described in the PPPL Project Control System Description.  This document was reviewed and approved by DOE in 1996.  The PPPL PCS satisfies the principles of project management and control systems outlined in this PEP and DOE Order 413.3A (“Program and Project Management for the Acquisition of Capital Assets”).  The PCS provides a centralized work authorization system that the project will use.

The PCS is an integrated earned value management control and reporting system that establishes the documentation, data requirements, information flow, and system disciplines necessary to operate and maintain a system for control of the NSTX Upgrade Project work, costs, and schedules.  The overall objective of the PCS is to provide PPPL and DOE with timely and auditable cost and schedule performance information that can be used to monitor, control and manage Project progress.  To accomplish this objective, the PCS provides a formal process for:

- Organizing the project work scope via the WBS;

- Planning and estimating the work scope via the project resource loaded schedule;

- Authorizing work and forecasting resource requirements via the Work Authorization Form (WAF);

- Controlling management reserve and authorized allocated contingency via the change control process;

- Monitoring progress relative to schedule status and completion estimates and reporting cost and schedule performance against established cost and schedule baselines using the Level III schedules;

- Documenting approved changes to the performance measurement technical, cost, and schedule baselines via the change control process; and

- Analyzing variances to the cost and schedule baselines, including critical path analyses resulting from status results of the Level III schedules.

The key planning and measurement tool for the project is the Level III schedule, but the PPPL work authorization process forms the basis for development of these schedules.  Through the work authorization process, details of work scope, schedule, budget, and responsibility will be integrated, documented, reviewed, and agreed to by both project management and the performing organization.  The cognizant job manager will be responsible and accountable for accomplishing the scope of the work, as defined, with established Level IV schedule milestones and cost targets.  The vehicle for documenting and authorizing work is the Work Approval Form (WAF).  The WAF formally documents the work scope to be performed, establishes a schedule, provides a cost estimate, identifies a responsible person for accomplishing the work, and provides time phased cost and manpower profiles.

## Cost and Schedule Reviews

Nominally the Project will schedule quarterly reviews of Project status with the NSTX Upgrade Project Federal Project Director and the OFES Management.  These reviews will focus on cost and schedule aspects of the Project.  At these meetings the project will report the status of the project in general and the cost variances that potentially impact the level of contingency in particular.  Progress on detailed planning will also be reported.  Based on these inputs, the project will recommend to DOE changes to the Project Baseline.  This recommendation will be documented in the form of a formal change.  In addition, as needed to support Critical Decision milestones or as requested by the NSTX Upgrade Project Acquisition Executive, these reviews may be expanded to include external reviewers organized by the Office of Science Office of Construction Management Support (the “Lehman” Review).

Every 6 months a bottoms-up estimate at completion (EAC) will be performed for either the entire project, or for selected WBS elements of concern as determined by the NSTX Upgrade Project Manager or the NSTX Upgrade Project Federal Project Director.  This may involve the re-scheduling of work previously scheduled but not completed.  This is done in order to ensure that the current performance measurement baseline remains up-to-date and consistent with the approved performance baseline parameters (TEC, completion date, etc.), and remains a reliable basis for budgeting, resource planning, and measurement of future performance.  The elapsed time from the start of the re-planning activity until approval of an ECP establishing the new performance measurement baseline may be several weeks.  During the time when work is in the process of being re-scheduled, the reporting of scheduled work (incremental BCWS) may be based on estimates which will require later revision.

## Reporting

Quarterly project reports to OFES will be prepared by the NSTX Upgrade Project Federal Project Director.  All monthly PCS status will be provided to the NSTX Upgrade Project Federal Project Director.  The data should include, but not limited to, the following:

- Actual cost of work performed (ACWP) - cumulative and incremental for overall project and lower tier WBS work packages

- Budgeted cost of work performed (BCWP) - cumulative and incremental for overall project and lower tier WBS work packages

- Budgeted cost of work scheduled (BCWS) - cumulative and incremental for overall project and lower tier WBS work packages

- Schedule variance (SV) and cost variance (CV) with explanation and planned corrective action

- Cost performance indices (CPI) and schedule performance indices (SPI) (cumulative and incremental) for overall project and lower tier 3 active WBS work packages.

- Cost and schedule contingency analysis reconciled against CV and SV with an updated risk registry changes

- Critical path analysis and near term ‘look ahead’

- Status of near term Level 2 milestones

Additionally, the NSTX Upgrade Project Federal Project Director, and other members of DOE-PSO, will participate in scheduled status meetings as well as design reviews

The DOE NSTX Upgrade Project Federal Project Director is responsible for entering monthly performance data and narrative into the DOE Project Assessment and Reporting System (PARS) database.

# Funds Management

## Project Funding Mechanisms

All project work and expenditure of project funds will be centrally authorized and controlled by the project office via the PCS. The annual NSTX Upgrade Project funding requirements will be updated each year by PPPL through the DOE Field Work Proposal (FWP) processes.

## Management Reserve Funds

All funds authorized for the Project by the DOE Financial Plan will be disbursed to the Project. Management reserve funds are a portion of each year’s approved funding allowance that are set aside at the beginning of each fiscal year instead of being immediately used to authorize work. Management reserve funds will be held in a unique management reserve account controlled by the NSTX Upgrade Project Manager. As needs arise, the Project Manager will authorize disbursement of the management reserve funds to authorize as yet un-funded work scheduled for the current year or future years, or resolve approved changes arising within the current year’s authorized scope of work. Changes requiring the application of contingency, will be handled via the change control process defined in Section 8 and will, as stated there, require DOE Federal Project Director or higher DOE approval. As part of the reporting process, the NSTX Upgrade Project Manager will report on management reserve disbursements regularly, and as part of the cost and schedule project review meetings, including the IPT meetings,  with DOE.

# RISK MANAGEMENT

The NSTX Upgrade Project will manage risks, where “risk” refers to factors within the Project’s control that both threaten and provide opportunities to improve project cost and schedule performance and the achievement of project technical objectives.  During all phases of the NSTX Upgrade Project, priority is placed on identifying and mitigating risks.  Risk mitigation activities are incorporated into the project’s cost and schedule baselines, as appropriate.  Contingency is used to address realized risks.  A quantitative, analysis of outstanding risks and estimating uncertainties is used to estimate the amount of contingency required.

Control of the environment, safety, and health hazards, while part of risk management in a broader sense, are not unique to the NSTX Upgrade Project and are enveloped by the Princeton Plasma Physics Laboratory (PPPL) Integrated Safety Management (ISM) program that is applicable to all PPPL projects and operations.  The PPPL ISM clearly indicates that risk management is everybody’s business and will be factored into every project decision throughout the life of the NSTX Upgrade Project.

While any member of the NSTX Upgrade Project Team is expected to identify risks that become apparent, the responsibility for risk management for the NSTX Upgrade Project rests with the NSTX Upgrade Project line management.

# ACQUISITION PLAN

During Final Design, the project, in conjunction with the PPPL Procurement organization, will develop a formal NSTX Upgrade Project procurement plan that identifies all planned procurements by type, dollar amount, key dates, and special requirements such as incentive, or shared savings, provisions.

At this time, it is anticipated that the following work/acquisitions will be performed as follows:

- Project Management:  In-house staff

- Construction Management:  In-house staff

- Engineering and Design:  In-house staff

- Large Components:  Combination of fixed price vendor contracts and in-house fabrication

- Assembly:  In-house staff and fixed price vendor contracts

- Decontamination:  In-house staff

- Ancillary Systems:  Combination of vendor contracts and in-house staff

- System Start-up, Test and Troubleshoot:  In-house staff

Long lead procurements will be identified for the procurement of critical components such as the copper for the coils and the tri-ax cables for the neutral beamline.

# DATA MANAGEMENT SYSTEM

A system for controlling documents and drawings, adapted from existing PPPL document and drawing control systems using hard copy and electronic media, will be developed to ensure the organized and consistent treatment and format of NSTX Upgrade Project documents including procedures, plans, memos, drawings, calculations, requirement documents, design documents, and procurement documents.  This system will utilize web-based file servers for rapid review, authorization, updating, and retrieval of documents and drawings.  The majority of project documents (other than drawings) can presently be retrieved from the NSTX UPGRADE PROJECT web page located at http://nstx-upgrade.pppl.gov/index.htm  Drawings in electronic format can be accessed via the Pro/INTRALINK database. Legacy drawings only in hard copy can be obtained from the PPPL Drafting Center.

# SYSTEMS ENGINEERING AND TECHNICAL MANAGEMENT

## Systems Engineering

The Engineering Support group has responsibility for implementing a systems engineering program on the NSTX Upgrade Project.  The systems engineering program includes the development and allocation of requirements; system design and verification; risk management; value engineering; configuration management; interface management; data management; and technical reviews.

## Quality Assurance

The NSTX Upgrade Project QA Plan will demonstrate how the existing PPPL Quality Assurance Plan and implementing policies and procedures will satisfy the requirements of the DOE Order on Quality Assurance, 414.1A, and provide an appropriate level of quality on the project.

14.3	NEPA Documentation and Safety Assessment

Input to the NEPA Documentation, the Environmental Evaluation Notification Form (EENF) and the Preliminary Hazards Analysis (PHA) will be submitted to DOE.  The NSTX Safety Assessment Document (SAD) will be updated and approved by PPPL prior to the restart of operations.

# INTEGRATED SAFETY MANAGEMENT

PPPL follows the institutional Integrated Safety Management System Description (ISMS) that has been approved by DOE.  The NSTX Upgrade Project intends to follow the ISMS and to adopt this as its own for the conduct of NSTX Upgrade Project work performed at PPPL.

ISM at PPPL is comprised of:

- The governing policy that safety be integrated into work management and work practices at all levels.

- The distinct policies, programs, procedures, and cultural beliefs that PPPL has developed as the structure that PPPL workers utilize in fulfilling PPPL’s environmental, safety, and health responsibilities.

The NSTX Upgrade Project will incorporate ISM into its management approach as follows:

- By accepting responsibility for safety as a line management responsibility. The NSTX Upgrade Project Manager is responsible for safe execution of the project.

- By following PPPL procedures for work planning (e.g., ENG-032, etc.), where applicable. These procedures incorporate the ISM core functions of folding safety into the work planning, establishing appropriate controls, operating within established parameters, and feedback.  The “core functions” of ISM include the following 5 step process:

- Defining the scope of work;

- Analyzing the hazard;

- Developing and implement hazard controls;

- Performing the work within these controls; and

- Providing feedback and continuous improvement to this process.

Where project-specific procedures must be developed, ISM core functions will be incorporated into them.

The ISMS is incorporated into the DOE-approved PPPL Worker Safety and Health Program (WSHP), which describes an integrated system that complies with the pertinent requirements of 10CFR851, the Worker Safety and Health Program Final Rule.  In addition, the DOE-approved PPPL Radiation Protection Program (RPP) indicates the Laboratory’s methods for implementing the requirements of 10CFR835, Occupational Radiation Protection.  The NSTX Upgrade Project will implement the relevant requirements of the PPPL WSHP and RPP in the execution of the project.  This will include preparation of a construction project health and safety plan for this project as required under the WHSP.

# SAFEGUARDS AND SECURITY

A physical security vulnerability assessment of the NSTX Upgrade Project was conducted to determine if any negative impact and associated cost increases to the safeguards and security program would occur as a result of the upgrades.  The assessment did not indicate any negative impact or increased cost to the physical protection, personnel security, emergency operations or protective forces. The Design Basis Threat (DBT) was included in this assessment.

# REVISIONS TO THE PROJECT EXECUTION PLAN

This plan, when adopted and approved in its final version at CD-2, will remain in effect until the completion of the NSTX Upgrade Project.  Revision and/or changes to this document will require approval in accordance with the project’s change approval levels.

Annex I - Work Breakdown Structure for the NSTX Upgrade Project

|  |  | 1.1 | Torus Systems |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 1.1.1 | Plasma Facing Components |
|  |  |  | 1.1.2 | Vacuum Vessel & Support Structure |
|  |  |  | 1.1.3 | Magnet Systems |
|  |  |  |  | 1.1.3.1 | Outer Polidal Field Coils |
|  |  |  |  | 1.1.3.2 | Outer Toroidal Field Coils |
|  |  |  |  | 1.1.3.3 | Center Stack Assembly |
|  |  |  |  |  | 1.1.3.3.1 | TF Inner legs |
|  |  |  |  |  | 1.1.3.3.2 | Ohmic Heating Solenoid |
|  |  |  |  |  | 1.1.3.3.3 | Shaping Coils |
|  |  |  |  |  | 1.1.3.3.4 | Center Stack Casing |
|  |  | 1.2 | Plasma Heating and Current Drive Systems |
|  |  |  | 1.2.1 | High Harmonic Fast Wave |
|  |  |  | 1.2.2 | Coaxial Helicity Injection Current Drive |
|  |  |  | 1.2.3 | Electron Cyclotron Heating |
|  |  |  | 1.2.4 | Neutral Beam Injection |
|  |  |  |  | 1.2.4.1 | NBI-Project Support & Integration |
|  |  |  |  | 1.2.4.2 | NBI-Sources |
|  |  |  |  | 1.2.4.3 | NBI-Decontamination |
|  |  |  |  | 1.2.4.4 | NBI-Beamline |
|  |  |  |  | 1.2.4.5 | NBI-Services |
|  |  |  |  | 1.2.4.6 | NBI-Armor/Protective Plates |
|  |  |  |  | 1.2.4.7 | NBI-Power & Controls |
|  |  |  |  | 1.2.4.8 | NBI-Nozzle/Duct |
|  |  |  |  | 1.2.4.9 | NBI-Equipment Relocations |
|  |  | 1.3 | Auxiliary Systems |
|  |  |  | 1.3.1 | Vacuum Pumping System |
|  |  |  | 1.3.2 | Coolant Systems |
|  |  |  | 1.3.3 | Bakeout System |
|  |  |  | 1.3.4 | Gas Delivery Systems |
|  |  |  | 1.3.5 | Glow Discharge Cleaning System |
|  |  | 1.4 | Plasma Diagnostics |
|  |  |  | 1.4.1 | Plasma Diagnostics |
|  |  | 1.5 | Power Systems |
|  |  |  | 1.5.1 | AC Power Systems |
|  |  |  | 1.5.2 | TF Power Conversion Systems |
|  |  |  | 1.5.3 | PF/OH Power Conversion System |
|  |  |  | 1.5.4 | CHI Power Conversion System |
|  |  |  | 1.5.5 | General Power Systems and Integration |
|  |  | 1.6 | Central Instrumentation & Control |
|  |  |  | 1.6.1 | Control System |
|  |  |  | 1.6.2 | Data Acquisition System |

|  |  | 1.7 | Project Support & Integration |
| --- | --- | --- | --- |
|  |  |  | 1.7.1 | Project Management & Integration |
|  |  |  | 1.7.2 | Project Physics |
|  |  |  | 1.7.3 | Integrated Systems Test |
|  |  | 1.8 | Site Preparation and Torus Assembly |
|  |  |  | 1.8.1 | Site Preparation |
|  |  |  | 1.8.2 | Torus Assembly & Construction |

# ANNEX II – NSTX UPGRADE PROJECT Contingency Approach

Contingencies are quantified based on a bottom-up assessment of uncertainties and risks at the job level.

Estimate uncertainties are a function of the complexity and maturity of a job.  Jobs are ranked on a high-medium-low scale for both parameters.  The rankings are documented in the job Work Authorization Forms (WAFs).  An uncertainty range is assigned based on the rankings: from -5% / +10% to -30% / +60%.

Risks are identified at the job level and higher levels, and documented in a project-wide risk registry. The risk registry provides a management tool that the project uses to track risks and mitigation activities so as to actively minimize their consequences.  For purposes of estimating contingency, the likelihood of each risk occurring and its cost and schedule impacts were estimated.

# Comments

Good.  This is important to remember from lessons learned from NCSX.

Ron to review.  This section of the PEP will be our “risk management plan”.  No stand alone PLAN-RMP will exist....just a living risk registry.  Further, move/incorporate Annex II into this section.  Also add verbiage about using scope contingency if necessary.

Erik to add verbiage to further describe how PPPL will acquire the material and labor.  Note:  The Acquisition Strategy is about how DOE will satisfy the mission need gap....the AS is a separate document signed by Synakowski.

Whats this?

Move/incorporate to Risk Management Section above.