## Slide 1
Closeout
of the
National Spherical Torus
Experiment (NSTX)
at
Princeton Plasma Physics Laboratory
December 16, 2009
Daniel R. Lehman
Review Committee Chair
Office of Science, U.S. Department of Energy
http://www.science.doe.gov/opa/

## Slide 2: Review Committee Participants
Department of Energy Daniel Lehman, SC, Chairperson
Review Committee Observers
Technical Ed Synakowski, DOE/SC
Charles Greenfield, GA Barry Sullivan, DOE/SC
Arnie Kellman, GA Jeff Makiel, DOE/PSO
Brad Nelson, ORNL Jerry Faul, DOE/PSO
Tom McManamy, ORNL* Brian Huizenga, DOE/OECM
Cost and Schedule
Kin Chao, DOE/SC*
Gordon Fox, DOE/SC
Management and ES&H
John Haines, ORNL*
Frank Crescenzo, SC-CH
*Lead

## Slide 3: 2.1 Magnets & Core Tom McManamy, ORNL; Brad Nelson, ORNL;
1. Is the selected approach to upgrade the NSTX device technically sound?
Yes, the approach to upgrade the centerstack field and pulse length capability appear to be conservative and technically sound.
Based on the current stage of project, have all the appropriate project risks been identified?
Yes, the project has identified important technical risks and provided mitigation plans in a risk register. However, availability of specific, key persons is included as a risk in only one case.
Has the project satisfied the documentation requirements for CD-1 as required by DOE Order 413.3A?
Yes, the project has provided all the prerequisite documentation.

## Slide 4: 2.1 Magnets & Core Tom McManamy, ORNL; Brad Nelson, ORNL;
4
Findings
The center stack upgrade task includes a new, larger diameter centerstack with additional PF coils, new PFC tiles, new TF joint design and structural reinforcement for the TF and PF coils.
The design process is well advanced for this stage of the project. Requirements are specified in an approved General Requirements Document. Significant electromagnetic, thermal, and mechanical analyses have been performed to evaluate design options and confirm design choices.
The project convened an external conceptual design review in October. The review committee provided a positive technical review with some recommendations. The project has evaluated the recommendations and accepted almost all of them.
Cost estimates are documented in Work Authorization Forms. The labor hours are based on previous experience doing very similar work. Most of the cost (78%) is PPPL labor. The costs of the more extensive coil support structure and the Digital Coil Protection System (DCPS) are both included at this point, representing conservative assumptions.

## Slide 5: 2.1 Magnets & Core Tom McManamy, ORNL; Brad Nelson, ORNL;
5
Comments
The inclusion of the DCPS to limit extreme load conditions seems prudent. However, there may be additional normal and fault load conditions that have not been considered, such as loss of cooling for single turns, and lateral and torsional loads on the centerstack bellows and insulators. It may be a good time to update the Failure Modes and Effects Analysis (FMEA) with an eye toward identifying as many of these loading conditions as possible
The shear stress in the TF bundle insulation is fairly high, and the project is embarking on R&D to confirm that the chosen solution is acceptable. Any design solutions that would reduce this shear stress should be investigated.
The centerstack has been removed, repaired, and replaces several times to date. It may be useful to consider how the existing centerstack could be re-used in the event of failure of the new centerstack.
It was not possible to review all the detailed analysis, which is very advanced for this stage of the project. Since it is all being done internally, the project could consider external peer reviews / verification of key aspects of the analysis.

## Slide 6: 2.1 Magnets & Core Tom McManamy, ORNL; Brad Nelson, ORNL;
6
Comments
The new TF joint design looks much better than the old design, although it results in a trapped OH coil. R&D planned for winding and flexible joint testing seems prudent.
Divertor tile temperature of 2400C seems too high for design point, 1500-1700C is more typical
PFC tiles are much thicker and larger than previous design, but electromagnetic loads have not been checked yet. Use of CFC tiles is not justified by heat loading, but may be justified from operational/handling standpoint.

## Slide 7: 2.1 Magnets & Core Tom McManamy, ORNL; Brad Nelson, ORNL;
7
Recommendations (prior to CD-2)
Update Failure Modes and Effects Analysis to ensure any new failure modes / loading conditions associated with the upgrade are mitigated
Consider the 40 kA design for the solenoid to reduce coolant pressure and voltage. The additional cabling from the power supplies to reach the higher current can be added later.
Add the availability of additional key personnel to risk registry

## Slide 8: 2.2 Neutral Beams Arnie Kellman, GA; Charles Greenfield, GA
1. Is the selected approach to upgrade the NSTX device technically sound?
The plan for decontaminating the TFTR beamline and sources and installation on NSTX is technically sound and meets all the requirements of the NB GRD.
2. Based on the current stage of project, have all the appropriate project risks been identified?
Yes. The risks have been identified and a risk registry has been prepared for the beamline task.
Has the project satisfied the documentation requirements for CD-1 as required by DOE Order 413.3A?
Yes. All documentation has been prepared.

## Slide 9
Findings
  The proposed neutral beam upgrade includes decontamination of a TFTR beamline and three ion sources, and installation on NSTX including all neutral beam support systems.
  Power supplies from TFTR will be reused. Although they use tubes that are no longer commercially available, there is an ample supply of spares and PPPL has the capability to rebuild them.
  Installation and operation of the second beamline follows, for the most part, the process of installation and operation of the original beamline, which has been in use for almost a decade on NSTX.
  Decontamination of three ion sources and beamline is presently underway and significant reductions in contamination are being obtained.
2.2 Neutral Beams Arnie Kellman, GA; Charles Greenfield, GA

## Slide 10: 2.2 Neutral Beams Arnie Kellman, GA; Charles Greenfield, GA
Comments:
  The plan presented by the NSTX on the NB upgrade team was clear, technically sound, and well advanced at this stage in the design process. The major technical issues have been sufficiently addressed to provide confidence in the success of this upgrade.
  The prior experience of low contamination of the NSTX vessel using decontaminated TFTR ion sources on BL1 provides confidence that the use of the three additional sources will not significantly impact NSTX contamination levels.
  Data presented on the progress on decontamination of ex-TFTR beamline for BL2 indicated that the process is successfully lowering contamination levels and indications are that these levels remain low. If this trend continues and the cleanup of the copper pieces remains low, this should provide cost saving opportunities to the project.
  Present decontamination efforts indicate that most of the copper parts can be reused because reappearance of surface contamination has not occurred. However, additional releases due to heating during operation cannot be ruled out based on experience so far.

## Slide 11: 2.2 Neutral Beams Arnie Kellman, GA; Charles Greenfield, GA
Comments:
  The evaluation of the tasks to move and reinstall the second beamline was thorough. Control and support systems will largely duplicate the systems on BL1 so there are no significant technical concerns associated with this task.
  The concern expressed by the CDR review panel on the large vessel cutout was well addressed by the design of the port cap. This design provides improved vessel strength and an improved margin between beam edge and the side of the port.
  The project should resist any inclination to delay reinstallation of existing diagnostics in order to save money
  Protection of the neutral beam armor based on plasma current or density is less reliable than real-time monitoring of the surface temperature
  Although it is not on critical path, the two large bellows are long lead and expensive items and early vendor searches and evaluations may be able to reduce cost and schedule risk. Large cost variations and levels of experience exist among manufacturers of large bellows in the US and abroad.

## Slide 12: 2.2 Neutral Beams Arnie Kellman, GA; Charles Greenfield, GA
Recommendations (Before CD-2):
  Perform tests of a heated decontaminated copper part to confirm that tritium levels remain low
  Consider methods to improve estimates of contamination levels in NSTX due to residual NBI source and beamline contamination and evaluate impact on operation and maintenance of NSTX
  Estimate the increased activation level of the vessel due to the longer pulse and high power operation and the resulting increased dose to workers
  Consider alternative methods of protecting the NB armor tiles from excessive heating using real time monitoring of the surface temperature
  Consider replacing old CAMAC hardware with modern technology
  Additional effort should be directed at evaluating the process of machining and installation of the large midplane port to reduce schedule and cost risk
  Perform early vendor (both domestic and foreign) search for the large bellows
  Re-examine the design to determine whether one of the large bellows can be eliminated
  The full cost of all diagnostic relocations should be included in the project costs

## Slide 13: 2.3 Ancillary Tom McManamy, ORNL; Brad Nelson, ORNL
. Is the selected approach to upgrade the NSTX device technically sound?
Yes – there is a very good basis from NSTX experience
Based on the current stage of project, have all the appropriate project risks been identified?
Yes – good development of risks
Has the project satisfied the documentation requirements for CD-1 as required by DOE Order 413.3A?
Yes – the level of documentation is actually more detailed then is typical for this stage

## Slide 14: 2.3 Ancillary Tom McManamy, ORNL; Brad Nelson, ORNL
Findings
The Ancillary Systems include the water cooling system modifications for the Central stack, bakeout System mods, gas delivery system mods., Center Stack Diagnostics for CSU and the CSU Power Systems
Documentation of design requirements, system design descriptions and cost estimates were provided for all systems
The OH Power Supply system is designed for 20 minutes between shots while the TF Power Supply system is designed for 40 minutes between shots.
Additional cables and approximately $400,000 would be needed to have a 20 minute capability for the TF system
An option to run the OH coils at 40 kA to reduce the coil insulation requirements and allow a lower cooling water pressure would require an additional power supply system cost of approximately $500,000.
A digital coil protection system which would limit off normal loads on the coil support systems has been included in the project

## Slide 15: 2.3 Ancillary Tom McManamy, ORNL; Brad Nelson, ORNL
Comments
Design requirements, tasks and design descriptions were well documented
The scope of work is very similar to previous experience with NSTX installation and upgrades
The Power Supply systems were the largest cost element and the cost estimate was well developed
Power Supply equipment from TFTR has been evaluated to ensure operability and spares are available from unused modules
The reliability of the protection system must be well defined if the structural system is reduced assuming it functions properly
The ability to run with a 20 minute period between shots would appear to be a significant benefit to the operational program.

## Slide 16: 2.3 Ancillary Tom McManamy, ORNL; Brad Nelson, ORNL
Recommendations – to be completed prior to CD-2
Evaluate including the additional TF cabling and bus leads to allow a 20 minute shot repetition rate
Obtain operational experience for control systems from other facilities in order to determine the expected reliability and the level of redundancy required to achieve a desired overall reliability
Complete a Failure Modes and Effects evaluation

## Slide 17: 3 and 4. Cost, Schedule, and Funding Kin Chao, DOE/SC Gordon Fox, DOE/SC
3. Is the proposed cost and schedule range, including contingency, realistic and reasonable? Yes, the cost appears adequate.
Has the project satisfied the documentation requirements for CD-1 as required by DOE Order 413.3A? Yes--the project has developed all the required documents. However, these documents need to be updated and approved prior to CD-1.

## Slide 18: 3. Cost Estimate Kin Chao, DOE/SC Gordon Fox, DOE/SC
18
Findings
At this stage of the project, the TPC range is estimated to be $74M to $98M including 10% to 35% contingency in the constrained case, and 10%to 36% contingency in the unconstrained case.
The project has spent ~$6.4M to date.
Overall cost estimate was generated via individual Work Authorization Forms (WAF) prepared by Job Managers. The basis of estimate consists of 41% engineering judgment, 23.6% previous PPPL experience, 5.3% catalog/vendor quote, and 29.7% other.
Risks have been identified, mitigation strategies considered and cost/schedule impacts quantified in the risk registry. Risks are reviewed and updated monthly.
The project engineering, design, management, inspection, administration, ES&H, (EDIA) is $24.3M or ~53% of construction costs excluding contingency.

## Slide 19: 3. Cost Estimate Kin Chao, DOE/SC Gordon Fox, DOE/SC
19
Findings
The cost breakdown consists of 78% PPPL labor, 12% sub-contract, and 10% in materials.
The standing army cost is ~$242K per month, needed for management and health physics support, and allocations.
The project has developed all required documents needed for CD-1 approval.
The project has not performed a value engineering study, but will be conducting such a study prior to CD-2. It is assumed by the project that some cost savings will result from the VE study.

## Slide 20: 3. Cost Estimate Kin Chao, DOE/SC Gordon Fox, DOE/SC
20
Management | $7,596
Engrg/Dsn/R&D(~<CD3) | $16,797
Non-Labor(Sub-Contract&Matl) | $18,001
Install/T-III (~>CD3) | $28,442
Total | $70,836
Chart: 
| Labor | Material | Sub-Contract
 | 54373.7 | 7299.1 | 8581.2
Labor | $54,374
Material | $7,299
Sub-Contract | $8,581
Total | $70,254

## Slide 21: 3. Cost Estimate Kin Chao, DOE/SC Gordon Fox, DOE/SC
21
Comments
At this stage of the project, the proposed cost estimate, including contingency appears adequate.
However, based on the management, engineering, and design cost breakdown presented, these costs appear high and project should find efficiencies to reduce this cost.
The project has also developed all the required documents. However, these documents need to be updated and approved prior to CD-1.
Project should work with OFES to develop a plan that is consistent with a mutually agreed funding profile and meets technical scope, cost, and schedule requirements with adequate contingency.

## Slide 22: 3. Cost Estimate Kin Chao, DOE/SC Gordon Fox, DOE/SC
22
Recommendations
Develop a mutually agreed funding profile between OFES Program and the project by January 2, 2010
Update all project documents and submit for CD-1 approval.

## Slide 23: 4. Schedule Estimate Kin Chao, DOE/SC Gordon Fox, DOE/SC
23
Findings
The project CD-4 date is scheduled for May 2014 or May 2015, which includes ~7.2months of contingency, depending on the funding profile assumed (constrained or unconstrained profiles).
The project schedule estimate is developed based on durations and resource requirement input from the Job Managers.
The project has a resource loaded schedule, including the critical path, which consists of ohmic heating coil design and fabrication, centerstack activities, and integrated system testing.
The project is proposing to purchase long lead items including
  Inner TF Bundle Manufacture Inner TF Copper extrusions ($240K)
  Inner TF Bundle Machine Inner TF conductors [grooves, lead area] ($250K)
  OHMIC Heating Coil (OH) Manufacture OH Copper conductor [extrusion] ($105K)
  Inner TF Bundle Friction Stir-Weld coil leads conductors ($250K)
The funding profiles are shown in the next page. At this time, the project has not assumed any impact from Continuing Resolution.
Schedules do not indicate anticipated Critical Decision approval dates, but rather the dates for the request or submissions.

## Slide 24: 4. Schedule Estimate Kin Chao, DOE/SC Gordon Fox, DOE/SC
24
Comments

## Slide 25: 4. Schedule Estimate Kin Chao, DOE/SC Gordon Fox, DOE/SC
25
Comments
The project expects to find potential schedule acceleration opportunities based on the VE analysis to be performed prior to CD-2. At this stage of the project, the proposed schedule estimate, including contingency appears generally reasonable.
Project should work with OFES to develop a plan that is consistent with a mutually agreed funding profile and meets technical scope, cost, and schedule requirements with adequate contingency.
Schedule should show actual CD approval dates, in lieu of request dates since the approval date provides the required authority for the project to proceed further.
The project should consider risk associated with reduced funding due to CR, especially those years where there is a large increase in funds from the previous year.

## Slide 26: 4. Schedule Estimate Kin Chao, DOE/SC Gordon Fox, DOE/SC
26
Recommendations
Develop a mutually agreed funding profile between OFES Program and the project by January 2, 2010.
Update all project documents and submit for CD-1 approval.

## Slide 27: 5. Management and ES&H John Haines, ORNL; Frank Crescenzo, SC-CH
3. Based on the current stage of project, have all the appropriate project risks been identified?
    Yes; risk registry developed with input from project team
4. Given the current stage of the project, is the project's management structure and team appropriate, and are the plans to support the next phase of the project sufficient?
    Yes; structure defined and all key positions filled
5. Has the project satisfied the documentation requirements for CD-1 as required by DOE Order 413.3A?
    All documents created, but some updating needed (see recommendation)
Are Environmental, Safety and Health aspects being properly addressed given the project's current stage of development?
  Yes; determination that project is below Haz Cat 3 nuclear facility looks robust

## Slide 28: 5. Management and ES&H
Findings
NSTX Upgrade project organization has been established and key management positions are filled with experienced staff members
All documents and submittals required for CD-1 have been developed, at least in draft form
An external Conceptual Design Review of the NSTX Upgrade project was held in preparation for CD-1
Two funding profiles, “unconstrained” and “constrained” by an assumed funding profile, were developed resulting in project durations from 48 months to 60 months

## Slide 29: 5. Management and ES&H
Findings (continued)
PPPL labor amounts to 75% of TPC
Project is seeking approval to procure four long lead items
Two potential scope optimization and reduction items were identified for value engineering consideration prior to CD-2
  Structure vs. machine protection
  Eliminate/defer supporting physics scenarios that are large cost drivers
Time-phased staffing needs were identified by labor category
CD-4 deliverables identified in PPEP
Assessment of vulnerable inventory shows that NSTX remains well below Hazard Category 3 Nuclear Facility

## Slide 30: 5. Management and ES&H
Comments
PPPL management should consider adding NSTX Upgrade Project advisory committees comprised of external members with experience on large DOE projects that meet regularly and provide advice and guidance to the PPPL director on status and health of the project
  Management advisory committee
  Technical advisory committee
Project should follow-through on proposed value engineering items prior to CD-2

## Slide 31: 5. Management and ES&H
Comments
Ensure engineering and technician resources are available in a timely fashion and used efficiently to minimize project costs
  A realistic load leveling exercise should be factored into the schedule to ensure that durations of key elements of the project, especially the two year NSTX shutdown, are adequate
The need for procuring long lead items prior to CD-2 should be reconsidered after the project schedule is updated with a more realistic funding profile
Consider external peer review of evaluation that resulted in Hazard Category 3 exclusion
Consider more clearly showing Mike William’s key role in project documentation

## Slide 32: 5. Management and ES&H
Recommendations
Work with OFES to develop a plan that is consistent with a mutually agreed funding profile and meets technical scope, cost, and schedule requirements with adequate contingency (Prior to CD-1)
  Include agreement on CD-4 completion requirements
  Update all documents based on this realistic project funding profile and submit for CD-1 approval
Establish project management and technical advisory committees that meet regularly and report to PPPL director on NSTX Upgrade project status