## Sheet1
Chit# | Comment/Recommendation/Concern | Originator | Board Disposition | Review Board Comment/ Recommendation | Cognizant Engineer Disposition | RLM Review | Cognizant Engineer Closeout
1 | Latest OH currents are -24, 0, +24 kA. The design so far is based on OH current of -24, 0, 13 kA. Need to determine if forces envelope has expanded and what consequence is to design (Mangra) | Mangra | Concur | Action Titus to check
2 | Jim C - Use correct no. of turns and current on PF coils in presentaion. | Menard | Concur | Action: Chrzanowski
3 | Make sure surface area of contact between tiles and backing surface is sufficient for disruption current and heat loads | Menard | Concur | Action: Tresemer
4 | TF coil alignment, what is the requirement can the spring supports be pushed / held in place for installation (note there is no metrology data on OTF leg locations) | Priniski | Concur | Action: Mangra
5 | “Organ pipe” elbows sealing gasket is trapped or unreplaceable | Priniski | Concur | Action: Chrzanowski
6 | Provide substantial clearance between TF coil brace and Thomson scattering support structure. Clearance should at least be 1 inch | LeBlanc | Concur | Action: Mangra to provide clearance
7 | Labik needs to get a model of the 30” flange modification to Danny Mangra to verify compatibiltiy with external upgrade hardware | Dudek | Concur | Action: Labik provide to Mangra
8 | Can the Bay K cap for NB be modified to accommodate the MPTS Laser Dump. | Dudek | Other | Action: Labik to investigate
9 | Raki - Check parameters on Inner PF coils on VG for correctness? (Typo) | Dudek | Concur | Action: Ramakrishnan
10 | Is the 10Gbit/sec network required as part of the GRD? | Dudek | Concur | Action: Sichta
11 | Consider allowing slight adjustment capability (+- 1/16”) for vertical tiles along center stack. Allows “flats” machine on tile surfaces as microwave reflectors to be moved to compensate for clocking difference between CS and outer vacuum vessel. | Kaita | Concur | Action: Tresemer
12 | Produce a TF/OH manufacturing plan, including a fabrication facility design, for the PDR. Identify hardware that needs to be purchased “a schedule” This is a task we want to get started on before the FR/CD3 thus we need to ask for DOE permission. | Strykowsky | Concur | Action: Chrzanowski
13 | Develop design for MPTS VV interface and incorporate into the project scope. Generate WAF for the entire MPTS relocation but only include the VV interface into the project Scope. | Strykowsky | Concur | Action: Labik
14 | What R&D wont be complete by the PDR and clearly show what assumptions are being made for estimating purposed. What impacts if R&R isnt successful (show in risk registry) | Strykowsky | Concur | Action: Chrzanowski
15 | Resolve I&C requirements. Paul should estimate scope as presented and resolve during a WAF review meeting. | Strykowsky | Concur | Action: Sichta
16 | Tresemer's bolt connection (Dzus fastening tech) looks like the profile will produce large stresses in the tile. Tailor the countersink appropriately. Interesting concept though. | Freudenberg | Concur | Action: Tresemer
17 | Corner stress on the TF leg shown by Willard looks like stress discontinuity, would tweak geometry, move hole and add more material before mesh refinement to see if it can be eliminated. Also, look at stress linearization and apply NSTX criteria for evaluation. | Freudenberg | Concur | Action: Willard
18 | I see both Von Mises and Tresca stress results shown, Typically Tresca is what is requested in codes, not sure what NSTX design criteria states. | Freudenberg | Concur | Action: Titus
19 | For Superbolts - torque-load curve may not match manufacturer. No bellevills with Supers. Presentation showed bolts designed typical sm value (2/3SY). Typically, bolts can do to at least 80% proof. | Freudenberg | Concur | Action: Willard
20 | CTD 101K - other large fusion projects use a variant of this which may offer a cost reduction (2X). | Freudenberg | Concur | Action: Chrzanowski
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52