## Sheet1
NSTX UPGRADE CD-2 COST ESTIMATE
| Project Estimate |  |  |  | Lehman Estimate
DESCRIPTION | BASE | Contingency | TPC | % Contingency (on ETC from 5/1/2010) | ACWP | ETC | Contingency | % | TPC | Actual Cost | ACT CODE | FY 2009 | FY 2010
Job: 1000 - CSU Analytical Support-TITUS | 393.5 | 132.7822 | 526.2822 | 36.83% | 33 | 360.5 |  | 0% |  | 1000 - Job: 1000 - CSU Analytical Support-TITUS | 1000 |  | 33 | 33
Job: 1001 - CS Plasma Facing Components-TRESEMER | 2499.4 | 760.1046 | 3259.5046 | 33.32% | 218.5 | 2280.9 |  | 0% |  | 1001 - Job: 1001 - CS Plasma Facing Components-TRESEMER | 1001 | 64.6 | 153.9 | 218.5
Job: 1002 -Passive Plate Analysis &Upgrade-TITUS | 170.8 | 31.6611 | 202.4611 | 33.4% | 76 | 94.8 |  | 0% |  | 1002 - Job: 1002 -Passive Plate Analysis &Upgrade-TITUS | 1002 |  | 76 | 76
Job: 1200 - Vacuum Vsl & Struct Support-SMITH | 1182.9 | 15 | 1197.9 | 0% | 1182.9 | 0 |  | 0% |  | 1200 - Job: 1200 - Vacuum Vsl & Struct Support-SMITH | 1200 | 571.7 | 611.2 | 1182.9
Job: 1201 - Outer TF Structures-SMITH | 427.4 | 92.5523 | 519.9523 | 21.65% | 0 | 427.4 |  | 0%
Job: 1202 - Outer PF2 Coil Structures-SMITH | 63 | 14.6786 | 77.6786 | 23.3% | 0 | 63 |  | 0%
Job: 1203 - PF3 Support.-SMITH | 34.7 | 6.8954 | 41.5954 | 19.87% | 0 | 34.7 |  | 0%
Job: 1204 - PF4/5 Leads & Radial Supports-SMITH | 28.2 | 20.9284 | 49.1284 | 74.21% | 0 | 28.2 |  | 0%
Job: 1205 - Umbrella-SMITH | 516.6 | 159.128 | 675.728 | 30.8% | 0 | 516.6 |  | 0%
Job: 1206 - Pedestal -SMITH | 111.9 | 29.2663 | 141.1663 | 26.15% | 0 | 111.9 |  | 0%
Job: 1207 - Vessel Legs -SMITH | 33.7 | 7.3026 | 41.0026 | 21.67% | 0 | 33.7 |  | 0%
Job: 1208 - PF4&5 Verticle Support-SMITH | 290.2 | 95.3162 | 385.5162 | 32.85% | 0 | 290.2 |  | 0%
Job: 1220 - Misc Structural Design-SMITH | 142.1 | 58.6266 | 200.7266 | 41.26% | 0 | 142.1 |  | 0%
Job: 1300 - Center Stack-CHRZANOWSKI | 1052.3 | 100.7581 | 1153.0581 | 10.02% | 47 | 1005.3 |  | 0% |  | 1300 - Job: 1300 - Center Stack-CHRZANOWSKI | 1300 |  | 47 | 47
Job: 1301 - Outer TF Coils-CHRZANOWSKI | 316 | 105.7548 | 421.7548 | 33.63% | 1.5 | 314.5 |  | 0% |  | 1301 - Job: 1301 - Outer TF Coils-CHRZANOWSKI | 1301 |  | 1.5 | 1.5
Job: 1303 - TF Joint Test Stand&Test-KOZUB | 350.2 | 89.293 | 439.493 | 27.7% | 27.8 | 322.4 |  | 0% |  | 1303 - Job: 1303 - TF Joint Test Stand&Test-KOZUB | 1303 |  | 27.8 | 27.8
Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | 2380.8 | 1122.4916 | 3503.2916 | 49.31% | 104.3 | 2276.5 |  | 0% |  | 1304 - Job: 1304 - Inner TF Bundle (Ds/Fab)-CHRZANOWSKI | 1304 |  | 104.3 | 104.3
Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | 4446.7 | 1183.6335 | 5630.3335 | 36.73% | 1224.1 | 3222.6 |  | 0% |  | 1305 - Job: 1305 - OHMIC Heating Coil (OH)-CHRZANOWSKI | 1305 | 1055.6 | 168.5 | 1224.1
Job: 1306 - Inner PF Coils-CHRZANOWSKI | 651.4 | 166.5748 | 817.9748 | 27.99% | 56.3 | 595.1 |  | 0% |  | 1306 - Job: 1306 - Inner PF Coils-CHRZANOWSKI | 1306 |  | 56.3 | 56.3
Job: 1307 - CS Casing Assembly -CHRZANOWSKI | 900.4 | 238.2588 | 1138.6588 | 28.14% | 53.8 | 846.6 |  | 0% |  | 1307 - Job: 1307 - CS Casing Assembly -CHRZANOWSKI | 1307 |  | 53.8 | 53.8
Job: 1310 - CSU Magnet Systems-CHRZANOWSKI | 459.9 | 0 | 459.9 | 0% | 459.9 | 0 |  | 0% |  | 1310 - Job: 1310 - CSU Magnet Systems-CHRZANOWSKI | 1310 |  | 459.9 | 459.9
Job: 1302 - Center Stack Assembly-CHRZANOWSKI | 891.7 | 245.6076 | 1137.3076 | 27.54% | 0 | 891.7 |  | 0%
Job: 2300 - ECH Analysis-TITUS | 142.7 | 75.7288 | 218.4288 | 54.64% | 4.1 | 138.6 |  | 0% |  | 2300 - Job: 2300 - ECH Analysis-TITUS | 2300 |  | 4.1 | 4.1
Job: 2420 - 2nd NBI Sources-CROPPER | 1090.7 | 173.9332 | 1264.6332 | 15.95% | 0 | 1090.7 |  | 0%
Job: 2425 - BL Relocation-DENAULT | 1656.4 | 221.748 | 1878.148 | 13.78% | 46.8 | 1609.6 |  | 0% |  | 2425 - Job: 2425 - BL Relocation-DENAULT | 2425 | 15 | 31.8 | 46.8
Job: 2430 - 2nd NBI Decontamination-STEVENSON | 2087.7 | 54.5169 | 2142.2169 | 15% | 1724.3 | 363.4 |  | 0% |  | 2430 - Job: 2430 - 2nd NBI Decontamination-STEVENSON | 2430 | 1238.5 | 485.8 | 1724.3
Job: 2440 - 2nd NBI Beamline-DENAULT | 2436.3 | 349.7689 | 2786.0689 | 14.57% | 34.9 | 2401.4 |  | 0% |  | 2440 - Job: 2440 - 2nd NBI Beamline-DENAULT | 2440 | 28.6 | 6.3 | 34.9
Job: 2450 - 2nd NBI Services-DENAULT | 4433.6 | 512.407 | 4946.007 | 12.1% | 200 | 4233.6 |  | 0% |  | 2450 - Job: 2450 - 2nd NBI Services-DENAULT | 2450 | 76.7 | 123.3 | 200
Job: 2460 - 2nd NBI Armor-PRINISKI | 766.3 | 105.8608 | 872.1608 | 18.04% | 179.5 | 586.8 |  | 0% |  | 2460 - Job: 2460 - 2nd NBI Armor-PRINISKI | 2460 | 35.8 | 143.7 | 179.5
Job: 2470 - 2nd NBI Power-RAKI | 3258.4 | 693.3027 | 3951.7027 | 22.63% | 195.4 | 3063 |  | 0% |  | 2470 - Job: 2470 - 2nd NBI Power-RAKI | 2470 | 115.2 | 80.2 | 195.4
Job: 2475 - 2nd NBI Controls-CROPPER | 1911.7 | 267.7382 | 2179.4382 | 14.01% | 0 | 1911.7 |  | 0%
Job: 2480 - 2nd NBI/TVPS Duct | 2214.6 | 509.8123 | 2724.4123 | 26.41% | 283.9 | 1930.7 |  | 0% |  | 2480 - Job: 2480 - 2nd NBI/TVPS Duct & VV-PRINISKI | 2480 | 183.4 | 100.5 | 283.9
Job: 2485 - Vacuum Pumping System-PRINISKI | 328.2 | 46.8183 | 375.0183 | 14.51% | 5.5 | 322.7 |  | 0% |  | 2485 - Job: 2485 - Vacuum Pumping System-PRINISKI | 2485 |  | 5.5 | 5.5
Job: 2490 - NTC Equipt Relocations-PERRY | 3482.4 | 612.1772 | 4094.5772 | 19.02% | 263.4 | 3219 |  | 0% |  | 2490 - Job: 2490 - NTC Equipt Relocations-PERRY | 2490 | 143 | 120.4 | 263.4
Job: 3200 - Water Cooling System Mods-DENAULT | 229.5 | 22.2684 | 251.7684 | 9.999% | 6.8 | 222.7 |  | 0% |  | 3200 - Job: 3200 - Water Cooling System Mods-DENAULT | 3200 | 5.4 | 1.4 | 6.8
Job: 3300 - Bakeout System Mods for CSU-RAKI | 83.1 | 16.6354 | 99.7354 | 20.02% | 0 | 83.1 |  | 0%
Job: 3400 - Gas Delivery System Mods-BLANCHARD | 125.9 | 25.9607 | 151.8607 | 20.95% | 2 | 123.9 |  | 0% |  | 3400 - Job: 3400 - Gas Delivery System Mods-BLANCHARD | 3400 |  | 2 | 2
Job: 4100 - Center Stack Diagnostics-KAITA | 808.6 | 129.033 | 937.633 | 16.45% | 24 | 784.6 |  | 0% |  | 4100 - Job: 4100 - Center Stack Diagnostics-KAITA | 4100 | 11 | 13 | 24
Job: 4500 - MPTS VV Modification | 1028.8 | 375.7133 | 1404.5133 | 36.52% | 0 | 1028.8 |  | 0%
Job: 5000 - CSU Power Systems-RAKI | 1068.5 | 0 | 1068.5 | 0% | 1068.5 | 0 |  | 0% |  | 5000 - Job: 5000 - CSU Power Systems-RAKI | 5000 | 385.8 | 682.7 | 1068.5
Job: 5001 - AC Power-RAKI | 71.5 | 7.157 | 78.657 | 10.01% | 0 | 71.5 |  | 0%
Job: 5002 - AC/DC Converters-RAKI | 56.6 | 5.6568 | 62.2568 | 9.994% | 0 | 56.6 |  | 0%
Job: 5003 - FCPC PF5 DC Systems-RAKI | 0 | 0 | 0 | 0% | 0 | 0 |  | 0%
Job: 5004 - TA-NTC DC Systems-RAKI | 112.6 | 27.6865 | 140.2865 | 24.59% | 0 | 112.6 |  | 0%
Job: 5005 - FCPC DC PF1 & TF Systems-RAKI | 1673.3 | 392.2583 | 2065.5583 | 23.44% | 0 | 1673.3 |  | 0%
Job: 5006 - Control & Protection-RAKI | 1889.7 | 303.945 | 2193.645 | 16.08% | 0 | 1889.7 |  | 0%
Job: 5007 - Systems Design & Integration-RAKI | 683.8 | 68.3183 | 752.1183 | 9.991% | 0 | 683.8 |  | 0%
Job: 5008 - Digital Coil Protection-RAKI | 1490 | 372.503 | 1862.503 | 25% | 0 | 1490 |  | 0%
Job: 5501 - Coil Bus Runs-SMITH | 1104.5 | 286.1064 | 1390.6064 | 27.26% | 54.8 | 1049.7 |  | 0% |  | 5501 - Job: 5501 - Coil Bus Runs-SMITH | 5501 |  | 54.8 | 54.8
Job: 6100 - Control Sys Data Acquisition -SICHTA | 920.9 | 180.6026 | 1101.5026 | 19.95% | 15.5 | 905.4 |  | 0% |  | 6100 - Job: 6100 - Control Sys Data Acquisition -SICHTA | 6100 |  | 15.5 | 15.5
Job: 7100 - Project Mgt & Integration-STRYKOWSKY | 5579.4 | 475 | 6054.4 | 10.83% | 1194.9 | 4384.5 |  | 0% |  | 7100 - Job: 7100 - Project Mgt & Integration-STRYKOWSKY | 7100 | 625.8 | 569.1 | 1194.9
Job: 7200 - Center Stack Management-DUDEK | 1480.4 | 208.324 | 1688.724 | 14.94% | 85.6 | 1394.8 |  | 0% |  | 7200 - Job: 7200 - Center Stack Management-DUDEK | 7200 |  | 85.6 | 85.6
Job: 7300 - NB2 Management-STEVENSON | 1597 | 210.1747 | 1807.1747 | 14.29% | 126.4 | 1470.6 |  | 0% |  | 7300 - Job: 7300 - NB2 Management-STEVENSON | 7300 | 63.3 | 63.1 | 126.4
Job: 7400 - Health Physics Support-STEVENSON | 2562.9 | 332.4771 | 2895.3771 | 13.83% | 158.1 | 2404.8 |  | 0% |  | 7400 - Job: 7400 - Health Physics Support-STEVENSON | 7400 |  | 158.1 | 158.1
JOB: 7700 - NSTX-U HP Allocations-STRYKOWSKY | 2452.5 | 277.287 | 2729.787 | 12.64% | 259.5 | 2193 |  | 0% |  | 7700 - JOB: 7700 - NSTX-U HP Allocations-STRYKOWSKY | 7700 |  | 259.5 | 259.5
Job: 7710 - Upgrade Allocations-STRYKOWSKY | 761.9 | 55.237 | 817.137 | 26.84% | 556.1 | 205.8 |  | 0% |  | 7710 - Job: 7710 - Upgrade Allocations-STRYKOWSKY | 7710 | 526.3 | 29.8 | 556.1
Job; 8200 - CS & Coil Sprt Struc Install- VIOLA | 5707.1 | 2072 | 7779.1 | 36.43% | 20.2 | 5686.9 |  | 0% |  | 8200 - Job; 8200 - CS & Coil Sprt Struc Install- VIOLA | 8200 |  | 20.2 | 20.2
Job: 8250 - Remove/Install Centerstack-PERRY | 1130.9 | 230.6525 | 1361.5525 | 20.4% | 0 | 1130.9 |  | 0%
Job: 7900 - Integrated System-GENTILE | 76 | 15.9457 | 91.9457 | 22.21% | 4.2 | 71.8 |  | 0% |  | 7900 - Job: 7900 - Integrated System Test-GENTILE | 7900 |  | 4.2 | 4.2
schedule (months) |  | 2259.5333 | 2259.5333 |  |  |  | 2259.5333 | - | 2259.5333 |  |  | 5145.7 | 4853.8 | 9999.5
Base Estimate(early schedule)= | 73848.2 | 16650.9031 | 90499.1031 |  | 9999.5 | 63848.7 | 2259.5333 | 3.539% | 2259.5333
Contingency % = | 26.08%
26.08%