## risk cost incurred profile
Cost incurred profile (weighted cost)
Sum of Weighted Cost included in contingency | Cost incurred plan (if not retired)
Affected Job | FY11 | FY11,12 | FY11,12,13,14 | FY12 | FY12,13,14 | FY13 | FY14 | (blank) | Grand Total
1000 | 26 | [7 empty] | 26
1001 | [5 empty] | 145 |  | 0 | 145
1002 | 12 | [7 empty] | 12
1200 | 15 | [6 empty] | 0 | 15
1300 | [7 empty] | 0 | 0
1301 | [5 empty] | 25 |  |  | 25
1302 | [7 empty] | 0 | 0
1303 | 26.5 | [7 empty] | 26.5
1304 | 25 |  |  |  |  | 82.5 |  |  | 107.5
1305 | [5 empty] | 431.25 |  | 0 | 431.25
1306 | [5 empty] | 25 |  |  | 25
1307 | [7 empty] | 0 | 0
2300 | 47.5 | [6 empty] | 0 | 47.5
2420 | [7 empty] | 0 | 0
2425 | [7 empty] | 0 | 0
2430 | [7 empty] | 0 | 0
2440 | [7 empty] | 0 | 0
2450 | [7 empty] | 0 | 0
2460 | [7 empty] | 0 | 0
2470 | [7 empty] | 0 | 0
2475 | [7 empty] | 0 | 0
2480 | [7 empty] | 0 | 0
2485 | [7 empty] | 0 | 0
2490 |  |  |  | 73.5 |  |  |  | 0 | 73.5
3200 | [7 empty] | 0 | 0
3300 | [7 empty] | 0 | 0
3400 | [6 empty] | 0.5 |  | 0.5
4100 | [7 empty] | 0 | 0
5100 | [7 empty] | 0 | 0
5200 | [7 empty] | 0 | 0
5300 | [7 empty] | 0 | 0
5400 | [7 empty] | 0 | 0
5500 | [7 empty] | 0 | 0
5501 | [7 empty] | 0 | 0
6100 | 1.25 |  |  |  |  | 0 | 87.5 |  | 88.75
7100 | 37.5 | [6 empty] | 0 | 37.5
7200 |  | 26.75 | [5 empty] | 0 | 26.75
7300 |  | 18.75 | [6 empty] | 18.75
7400 |  |  |  |  | 21 |  |  | 0 | 21
7700 | [5 empty] | 78 |  |  | 78
7710 |  |  | 51.6 | [5 empty] | 51.6
7900 | [7 empty] | 0 | 0
8200 | [5 empty] | 502 | 34 | 0 | 536
8250 | [6 empty] | 60.55 |  | 60.55
Grand Total | 190.75 | 45.5 | 51.6 | 73.5 | 21 | 1288.75 | 182.55 | 0 | 1853.65
| 190.75 | 45.5 | 51.6 | 73.5 | 21 | 1288.75 | 182.55 | 1853.65
| FY10 | FY11 | FY12 | FY13 | FY14
| 0 | 226.4 | 116.15 | 1308.65 | 202.45 |  | 1853.65 | 0

## risk by job
Data
Affected Job | Sum of Cost considered | Sum of Weighted Cost included in contingency
1000 | 80 | 26
1001 | 496 | 145
1002 | 20 | 12
1200 | 60 | 15
1300 | 0 | 0
1301 | 100 | 25
1302 | 0 | 0
1303 | 130 | 26.5
1304 | 430 | 107.5
1305 | 1725 | 431.25
1306 | 100 | 25
1307 | 0 | 0
2300 | 125 | 47.5
2420 | 0 | 0
2425 | 0 | 0
2430 | 0 | 0
2440 | 0 | 0
2450 | 0 | 0
2460 | 0 | 0
2470 | 0 | 0
2475 | 0 | 0
2480 | 0 | 0
2485 | 0 | 0
2490 | 294 | 73.5
3200 | 0 | 0
3300 | 0 | 0
3400 | 10 | 0.5
4100 | 0 | 0
5100 | 0 | 0
5200 | 0 | 0
5300 | 0 | 0
5400 | 0 | 0
5500 | 0 | 0
5501 |  | 0
6100 | 375 | 88.75
7100 | 150 | 37.5
7200 | 107 | 26.75
7300 | 75 | 18.75
7400 | 35 | 21
7700 | 130 | 78
7710 | 86 | 51.6
7900 | 0 | 0
8200 | 1120 | 786
8250 | 287 | 60.55
Grand Total | 5935 | 2103.65

## Sheet1
Sum of Cost considered | Deadline to Retire Risk or Absorb Impact
Risk Description | CD-4 | FY10 PDR | FY11 1304-0600 | FY11 FDR | FY12 1001-0066 | FY13 | FY13 1301-0060 | FY13 1302-1500 | FY13 1304-1890 | FY13 1304-5400 | FY13 1305-8700 | FY13 1305-8800 | FY13 1306-5050 | FY13 1307-2030 | FY14 | FY14 3400-0052 | FY14 CD-4 | Installation of cryo lines | Issue requisition for bellows fabrication | OH coil fabrication | Vessel machining | (blank) | Grand Total
Additional reviews | [16 empty] | 182 | [5 empty] | 182
After press mold operation, numerous dry areas are found | [6 empty] | 50 | [15 empty] | 50
All interferences with existing equipment have not been identified |  | 60 | [20 empty] | 60
Analysis indicates a minor component needs upgrade that previously hasn't been identified - weld details, details that are inconsistent with the Pro-E model |  | 40 | [20 empty] | 40
Analysis indicates a significant component needs upgrade that previously hasn't been identified |  | 40 | [20 empty] | 40
Availability of key personnel: Chrzanowski, Mangra, Titus |  | 0 | [20 empty] | 0
Availability of V. Garzotto | [21 empty] | 0 | 0
Beam too close to bellows/duct |  | 0 | [20 empty] | 0
CFC tiles needed for thermal/structural reasons |  | 0 | [20 empty] | 0
Coil does not pass final acceptance tests | [6 empty] | 50 | [15 empty] | 50
Coil fails final acceptance tests. | [12 empty] | 50 | [9 empty] | 50
Components arrive late | [13 empty] | 0 | [8 empty] | 0
Components do not arrive when required | [7 empty] | 0 | [14 empty] | 0
Copper extrusion vendor has difficulty making full length conductors |  |  | 100 | [19 empty] | 100
Damage to coil insulation during removal - This is in case we accidentally nick or gouge the outer insulation. | [5 empty] | 40 | [16 empty] | 40
Data acquisition takes too long |  |  |  | 25 | [18 empty] | 25
Diagnostic/waveguide hqas a present weakness that hasn't been seen in operation |  |  |  | 0 | [18 empty] | 0
Diagnostic/waveguide requires more analysis to qualify |  |  |  | 25 | [18 empty] | 25
Difficulty machining vessel | [20 empty] | 0 |  | 0
Engineering total man-hours >1 engineer | [21 empty] | 0 | 0
EPICS data acquisition takes too long |  | 0 | [20 empty] | 0
EVMS implementation requires more project controls, supporrt for training, etc than expected |  |  |  | 150 | [18 empty] | 150
Existing copper parts may be reusable (except for the dump) |  | 0 | [20 empty] | 0
Flex bus require more than two fit-ups / reworks prior to final installation | [16 empty] | 189 | [5 empty] | 189
Fueling lines do not adequately deliver gas because of occlusions or leaks | [15 empty] | 10 | [6 empty] | 10
Further inspections may require additional parts and labor |  | 0 | [20 empty] | 0
Halo and New/other disruption loads are beyond the capacity of the present hardware |  | 20 | [20 empty] | 20
Heat load may be too high | [17 empty] | 0 |  |  |  |  | 0
Increased number of redesign/retest cycles |  | 50 | [20 empty] | 50
J-K cap may not be able to be installed in one piece | [21 empty] | 0 | 0
Longer time to remove diagnostics for access | [21 empty] | 0 | 0
Loss of key personnel | 50 | [21 empty] | 50
LOWEUS re-design and re-installation may require more effort than estimated due to the physical constraints in the area of bay L |  |  |  | 147 | [18 empty] | 147
MPTS Beam Dump Window re-design and re-installation may require more effort than estimated due to the physical constraints in the area of bay L |  |  |  | 0 | [18 empty] | 0
No vendor bids for OH/TF fabrication | [19 empty] | 0 |  |  | 0
None | [21 empty] | 0 | 0
NSTX operations does not fund work scope as listed in WBS6100 PDR | 300 | [21 empty] | 300
OH bundle - poor VPI impregnation | [11 empty] | 500 | [10 empty] | 500
OH coil fails electrical tests | [11 empty] | 500 | [10 empty] | 500
Old 100 micron fiber cables that are proposed to be used may not be in good condition |  |  |  | 0 | [18 empty] | 0
Old RCA tubes are being used and may need a tune-up | [21 empty] | 0 | 0
Outboard Divertor tile and hardware replacement, approx 1300 tiles, 26000 in^3 of material |  |  |  | 0 | [18 empty] | 0
Passive Plate Tiles/hardware need upgrading: Possibly ~2050 tiles |  |  |  | 436 | [18 empty] | 436
Passive Plate Tiles/hardware need upgrading: Possibly ~3500 tiles, 70000 in^3, replacing with 2D CFC |  |  |  | 1000 | [18 empty] | 1000
Poor impregnation | [12 empty] | 50 | [9 empty] | 50
Poor VPI of TF bundle | [8 empty] | 165 | [13 empty] | 165
PPPL overhead rates | [16 empty] | 0 | [5 empty] | 0
Previous fabricators of rectangular bellows not available | [18 empty] | 0 |  |  |  | 0
Realign Coils - This is in case the coils spring or change shape after releasing them from their existing clamps. This could afect the algnment of all any coil mounted to the vessel wall/ribs. | [14 empty] | 40 | [7 empty] | 40
Realign vacuum vessel - This is in case the vessel springs or changes shape after cutting the new port opening. This could affect the algnment of all the vessel internals mounted to the vessel wall. | [14 empty] | 40 | [7 empty] | 40
remove LLD and replace with existing OD tiles | [21 empty] | 0 | 0
Schedule is front end loaded | [21 empty] | 0 | 0
Significant change in TF design concept |  | 50 | [20 empty] | 50
Special diagnostics for tiles not received on time
SPRED re-design and re-installation may require more effort than estimated due to the physical constraints in the area of bay L |  |  |  | 147 | [18 empty] | 147
TF coil fails electrical tests | [8 empty] | 165 | [13 empty] | 165
TF full bundle - poor VPI impregnation | [9 empty] | 250 | [12 empty] | 250
TF full bundle fails electrical tests | [9 empty] | 75 | [12 empty] | 75
TF quadrant - poor VPI impregnation | [8 empty] | 200 | [13 empty] | 200
TF quadrant fails electrical tests | [8 empty] | 200 | [13 empty] | 200
Tiles not delivered on time
Tiles require unforseen machining | [7 empty] | 60 | [14 empty] | 60
Umbrella lids require more than two fit-ups / reworks prior to final installation | [16 empty] | 42 | [5 empty] | 42
Unable to completely remove temporary spacer between OH and TF after completion of fabrication | [10 empty] | 0 | [11 empty] | 0
Unexpected technical challenges in implementing testing apparatus and procedures |  | 30 | [20 empty] | 30
Unplanned overtime | [16 empty] | 35 | [5 empty] | 35
Upgrade may increase EM loads to small items on vessel that may need reinforcement, e.g. shutters, ECH, brackets,diagnostic supports. |  | 100 | [20 empty] | 100
Vacuum seals don't pass leakcheck | [16 empty] | 56 | [5 empty] | 56
Volatility of base estimates for the allocated cost centers | [5 empty] | 108 | [16 empty] | 108
Volatility of head rates | [5 empty] | 43 | [16 empty] | 43
Volatility of overhead rates | [5 empty] | 65 | [16 empty] | 65
Volume of data from diagnostic camera systems exceed capability of network, storage, and backup systems |  | 0 | [20 empty] | 0
Grand Total | 350 | 390 | 100 | 1930 |  | 256 | 100 | 60 | 730 | 325 | 0 | 1000 | 100 | 0 | 80 | 10 | 504 | 0 | 0 | 0 | 0 | 0 | 5935

## RISK REGISTRY
| NSTX Upgrade Project Risk Registry, rev 15 |  |  |  |  | Revisions shown in red. |  |  | VL= | 90% |  |  | L= | 60% | U= | 25% | VU= | 5%
Project Manager's assessment
Updated | Number | Affected Job | Job Title | Risk Description | Mitigation Plan (& job where budgeted) | Deadline to Retire Risk or Absorb Impact | Cost incurred plan (if not retired) | Owner | Current Status | Likelihood of Occurrence | Consequences | Risk Ranking | Basis of Estimate | Cost Impact ($K) | Critical Path Schedule Impact (weeks) | Cost and Schedule Impact Calculation Basis | Cost considered | Weighted Cost included in contingency | Rationale
2010-07-16 | 1001d | 1001 |  | Passive Plate Tiles/hardware need upgrading: Possibly ~2050 tiles | Design and fab 2D CFC | FY11 FDR | FY13 | Tresemer | open | U | Significant | Moderate |  | 436 |  |  | 436 | 109
2009-12-08 | 1000b | 1000 |  | Analysis indicates a minor component needs upgrade that previously hasn't been identified - weld details, details that are inconsistent with the Pro-E model | Identify these areas early with site surveys and as-builts | FY10 PDR | FY11 | Titus | open | L | Negligible | Low | manager's experience | 10 to 40 |  | manager's estimate | 40 | 24
2009-12-08 | 1000a | 1000 | Centerstack Analytical Support | Analysis indicates a significant component needs upgrade that previously hasn't been identified | Maintain upgrades of the model and keep ahead of the scenario changes | FY10 PDR | FY11 | Titus | open | VU | Negligible | Low | manager's experience | 10 to 40 |  | manager's estimate | 40 | 2
2010-07-29 | 1001d | 1001 |  | Outboard Divertor tile and hardware replacement, approx 1300 tiles, 26000 in^3 of material | Finalize disruprtion and thermal load analysis by FDR. Should replcement be necessary option to defer until later in ops by limiting machine paramters (no cost/schedule impact but tech perf impact) or replace all affetced PP and tiles during the planned outage (sign cost impact little schedule impact) | FY11 FDR | FY13 | Tresemer | open | L | Significant | Moderate | Retired. Existing OBD tiles will be used inplace of the LLD. | 2200 |  |  | 0 | 0 | 145 | 48
2010-06-15 | 1001c | 1001 |  | Tiles require unforseen machining | If schedule critical, and in-house machinining will not suffice, seek external machining sources. Additional machining time added to WAF | FY13 1302-1500 | FY13 | Tresemer | open | L | Negligible | Low | prior experience on NSTX | 15 to 60 | 1 to 4 | 3 machinists for 1 to 4 weeks | 60 | 36
2009-12-08 | 1001b | 1001 |  | Special diagnostics for tiles not received on time | If schedule critical, install tiles in vessel. | FY12 1001-0066 |  | Tresemer | open | U |  |  | prior experience on NSTX | 0 |  |  |  | 0
2009-12-08 | 1001a | 1001 | Centerstack Plasma Facing Components | Tiles not delivered on time | If schedule critical, install tiles in vessel. | FY12 1001-0066 |  | Tresemer | open | U |  |  | prior experience on NSTX | 0 |  |  |  | 0
2010-06-15 | 1002a | 1002 | Passive Plate Analysis | Halo and New/other disruption loads are beyond the capacity of the present hardware | Size modifications based on calculations and implement | FY10 PDR | FY11 | Titus | open | L | Negligible | Low | Project Manager's estimate | 5 to 20 | 0 | 1 to 4 weeks of designer | 20 | 12
2010-06-15 | 1200c | 1200 |  | Schedule is front end loaded | obtain requested resources |  |  | Mangra | open | VL | Negligible | Low |  | 0 |  |  | 0 | 0
2010-06-15 | 1200b | 1200 |  | Engineering total man-hours >1 engineer | obtain requested resources |  |  | Mangra | open | VL | Negligible | Low |  | 0 |  |  | 0 | 0
2009-12-08 | 1200a | 1200 | Centerstack Structural Supports | All interferences with existing equipment have not been identified | Field audit of interferences is included in estimate. audit included in base estimate | FY10 PDR | FY11 | Mangra | Retired | U |  |  | manager's experience | 60 | 0 | 6 weeks of engineer and designer | 60 | 15
2010-06-15 | 1301b | 1301 |  | Coil does not pass final acceptance tests | Attempt local repair; if unsuccessful, rebuild coil | FY13 1301-0060 | FY13 | Chrzanowski | open | U | Negligible | Low | manager's estimate | 50 | 0 | repeat existing tasks | 50 | 12.5
2010-06-15 | 1301a | 1301 | Outer TF Coil Repairs | After press mold operation, numerous dry areas are found | Attempt local repair; if unsuccessful, rebuild coil | FY13 1301-0060 | FY13 | Chrzanowski | open | U | Negligible | Low | manager's estimate | 50 | 0 | repeat existing tasks | 50 | 12.5
2009-12-08 | 1302a | 1302 | Centerstack Assembly | Components do not arrive when required | If schedule is critical, OT or second shift would be required to regain schedule | FY13 1302-1500 |  | Chrzanowski | open | U | Negligible | Low |  | 0 |  |  | 0 | 0
2009-12-08 | 1303c | 1303 |  | Unexpected technical challenges in implementing testing apparatus and procedures | Perform additional work | FY10 PDR | FY11 | Kozub | open | VU | Negligible | Low | manager's estimate | 0 to 30 |  | past experience | 30 | 1.5
2009-12-08 | 1303b | 1303 |  | Increased number of redesign/retest cycles | Perform additional work | FY10 PDR | FY11 | Kozub | open | U | Negligible | Low | manager's estimate | 10 to 50 |  | past experience | 50 | 12.5
2009-12-08 | 1303a | 1303 | TF Joint Test Stand and Testing | Significant change in TF design concept | Perform additional work | FY10 PDR | FY11 | Kozub | open | U | Negligible | Low | manager's estimate | 10 to 50 |  | past experience | 50 | 12.5
2010-06-15 | 1304c | 1304 |  | Copper extrusion vendor has difficulty making full length conductors |  | FY11 1304-0600 | FY11 | Chrzanowski | open | U | Marginal | Low | manager's estimate | 100 |  |  | 100 | 25
2009-12-08 | 1304b | 1304 |  | TF coil fails electrical tests | If fault area cannot be repaired, rebuild coil | FY13 1304-1890 | FY13 | Chrzanowski | open | U | Marginal | Low | manager's estimate | 165 | 0 | repeat fabrication tasks | 165 | 41.25
2009-12-08 | 1304a | 1304 | Inner TF Bundle Design and Fabrication | Poor VPI of TF bundle | If repairs cannot be made, rebuild coil | FY13 1304-1890 | FY13 | Chrzanowski | open | U | Marginal | Low | manager's estimate | 165 | 0 | repeat fabrication tasks | 165 | 41.25
2010-06-15 | 1305h | 1305 |  | Unable to completely remove temporary spacer between OH and TF after completion of fabrication | Administrative controls during operation requiring OH and TF to be powered together | FY13 1305-8700 |  | Chrzanowski | open | U | Marginal | Low |  | 0 |  |  | 0 | 0
2010-06-15 | 1305g | 1305 |  | OH coil fails electrical tests | If fault can not be repaired, Coil must be cut off and rebuilt | FY13 1305-8800 | FY13 | Chrzanowski | open | U | Significant | Moderate |  | 500 |  |  | 500 | 125
2010-06-15 | 1305f | 1305 |  | OH bundle - poor VPI impregnation | Evaluate condition of coil - Local dry areas could be repaired, but larger failure would require cutting OH coil from TF and rebuilding OH | FY13 1305-8800 | FY13 | Chrzanowski | open | U | Significant | Moderate |  | 500 |  |  | 500 | 125
2010-06-15 | 1305e | 1305 |  | TF full bundle fails electrical tests | Repair electrical short | FY13 1304-5400 | FY13 | Chrzanowski | open | U | Negligible | Low |  | 75 |  |  | 75 | 18.75
2010-06-15 | 1305d | 1305 |  | TF full bundle - poor VPI impregnation | Evaluate condition of coil - Local dry areas could be repaired, but larger failure would requireseparating quadrants and re-assy and VPI of bundle | FY13 1304-5400 | FY13 | Chrzanowski | open | U | Marginal | Low |  | 250 |  |  | 250 | 62.5
2010-06-15 | 1305c | 1305 |  | TF quadrant fails electrical tests | If unable to repair short, rebuild quadrant | FY13 1304-1890 | FY13 | Chrzanowski | open | U | Marginal | Low | manager's estimate | 200 | 0 | cost to cut off coil and repeat fabrication tasks | 200 | 50
2010-06-15 | 1305b | 1305 |  | TF quadrant - poor VPI impregnation | Evaluate condition of coil - Local dry areas could be repaired, but larger failure would require rebuilding TF quadrant | FY13 1304-1890 | FY13 | Chrzanowski | open | U | Marginal | Low | manager's estimate | 200 | 0 | repeat fabrication tasks | 200 | 50
2009-12-08 | 1305a | 1305 | OH Coil Design and Fabrication | No vendor bids for OH/TF fabrication | Fabricate coil in-house [Suggest having bid process include both domestic and international] PPPL to fab | OH coil fabrication |  | Chrzanowski | Retired | U | [6 empty] | 0 | 0
2010-06-15 | 1306b | 1306 |  | Coil fails final acceptance tests. | If coil cannot be repaired, a new coil will need to be wound. | FY13 1306-5050 | FY13 | Chrzanowski | open | U | Negligible | Low | manager's estimate | 50 | 0 | repeat fabrication tasks | 50 | 12.5
2010-06-15 | 1306a | 1306 | Inner PF Coils Design and Fabrication | Poor impregnation | Local dry areas can be repaired. Extensive areas of poor VPI may require rewinding new coil. | FY13 1306-5050 | FY13 | Chrzanowski | open | U | Negligible | Low | manager's estimate | 10 to 50 | 0 | repeat fabrication tasks | 50 | 12.5
2009-12-08 | 1307a | 1307 | Centerstack Casing Assembly Design and Fabrication | Components arrive late | OT required to recover schedule | FY13 1307-2030 |  | Chrzanowski | open | U | Negligible | Low |  | 0 | 0 |  | 0 | 0
2010-06-15 | 2300c | 2300 |  | Diagnostic/waveguide requires more analysis to qualify | Expand analysis models beyond those used in the scoping study | FY11 FDR | FY11 |  | open |  | Negligible | Low |  | 25 |  |  | 25 | 22.5
2010-06-15 | 2300b | 2300 |  | Diagnostic/waveguide hqas a present weakness that hasn't been seen in operation | Reinforce | FY11 FDR |  |  | open |  | Negligible | Low |  | 0 |  |  | 0 | 0
2010-03-17 | 2300a | 2300 | Miscellaneous small appendage reinforcements on vessel | Upgrade may increase EM loads to small items on vessel that may need reinforcement, e.g. shutters, ECH, brackets,diagnostic supports. | Upgrade may increase EM loads to small items on vessel that may need reinforcement, e.g. shutters, ECH, brackets,diagnostic supports. | FY10 PDR | FY11 | Titus | open | U | Marginal | Low | project manager's estimate | 100 |  |  | 100 | 25
2010-02-17 | 2440b | 2440 |  | Existing copper parts may be reusable (except for the dump) | Negative risk - reduce scope of job - job estimate now includes reduced scope | FY10 PDR |  | Denault | Retired | L |  |  | project manager's estimate | -234 |  |  | 0 | 0
2010-02-16 | 2440a | 2440 | Beamline Refurbishment | Further inspections may require additional parts and labor | Inspect all parts promptly so damaged ones can be identified early - all parts and labor now in job estimate | FY10 PDR |  | Denault | Retired | U |  |  | project manager's estimate | 50 |  |  | 0 | 0
2010-02-17 | 2450b | 2450 |  | Heat load may be too high | Remake He lines - not a concern | Installation of cryo lines |  | Denault | Retired | U |  |  | project manager's estimate | 50 | 0 |  | 0 | 0
2009-12-08 | 2450a | 2450 | NB2 Services | Availability of V. Garzotto | Desandro / Denault could do this work- replacements available |  |  |  | Retired | [7 empty] | 0 | 0
2009-12-08 | 2460a | 2460 | NB Armor | CFC tiles needed for thermal/structural reasons | Add requirement for redundant plasma control to eliminate need for CFC tiles - Now in job | FY10 PDR |  | Priniski | Retired | L | [6 empty] | 0 | 0
2010-02-17 | 2470b | 2470 |  | Old 100 micron fiber cables that are proposed to be used may not be in good condition | Test a prototype with a 62.5 micron cable fused to 100 micron cable - sufficient 100 micron cable located on-site | FY11 FDR |  | Ramakrishnan | Retired | U |  |  | project manager's estimate | 50 |  | Past experience in installing the NB1 line up for NSTX | 0 | 0
2009-12-08 | 2470a | 2470 | NB Power System | Old RCA tubes are being used and may need a tune-up | Use the 8 additional tubes from TFTR - replacements available |  |  | Ramakrishnan | Retired | U | [5 empty] | Budgetary quotes received for Tiax and other cables and used in estimates | 0 | 0
2010-03-17 | 2480d | 2480 |  | Previous fabricators of rectangular bellows not available | Locate alternate vendors - RFQ with multiple vendors to access vendor and cost for PDR. | Issue requisition for bellows fabrication |  | Priniski | Retired | U |  |  | Project Manager's estimate | 10 to 100 |  |  | 0 | 0
2009-12-08 | 2480c | 2480 |  | J-K cap may not be able to be installed in one piece | Include removal of one TF outer leg (to facilitate access) in the baseline estimate - now in job |  |  | Priniski | Retired | U | [6 empty] | 0 | 0
2010-03-17 | 2480b | 2480 |  | Difficulty machining vessel | Double estimate for this portion of the job - several methods exist for cutting and job estimate was increased for least efficient process. | Vessel machining |  | Priniski | Retired | L |  |  | project manager's estimate | 10 to 70 | 1 to 8 | Past experience on NSTX | 0 | 0
2010-03-17 | 2480a | 2480 | NB2 Duct and VV Mods | Beam too close to bellows/duct | Include molybdenum shielding in estimate - Bay K port plug provides larger free apeture than BL. Some Moly shield for bellows included in job. | FY10 PDR |  | Priniski | Retired | L |  |  | project manager's estimate | 30 to 60 | 0 | Past experience on NSTX | 0 | 0
2010-06-15 | 2490c | 2490 |  | MPTS Beam Dump Window re-design and re-installation may require more effort than estimated due to the physical constraints in the area of bay L | Preliminary design work started to layout MPTS and included VV modifdactions and interfaces.- Job 4500 estimate included to provide larger Bay L port and MPTS interfaces. | FY11 FDR |  | Jones | Retired | U |  |  | Engineering estimate | included in NSTXU cost |  | Past experience designing and installing this diagnostic on NSTX | 0 | 0
2010-06-15 | 2490b | 2490 |  | LOWEUS re-design and re-installation may require more effort than estimated due to the physical constraints in the area of bay L | Start design work immediately so potential schedule impact can be accomodated if necessary. | FY11 FDR | FY12 | Jones | open | U | Marginal | Low | manager's estimate | 98 to 147 |  | Past experience designing and installing this diagnostic on NSTX | 147 | 36.75
2010-06-15 | 2490a | 2490 | Relocations to Support NB2 Installation | SPRED re-design and re-installation may require more effort than estimated due to the physical constraints in the area of bay L | Start design work immediately so potential schedule impact can be accomodated if necessary. | FY11 FDR | FY12 | Jones | open | U | Marginal | Low | manager's estimate | 98 to 147 |  | Past experience designing and installing this diagnostic on NSTX | 147 | 36.75
2009-12-08 | 3400a | 3400 | Gas Delivery system mods for Centerstack upgrade | Fueling lines do not adequately deliver gas because of occlusions or leaks | Replace gas delivery line | FY14 3400-0052 | FY14 | Blanchard | open | VU | Negligible | Low | Project manager's estimate | 10 |  | Similar installation on NSTX | 10 | 0.5
2009-12-08 | 6100b | 6100 |  | EPICS data acquisition takes too long | Include in the base job the upgrade of some data acquisition systems (CAMAC) | FY10 PDR | FY13 | Sichta | RETIRED | VL | Marginal | Moderate | Engineering estimate | 10 to 100 |  | Similar work at PPPL | 0 | 0
2010-07-25 | 6100d | 6100 | Loss of key personnel | Loss of key personnel | Assure project schedule has free float to absorb potential schedule impact. hire replacement and assess schedule impact | CD-4 | FY14 | Sichta | open | U | Marginal | Low | Estimated impact is < 1 months on the critical path. Impact on cost because untrained personnel will be less effective. | 10 to 50 | 0 to 4 |  | 50 | 12.5
2010-07-25 | 6100e | 6100 | Additional work scope | NSTX operations does not fund work scope as listed in WBS6100 PDR | Continued diligence to assure the program office funds req'd infrastructure improvements. Additional work scope for upgrade | CD-4 | FY14 | Sichta | open | U | Marginal | Low | Estimated impact is < 1 months on the critical path. Impact on cost due to additional workscope. | 50 to 300 | o to 4 |  | 300 | 75
2009-12-08 | 6100c | 6100 | Data Acquisition rate | Data acquisition takes too long | Upgrade additional data acq systems and/or networks, revise software | FY11 FDR | FY11 | Sichta | open | VU | Marginal | Low | Manager's estimate | 5 to 25 | 0 to 2 |  | 25 | 1.25
2009-12-08 | 6100a | 6100 | Central Instrumentation and Control | Volume of data from diagnostic camera systems exceed capability of network, storage, and backup systems | Install 10 Gb networks and enhance storage and backup systems | FY10 PDR | FY13 | Sichta | RETIRED | U | Marginal | Low | Engineering estimate | 30 to 200 |  | Similar work at PPPL | 0 | 0
2009-12-08 | 7100b | 7100 |  | PPPL overhead rates | Continue to ensure that outyear rates are conservative | FY14 CD-4 |  | Strykowsky | open | L |  |  | Project Manager's estimate | 682 (+/-) |  | Rates are typically conservative when set, but fluctuate as a function of the total lab funding. Pressure from indirect department may result in increased staff thus higher rates. -1% to +1% | 0 | 0
2010-03-17 | 7100a | 7100 | Project Management and Integration | EVMS implementation requires more project controls, supporrt for training, etc than expected | Assign experienced engineers as CAMs. Minimize the number of CAMs. New PM office. | FY11 FDR | FY11 | Strykowsky | open | U | Marginal | Low | Project Manager's estimate | 150 |  | 1/2 FTE for one year | 150 | 37.5
2010-03-24 | 7200b | 7200 |  | Availability of key personnel: Chrzanowski, Mangra, Titus | Chrzanowski by Heitzenroeder and Kalish; Mangra by Smith: Titus by Brooks and Heitzenroeder - back-up persons identified for key personnel | FY10 PDR |  | Dudek | Retired | [7 empty] | 0 | 0
2009-12-08 | 7200a | 7200 | Centerstack Management | Additional reviews | Increase scope as required | FY14 CD-4 | FY11,12 | Dudek | open | U | Marginal | Low | Manager's estimate | 107 |  | additional review every other year | 107 | 26.75
2010-03-17 | 7300a | 7300 | NB2 Management | Additional reviews | Increase scope as required | FY14 CD-4 | FY11,12 | Stevenson | Retired | U | Negligible | Low | Manager's estimate | 75 |  | additional review every other year | 75 | 18.75
2010-03-17 | 7400a | 7400 | Health Physics Support | Unplanned overtime | Increase scope as required included in job | FY14 CD-4 | FY12,13,14 | Stevenson | Retired | L |  |  | Project Manager's estimate | 35 |  | additional 10% | 35 | 21
2009-12-08 | 7700b | 7700 |  | Volatility of base estimates for the allocated cost centers | Increase as required | FY13 | FY13 | Strykowsky | open | L | Negligible | Low | Project Manager's estimate | 65 |  | 3% variation | 65 | 39
2009-12-08 | 7700a | 7700 | HP Allocations | Volatility of overhead rates | Increase as required | FY13 | FY13 | Strykowsky | open | L | Negligible | Low | Project Manager's estimate | 65 |  | 3% variation | 65 | 39
2009-12-08 | 7710b | 7710 |  | Volatility of base estimates for the allocated cost centers | Increase as required | FY13 | FY11,12,13,14 | Strykowsky | open | L | Negligible | Low | Project Manager's estimate | 65 |  | 100% | 43 | 25.8
2009-12-08 | 7710a | 7710 | Direct Allocations | Volatility of head rates | Increase as required | FY13 | FY11,12,13,14 | Strykowsky | open | L | Negligible | Low | Project Manager's estimate | 65 |  | 100% | 43 | 25.8
2010-06-15 | 8200e | 8200 |  | Passive Plate Tiles/hardware need upgrading: Possibly ~3500 tiles, 70000 in^3, replacing with 2D CFC | Finalize disruprtion and thermal load analysis by FDR. Should replcement be necessary option to defer until later in ops by limiting machine paramters (no cost/schedule impact but tech perf impact) or replace all affetced PP and tiles during the planned outage (sign cost impact little schedule impact) | FY11 FDR | FY13 | Tresemer | open | U | Significant | Moderate |  | 1000 |  | field removal of PP upgrade attachments and re-installPP | 1000 | 750
2010-07-16 | 8200d | 8200 |  | Realign Coils - This is in case the coils spring or change shape after releasing them from their existing clamps. This could afect the algnment of all any coil mounted to the vessel wall/ribs. | Metrology - new clamps | FY14 | FY14 | Viola | open | U | Negligible | Low | Manager's estimate | 40 |  |  | 40 | 10
2010-07-16 | 8200c | 8200 |  | Realign vacuum vessel - This is in case the vessel springs or changes shape after cutting the new port opening. This could affect the algnment of all the vessel internals mounted to the vessel wall. | Metrology | FY14 | FY14 | Viola | open | L | Negligible | Low | Manager's estimate | 40 |  |  | 40 | 24 | 786
2010-07-16 | 8200c | 8200 |  | remove LLD and replace with existing OD tiles | Perform disruption analysis on LLD or program decision on limiting operation.INCLUDE IN BASELINE |  |  | Viola | Retired | L |  |  | Manager's estimate | 0 |  |  | 0 | 0
2010-07-16 | 8200b | 8200 |  | Damage to coil insulation during removal - This is in case we accidentally nick or gouge the outer insulation. | repair coil | FY13 | FY13 | Viola | open | VU | Negligible | Low | Coil engineer (Chrzanowski) estimate | 40 |  |  | 40 | 2
2009-12-08 | 8200a | 8200 | Centerstack and Coil Structure Installation | Longer time to remove diagnostics for access | - incorporated into base plan |  |  | Viola | Retired | L | [6 empty] | 0 | 0
2009-12-08 | 8250c | 8250 |  | Umbrella lids require more than two fit-ups / reworks prior to final installation | Repeat "remove, rework, re-install" | FY14 CD-4 | FY14 | Viola | open | U | Negligible | Low | Construction Manager's estimate | 14 to 42 | 1 to 2 | Same work previous done on NSTX | 42 | 10.5
2009-12-08 | 8250b | 8250 |  | Flex bus require more than two fit-ups / reworks prior to final installation | Repeat "remove, rework, re-install" | FY14 CD-4 | FY14 | Viola | open | U | Marginal | Low | Construction Manager's estimate | 63 to 189 | 2 to 6 | Same work previous done on NSTX | 189 | 47.25
2009-12-08 | 8250a | 8250 | Centerstack Removal and Re-installation / Pumpdown / Bakeout | Vacuum seals don't pass leakcheck | Lift centerstack out, rework seals, re-install centerstack | FY14 CD-4 | FY14 | Viola | open | VU | Negligible | Low | Construction Manager's estimate | 28 to 56 | 1 to 2 | Same work previous done on NSTX | 56 | 2.8
2009-12-08 |  | 1300 | Centerstack Design Support | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 2420 | Source Refurbishment | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 2425 | NB2 Relocation | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 2430 | NB2 Decontamination | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 2475 | NB Controls and Instrumentation | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 2485 | NB2 TVPS | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 3200 | Water Cooling System Mods for Centerstack Upgrade | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 3300 | Bakeout System mods for Centerstack upgrade | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 4100 | Centerstack Diagnostics for Centerstack Upgrade | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 5100 | AC Power Systems | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 5200 | TF Power Conversion systems | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 5300 | PF/OH Power conversion System | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 5400 | CHI Power Conversion System | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 5500 | General Power Systems and Integration | None |  |  |  |  | None | [7 empty] | 0 | 0
2009-12-08 |  | 5501 | Coil Bus runs | None | [13 empty] | 0
2009-12-08 |  | 7400 | Health Physics support | none | [12 empty] | 0 | 0
2009-12-08 |  | 7900 | Integrated Systems Test | none | [12 empty] | 0 | 0
2009-12-08 |  | 7900 | Integrated System Test | none | [12 empty] | 0 | 0
[17 empty] | 5935 | 2103.65
Risks Identified at CD-0
35.44%
2009-12-08 | CD0-a |  |  | Uncertain of ability to find a cost effective TF joint that works at higher fields | Perform extensive analysis (all operating scenarios) for new joint designs |  |  | Dudek | Retired - extensive analysis proves joint design is more robust even at new operational levels
2009-12-08 | CD0-b |  |  | Little room to re-enforce outer TF legs and umbrella structure to handle higher loads | Perform detailed design |  |  | Dudek | Retired - detailed design shows that sufficient space exists
2009-12-08 | CD0-c |  |  | The vacuum vessel may need to be reinforced to accommodate higher loads |  |  |  | Dudek | Analysis shows that re-inforcing the vessel is only needed in a few locations
2010-03-17 | CD0-d |  |  | Uncertain of level of effort required to decontaminate TFTR NB |  |  |  | Stevenson | Retired - Decon has progressed such that BL can be characterized and NSTX impact projected for PDR.
2009-12-08 | CD0-e |  |  | Uncertain of the commercial availability of high voltage switch-tubes |  |  |  | Stevenson | Retired - There are enough tubes left from TFTR to support a second NB on NSTX
2009-12-08 | CD0-f |  |  | Uncertain of the commercial availability of cabling and terminations for the 100kV accelerator system |  |  |  | Stevenson | Retired - Contact with vendors has confirmed availability
2009-12-08
2009-12-08 | NCSX Lessons Learned
2009-12-08
2009-12-08 | NCSX-1 |  |  | Complete requisite R&D and designs prior to establishing a baseline. |  | PDR |  | Strykowsky | open
2009-12-08 | NCSX-2 |  |  | Implement rigorous, disciplined, and realistic cost estimating techniques early on. |  | CD-1 |  | Strykowsky | Retired - implemented
2009-12-08 | NCSX-3 |  |  | Conduct regular bottom-up estimates to complete (ETC) to identify and address cost and schedule issues. |  | CD-4 |  | Strykowsky | open
2010-03-17 | NCSX-4 |  |  | Develop and execute an effective risk management plan early on. |  | PDR |  | Strykowsky | Retired - implemented
2010-03-17 | NCSX-5 |  |  | Develop, maintain, and execute a staffing plan. |  | PDR |  | Strykowsky | Retired - implemented
2009-12-08 | NCSX-6 |  |  | Recognize the cost and schedule implications of using high technology tools at or near their capability limits. |  | PDR |  | Strykowsky | open
2010-03-17 | NCSX-7 |  |  | Develop strong ties with external resources in key technology areas, including those outside of your area of expertise. |  | PDR |  | Strykowsky | open, but note that CDR was performed by an independent committee of external experts
2010-03-17 | NCSX-8 |  |  | Build a strong, effective project managemnet organization early. |  | PDR |  | Strykowsky | Retired - implemented
2010-03-17 | NCSX-9 |  |  | Communicate and act. |  | CD-4 |  | Strykowsky | open
edp
2010-06-15