## Tab A Description
Work Approval Form (WAF)
Cost Center: 9417
Job Number:1001
Job Title: NSTX CS Upgrade PFCs
Job Manager: Kelsey Tresemer
Rev 5 7/13/2010
Description:
Provide adequate thermal coverage for the upgraded center stack via tiles. 1) Includes the design and analysis for both the CS and IBD plasma facing components. 2) Includes design modifications to the tiles to accommodate surface diagnostics 3) Includes design of tile mounting schemes and routing plan for diagnostics wires 4) Includes generation of required documentation such as checked calculations, specs and procedures. 5) Includes the procurement of all PFC tiles and hardware for the CS and IBD
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: 9417
Job Number:1001
Job Title: NSTX CS Upgrade PFCs
Job Manager: Kelsey Tresemer
Estimate (user input)
[5 empty] | SCHEDULE | [12 empty] | FY09$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10 | [16 empty] | FY11
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | ±% Risk | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-02 | 2011-07-03 | 2011-08-04 | 2011-09-05
numb | P3 cross ref (optinal) | [16 empty] | 1.18 | 1.18 | 1.63 | 1.1 | 1.77 | 176.86 | 118.62 | 135.02 | 101.34 | 172.17 | 83.39 | 150.89 | 89.06 | 145.67 | 120.58 | 158.91 | 150 | 150 | 150
1 |  | Conceptual Design | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
2 |  | Preliminary Planning / Fact finding |  | Tresemer | 20 |  |  |  | 2009-06-29 | 2009-06-29 | 2009-07-27 | 2009-06-29 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 80 | [9 empty] | 2
3 |  | Tile Layout/Prelimiinary Tile Design |  | Tresemer | 15 |  |  |  | 2009-07-06 | 2009-07-06 | 2009-07-27 | 2009-07-06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 120 | [14 empty] | 2
4 |  | Diagnostic Layout |  | Tresemer | 10 |  |  |  | 2009-07-27 | 2009-07-27 | 2009-08-10 | 2009-07-27 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 80 |  |  |  |  | 20 | [9 empty] | 2
5 |  | PPPL peer review prep |  | Tresemer | 4 |  |  |  | 2009-08-08 | 2009-08-08 | 2009-08-13 14:24 | 2009-08-08 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 32 |  |  |  |  | 16 | [9 empty] | 2
6 |  | PPPL peer review |  | Tresemer | 1 |  |  |  | 2009-08-13 | 2009-08-13 | 2009-08-14 09:36 | 2009-08-13 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 8 |  |  |  |  | 8 | [9 empty] | 2
7 |  | Tile/Diagnostic/Hardware Reconfig, Mat Research |  | Tresemer | 40 |  |  |  | 2009-08-14 | 2009-08-14 | 2009-10-09 | 2009-08-14 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 100 |  |  |  |  | 100 | [9 empty] | 2
8 |  | Initial Tile Thermal Analysis |  | Tresemer | 15 |  |  |  | 2009-09-14 | 2009-09-14 | 2009-10-05 | 2009-09-14 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [6 empty] | 80 | [5 empty] | 30 | [9 empty] | 2
9 |  | CDR prep |  | Tresemer | 5 |  |  |  | 2009-10-05 | 2009-10-05 | 2009-10-12 | 2009-10-05 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 40 |  |  |  |  | 30 | [9 empty] | 2
10 |  | CONDUCT CDR |  | Tresemer | 1 |  |  |  | 2009-10-13 | 2009-10-13 | 2009-10-14 09:36 | 2009-10-13 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 8 |  |  |  |  | 8 | [9 empty] | 2
11 | [11 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
12 |  | Preliminary Design | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
13 |  | CDR chit resolution |  | Tresemer | 10 |  |  |  | 2009-10-14 | 2009-10-14 | 2009-10-28 | 2009-10-14 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 30 | [12 empty] | -20% +20% |  | 2
14 |  | Tile Design Work |  | Tres/Jari | 160 |  |  |  | 2009-10-28 | 2009-10-28 | 2010-06-09 | 2009-10-28 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 1200 |  |  |  |  | 320 | [7 empty] | -20% +20% |  | 2
15 |  |  | Tile Fit and diagnostic Fit (and re-fit, per analysis) | Tres/Jari | [7 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [20 empty] | -20% +20%
16 |  |  | Wireway routes, diagnostic placement | Tres/Jari | [7 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [20 empty] | -20% +20%
17 |  |  | Preliminary Hardware fit (and re-fit, per analysis) | Tres/Jari | [7 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [20 empty] | -20% +20%
18 |  |  | Update preliminary drawings (non-assembly) | Tres/Jari | [7 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [20 empty] | -20% +20%
19 |  | Material Specs | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
20 |  |  | Make vendor contacts | Tresemer | 80 |  |  |  | 2009-10-28 | 2009-10-28 | 2010-02-17 | 2009-10-28 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 64 | [7 empty] | -20% +20% |  | 2
21 |  |  | NDA, Export Control Issues | Tresemer | 100 |  |  |  | 2010-03-18 | 2010-03-18 | 2010-08-05 | 2010-03-18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 32 | [7 empty] | -20% +20% |  | 2
22 |  | Preliminary Tile Analysis |  | Tresemer | [7 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
23 |  |  | Thermal | Tres/Jari | 80 |  |  |  | 2009-10-28 | 2009-10-28 | 2010-02-17 | 2009-10-28 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 20 |  |  |  |  | 64 | [7 empty] | -20% +20% |  | 2
24 |  |  | Forces | Tresemer | 50 |  |  |  | 2010-02-17 | 2010-02-17 | 2010-04-28 | 2010-02-17 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 20 |  |  |  |  | 40 | [7 empty] | -20% +20% |  | 2
25 |  |  | Fasteners | Tres/Jari | 30 | 24 |  |  | 2010-04-28 | 2010-04-28 | 2010-06-09 | 2010-04-28 | 2010-04-28 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 20 |  |  |  |  | 40 | [7 empty] | -20% +20% |  | 2
26 |  | PPPL Peer Review prep |  | Tresemer | 5 |  |  |  | 2010-04-21 | 2010-04-21 | 2010-04-28 | 2010-04-21 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 20 |  |  |  |  | 20 | [7 empty] | -20% +20% |  | 8, 2
27 |  | PPPL Peer Review |  | Tresemer | 1 |  |  |  | 2010-04-29 | 2010-04-29 | 2010-04-30 09:36 | 2010-04-29 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [6 empty] | 4 | 4 |  |  |  |  | 4 | [7 empty] | -20% +20% |  | 8, 2
28 |  | Update CS WAF |  | Tresemer | 25 |  |  |  | 2010-04-22 | 2010-04-22 | 2010-05-27 | 2010-04-22 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 40 | [7 empty] | -20% +20% |  | 8, 2
29 |  | PDR Prep |  | Tresemer | 10 |  |  |  | 2010-06-09 | 2010-06-09 | 2010-06-23 | 2010-06-09 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [6 empty] | 24 | 40 |  |  |  |  | 40 | [7 empty] | -20% +20% |  | 8
30 |  | CONDUCT PDR |  | Tresemer | 2 | 29 |  |  |  | 2010-07-30 08:06 | 2010-08-02 03:18 | 2010-07-30 08:06 | 2010-06-23 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [6 empty] | 16 | 16 |  |  |  |  | 16 | [7 empty] | -10% +10% |  | 8
31 |  |  | Receipt of Material data | Tresemer | 1 | 21 | 30 |  |  | 2010-08-05 | 2010-08-06 09:36 | 2010-07-30 08:06 | 2010-08-05 | 2010-08-02 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 2 | [7 empty] | -20% +20% |  | 2
32 |  |  | Order Samples for testing (6 wks lead) | Tresemer | 32 | 21 | 30 |  |  | 2010-08-05 | 2010-09-18 19:12 | 2010-07-30 08:06 | 2010-08-05 | 2010-08-02 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 |  | 15 | [10 empty] | 8 | [7 empty] | -20% +20% |  | 2, 6
33 |  | Final Design | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
34 |  | PDR chit resolution |  | Tresemer | 30 | 30 |  |  |  | 2010-08-02 03:18 | 2010-09-13 03:18 | 2010-07-30 08:06 | 2010-08-02 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 160 |  |  |  |  | 60 | [7 empty] | -20% +20% |  | 8, 2
35 |  |  | Drawings (with ongoing revisions) | Tresemer | 300 | 34 |  |  |  | 2010-09-13 03:18 | 2011-11-07 03:18 | 2010-07-30 08:06 | 2010-09-13 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 2200 | [12 empty] | -20% +20% |  | 8, 2
36 |  | Update WAF for Lehman Review (prep) |  | Tresemer | 30 | 30 |  |  |  | 2010-08-02 03:18 | 2010-09-13 03:18 | 2010-07-30 08:06 | 2010-08-02 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 24 |  |  |  |  | 60 | [7 empty] | -20% +20% |  | 4, 2
37 |  | Generic Tile Qualitfication Program |  | Brks/Tts/Brnt | 30 | 30 |  |  |  | 2010-08-02 03:18 | 2010-09-13 03:18 | 2010-07-30 08:06 | 2010-08-02 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [6 empty] | 200 | [5 empty] | 20 | [7 empty] | -20% +20%
[12 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
38 |  | Lehman Review |  | Tresemer | 2 | 36 |  |  | 2010-08-10 | 2010-08-10 | 2010-08-12 19:12 | 2010-08-10 | 2010-09-13 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 16 |  |  |  |  | 16 | [7 empty] | -10% +10% |  | 8
39 |  | Final Tile Analysis | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
40 |  |  | Disruption Forces | Brooks | 40 | 37 |  |  |  | 2010-09-13 03:18 | 2010-11-08 03:18 | 2010-07-30 08:06 | 2010-09-13 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [6 empty] | 280 | 40 |  |  |  |  | 20 | [7 empty] | -20% +20% |  | 4, 2
41 |  |  | Thermal system | Brooks | 15 | 40 |  |  |  | 2010-11-08 03:18 | 2010-11-29 03:18 | 2010-07-30 08:06 | 2010-11-08 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [6 empty] | 80 | [5 empty] | 10 | [7 empty] | -20% +20% |  | 4, 2
42 |  |  | Fastener Scheme | Tres/Jari | 10 | 40 | 41 |  |  | 2010-11-29 03:18 | 2010-12-13 03:18 | 2010-07-30 08:06 | 2010-11-08 03:18 | 2010-11-29 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 64 |  |  |  |  | 32 | [7 empty] | -20% +20% |  | 4, 2
43 |  | Fastener Design | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [22 empty] | 2
44 |  |  | Part re-design | Tres/Jari | 20 | 42 |  |  |  | 2010-12-13 03:18 | 2011-01-10 03:18 | 2010-07-30 08:06 | 2010-12-13 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 128 |  |  |  |  | 64 | [7 empty] | -20% +20% |  | 2
45 |  |  | Tile adjustments/drawings | Tres/Jari | 15 | 44 |  |  |  | 2011-01-10 03:18 | 2011-01-31 03:18 | 2010-07-30 08:06 | 2011-01-10 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 96 |  |  |  |  | 16 | [7 empty] | -20% +20% |  | 2
46 |  |  | Fastener Mock-up | Tresemer | 20 | 44 | 42 |  |  | 2011-01-10 03:18 | 2011-02-07 03:18 | 2010-07-30 08:06 | 2011-01-10 03:18 | 2010-12-13 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 64 |  |  |  |  | 32 | [7 empty] | -20% +20% |  | 2
47 |  |  | Testing | Tresemer | 15 | 46 |  |  |  | 2011-02-07 03:18 | 2011-02-28 03:18 | 2010-07-30 08:06 | 2011-02-07 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 30 | 40 | [6 empty] | -20% +20% |  | 2,6
48 |  | Material Testing | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
49 |  |  | Mechanical | Tresemer | 40 | 24 | 44 |  |  | 2011-01-10 03:18 | 2011-03-07 03:18 | 2010-07-30 08:06 | 2010-04-28 | 2011-01-10 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 80 |  |  |  |  | 64 | 72 | [6 empty] | -20% +20% |  | 8, 2
50 |  |  | Thermal | Tresemer | 20 | 49 |  |  |  | 2011-03-07 03:18 | 2011-04-04 03:18 | 2010-07-30 08:06 | 2011-03-07 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 20 | 128 | [6 empty] | -20% +20% |  | 8, 2
51 |  |  | Review Data | Tresemer | 10 | 50 |  |  |  | 2011-04-04 03:18 | 2011-04-18 03:18 | 2010-07-30 08:06 | 2011-04-04 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 32 | [7 empty] | -20% +20% |  | 8, 2
52 |  | PPPL Peer Review Prep |  | Tresemer | 5 |  |  |  | TBA |  |  |  |  | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 20 |  |  |  |  | 20 | [9 empty] | 8, 2
53 |  | PPPL Peer Review |  | Tresemer | 1 |  |  |  | TBA |  |  | TBA | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [6 empty] | 4 | 4 |  |  |  |  | 4 | [9 empty] | 8
54 |  | Make Material Choices |  | Tresemer | 5 | 51 |  |  |  | 2011-04-18 03:18 | 2011-04-25 03:18 | 2010-07-30 08:06 | 2011-04-18 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 20 | [7 empty] | -20% +20% |  | 2
55 |  | Finalize Designs/Drawings |  | Tresemer | 45 | 47 | 49 |  |  | 2011-03-07 03:18 | 2011-05-09 03:18 | 2010-07-30 08:06 | 2011-02-28 03:18 | 2011-03-07 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 320 |  |  |  |  | 144 | [7 empty] | -20% +20% |  | 8, 2
56 |  | Prep Procurement Specs |  | Tresemer | 15 | 55 |  |  |  | 2011-05-09 03:18 | 2011-05-30 03:18 | 2010-07-30 08:06 | 2011-05-09 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 30 | [7 empty] | -20% +20% |  | 4, 2
57 |  | FDR Prep |  | Tresemer | 20 |  |  |  | 2011-03-01 | 2011-03-01 | 2011-03-29 | 2011-03-01 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [7 empty] | 160 |  |  |  |  | 128 | [7 empty] | -20% +20% |  | 8, 2
58 |  | CONDUCT FDR |  | Tresemer | 2 | 57 |  |  | 2011-03-30 | 2011-03-30 | 2011-04-01 19:12 | 2011-03-30 | 2011-03-29 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [6 empty] | 16 | 16 |  |  |  |  | 16 | [7 empty] | -10% +10% |  | 8
59 | [23 empty] | 3392
60 | [11 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
61 |  | Procurement: |  | Tresemer | [7 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
62 |  | Item 1: Tiles (CFC) | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 |  | 900 | [19 empty] | tab D | 2, 6, 8
63 |  |  | Prep Requisition and Procurement Package |  | 10 | 58 | 56 |  |  | 2011-05-30 03:18 | 2011-06-13 03:18 | 2010-07-30 08:06 | 2011-04-01 19:12 | 2011-05-30 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 |  |  |  |  | 15 | [7 empty] | 20 | [7 empty] | -20% +20% |  | 2
64 |  |  | Submit Req. to Procurement |  | 2 | 63 |  |  |  | 2011-06-13 03:18 | 2011-06-15 22:30 | 2010-07-30 08:06 | 2011-06-13 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 4 | [7 empty] | -10% +10% |  | 2
65 |  |  | Procurement Lead Time |  | 40 | 64 |  |  |  | 2011-06-15 22:30 | 2011-08-10 22:30 | 2010-07-30 08:06 | 2011-06-15 22:30 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 32 | [7 empty] | -20% +20%
66 |  |  | Award |  | 1 | 65 |  |  |  | 2011-08-10 22:30 | 2011-08-12 08:06 | 2010-07-30 08:06 | 2011-08-10 22:30 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [20 empty] | -10% +10% |  | 2
68 |  |  | Fabricate and Deliver |  | 450 | 66 |  |  |  | 2011-08-12 08:06 | 2013-05-03 08:06 | 2010-07-30 08:06 | 2011-08-12 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 |  | 150 |  |  | 15 | [7 empty] | 384 | [7 empty] | -30% +30% | tab D | 8, 2
69 |  |  | Machine Tiles for Diagnostics |  | 50 | 68 |  |  |  | 2013-05-03 08:06 | 2013-07-12 08:06 | 2010-07-30 08:06 | 2013-05-03 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 |  | 23 | [18 empty] | -30% +30% | tab D | 8, 2
70 |  |  | Tile Bakeout |  | 40 | 69 |  |  |  | 2013-07-12 08:06 | 2013-09-06 08:06 | 2010-07-30 08:06 | 2013-07-12 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 |  | 20 | [18 empty] | -30% +30% |  | 2, 6, 8
71 |  | Item 2: hardware, other materials | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 |  | 170 | [20 empty] | 6, 8
72 |  |  | Prep Requisition and Procurement Package |  | 10 | 64 |  |  |  | 2011-06-15 22:30 | 2011-06-29 22:30 | 2010-07-30 08:06 | 2011-06-15 22:30 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 20 | [7 empty] | -20% +20% |  | 2
73 |  |  | Submit Req. to Procurement |  | 2 | 72 |  |  |  | 2011-06-29 22:30 | 2011-07-02 17:42 | 2010-07-30 08:06 | 2011-06-29 22:30 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 4 | [7 empty] | -10% +10% |  | 2
74 |  |  | Procurement Lead Time |  | 40 | 73 |  |  |  | 2011-07-02 17:42 | 2011-08-27 17:42 | 2010-07-30 08:06 | 2011-07-02 17:42 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 32 | [7 empty] | -20% +20% |  | 2
75 |  |  | Award |  | 1 | 74 |  |  |  | 2011-08-27 17:42 | 2011-08-29 03:18 | 2010-07-30 08:06 | 2011-08-27 17:42 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [20 empty] | -10% +10% |  | 2
76 |  |  | Fabricate and Deliver |  | 160 | 75 |  |  |  | 2011-08-29 03:18 | 2012-04-09 03:18 | 2010-07-30 08:06 | 2011-08-29 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 128 | [7 empty] | -30% +30% |  | 2
77
78 |  | Fab/Assembly | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
79 |  |  | Fab/Assembly Procedures | Tresemer | 30 | 73 | 56 |  |  | 2011-07-02 17:42 | 2011-08-13 17:42 | 2010-07-30 08:06 | 2011-07-02 17:42 | 2011-05-30 03:18 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 80 | [7 empty] | -30% +30% |  | 2
80 |  |  | Tile Assembly with Hardware | Tresemer | 40 | 76 | 70 | 79 |  | 2013-09-06 08:06 | 2013-11-01 08:06 | 2010-07-30 08:06 | 2012-04-09 03:18 | 2013-09-06 08:06 | 2011-08-13 17:42 | 2010-07-30 08:06 | [12 empty] | 32 | 300 | [6 empty] | -30% +30% |  | 2
81 | [11 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
82 |  | Installation | [9 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
83 |  | Installation Procedure |  | Tresemer | 30 | 79 |  |  |  | 2011-08-13 17:42 | 2011-09-24 17:42 | 2010-07-30 08:06 | 2011-08-13 17:42 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 60 | [7 empty] | -30% +30% |  | 2
84 |  | Tile Re-fit, as needed, additional machining |  | Tresemer | 30 | 83 | 80 |  |  | 2013-11-01 08:06 | 2013-12-13 08:06 | 2010-07-30 08:06 | 2011-09-24 17:42 | 2013-11-01 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | [12 empty] | 40 | 160 | [6 empty] | -30% +30% |  | 2
[12 empty] | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06 | 2010-07-30 08:06
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
|  | TOTALS | [15 empty] | 1278 | 0 | 0 | 30 | 0 | 704 | 8542 | 0 | 0 | 0 | 0 | 2656 | 700 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 3141.9073 | [12 empty] | 1508.04 | 0 | 0 | 33 | 0 | 124.5094 | 1013.252 | 0 | 0 | 0 | 0 | 400.7638 | 62.342 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [25 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [8 empty] | Weeks | [15 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [7 empty] | 3 | [15 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [7 empty] | 5 | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [7 empty] | 8 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [7 empty] | 9 | [15 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | cost center 1170
Job Number: |  | Job Number 1101
Job Title: |  | Title: CS Plasma Facing Components
Job Manager: |  | Job Manager: Kelsey Tresemer
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  | -10% , 15%
| Design Complexity |  | X |  | -15%, +25%
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Tiles not delivered on time |  |  |  | U | If schedule critical, install tiles in vessel |  |  | Conservative vendor quote, engineering experience | X |  | X
2 | Special diagnostics for tiles not received on time |  |  |  | U | If schedule critical, install tiles in vessel |  |  | Engineering experience | X |  | X
3 | Tiles requiring unforseen machining |  |  |  | L | If schedule critical, and in-house machinining will not suffice, seek external machining sources. Additional machining time added to WAF |  |  | Engineering experience | X |  | X
4 | Passive Plate hardware needs upgrading: Approx 2050 tiles |  |  |  | U |  |  |  | Hardware ONLY |  | 436 |  | X
5 | Outboard Divertor tile and hardware replacement, approx 1300 tiles, 26000 in^3 of material |  |  |  | L |  |  |  | Material and Harware ONLY |  | 2200 |  | X
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M & S breakdown
M & S Breakdown
TILES
Approx. 600 tiles
|  |  |  | Spare Parts |  |  | Handling Loss
| No. of tiles | Avg Dimensions | Volume (in^3) | No. of tiles, +20% | Volume (in^3) |  | No. of tiles, +10% | Volume (in^3)
Upper
Row 1 | 24 | 2"x7"x7' | 2352 | 30 | 2940 |  | 33 | 3234
Row 2 - 4 | 72 | 1"x4.5"x4" | 1296 | 87 | 1566 |  | 95.7 | 1722.6
Row 5 | 24 | 1"x10"x3.7" | 888 | 30 | 1110 |  | 33 | 1221
Center
Row 6 - 20 | 360 | .75"x3.4"x5.8" | 5324.4 | 430 | 6359.7 |  | 473 | 6995.67
Lower
Row 1 | 24 | 2"x7"x7' | 2352 | 30 | 2940 |  | 33 | 3234
Row 2 - 4 | 72 | 1"x4.5"x4" | 1296 | 87 | 1566 |  | 95.7 | 1722.6
Row 5 | 24 | 1"x10"x3.7" | 888 | 30 | 1110 |  | 33 | 1221
Total | 600 |  | 14396.4 | 724 | 17591.7 |  | 796.4 | 19350.87
|  | Vol/section (in^3) | Vol/section (cm^3) | Density(g/cm^3) | Lbs
Rows 1-5: high-k CFC |  | 7900.2 | 129461.083 | 1.9 | 542.2844
Rows 6-20: low-k CFC |  | 11450.67 | 187642.8621 | 1.75 | 723.943
high-k CFC Costs: $1000/lb (avg)
@$1000 | 542284.3808
low-k CFC Costs: $400/lb (avg)
@400 | 289577.1888
Subtotal:
831861.5697
Billets for spare parts (not finished tiles):
50000
TOTAL
881861.5697 | ~$900,000.00
TILE MACHINING (not diagnostics)
Rate of machining | 3 tiles/day
Avg cost of machining | $72.5/hr
800 tiles @ | $193.00/tile
total | 150000
DIAGNOSTIC MACHINING
Rate of machining | 6 tiles/day
Avg cost of machining | $72.5/hr
235 tiles @ | $96.67/tile
total | 22216.67
HARDWARE | (nuts, bolts, weld studs, Grafoil, locating pins, rails) |  |  |  |  | Compared M&S data from old Job Cost Reports (circa 1997 - 2001)
Bolts | 2000 | [6 empty] | Inflation adjusted
Nuts | 20000 | new tech | 50000 |  |  | 1997 | 0 | 0
Rail | 20000 |  |  |  |  | 1998 | 59720 | 76823.808
T-bar | 20000 |  |  |  |  | 1999 | 7070 | 8959.811
Pins | 5000 |  |  |  |  | 2000 | 0 | 0
Studs | 10000 |  |  |  |  | 2001 | 28974 | 34977.4128
Grafoil | 5000
Locating pins | 1000 |  |  |  |  | TOTAL | 95764 | 120761.0318
Belville washer | 3000
86000
Reflect a 25% increase due to increase in amount of material (larger surface area)
TOTAL | Reflect a 25% increase due to increase in amount of material (larger surface area) | [5 empty] | TOTAL
136000 | 170000 | [5 empty] | 150951.2897 | ~$160,000.00
USE $170,000.00