## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9418
Job Number: | 2420
Job Title: | Source Refurbishment
Job Manager: | Mark Cropper
Rev 1 6/8/2010
Description:
This scope includes the activities to refurbish three neutral beam ion sources for BL2 just as we currently do for the installed BL1. The refurbishment tasks will follow established procedures that have been utilized for both TFTR and NSTX.
Schedule: | Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9418
| Job Number: |  |  | 2420
| Job Title: |  |  | Source Refurbishment
| Job Manager: |  |  | Mark Cropper
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS (priced at FY10 rates) | [19 empty] | % | % |  |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Contingency | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.178 | 1.178 | 1.712 | 1.232 | 1.859 | 177.11 | 118.8 | 139.7 | 101.3 | 74.4 | 172.42 | 150.61 | 122.43 | 83.52 | 149.15 | 148.87 | 115.61 | 89.2 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1 |  | Preliminary Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
2 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
3 |  | PDR Prep PPL |  |  | 2 |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [16 empty] | cropper | Prior work
4 |  | PDR Prep PU |  |  | 2 |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | 5% | cropper | Prior work
5 |  | PDR Prep DOE |  |  | 2 |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | 5% | cropper | Prior work
6 |  | CONDUCT PDR |  |  | 1 |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 8 | [15 empty] | 5% | cropper | Prior work
7 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
8 |  | Final Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
9 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
10 |  | FDR Prep PPL |  |  | 2 |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | 15% | cropper | Prior work
11 |  | FDR Prep PU |  |  | 2 |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | 15% | cropper | Prior work
12 |  | FDR Prep DOE |  |  | 2 |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | 15% | cropper | Prior work
13 |  | FONDUCT PDR |  |  | 1 |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 1 | [15 empty] | 15% | cropper | Prior work
14 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
15 |  | Procurement | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
16 |  | Item 1: | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
17 |  |  | Prep Requisition and procurement package |  | 5 |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [15 empty] | 15% | cropper | Prior work
18 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 66 | [10 empty] | 8 | [15 empty] | 15% | cropper | Prior work
19 |  |  | Procurement lead time (1) |  | 15 |  |  | 2007-10-01 | 2007-10-22 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
20 |  |  | AWARD |  | 1 |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
21 |  |  | Fabricate or delivery |  | 40 |  |  | 2007-10-01 | 2007-11-26 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
22 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
23 |  | Fab/Assembly | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
24 |  | Refurbish Source A |  |  | 80 |  | 2011-01-01 | 2011-01-01 | 2011-04-23 | 2011-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 160 | 640 | 1920 | [13 empty] | 15% | cropper,bush,hynes,palmer,sabo | Prior work
25 |  | Refurbish Source B |  |  | 80 | 24 |  | 2011-04-23 | 2011-08-13 | 2007-10-01 | 2011-04-23 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 160 | 640 | 1920 | [13 empty] | 15% | cropper,bush,hynes,palmer,sabo | Prior work
26 |  | Refurbish Source c |  |  | 80 | 25 |  | 2011-08-13 | 2011-12-03 | 2007-10-01 | 2011-08-13 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 160 | 640 | 1920 | [13 empty] | 15% | cropper,bush,hynes,palmer,sabo | Prior work
28 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
29 |  | Build Probe tips (10 Long, 20 short) |  |  | 60 |  |  | 2007-10-01 | 2007-12-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2 | [10 empty] | 80 | 24 |  |  |  | 480 | [10 empty] | 30% | cropper,jurczynski | Prior work
30 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
31 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
33 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [13 empty] | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713 | 1944 | 5760 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 962.0608 | [10 empty] | 80.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.3849 | 238.0039 | 481.0752 | 0 | 0 | 55.4928 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [15 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: |  |  |  |  | Weeks | [9 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items |  |  |  | 3 | [9 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items |  |  |  | 5 | [9 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) |  |  |  | 8 | [9 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts |  |  |  | 9 | [9 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9418
Job Number: |  | 2420
Job Title: |  | Source Refurbishment
Job Manager: |  | Mark Cropper
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X
| Design Complexity |  |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9418
Job Number: | 2420
Job Title: | Source Refurbishment
Job Manager: | Mark Cropper
Materials and Subcontracts (M&S) |  |  |  |  | Basis of Estimate
Description:
Water Hose and Fittings |  |  | 38000 |  | past purchase
Mylar gaskets |  |  | 5000 |  | past purchase
Filament Chucks |  |  | 11000 |  | past purchase
O-rings |  |  | 5000 |  | past purchase
MOV's |  |  | 2000 |  | past purchase
Tubing fittings |  |  | 5000 |  | past purchase
Stainless Steel tubing |  |  | 500 |  | past purchase
Alumina tube |  |  | 660 |  | past purchase
Molybdenum rod |  |  | 500 |  | past purchase
brase |  |  | 500 |  | past purchase
|  | Total | 68160
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS