## Tab A Description
Work Approval Form (WAF)
Cost Center: 9418
Job Number: 2460
Job Title: NBI Armor
Job Manager: Craig Priniski
REV 1 6/10/2010
Description:
This job includes design, fabrication, and installation of upgraded and relocated neutral beam armor including cooling and instrumentation work
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: 9418
Job Number: 2460
Job Title: NBI Armor
Job Manager: Craig Priniski
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Resp | Duration in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | % Uncertanty Positive | Negative
numb | P3 cross ref | [14 empty] | 1.178 | 1.178 | 1.617 | 1.232 | 1.859 | 177.11 | 118.8 | 143.5 | 144.4 | 172.42 | 150.61 | 149.15 | 148.87 | 156.85 | 120.76 | 180.23 | 150 | 150 | 150
|  | Physics Requirements | [7 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
[10 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
|  | Conceptual Design | [7 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
1 |  |  | Armor Layout | PRINISKI | 5 |  | 2009-08-10 | 2009-08-10 | 2009-08-17 | 2009-08-10 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [7 empty] | 4 |  |  |  |  | 20 | [7 empty] | COMPLETED | 8
2 |  |  | Thermal Analysis of Second Beam | TRESEMER | 10 |  | 2009-08-17 | 2009-08-17 | 2009-08-31 | 2009-08-17 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [7 empty] | 40 |  |  |  |  | 64 | [7 empty] | COMPLETED | 8
3 |  |  | CD of Supports and plates | PRINISKI | 15 |  | 2009-08-17 | 2009-08-17 | 2009-09-07 | 2009-08-17 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [7 empty] | 60 |  |  |  |  | 60 | [7 empty] | COMPLETED | 8
4 |  |  | Tile modifications | TRESEMER | 10 |  | 2009-08-31 | 2009-08-31 | 2009-09-14 | 2009-08-31 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [7 empty] | 80 |  |  |  |  | 40 | [7 empty] | COMPLETED | 8
5 |  |  | Bay H Port Cover Design | PRINISKI | 10 |  | 2009-09-15 | 2009-09-15 | 2009-09-29 | 2009-09-15 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [7 empty] | 40 |  |  |  |  | 40 | [7 empty] | COMPLETED | 8
7 |  | CDR Prep |  | TRESEMER | 8 |  | 2009-09-29 | 2009-09-29 | 2009-10-10 04:48 | 2009-09-29 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 16 | 56.32 |  |  |  |  | 54.4 | [7 empty] | COMPLETED | 8
6 |  | PPPL CDR |  | PRINISKI | 2 |  | 2009-10-28 | 2009-10-28 | 2009-10-30 19:12 | 2009-10-28 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [7 empty] | 16 |  |  |  |  | 16 | [7 empty] | COMPLETED | 8
[10 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
|  | Preliminary Design | [8 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
7 |  | CDR Chit Resolution |  | TRESEMER | 30 |  | 2009-10-30 | 2009-10-30 | 2009-12-11 |  | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 48 |  |  |  |  | 108 | [7 empty] | COMPLETED | 8
8 |  | Design Components |  |  |  |  | 2009-12-15 |  |  | 2009-12-15 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [21 empty] | 8
9 |  |  | New Support Design | PRINISKI | 50 |  | 2010-01-11 | 2010-01-11 | 2010-03-22 |  | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 40 |  |  |  |  | 28 | [7 empty] | COMPLETED | 8
10 |  |  | Tile Thermal Modeling | TRESEMER | 51 |  | 2009-12-15 | 2009-12-15 | 2010-02-24 09:36 | 2009-12-15 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 0 |  |  |  |  | 40.8 | [7 empty] | COMPLETED | 8
11 |  |  | Tile Material Selection | TRESEMER | 60 |  | 2010-02-24 | 2010-02-24 | 2010-05-19 | 2010-02-24 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 0 |  |  |  |  | 48 | [7 empty] | COMPLETED | 8
12 |  | MSE-LIF Integration |  | PRINISKI | 30 |  | 2009-12-11 | 2009-12-11 | 2010-01-22 | 2009-12-11 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 48 |  |  |  |  | 36 | [7 empty] | COMPLETED | 8
13 |  | Armor E-Mag Analysis |  | BRYANT | 13 |  | 2010-04-12 | 2010-04-12 | 2010-04-30 04:48 | 2010-04-12 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 72.8 | 0 |  |  |  |  | 10.4 | [7 empty] | COMPLETED | 8
14 |  | Armor Thermal Analysys |  | BRYANT | 25 |  | 2010-04-29 | 2010-04-29 | 2010-06-03 | 2010-04-29 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 40 | 0 |  |  |  |  | 40 | [7 empty] | COMPLETED | 8
15 |  | Support Hardware Design |  | PRINISKI | 10 |  | 2010-06-03 | 2010-06-03 | 2010-06-17 | 2010-06-03 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 16 |  |  |  |  | 16 | [7 empty] | COMPLETED | 8
[36 empty] | 8 | [27 empty] | 10
16 |  | Update Cost & Schedule Estimate |  | PRINISKI | 4 |  | 2010-04-14 | 2010-04-14 | 2010-04-19 14:24 | 2010-04-14 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 0 |  |  |  |  | 22.4 | [7 empty] | COMPLETED | 8
17 |  | PDR Prep |  | TRESEMER | 5 |  | 2010-06-17 | 2010-06-17 | 2010-06-24 | 2010-06-17 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 0 |  |  |  |  | 0 | [7 empty] | Prev. Reviews | 8 | [27 empty] | 10
18 |  | CONDUCT PDR |  | TRESEMER | 2 |  | 2010-06-24 | 2010-06-24 | 2010-06-26 19:12 | 2010-06-24 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [20 empty] | Prev. Reviews | 8 | [27 empty] | 10
|  | Final Design | [7 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
19 |  |  | Disposition PDR Chits | TRESEMER | 20 |  | 2010-06-28 | 2010-06-28 | 2010-07-26 | 2010-06-28 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 16 |  |  |  |  | 48 | 0 | [6 empty] | Prev. Reviews
20 |  | Armor Service connection (Bay H) | Armor Service connection (Bay H) | PRINISKI | 10 |  | 2010-06-30 | 2010-06-30 | 2010-07-14 | 2010-06-30 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 24 |  |  |  |  | 20 | [7 empty] | Work to date | 8 | [27 empty] | 20 | -10
21 |  |  | Revise Armor Backing | PRINISKI | 20 |  | 2010-06-28 | 2010-06-28 | 2010-07-26 | 2010-06-28 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 32 |  |  |  |  | 64 | 0 | [6 empty] | Prev. Reviews | 2 | [27 empty] | 10 | -10
22 |  |  | Design Drawings | TRESEMER | 30 |  | 2010-07-26 | 2010-07-26 | 2010-09-06 | 2010-07-26 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 100.8 |  |  |  |  | 28.8 | 0 | [6 empty] | Work to date | 8 | [27 empty] | 10 | -10
23 |  |  | Tile Material Evaluation | TRESEMER | 40 |  | 2010-05-19 | 2010-05-19 | 2010-07-14 | 2010-05-19 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 |  | 6 |  |  | 10 |  | 0 | 0 |  |  |  |  | 48 | 64 | [6 empty] | Prev. Testing | 4 | [27 empty] | 30 | -10
24 |  |  | Armor Instrumentation (thermocouples) | TRESEMER | 10 |  | 2010-07-26 | 2010-07-26 | 2010-08-09 | 2010-07-26 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 12 |  |  |  |  | 52 | 0 | [6 empty] | Past Desings | 8 | [27 empty] | 20 | -10
25 |  |  | Develop Installation Techniques | PRINISKI | 20 |  | 2010-08-09 | 2010-08-09 | 2010-09-06 | 2010-08-09 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 8 |  |  |  |  | 64 | 0 | [6 empty] | Past Desings | 8 | [27 empty] | 10 | -10
26 |  |  | Update Analysis | BRYANT | 36 |  | 2010-09-06 | 2010-09-06 | 2010-10-26 09:36 | 2010-09-06 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 230 | 0 |  |  |  |  | 30 | 0 | [6 empty] | Work to date | 8 | [27 empty] | 20 | -10
27 |  | Update Cost & Schedule |  | PRINISKI | 4 |  | 2010-10-18 | 2010-10-18 | 2010-10-23 14:24 | 2010-10-18 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 0 |  |  |  |  | 32 | 0 | [6 empty] | Prev. Updates | 8 | [27 empty] | 10 | -10
28 |  | FDR Prep |  | TRESEMER | 20 |  | 2010-10-22 | 2010-10-22 | 2010-11-19 | 2010-10-22 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 0 | 0 |  |  |  |  | 0 | [7 empty] | Prev. Reviews | 8 | [27 empty] | 10 | -10
29 |  | CONDUCT FDR |  | TRESEMER | 1 |  | 2011-03-28 | 2011-03-28 | 2011-03-29 09:36 | 2011-03-28 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [20 empty] | Prev. Reviews | 8 | [27 empty] | 0 | 0
30 |  | FDR Chit Resolution |  | PRINISKI | 20 |  |  | 2010-06-17 12:00 | 2010-07-15 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [6 empty] | 20 | 80 |  |  |  |  | 80 | [7 empty] | Prev. Reviews | 4 | [27 empty] | 10 | -20
|  | Procurement | [7 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
|  | Item 1: Armor Tiles, CFCs | [7 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 |  | 95 |  |  | 6 | [15 empty] | Initial quotes | 6 | [27 empty] | 10 | -40 | Supplier Availblity/Discounts
31 |  |  | Prep Requisition and procurement package | TRESEMER | 10 |  | 2011-03-29 | 2011-03-29 | 2011-04-12 | 2011-03-29 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 48 | [7 empty] | Prev. Experience | 4 | [27 empty] | 20 | -10
32 |  |  | SUBMIT REQ TO PROCUREMENT | TRESEMER | 1 |  | 2011-04-05 | 2011-04-05 | 2011-04-06 09:36 | 2011-04-05 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 4
33 |  |  | Procurement lead time (1) | TRESEMER | 40 |  | 2011-04-06 | 2011-04-06 | 2011-06-01 | 2011-04-06 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0
34 |  |  | AWARD | TRESEMER | 1 |  | 2011-06-01 | 2011-06-01 | 2011-06-02 09:36 | 2011-06-01 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0
35 |  |  | Fabricate for delivery | TRESEMER | 260 |  | 2011-06-02 | 2011-06-02 | 2012-05-31 | 2011-06-02 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0 | [36 empty] | 20 | -10
36 |  | Item 2: Bay-H Port Cover - Armor Suports | [7 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 |  | 45 | [18 empty] | Prev. Cover | 6 | [27 empty] | 10 | -10
37 |  |  | Prep Requisition and procurement package | PRINISKI | 10 |  | 2011-04-05 | 2011-04-05 | 2011-04-19 | 2011-04-05 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 72 | [7 empty] | purchase | 4 | [27 empty] | 10 | -10
38 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-04-12 | 2011-04-12 | 2011-04-13 09:36 | 2011-04-12 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 4
39 |  |  | Procurement lead time (1) | PRINISKI | 25 |  | 2011-04-13 | 2011-04-13 | 2011-05-18 | 2011-04-13 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0
40 |  |  | AWARD | PRINISKI | 1 |  | 2011-05-18 | 2011-05-18 | 2011-05-19 09:36 | 2011-05-18 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0
41 |  |  | Fabricate for delivery | PRINISKI | 60 |  | 2011-05-19 | 2011-05-19 | 2011-08-11 | 2011-05-19 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0 | [36 empty] | 20 | -10
42 |  | Item 3: New Backing Plates | [7 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 |  | 20 | [18 empty] | Catalog matreials | 6 | [27 empty] | 10 | -10
43 |  |  | Prep Requisition and procurement package | PRINISKI | 2 |  | 2011-11-29 | 2011-11-29 | 2011-12-01 19:12 | 2011-11-29 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 14.4 | [8 empty] | 4
44 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-12-01 | 2011-12-01 | 2011-12-02 09:36 | 2011-12-01 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 4
45 |  |  | Procurement lead time (1) | PRINISKI | 15 |  | 2011-12-02 | 2011-12-02 | 2011-12-23 | 2011-12-02 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0
46 |  |  | AWARD | PRINISKI | 1 |  | 2011-12-23 | 2011-12-23 | 2011-12-24 09:36 | 2011-12-23 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0
47 |  |  | Delivery | PRINISKI | 20 |  | 2011-12-26 | 2011-12-26 | 2012-01-23 | 2011-12-26 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0 | [36 empty] | 20 | 0
48 |  | Pre-Assemble Armor | [7 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
49 |  |  | Fabricate Backing Plates | PRINISKI | 15 |  | 2012-01-23 | 2012-01-23 | 2012-02-13 | 2012-01-23 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 12 | 84 | [6 empty] | Prev. Experience | 4 | [27 empty] | 10 | 0
50 |  |  | Assemble Armor Quad #1 | PRINISKI | 7 |  | 2012-02-13 | 2012-02-13 | 2012-02-22 19:12 | 2012-02-13 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0 | 70 | [6 empty] | Prev. Experience | 4 | [27 empty] | 25 | -10
51 |  |  | Assemble Armor Quad #2 | PRINISKI | 5 |  | 2012-02-22 | 2012-02-22 | 2012-02-29 | 2012-02-22 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0 | 50 | [6 empty] | Prev. Experience | 4 | [27 empty] | 10 | 0
52 |  |  | Assemble Armor Quad #3 | PRINISKI | 5 |  | 2012-02-29 | 2012-02-29 | 2012-03-07 | 2012-02-29 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0 | 50 | [6 empty] | Prev. Experience | 4 | [27 empty] | 10 | 0
53 |  |  | Assemble Armor Quad #4 | PRINISKI | 5 |  | 2012-03-07 | 2012-03-07 | 2012-03-14 | 2012-03-07 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0 | 50 | [6 empty] | Prev. Experience | 4 | [27 empty] | 10 | 0
54 |  | Assembly Procedure Finalized |  | TRESEMER | 15 |  | 2012-02-16 | 2012-02-16 | 2012-03-08 | 2012-02-16 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 72 | 0 | [6 empty] | Prev. Experience | 2 | [27 empty] | 15 | 0
55 |  | Outage Begins |  |  |  |  | 2012-08-29 |  |  | 2012-08-29 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
56 |  | Installation | [7 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
57 |  |  | In Vessel Work Remove Armor | WINSTON | 20 |  | 2012-08-30 | 2012-08-30 | 2012-09-27 | 2012-08-30 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0 | 136 | [6 empty] | Prev. Experience | 4 | [27 empty] | 20 | -10
58 |  |  | Armor Support Installation | PRINISKI | 10 |  | 2012-09-27 | 2012-09-27 | 2012-10-11 | 2012-09-27 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 |  | 8 | [10 empty] | 8 | 112 | [6 empty] | Prev. Experience | 4 | [27 empty] | 15 | -5
59 |  |  | Armor Quadrant Installations | TRESEMER | 15 |  | 2012-10-11 | 2012-10-11 | 2012-11-01 | 2012-10-11 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 12 | 240 | [6 empty] | Prev. Experience | 4 | [27 empty] | 20 | -5
60 |  |  | Service Connections | PRINISKI | 4 |  | 2012-11-01 | 2012-11-01 | 2012-11-06 14:24 | 2012-11-01 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 0 | 36.8 | [6 empty] | Prev. Experience | 4 | [27 empty] | 25 | 0
61 |  |  | Bay-H Port Cover Install | PRINISKI | 3 |  | 2012-11-07 | 2012-11-07 | 2012-11-11 04:48 | 2012-11-07 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 2.4 | 28.8 | [6 empty] | Prev. Experience | 8 | [27 empty] | 15 | 0
62 |  | Testing |  | TRESEMER | 2 |  | 2012-11-12 | 2012-11-12 | 2012-11-14 19:12 | 2012-11-12 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | [12 empty] | 8 | 8 | [6 empty] | Prev. Experience | 4 | [27 empty] | 15 | 0
63 |  | Outage Ends |  |  |  |  | 2014-10-01 |  |  | 2014-10-01 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
64 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
65 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
66 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
67 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
68 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
69 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
70 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
71 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
72 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
73 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
74 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
75 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
76 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
77 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
78 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
79 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
80 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
81 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
82 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
83 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
84 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
85 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
86 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
87 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
88 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
89 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
90 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
91 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
92 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
93 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
94 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
95 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
96 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
97 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
98 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
99 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
100 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
101 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
102 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
103 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
104 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
105 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
106 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
107 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
108 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
109 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
110 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
111 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
112 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
113 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
114 | [9 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
[10 empty] | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00 | 2010-06-17 12:00
|  | TOTALS | [13 empty] | 174 | 0 | 0 | 16 | 0 | 378.8 | 721.12 | 0 | 0 | 0 | 0 | 1371.6 | 929.6 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 720.406 | [10 empty] | 204.972 | 0 | 0 | 19.712 | 0 | 67.0893 | 85.6691 | 0 | 0 | 0 | 0 | 204.5741 | 138.3896 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [15 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  | Weeks | [11 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  |  | 3 | [11 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  |  | 5 | [11 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  |  | 8 | [11 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  |  | 9 | [11 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: 9418
Job Number: 2460
Job Title: NBI Armor
Job Manager: Craig Priniski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: 9418
Job Number: 2460
Job Title: NBI Armor
Job Manager: Craig Priniski
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
PFC Armor Tiles CFC and ATJ Graphite | $121K | Up dated with CFC Tiles in all beam overlap areas, plus spares. Also includes upgraded shileding behind tiles | 6
New Bay H Port Cover (modifed 27" Flange) | 50 | Based on costs for current Bay-H portcover also installed in (FY 2004) | 4
New NB Armor Backing Plates | 20 | Cost of steel and hardware to manufacture new plates (catalog items) | 6
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
| 70 |  | TOTALS