## Tab A Description
Work Approval Form (WAF)
Cost Center: 9418
Job Number: 2480
Job Title: NSTX NB2 Duct & VV Mods
Job Manager: Craig Priniski
Rev 1 6/10/2010
Description:
This job includes the design, and fabrication of all components connecting NB Box to NSTX, the connecting ductwork and modifications to NSTX Vacuum Vessel are inculded in this job.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: 9418
Job Number: 2480
Job Title: NSTX NB2 Duct & VV Mods
Job Manager: Craig Priniski
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | Duration in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | % Uncertanty positive | negative
numb | P3 cross ref | [14 empty] | 1.178 | 1.178 | 1.617 | 1.232 | 1.859 | 177.11 | 118.8 | 143.5 | 144.4 | 172.42 | 150.61 | 149.15 | 148.87 | 156.85 | 142.83 | 180.23 | 150 | 150 | 150
|  | Physics Requirements | [7 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
[10 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
|  | Conceptual Design | [7 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
1 |  | CD for NSTX VV in Bay J-K area |  | PRINISKI | 10 |  | 2009-08-10 | 2009-08-10 | 2009-08-24 | 2009-08-10 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 20 |  |  |  |  | 20 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
2 |  | CD of Port K Extension |  | PRINISKI | 3 |  | 2009-08-24 | 2009-08-24 | 2009-08-28 04:48 | 2009-08-24 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 12 |  |  |  |  | 7.92 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
3 |  | CD Ceramic Break Flanges |  | PRINISKI | 10 |  | 2009-08-10 | 2009-08-10 | 2009-08-24 | 2009-08-10 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 20 |  |  |  |  | 20 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
4 |  | CD Spool Piece |  | PRINISKI | 3 |  | 2009-08-10 | 2009-08-10 | 2009-08-14 04:48 | 2009-08-10 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 16.08 |  |  |  |  | 7.92 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
5 |  | C&S Development |  | PRINISKI | 10 |  | 2009-07-13 | 2009-07-13 | 2009-07-27 | 2009-07-13 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 8 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
6 |  | C&S Review |  | PRINISKI | 1 |  | 2009-07-27 | 2009-07-27 | 2009-07-28 09:36 | 2009-07-27 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 2 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
7 |  | NSTX J-K Mockup purchase |  | PRINISKI | 25 |  | 2009-08-24 | 2009-08-24 | 2009-09-28 |  |  | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 4 | [10 empty] | 2 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
8 |  | Prep for PPPL/Ext CDR |  | PRINISKI | 5 |  | 2009-08-27 | 2009-08-27 | 2009-09-03 | 2009-08-27 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | COMPLETED | 8 | [27 empty] | NA
9 |  | PPPL CDR |  | PRINISKI | 1 |  | 2009-09-28 | 2009-09-28 | 2009-09-29 09:36 | 2009-09-28 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | COMPLETED | 8 | [27 empty] | NA
|  | Preliminary Design | [7 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
10 |  | CDR Chit Resolution (all areas) |  | PRINISKI | 30 |  | 2009-09-29 | 2009-09-29 | 2009-11-10 |  | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 40.8 |  |  |  |  | 120 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
11 |  | FMEA Analysis |  | PRINISKI | 2 |  | 2010-02-15 | 2010-02-15 | 2010-02-17 19:12 |  | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 16 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
12 |  | NSTX VV Modification Prototyping |  | PRINISKI | 60 |  | 2010-02-18 | 2010-02-18 | 2010-05-13 | 2010-02-18 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 6 | [5 empty] | 19.2 |  |  |  |  | 120 | 5 | [6 empty] | COMPLETED | 8 | [27 empty] | NA
13 |  | Update Cost & Schedule Estimate |  | PRINISKI | 18 |  | 2010-03-23 | 2010-03-23 | 2010-04-17 04:48 | 2010-03-23 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 72 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
14 |  | Design Components |  | PRINISKI |  |  | 2009-11-10 |  |  | 2009-11-10 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 169.2 | [8 empty] | 8
15 |  |  | J-K Cap Weldment | PRINISKI | 45 |  | 2009-11-10 | 2009-11-10 | 2010-01-12 |  | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 144 |  |  |  |  | 54 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
16 |  |  | K-Port Extension | PRINISKI | 10 |  | 2010-02-17 | 2010-02-17 | 2010-03-03 |  | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 28 |  |  |  |  | 12 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
17 |  |  | NB-Ceramic Beak | PRINISKI | 7 |  | 2010-01-15 | 2010-01-15 | 2010-01-24 19:12 | 2010-01-15 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 16.8 |  |  |  |  | 2.8 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
18 |  |  | Spool Piece | PRINISKI | 10 |  | 2010-01-26 | 2010-01-26 | 2010-02-09 | 2010-01-26 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 28 |  |  |  |  | 4 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
19 |  |  | Round Bellows | PRINISKI | 10 |  | 2010-02-09 | 2010-02-09 | 2010-02-23 | 2010-02-09 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 24 |  |  |  |  | 4 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
20 |  |  | Rectangular Bellows | PRINISKI | 10 |  | 2010-03-01 | 2010-03-01 | 2010-03-15 | 2010-03-01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 32 |  |  |  |  | 16 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
21 |  |  | Bay K/NB Duct Supports | PRINISKI | 59 |  | 2010-02-09 | 2010-02-09 | 2010-05-02 14:24 | 2010-02-09 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 70.8 |  |  |  |  | 4.72 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
22 |  | J-K RWM Coil Redesign |  | PRINISKI | 32 |  | 2010-04-12 | 2010-04-12 | 2010-05-26 19:12 | 2010-04-12 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [21 empty] | 8
23 |  |  | New Layout/Supports | PRINISKI | 10 |  | 2010-04-12 | 2010-04-12 | 2010-04-26 | 2010-04-12 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 20 |  |  |  |  | 12 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
24 |  |  | New Coil Components | PRINISKI | 22 |  | 2010-04-26 | 2010-04-26 | 2010-05-26 19:12 | 2010-04-26 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 17.6 |  |  |  |  | 17.6 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
25 |  | NB Duct Thermal Shielding |  | PRINISKI | 25 |  | 2010-04-19 | 2010-04-19 | 2010-05-24 | 2010-04-19 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 10 |  |  |  |  | 50 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
26 |  | PDR Prep |  | PRINISKI | 43 |  | 2010-04-15 | 2010-04-15 | 2010-06-14 04:48 | 2010-04-15 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [6 empty] | 0 | 0 |  |  |  |  | 0 | [7 empty] | Work to date | 8 | [27 empty] | NA
27 |  | CONDUCT PDR |  | PRINISKI | 1 |  | 2010-06-23 | 2010-06-23 | 2010-06-24 09:36 | 2010-06-23 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Prev. Reviews | 8 | [27 empty] | 0
28 |  | Disposition PDR Chits |  | PRINISKI | 33 |  | 2010-06-24 | 2010-06-24 | 2010-08-09 04:48 | 2010-06-24 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [6 empty] | 26 | 132 |  |  |  |  | 158.4 | [7 empty] | Prev. Reviews | 8 | [27 empty] | 20 | -10
|  | Final Design | [7 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
29 |  |  | Seismic Analysis | PRINISKI | 5 |  | 2010-07-06 | 2010-07-06 | 2010-07-13 | 2010-07-06 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 24 | [7 empty] | Prev. Experince | 8 | [27 empty] | 10 | -10
29 |  |  | J-K Cap/Installation Procedure | PRINISKI | 24 |  | 2010-08-10 | 2010-08-10 | 2010-09-12 14:24 | 2010-08-10 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 48 |  |  |  |  | 48 | [7 empty] | Work to date | 8 | [27 empty] | 25 | -5
30 |  |  | K- Port Extension | PRINISKI | 7 |  | 2010-09-13 | 2010-09-13 | 2010-09-22 19:12 | 2010-09-13 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 14 |  |  |  |  | 14 | [7 empty] | Work to date | 8 | [27 empty] | 15 | -10
31 |  |  | NB- Ceramic-Break | PRINISKI | 6 |  | 2010-09-22 | 2010-09-22 | 2010-09-30 09:36 | 2010-09-22 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 12 |  |  |  |  | 12 | [7 empty] | Work to date | 8 | [27 empty] | 15 | -5
32 |  |  | Spool Piece/Round Bellows | PRINISKI | 5 |  | 2010-09-30 | 2010-09-30 | 2010-10-07 | 2010-09-30 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 10 |  |  |  |  | 2 | [7 empty] | Work to date | 8 | [27 empty] | 15 | -15
33 |  |  | Rectangular Bellows Assembly | PRINISKI | 5 |  | 2010-09-30 | 2010-09-30 | 2010-10-07 | 2010-09-30 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 20 |  |  |  |  | 4 | [7 empty] | Work to date | 8 | [27 empty] | 15 | 0
34 |  | Design Drawings |  | PRINISKI | 45 |  | 2010-10-07 | 2010-10-07 | 2010-12-09 | 2010-10-07 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 360 |  |  |  |  | 72 | [7 empty] | Prev. Experince | 4 | [27 empty] | 10 | -10
35 |  | Installation Prototyping |  | PRINISKI | 15 |  | 2010-09-13 | 2010-09-13 | 2010-10-04 | 2010-09-13 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 5 | [10 empty] | 12 | 40 | [6 empty] | Work to date | 8 | [27 empty] | 20 | -10
36 |  | Update Analyses |  | PRINISKI | 35 |  | 2010-08-10 | 2010-08-10 | 2010-09-28 | 2010-08-10 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [6 empty] | 40 | [5 empty] | 14 | [7 empty] | Work to date | 8 | [27 empty] | 20 | -40
37 |  | Update Cost & Schedule Estimate |  | PRINISKI | 5 |  | 2010-10-07 | 2010-10-07 | 2010-10-14 | 2010-10-07 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 20 | [7 empty] | Prev. Updates | 8 | [27 empty] | 10 | -10
38 |  | FDR Prep |  | PRINISKI | 20 |  | 2011-01-10 | 2011-01-10 | 2011-02-07 | 2011-01-10 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [6 empty] | 0 | 0 |  |  |  |  | 0 | [7 empty] | Prev. Reviews | 8 | [27 empty] | 10 | -10
39 |  | CONDUCT FDR |  | PRINISKI | 1 |  | 2011-03-28 | 2011-03-28 | 2011-03-29 09:36 | 2011-03-28 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Prev. Reviews | 8 | [27 empty] | NA | 0
40 |  | Disposition FDR Chits |  | PRINISKI | 20 |  | 2011-03-29 | 2011-03-29 | 2011-04-26 | 2011-03-29 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [7 empty] | 100 |  |  |  |  | 100 | [7 empty] | Prev. Reviews | 8 | [27 empty] | 20 | -20
[10 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
|  | Procurement |  | PRINISKI | [5 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
41 |  | Prep Procurement Specs (Early Action Items) |  | PRINISKI | 30 |  | 2011-02-07 | 2011-02-07 | 2011-03-21 | 2011-02-07 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 48 | [7 empty] | Prev. Experince | 4 | [27 empty] | 20 | -10
42 |  | Item 1: 40 VAT VALVES x2 " |  | PRINISKI |  |  | 2011-03-21 |  |  | 2011-03-21 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 250 | [18 empty] | Prev. Quotes | 6 | [27 empty] | 15 | 0
43 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-03-21 | 2011-03-21 | 2011-03-22 09:36 | 2011-03-21 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 8 | [7 empty] | Prev. Experince | 4
44 |  |  | Procurement lead time (1) | PRINISKI | 25 |  | 2011-03-22 | 2011-03-22 | 2011-04-26 | 2011-03-22 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
45 |  |  | AWARD | PRINISKI | 3 |  | 2011-04-26 | 2011-04-26 | 2011-04-30 04:48 | 2011-04-26 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
46 |  |  | Fabricate and Delivery | PRINISKI | 100 |  | 2011-04-29 | 2011-04-29 | 2011-09-16 | 2011-04-29 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Prev. Experince | 4 | [27 empty] | 15 | 0
47 |  | Item 2: 40 Bellows Section " |  | PRINISKI |  |  | 2011-03-21 |  |  | 2011-03-21 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 200 |  |  | 8 | [15 empty] | Vendor Quote | 6 | [27 empty] | 30 | -20 | Vendor Availibility, final cost
48 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-03-21 | 2011-03-21 | 2011-03-22 09:36 | 2011-03-21 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 8 | [7 empty] | Prev. Experince | 4
49 |  |  | Procurement lead time (1) | PRINISKI | 25 |  | 2011-03-22 | 2011-03-22 | 2011-04-26 | 2011-03-22 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
50 |  |  | AWARD | PRINISKI | 3 |  | 2011-04-26 | 2011-04-26 | 2011-04-30 04:48 | 2011-04-26 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
51 |  |  | Fabricate and Delivery | PRINISKI | 130 |  | 2011-04-29 | 2011-04-29 | 2011-10-28 | 2011-04-29 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Vendor Quote | 6 | [27 empty] | 20 | 0
52 |  | Item 3: Rectangular Bellows Section |  | PRINISKI |  |  | 2011-03-21 |  |  | 2011-03-21 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 400 |  |  | 15 | [15 empty] | Prev. Experince | 4 | [27 empty] | 35 | -20 | Vendor Availibility, final cost
53 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-03-21 | 2011-03-21 | 2011-03-22 09:36 | 2011-03-21 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 8 | [7 empty] | Prev. Experince | 4
54 |  |  | Procurement lead time (1) | PRINISKI | 25 |  | 2011-03-22 | 2011-03-22 | 2011-04-26 | 2011-03-22 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
55 |  |  | AWARD | PRINISKI | 1 |  | 2011-04-26 | 2011-04-26 | 2011-04-27 09:36 | 2011-04-26 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
56 |  |  | Fabricate or delivery | PRINISKI | 400 |  | 2011-04-27 | 2011-04-27 | 2012-11-07 | 2011-04-27 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Vendor Quote | 6 | [27 empty] | 50 | 0
57 |  | Item 4: Vessel Cap & Port Extension |  |  |  |  | 2011-04-19 |  |  | 2011-04-19 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 100 |  |  | 8 | [15 empty] | Prev. Experince | 4 | [27 empty] | 20 | -5
58 |  |  | Prep Requisition and procurement package | PRINISKI | 8 |  | 2011-04-19 | 2011-04-19 | 2011-04-30 04:48 | 2011-04-19 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 64 | [7 empty] | Prev. Experince | 4
59 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-04-29 | 2011-04-29 | 2011-04-30 09:36 | 2011-04-29 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Prev. Experince | 4
60 |  |  | Procurement lead time (1) | PRINISKI | 25 |  | 2011-05-02 | 2011-05-02 | 2011-06-06 | 2011-05-02 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
61 |  |  | AWARD | PRINISKI | 1 |  | 2011-06-06 | 2011-06-06 | 2011-06-07 09:36 | 2011-06-06 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
62 |  |  | Fabricate and delivery | PRINISKI | 180 |  | 2011-06-07 | 2011-06-07 | 2012-02-14 | 2011-06-07 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Prev. Experince | 4 | [27 empty] | 15 | 0
63 |  | Item 5: Spool Piece |  | PRINISKI |  |  | 2011-04-19 |  |  | 2011-04-19 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 40 | [18 empty] | Prev. Experince | 4 | [27 empty] | 15 | -5
64 |  |  | Prep Requisition and procurement package | PRINISKI | 5 |  | 2011-04-29 | 2011-04-29 | 2011-05-06 | 2011-04-29 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 30 | [7 empty] | Prev. Experince | 4
65 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-05-06 | 2011-05-06 | 2011-05-07 09:36 | 2011-05-06 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Prev. Experince | 4 | [27 empty] | NA
66 |  |  | Procurement lead time (1) | PRINISKI | 25 |  | 2011-05-09 | 2011-05-09 | 2011-06-13 | 2011-05-09 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
67 |  |  | AWARD | PRINISKI | 1 |  | 2011-06-13 | 2011-06-13 | 2011-06-14 09:36 | 2011-06-13 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
68 |  |  | Fabricate or delivery | PRINISKI | 120 |  | 2011-06-14 | 2011-06-14 | 2011-11-29 | 2011-06-14 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Prev. Experince | 4 | [27 empty] | 15
69 |  | Item 6: RWM Coil Materials (copper) |  | PRINISKI | 1 |  | 2011-04-19 | 2011-04-19 | 2011-04-20 09:36 | 2011-04-19 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 12 | [10 empty] | 8 | [7 empty] | Material Prices | 6 | [27 empty] | 15
70 |  | Item 7: Raw materials for duct (added shield) |  | PRINISKI |  |  | 2011-04-19 |  |  | 2011-04-19 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 100 | [18 empty] | Material Prices | 6 | [27 empty] | 15 | -10
71 |  |  | Prep Requisition and procurement package | PRINISKI | 3 |  | 2011-05-06 | 2011-05-06 | 2011-05-10 04:48 | 2011-05-06 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 18 | [7 empty] | Prev. Experince | 4 | [27 empty] | 10
72 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-05-11 | 2011-05-11 | 2011-05-12 09:36 | 2011-05-11 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 4 | [7 empty] | Prev. Experince | 4
73 |  |  | Procurement lead time (1) | PRINISKI | 25 |  | 2011-05-12 | 2011-05-12 | 2011-06-16 | 2011-05-12 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
74 |  |  | AWARD | PRINISKI | 1 |  | 2011-06-16 | 2011-06-16 | 2011-06-17 09:36 | 2011-06-16 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
75 |  |  | Fabricate or delivery | PRINISKI | 100 |  | 2011-06-17 | 2011-06-17 | 2011-11-04 | 2011-06-17 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [20 empty] | Prev. Experince | 4 | [27 empty] | 15 | -5
|  | Installation | [7 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
76 |  | Installation Procedure |  | PRINISKI | 60 |  | 2011-07-08 | 2011-07-08 | 2011-09-30 | 2011-07-08 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 144 | 24 | [6 empty] | Prev. Experince | 4,2 | [27 empty] | 20 | -5
|  | OUTAGE BEGINS |  |  |  |  | 2012-08-29 |  |  | 2012-08-29 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
77 |  | Installation materials purchase |  | PRINISKI | 20 |  | 2012-08-30 | 2012-08-30 | 2012-09-27 | 2012-08-30 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 |  | 10 | [18 empty] | Material Prices | 6 | [27 empty] | 30 | -20
78 |  | Installation |  | PRINISKI |  |  | 2012-11-19 |  |  | 2012-11-19 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
79 |  | J-K Vessel Modification |  | PRINISKI |  |  | 2013-02-06 |  |  | 2013-02-06 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
80 |  |  | Install Vessel Supports | PRINISKI | 8 |  | 2013-02-06 | 2013-02-06 | 2013-02-17 04:48 | 2013-02-06 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 6.4 | 51.2 | [6 empty] | Exper./Judgent | 4,2 | [27 empty] | 15 | -5
81 |  |  | Remove Bay-K Nozzle | PRINISKI | 4 |  | 2013-02-18 | 2013-02-18 | 2013-02-23 14:24 | 2013-02-18 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 8 | 64 | [6 empty] | Exper./Judgent | 4,2 | [27 empty] | 15 | -5
82 |  |  | Cut J-K opening | PRINISKI | 30 |  | 2013-02-28 | 2013-02-28 | 2013-04-11 | 2013-02-28 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 80 | 720 | [6 empty] | Exper./Judgent | 4,2 | [27 empty] | 25 | -20
83 |  |  | Fit Up/Install Cap | PRINISKI | 25 |  | 2013-04-05 | 2013-04-05 | 2013-05-10 | 2013-04-05 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 20 | 400 | [6 empty] | Exper./Judgent | 4,2 | [27 empty] | 30 | -15
84 |  |  | Install Duct Supports | PRINISKI | 3 |  | 2013-09-02 | 2013-09-02 | 2013-09-06 04:48 | 2013-09-02 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 2.4 | 28.8 | [6 empty] | Exper./Judgent | 4,2 | [27 empty] | 15 | -5
85 |  |  | Install K Extension | PRINISKI | 2 |  | 2013-09-02 | 2013-09-02 | 2013-09-04 19:12 | 2013-09-02 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 1.6 | 16 | [6 empty] | Prev. Experince | 4 | [27 empty] | 15 | -5
86 |  | NB2 Duct Construction |  | PRINISKI |  |  | 2012-11-19 |  |  | 2012-11-19 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 9.6
87 |  |  | Make up NB2 Transition Duct | PRINISKI | 7 |  | 2012-11-19 | 2012-11-19 | 2012-11-28 19:12 | 2012-11-19 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 5.6 | 78.4 | [6 empty] | Prev. Experince | 4 | [27 empty] | 15 | -5
88 |  |  | Leak Check Duct | PRINISKI | 5 |  | 2012-11-28 | 2012-11-28 | 2012-12-05 | 2012-11-28 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [13 empty] | 40 | [6 empty] | Prev. Experince | 4 | [27 empty] | 20 | -5
89 |  |  | Install Transition Duct | PRINISKI | 5 |  | 2014-06-04 | 2014-06-04 | 2014-06-11 | 2014-06-04 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [13 empty] | 80 | [6 empty] | Prev. Experince | 4 | [27 empty] | 20 | -5
90 |  |  | Install, Connect Bake Out Lines | PRINISKI | 1 |  | 2014-06-11 | 2014-06-11 | 2014-06-12 09:36 | 2014-06-11 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [12 empty] | 0.8 | 8 | [6 empty] | Prev. Experince | 4 | [27 empty] | 15 | -5
91 |  | Testing |  | PRINISKI | 5 |  | 2014-06-12 | 2014-06-12 | 2014-06-19 | 2014-06-12 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | [13 empty] | 20 | [6 empty] | Exper./Judgent | 2 | [27 empty] | 15
|  | END OUTAGE |  |  |  |  | 2014-10-01 |  |  | 2014-10-01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
1 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
2 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
3 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
4 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
5 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
6 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
7 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
8 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
9 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
10 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
11 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
12 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
13 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
14 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
15 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
16 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
17 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
18 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
19 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
20 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
21 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
22 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
23 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
24 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
25 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
26 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
27 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
28 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
29 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
30 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
31 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
32 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
33 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
34 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
35 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
36 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
37 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
38 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
39 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
40 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
41 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
42 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
43 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
44 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
45 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
46 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
47 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
48 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
49 | [9 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
[10 empty] | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01 | 2010-06-15 13:01
|  | TOTALS | [13 empty] | 1127 | 0 | 0 | 31 | 0 | 66 | 1215.28 | 0 | 0 | 0 | 0 | 1696.96 | 1575.4 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 2009.4939 | [10 empty] | 1327.606 | 0 | 0 | 38.192 | 0 | 11.6893 | 144.3753 | 0 | 0 | 0 | 0 | 253.1016 | 234.5298 | 0 | 0 | 0 | 0 | 0
| Notes: | [15 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  | Weeks | [11 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  |  | 3 | [11 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  |  | 5 | [11 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  |  | 8 | [11 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  |  | 9 | [11 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: 9418
Job Number: 2480
Job Title: NSTX NB2 Duct & VV Mods
Job Manager: Craig Priniski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  | 15
| Design Complexity |  |  | X | 10
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Price increase for Rectangular Bellows |  |  |  | U | Conginancy money may be need to be set aside |  |  | Dicussions with vendors | 0 | 170 | 0 | 0
2
3
4
5
Notes: | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(1) | The schedule impacts should be entered as the min and max impacts on the critical path.
(2) | If there is no critical path impact then the schedule entries should be zero.
Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
(3) | VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: 9418
Job Number: 2480
Job Title: NSTX NB2 Duct & VV Mods
Job Manager: Craig Priniski
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Item 1: 40" VAT VALVES x2 | $250K | Based on quotes for propes upgrade, scaled to FY 09 dollars | 6- Quote
Item 2: 40" Bellows Section | $200K | Based on Vendor Quotes | 6- Quote
Item 3: Rectangular Bellows Section | $400K | Based on OEM Quote | 6- Quote and Actual Costs
Item 4: Spool Piece | $40K | Scale up of costs of other vacuum vessel extensions ordered | 4 - Experience
Item 5: Vessel Cap & Port Extension | $80K | Scale up of costs of other vacuum vessel extensions ordered | 4 - Experience
Item 7: Duct Shielding Material | $140K | Based on recent PPPL purchases of Molly Plate Shielding | 8- Actual NSTX Work
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS