## Tab A Description
Work Approval Form (WAF)
Cost Center: 1180
Job Number: 2485
Job Title: NSTX NB2 TVPS
Job Manager: Craig Priniski
Rev 1 6/10/2010
Description:
This job includes the design, fabrication, and installation of new Vessel Pumping System. The job scope includes new pump ducts off of NB2 duct, mechanical and electrical isolation of system, vacuum diagnostic relocation, magnetic shielding and support of TVPS TMPs, and TMP service connections
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: 1180
Job Number: 2485
Job Title: NSTX NB2 TVPS
Job Manager: Craig Priniski
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Resp | Duration in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | Uncertanty % positive | negative
numb | P3 cross ref | [14 empty] | 1.178 | 1.178 | 1.617 | 1.232 | 1.859 | 177.11 | 118.8 | 135.2 | 101.48 | 172.42 | 150.61 | 149.15 | 148.87 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
|  | Physics Requirements | [7 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
[10 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
|  | Conceptual Design | [7 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
1 |  |  | CD of System Layout | PRINISKI | 20 |  | 2009-07-07 | 2009-07-07 | 2009-08-04 | 2009-07-07 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 96 |  |  |  |  | 16 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
2 |  |  | CD of Pump Duct(s) | PRINISKI | 5 |  | 2009-08-04 | 2009-08-04 | 2009-08-11 | 2009-08-04 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 24 |  |  |  |  | 8 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
3 |  |  | CD of Magnetic Shield | PRINISKI | 5 |  | 2009-08-11 | 2009-08-11 | 2009-08-18 | 2009-08-11 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 8 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
4 |  |  | C&S Review | PRINISKI | 1 |  | 2009-08-18 | 2009-08-18 | 2009-08-19 09:36 | 2009-08-18 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 1.6 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
5 |  | Prep for PPPL/Ext CDR |  | PRINISKI | 5 |  | 2009-08-19 | 2009-08-19 | 2009-08-26 | 2009-08-19 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 12 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
6 |  | PPPL CDR |  | PRINISKI | 2 |  | 2009-10-28 | 2009-10-28 | 2009-10-30 19:12 | 2009-10-28 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [49 empty] | NA
[10 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [49 empty] | NA
|  | Preliminary Design | [8 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [49 empty] | NA
7 |  |  | CDR Chit Resolution (all areas) | PRINISKI | 20 |  | 2009-10-30 | 2009-10-30 | 2009-11-27 | [12 empty] | 32 |  |  |  |  | 96 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
8 |  |  | FMEA Analysis | PRINISKI | 1 |  | 2009-11-27 | 2009-11-27 | 2009-11-28 09:36 | 2009-11-27 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 8 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
9 |  |  | Preliminary CAD Designs | PRINISKI | 10 |  | 2009-11-27 | 2009-11-27 | 2009-12-11 |  | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 80 |  |  |  |  | 8 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
10 |  |  | Identify COTS Vendors | PRINISKI | 25 |  | 2010-04-13 | 2010-04-13 | 2010-05-18 | 2010-04-13 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 100 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
11 |  |  | Update Cost & Schedule Estimate | PRINISKI | 3 |  | 2010-04-19 | 2010-04-19 | 2010-04-23 04:48 | 2010-04-19 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 7.2 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
12 |  |  | Update CAD Models | PRINISKI | 10 |  | 2010-05-18 | 2010-05-18 | 2010-06-01 | 2010-05-18 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 32 |  |  |  |  | 12 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
13 |  | PDR Prep |  | PRINISKI | 10 |  | 2010-06-01 | 2010-06-01 | 2010-06-15 | 2010-06-01 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [6 empty] | 0 | 0 |  |  |  |  | 0 | [7 empty] | COMPLETED | 8 | [27 empty] | NA
14 |  | CONDUCT PDR |  | PRINISKI | 2 |  | 2010-06-23 | 2010-06-23 | 2010-06-25 19:12 | 2010-06-23 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [20 empty] | Prev. Reviews | 8 | [27 empty] | NA
[10 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
|  | Final Design | [7 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
15 |  |  | Disposition PDR Chits | PRINISKI | 15 |  | 2010-06-25 | 2010-06-25 | 2010-07-16 | 2010-06-25 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 18 |  |  |  |  | 18 | [7 empty] | Prev. Reviews | 8 | [27 empty] | 25 | -20
16 |  |  | Vacuum Diagnostic Layout | PRINISKI | 10 |  | 2010-07-16 | 2010-07-16 | 2010-07-30 | 2010-07-16 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 32 |  |  |  |  | 8 | [7 empty] | Prev. Experince | 8 | [27 empty] | 20 | -10
17 |  |  | Design Drawings | PRINISKI | 30 |  | 2010-07-16 | 2010-07-16 | 2010-08-27 | 2010-07-16 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 24 |  |  |  |  | 96 | [7 empty] | Work to date | 8 | [27 empty] | 10 | -5
18 |  |  | Update Cost & Schedule Estimate | PRINISKI | 3 |  | 2010-07-30 | 2010-07-30 | 2010-08-03 04:48 | 2010-07-30 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 12 | [12 empty] | Prev. Updates | 8 | [27 empty] | 15 | -5
19 |  | FDR Prep |  | PRINISKI | 10 |  | 2010-08-27 | 2010-08-27 | 2010-09-10 | 2010-08-27 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 0 |  |  |  |  | 0 | [7 empty] | Prev. Reviews | 8 | [27 empty] | NA
20 |  | CONDUCT FDR |  | PRINISKI | 2 |  | 2011-03-28 | 2011-03-28 | 2011-03-30 19:12 | 2011-03-28 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [20 empty] | Prev. Reviews | 8 | [27 empty] | NA
21 |  | FDR Chit Resolution (all areas) |  | PRINISKI | 20 |  |  | 2010-06-15 13:14 | 2010-07-13 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [7 empty] | 80 |  |  |  |  | 80
|  | Procurement | [7 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
21 |  | Item 1: 2600 l/s TMPs x 2 |  | PRINISKI |  |  | 2011-03-30 |  |  | 2011-03-30 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 |  | 65 | [18 empty] | Vendor Quotes | 6 | [27 empty] | 15 | -20
22 |  |  | Prep Requisition and procurement package | PRINISKI | 4 |  | 2011-03-30 | 2011-03-30 | 2011-04-04 14:24 | 2011-03-30 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 19.2 | [7 empty] | Prev. Experince | 4 | [27 empty] | 20 | -10
23 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-04-05 | 2011-04-05 | 2011-04-06 09:36 | 2011-04-05 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 0.8 | [36 empty] | 10
24 |  |  | Procurement lead time | PRINISKI | 15 |  | 2011-04-06 | 2011-04-06 | 2011-04-27 | 2011-04-06 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
25 |  |  | AWARD | PRINISKI | 1 |  | 2011-04-27 | 2011-04-27 | 2011-04-28 09:36 | 2011-04-27 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [20 empty] | Prev. Experince | 8
26 |  |  | Fabricate and delivery Fabricate or delivery | PRINISKI | 90 |  | 2011-04-28 | 2011-04-28 | 2011-09-01 | 2011-04-28 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [20 empty] | Vendor Quotes | 6 | [27 empty] | 10
27 |  | Item 2: New Gate Valves |  | PRINISKI | 99 |  | 2011-04-05 | 2011-04-05 | 2011-08-21 14:24 | 2011-04-05 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 |  | 22 | [18 empty] | Catalog Price | 6 | [27 empty] | 15
28 |  |  | Prep Requisition and procurement package | PRINISKI | 2 |  | 2011-04-05 | 2011-04-05 | 2011-04-07 19:12 | 2011-04-05 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 1.6 | [7 empty] | Prev. Experince | 4 | [27 empty] | 20
29 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-04-07 | 2011-04-07 | 2011-04-08 09:36 | 2011-04-07 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 0.8 | [7 empty] | Prev. Experince | 4 | [27 empty] | 10
30 |  |  | Procurement lead time (1) | PRINISKI | 15 |  | 2011-04-08 | 2011-04-08 | 2011-04-29 | 2011-04-08 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
31 |  |  | AWARD | PRINISKI | 1 |  | 2011-04-29 | 2011-04-29 | 2011-04-30 09:36 | 2011-04-29 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
32 |  |  | Fabricate or delivery Fabricate or delivery | PRINISKI | 80 |  | 2011-05-02 | 2011-05-02 | 2011-08-22 | 2011-05-02 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [20 empty] | Catalog lead | 6 | [27 empty] | 10
33 |  | Item 3: Vacuum Instrumentation |  | PRINISKI |  |  | 2011-04-07 |  |  | 2011-04-07 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 |  | 4 | [18 empty] | Catalog Price | 6 | [27 empty] | 15
34 |  |  | Prep Requisition and procurement package | PRINISKI | 4 |  | 2011-04-07 | 2011-04-07 | 2011-04-12 14:24 | 2011-04-07 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 19.2 | [7 empty] | Prev. Experince | 4 | [27 empty] | 20
35 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-04-13 | 2011-04-13 | 2011-04-14 09:36 | 2011-04-13 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 0.8 | [7 empty] | Prev. Experince | 4 | [27 empty] | 10
36 |  |  | Procurement lead time (1) | PRINISKI | 15 |  | 2011-04-14 | 2011-04-14 | 2011-05-05 | 2011-04-14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
37 |  |  | AWARD | PRINISKI | 1 |  | 2011-05-05 | 2011-05-05 | 2011-05-06 09:36 | 2011-05-05 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
38 |  |  | Fabricate and delivery | PRINISKI | 90 |  | 2011-05-06 | 2011-05-06 | 2011-09-09 | 2011-05-06 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [20 empty] | Catalog lead | 4 | [27 empty] | 20 | Depends on final configuration
39 |  | Item 4: Ceramic Breaks x 2 (one per TMP) |  |  |  |  | 2011-04-07 |  |  | 2011-04-07 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 |  | 24 | [18 empty] | Vendor Quote | 6 | [27 empty] | 15 | -5
40 |  |  | Prep Requisition and procurement package | PRINISKI | 4 |  | 2011-04-07 | 2011-04-07 | 2011-04-12 14:24 | 2011-04-07 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 12.8 | [7 empty] | Prev. Experince | 4 | [27 empty] | 15 | -5
41 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 |  | 2011-04-11 | 2011-04-11 | 2011-04-12 09:36 | 2011-04-11 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 0.8 | [7 empty] | Prev. Experince | 4
42 |  |  | Procurement lead time (1) | PRINISKI | 15 |  | 2011-04-12 | 2011-04-12 | 2011-05-03 | 2011-04-12 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
43 |  |  | AWARD | PRINISKI | 1 |  | 2011-05-03 | 2011-05-03 | 2011-05-04 09:36 | 2011-05-03 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
44 |  |  | Fabricate and delivery | PRINISKI | 70 |  | 2011-05-04 | 2011-05-04 | 2011-08-10 | 2011-05-04 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [20 empty] | Prev. Experince | 4 | [27 empty] | 20
|  | All other Materials/Components |  | PRINISKI | 90 |  | 2011-04-15 | 2011-04-15 | 2011-08-19 | 2011-04-15 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 |  | 25 | [10 empty] | 20 | [7 empty] | Prev. Experince | 4 | [27 empty] | 20
45 |  | Installation | [7 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
46 |  | Installation Procedure |  | PRINISKI | 10 |  | 2011-11-01 | 2011-11-01 | 2011-11-15 | 2011-11-01 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 40 | [7 empty] | Prev. Experince | 4 | [27 empty] | 10
47 |  |  | Pre-Assemble Duct Legs 1 and 2 | PRINISKI | 15 |  | 2012-09-20 | 2012-09-20 | 2012-10-11 | 2012-09-20 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 |  | 6 | [10 empty] | 12 | 150 | [6 empty] | Exper./Judgent | 4,2 | [27 empty] | 15
48 |  |  | Leak Checking | PRINISKI | 3 |  | 2012-10-11 | 2012-10-11 | 2012-10-15 04:48 | 2012-10-11 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [13 empty] | 12 | [6 empty] | Exper./Judgent | 4,2 | [27 empty] | 25
49 |  |  | Install TVPS Supports/ | PRINISKI | 8 |  | 2014-04-01 | 2014-04-01 | 2014-04-12 04:48 | 2014-04-01 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 26 | 89.6 | [6 empty] | Exper./Judgent | 4,2 | [27 empty] | 20
50 |  |  | Install Ducts/Pumps | PRINISKI | 10 |  | 2014-04-11 | 2014-04-11 | 2014-04-25 | 2014-04-11 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 20 | 96 | [6 empty] | Exper./Judgent | 4,2 | [27 empty] | 20
51 |  |  | PTP Testing | PRINISKI | 3 |  | 2014-04-25 | 2014-04-25 | 2014-04-29 04:48 | 2014-04-25 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | [12 empty] | 6 | 9.6 | [6 empty] | Prev. Experince | 4 | [27 empty] | 10
52 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
53 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
54 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
55 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
56 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
57 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
58 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
59 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
60 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
61 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
62 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
63 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
64 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
65 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
66 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
67 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
68 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
69 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
70 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
71 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
72 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
73 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
74 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
75 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
76 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
77 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
78 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
79 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
80 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
81 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
82 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
83 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
84 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
85 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
86 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
87 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
88 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
89 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
90 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
91 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
92 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
93 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
94 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
95 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
96 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
97 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
98 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
99 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
100 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
101 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
102 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
103 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
104 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
105 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
106 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
107 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
108 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
109 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
110 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
111 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
112 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
113 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
114 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
115 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
116 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
117 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
118 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
119 | [9 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
[10 empty] | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14 | 2010-06-15 13:14
|  | TOTALS | [13 empty] | 146 | 0 | 0 | 0 | 0 | 0 | 430 | 0 | 0 | 0 | 0 | 658.8 | 357.2 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 374.5084 | [10 empty] | 171.988 | 0 | 0 | 0 | 0 | 0 | 51.084 | 0 | 0 | 0 | 0 | 98.26 | 53.1764 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [14 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  | Weeks | [10 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  |  | 3 | [10 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  |  | 5 | [10 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  |  | 8 | [10 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  |  | 9 | [10 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: 1180
Job Number: 2485
Job Title: NSTX NB2 TVPS
Job Manager: Craig Priniski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  | 10
| Design Complexity |  |  | X | 10
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Leaks discovered durring intallation/testing |  |  |  | L | Depending on location, field fix or replace with spares |  |  | Past NSTX Experience | 0 | 20 | 0 | 2
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: 1180
Job Number: 2485
Job Title: NSTX NB2 TVPS
Job Manager: Craig Priniski
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Item 1: 3200 l/s TMPs x 2 | $64K | Vednor Quote, summer 2009 | 6- Vendor Quote
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS