## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 4100
Job Title: | Center Stack (CS) Upgrade Diagnostics
Job Manager: | Robert Kaita/Jeff Abramson
Description:
Design and fabrications of CS magnetics diagnostics to replace units removed with old center stack. They consist of the following. Internal (in vacuum): Thermocouples Mirnov/Pickup Coils Halo Current Rogowski Coils Tile-Mounted Langmuir Probes External (in air): Thermocouples Flux Loops Plasma Current Rogowski Coils
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  | 9417
| Job Number: |  | 4100
| Job Title: |  | Center Stack (CS) Upgrade Diagnostics
| Job Manager: |  | Robert Kaita/Jeff Abramson
Estimate (user input)
| Robert Kaita/Jeff Abramson |  |  |  | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS | [16 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [22 empty] | 116.7
task | TASK DESCRIPTION |  |  | Responsible | Duration in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** SB (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SB (Electr Tech) | EM** EM (FO&M Engr) | EM** SB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other: Machinast | Other:__________ | Other:__________ | Cont | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
numb | [15 empty] | 1.178 | 1.178 | 1.617 | 1.232 | 1.859 | 177.11 | 118.8 | 143.5 | 144.4 | 172.42 | 122.43 | 149.15 | 115.61 | 150.77 | 142.83 | 180.23 | 89.2 | 150 | 150
1 |  | Physics Requirements |  | Kaita | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
2 |  |  | Similar coils and sensors used extensively for research on NSTX | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
3 |  | Conceptual Design | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
4 |  | PREPARE WORK PLANNING FORM |  | Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [12 empty] | 20 | [9 empty] | 2 & 4
5 |  | Prep System Description |  | Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 40 | 10 | 40 | 10 | [8 empty] | 2 & 4
6 |  | Prep System Requirements |  | Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 40 | 10 | 40 | 10 | [8 empty] | 2 & 4
7 |  | R&D | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
8 |  | Ananlysis | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
9 |  | CDR |  | Kaita/Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 20 | 10 | 30 | 10 | [8 empty] | 2 & 4
10 |  |  | Similar coils and sensors used extensively for research on NSTX | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
11 |  | Preliminary Design |  |  | 35 |  |  | 2010-07-12 12:55 | 2010-08-30 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
16 |  | Update Cost & Schedule Estimate |  | Kaita/Egebo | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 20 |  | 40 | [7 empty] | 10% |  | 2 & 4
17 |  | Design Drawings |  | Kaita/Jariwala | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [7 empty] | 120 |  |  | 80 |  | 40 | [7 empty] | 10% |  | 2 & 4
18 |  | PDR Prep |  | Kaita/Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 20 |  | 40 | [7 empty] | 10% |  | 2 & 4
19 |  | CONDUCT PDR |  | Kaita/Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 4 |  | 4 | [7 empty] | 10% |  | 2 & 4
20 |  |  | Similar coils and sensors used extensively for research on NSTX | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
21 |  | Final Design |  |  | 180 |  |  | 2010-07-12 12:55 | 2011-03-21 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
22 |  | Disposition PDR Chits |  | Kaita/Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 40 |  | 40 | [7 empty] | 10% |  | 2 & 4
23 |  | Design Drawings |  | Kaita/Jariwala | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [7 empty] | 120 |  |  | 80 | 20 | 40 | 20 | [6 empty] | 10% |  | 2 & 4
25 |  | Update Cost & Schedule Estimate |  | Kaita/Egebo | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 80 |  | 40 | [7 empty] | 10% |  | 2 & 4
26 |  | Prep Procurement Specs |  | Kaita/Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 40 |  | 20 | [7 empty] | 10% |  | 2 & 4
27 |  | FDR Prep |  | Kaita/Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 40 |  | 80 | [7 empty] | 10% |  | 2 & 4
28 |  | CONDUCT FDR |  | Kaita/Abramson | [5 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 4 |  | 4 | [7 empty] | 10% |  | 2 & 4
29 |  |  | Similar coils and sensors used extensively for research on NSTX | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
30 |  | Procurement | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
31 |  | Item 1: Wire & Cables |  |  | 40 |  |  | 2010-07-12 12:55 | 2010-09-06 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 |  | 19 | [18 empty] | 20% |  | 2 & 4
32 |  |  | Prep Requisition and procurement package | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 40 | 40 | 80 | 40 | [6 empty] | 20% |  | 2 & 4
33 |  |  | SUBMIT REQ TO PROCUREMENT | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 20 |  | 20 | [7 empty] | 20% |  | 2 & 4
34 |  |  | Procurement lead time (1) | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
35 |  |  | AWARD | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 20 |  | 20 | [7 empty] | 20% |  | 2 & 4
36 |  |  | Fabricate or delivery | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [11 empty] | 120 |  | 240 | [6 empty] | 20% |  | 2 & 4
37 |  | Item 2:Coils w/ Mandrels |  |  | 120 |  |  | 2010-07-12 12:55 | 2010-12-27 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 |  | 40 | [18 empty] | 20% |  | 2 & 4
38 |  |  | Prep Requisition and procurement package | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 10 | 40 | 80 | 20 | [6 empty] | 20% |  | 2 & 4
39 |  |  | SUBMIT REQ TO PROCUREMENT | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 10 |  | 10 | [7 empty] | 20% |  | 2 & 4
40 |  |  | Procurement lead time (1) | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
41 |  |  | AWARD | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
42 |  |  | Fabricate or delivery | [6 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [11 empty] | 160 | 40 | 120 |  |  |  | 120 |  |  | 20% |  | 2 & 4
43 | [9 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
44 |  | Fab/Assembly | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
45 |  | Fab/Assy Procedure | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 12 | 20 | 60 | 20 | [6 empty] | 20% |  | 2 & 4
46 |  | Shop Fabrication | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 10 | 300 | 180 | 240 |  |  |  | 40 |  |  | 20% |  | 2 & 4
47 |  | Assembly | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 10 | 280 | 132 | 360 | [6 empty] | 20% |  | 2 & 4
48 | [9 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
49 |  | Installation | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
50 |  | Installation Procedure (ex-vessel only) | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 40 | 20 | 80 | 40 | [6 empty] | 10% |  | 2 & 4
51 |  | Machine Installation (ex-vessel only) | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 20 | 200 | 40 | 180 | [6 empty] | 10% |  | 2 & 4
52 |  | PTP Testing | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | [10 empty] | 20 | 100 | 40 | 80 | [6 empty] | 10% |  | 2 & 4
53 | [9 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
54 |  | OTHER TASKS | [7 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
55 | [9 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
[10 empty] | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55 | 2010-07-12 12:55
|  | TOTALS | [13 empty] | 59 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 720 | 1330 | 1260 | 1390 | 0 | 0 | 0 | 160 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 747.8872 | [10 empty] | 69.502 | 0 | 0 | 0 | 0 | 0 | 28.512 | 0 | 0 | 124.1424 | 162.8319 | 187.929 | 160.6979 | 0 | 0 | 0 | 14.272 | 0 | 0
| Notes: | [15 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: |  | Weeks | [12 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  | 3 | [12 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  | 5 | [12 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  | 8 | [12 empty] | 4 - Previous PPPL/ORNL Experience (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  | 9 | [12 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 4100
Job Title: |  | Center Stack (CS) Upgrade Diagnostics
Job Manager: |  | Robert Kaita/Jeff Abramson
Robert Kaita/Jeff Abramson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X |  |  | 10 | Reuse of existing design with extensive operational experience and high design maturity level
| Design Complexity |  |  | X | 10 | No new design required to replace any removed diagnostic equipment for CSU
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Procurement Delay |  |  |  | VU | adjust schedule |  |  | similar previous work
2 | QA problem with received items |  |  |  | VU | return item to vendor, adjust schedule |  |  | similar previous work
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Details Hours by Tasks
|  |  |  | FY09$K |  |  |  |  | HOURS
| USER INPUT TASKS AND DESCRIPTIONS |  |  | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other: Machining
numb | P3 cross ref (optinal) |  |  | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150
1 |  | Physics Requirements
2 | Robert Kaita/Jeff Abramson
3 |  | Conceptual Design
4 |  | PREPARE WORK PLANNING FORM
5 |  | Prep System Description
6 |  | Prep System Requirements
7 |  | R&D
8 |  | Ananlysis
9 |  | CDR
10
11 |  | Preliminary Design
Internal:
Thermocouples
|  |  | Design | [9 empty] | 20 |  | 20
|  |  | CS Layout-Design | [6 empty] | 40 |  |  | 10 |  | 20
|  |  | Procure Materials | 2000 | [8 empty] | 10 |  | 10
|  |  | Fabricate | [12 empty] | 80
|  |  | Attach to Tiles | [10 empty] | 80 | 10 | 10
|  |  | Inst. Procedure review/update | [11 empty] | 20
|  |  | CS Installation | [12 empty] | 80
|  |  | CS Termination | [10 empty] | 100 |  | 20
|  |  | CWD Update | [9 empty] | 40
Mirnov/Pickup Coils
|  |  | Design-Layout | [6 empty] | 60 |  |  | 40 |  | 60
|  |  | CS Design Interface | [11 empty] | 40
|  |  | Procure Materials; wire & Mandrels | 12000 | [10 empty] | 20
|  |  | Wind Coils | 7500 | [10 empty] | 20
|  |  | Testing | [10 empty] | 40
|  |  | Mount in Tiles | [11 empty] | 20 | 120
|  |  | Inst. Procedure review/update | [11 empty] | 20
|  |  | CS Installation | [10 empty] | 80 | 40 | 120
|  |  | CS Termination | [10 empty] | 120
|  |  | CWD Update | [9 empty] | 20
Halo Current Rogowski Coils
|  |  | Drawing Update | [6 empty] | 40 |  |  | 20 |  | 20
|  |  | Procure Materials; Mandrel, ceramic wire, ceramic wrap, foil, sleeving, cement | 6000 | [11 empty] | 40
|  |  | Wind Coils | 6000
|  |  | Perform Coil Testing | [12 empty] | 40
|  |  | Copper Foil Inst.and Wrap | [10 empty] | 80
|  |  | Mandrel sizing for center stack | [10 empty] | 40
|  |  | Testing Installed colis | [11 empty] | 40 | 40
|  |  | Inst. Procedure review/update | [11 empty] | 20
|  |  | Center Stack Installation | [9 empty] | 120
|  |  | CWD Update | [9 empty] | 20
Tile-Mounted Langmuir Probes
|  |  | Design-Layout | [9 empty] | 20 |  | 20
|  |  | CS Layout Design | [9 empty] | 20 |  | 60
|  |  | Procure Materials | 2000
|  |  | Fabricate | [12 empty] | 80
|  |  | Inst. Procedure review/update | [11 empty] | 20
|  |  | Install in Tile | [12 empty] | 120
|  |  | CS Installation | [12 empty] | 80
|  |  | CS Termination | [10 empty] | 160
|  |  | CWD Update | [9 empty] | 20
External:
Thermocouples
|  |  | Procure Materials | 1500 | [8 empty] | 20 |  | 20
|  |  | Design-Layout | [6 empty] | 20 |  |  | 20 |  | 20
|  |  | Fac TCs | [12 empty] | 40
|  |  | Inst. Procedure review/update | [11 empty] | 20
|  |  | CS Installation | [9 empty] | 120 |  | 40
|  |  | CS Termination | [10 empty] | 20 | 20 | 40
|  |  | Tokomak Installation | [9 empty] | 40 |  | 20
|  |  | CWD Update | [9 empty] | 20
Flux Loops
|  |  | Design-Layout, Dwg update | 1000 | [5 empty] | 20 |  |  | 20 |  | 40
|  |  | Procure Materials | 3000 | [10 empty] | 40
|  |  | Fabricate Mandrels | [11 empty] | 40 |  |  |  |  | 80
|  |  | Inst. Procedure review/update | [11 empty] | 20
|  |  | CS Installation | [9 empty] | 40 | 320 | 80
|  |  | Tokomak Installation | [12 empty] | 120
|  |  | Field Cable | 3000 | [8 empty] | 40 |  | 40 | 120
|  |  | Testing | [9 empty] | 40 |  |  | 40
|  |  | CWD Update | [11 empty] | 20
Plasma Current Rogowski Coils
|  |  | Design-Layout, Dwg update | [11 empty] | 40
|  |  | Procure Materials | 3000 | [10 empty] | 40
|  |  | Fabricate Mandrels | [11 empty] | 40 | 40 |  |  |  | 80
|  |  | Wind Rogowski Coils | 10000 | [10 empty] | 80
|  |  | Temp tooling | 2000
|  |  | Copper Foil Insulation and Kapton Wrap | [10 empty] | 80
|  |  | Testing | [11 empty] | 40 | 40
|  |  | Inst. Procedure review/update | [11 empty] | 20
|  |  | CS Installation | [9 empty] | 40 | 240 | 80
|  |  | Tokomak Installation | [9 empty] | 20 |  | 60 | 120
|  |  | TOTALS, $ & Hrs | 59000 |  |  |  |  | 0 | 180 | 0 | 0 | 780 | 1360 | 1300 | 1390 | 0 | 0 | 0 | 160