## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9417
Job Number: | 4500
Job Title: | Title : MPTS _ CSU_Vacuum Vessel Modifications
Job Manager: | Job Manager : George Labik
Rev 1 7/23/2010
Description:
The increased diameter of the Center Stack Upgrade requires changes to the laser path which requires a new laser input vessel penetration and plugging of the existing penetration, modification of the alignment probe, expansion of the South wall laser components enclosure, modification of the L port or new penetration for an external laser dump, a vacuum boundary extension for the laser dump, repositioning the RWM coil 'LA' vertical legs, special configuration of the PF coil support column near Bay G. repositioning of the Optics Box, possible reconfiguration of the Optics Box. Modifications are to anticipate a third laser in the future and accommodation of other diagnostics including CHERS background and FIDA
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9417 | [16 empty] | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours
| Job Number: |  |  | 4500
| Job Title: |  |  | Title : MPTS _ CSU_Vacuum Vessel Modifications
| Job Manager: |  |  | Job Manager : George Labik
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY10$K |  |  |  |  | HOURS (priced at FY10 rates) | [16 empty] | % | % |  |  |  |  | FY10 | [7 empty] | FY11 | [8 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WorkDays | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | Actual= A | M&S (41) K$ | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01
numb | P3 cross ref (optinal) | [14 empty] | 1.178 | 1.178 | 1.714 | 1.271 | 1.971 | 193.33 | 128.05 | 143.2 | 101.3 | 184.89 | 160.46 | 127.23 | 90.78 | 165.2 | 155.15 | 123.17 | 95.5 | 130.28 | 173.91 | 1 | 1 | 1
1 |  | Physics Requirements |  | BL,AD,BS | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
2 |  | Conceptual Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
3 |  | PREPARE WORK PLANNING FORM |  | GL,BS | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 10 | [11 empty] | 2 | bar: 2010-05-01
4 |  | Prep System Description |  | GL,BL,AD,BS | [5 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 40 |  |  |  |  | 80 | [6 empty] | 2 | bar: 2010-03-01 to 2010-08-01
Laser input new penetration and port
Plug existing penetration
Machining Bay F edge
Bay L Modify penetration & Install new port and port cover
5 |  | Prep Requirements | bar: 2010-06-01
6 |  | Preliminary Optics Design | [31 empty] | 40 |  |  |  | 30% | 30% |  | 2
7 |  | Mechanical Design | [19 empty] | 120 | [6 empty] | 80 |  |  |  |  | 40 |  |  |  | 30% | 30% |  | 2
8 |  | Machine Tool Support Design | [19 empty] | 120 | [6 empty] | 80 | [8 empty] | 30% | 30% |  | 2
9 |  | Stress Analysis | [18 empty] | 400 | [7 empty] | 40 |  |  |  |  | 20 |  |  |  | 30% | 30% |  | 2
10 |  | Technical Support | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 20 |  |  |  |  | 20 |  |  |  | 30% | 30% |  | 2 | bar: 2010-03-01 to 2011-03-01
12 |  | Preliminary Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
13 |  | Analysis | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [7 empty] | 10 |  |  |  |  | 10 |  |  |  | 30% | 30% |  | 2
14 |  | Mechanical Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 120 | [6 empty] | 120 |  |  |  |  | 30 |  |  |  | 30% | 30% |  | 2
15 |  | Machine Tool Support Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 200 | [6 empty] | 100 |  |  |  |  | 5 |  |  |  | 30% | 30% |  | 2
16 |  | Prepare NEPA Form | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
17 |  | Update Cost & Schedule Estimate | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-02-01
18 |  | Design Drawings | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
20 |  | CONDUCT PDR | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 10 | 20 | [6 empty] | 40 |  |  |  |  | 20 |  |  |  | 30% | 30% |  | 2
21 |  | Technical Support | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 20 |  |  |  |  | 20 |  |  |  | 30% | 30% |  | 2
22 |  | Final Design | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
23 |  | Disposition PDR Chits | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 20 | [6 empty] | 40 |  |  |  |  | 20 |  |  |  | 30% | 30% |  | 2
24 |  | Complete Optics Evaluation | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [19 empty] | 180 |  |  |  | 30% | 30% |  | 2
25 |  | Design Drawings | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 160 | [6 empty] | 40 |  |  |  |  | 20 |  |  |  | 30% | 30% |  | 2
26 |  | Update Analyses | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [7 empty] | 20 |  |  |  |  | 10 |  |  |  | 30% | 30% |  | 2
27 |  | Update Cost & Schedule Estimate | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 40 |  |  |  |  | 10 |  |  |  | 30% | 30% |  | 2
28 |  | Final Design Changes | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 30 | 40 | [6 empty] | 40 |  |  |  |  | 20 |  |  |  | 30% | 30% |  | 2
|  | CONDUCT FDR | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 10 | [7 empty] | 40 |  |  |  |  | 20 |  |  |  | 30% | 30% |  | 2 | bar: 2010-03-01 to 2013-02-01
29 |  | Detail Drawings | [19 empty] | 300 | [6 empty] | 60 |  |  |  |  | 10 |  |  |  | 30% | 30% |  | 2
30 |  | FDR Chit Response | [18 empty] | 20 | 20 | [6 empty] | 20 |  |  |  |  | 10 |  |  |  | 30% | 30% |  | 2
31 |  | Procurement | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 |  | 1 | Bay L Wire Seal Flange & Nozzle w/Weld Prep | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 20 | [12 empty] | 10 | [8 empty] | 30% | 30% |  | 2
33 |  | 2 | Bay L Port Cover | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 12 | [12 empty] | 10 | [8 empty] | 30% | 30% |  | 2
34 |  | 3 | Portable Milling Machine, Line Bore or Modified Bridgeport Head | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 15 | [12 empty] | 40 | [8 empty] | 30% | 30% |  | 2
35 |  | 4 | Misc Materials | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 20 | [12 empty] | 20 | [8 empty] | 30% | 30% |  | 2
36 |  |  | Tooling | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10
37 |  | Fab/Assembly | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
38 |  | Fabricate 3 Tooling Supports Assemblies | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 20 | 100 |  |  | 200 |  |  |  |  | 30% | 30% |  | 2
39 |  | POP Vessel Wall Plate and Nozzle Mockup | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 60 | 240 |  |  | 300 |  |  |  |  | 30% | 30% |  | 2
40 |  | Leak Check Fixture | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [18 empty] | 40 |  |  |  |  | 30% | 30% |  | 2
41 |  | Low Power Laser Holder for Bay L , F and F/G | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 | [6 empty] | 20 | 40 |  |  | 60 |  |  |  |  | 30% | 30% |  | 2
42 |  | Installation | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
43 |  | Assume Center Stack Removed and Vessel Preped _No Charges to MPTS
44 |  | Installation Procedure | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 60 | [8 empty] | 30% | 30% |  | 2
45 |  | Set Up Tooling Supports and Machine New Penetrations Bay L and F/G | [27 empty] | 160 |  |  | 300 |  |  |  |  | 30% | 30% |  | 2
46 |  | Set Up New Ports Support | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 |  |  | 60 |  |  |  |  | 30% | 30% |  | 2
47 |  | Weld New Ports | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [18 empty] | 120 |  |  |  |  | 30% | 30% |  | 2
48 |  | Set up and Machine Bay F Edge | [26 empty] | 20 | 60 |  |  | 90 |  |  |  |  | 30% | 30% |  | 2
49 |  | Laser Alignment of Ports and F Edge During Welding | [26 empty] | 24 | 10 | [7 empty] | 30% | 30% |  | 2
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | OTHER TASKS | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
50 |  |  | Metrology Support | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 120 | [8 empty] | 30% | 30% |  | 2 | bar: 2011-10-01 to 2012-02-01
51 |  |  | Reposition magnetics and glow discharge filaments | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 | [6 empty] | 160 | 60 |  |  | 120 |  |  |  |  | 30% | 30% |  | 2 | bar: 2011-10-01 to 2012-02-01
52 |  |  | Modify CHERS Razor dump | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 40 | [6 empty] | 60 | 20 |  |  | 20 |  |  |  |  | 30% | 30% |  | 2 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
53 |  |  | Chgrs Background View to Bay L Modified Port | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 120 | [6 empty] | 40 | bar: 2011-10-01 to 2012-02-01
54 |  |  | Other Diagnostics Views to Bay L Modified Port | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 120 | [6 empty] | 40 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2011-10-01 to 2012-02-01
|  | TOTALS | [13 empty] | 77 | 0 | 0 | 0 | 0 | 630 | 1560 | 0 | 0 | 0 | 0 | 0 | 0 | 1564 | 730 | 0 | 0 | 1310 | 585 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1056.2984 | [10 empty] | 90.706 | 0 | 0 | 0 | 0 | 121.7979 | 199.758 | 0 | 0 | 0 | 0 | 0 | 0 | 258.3728 | 113.2595 | 0 | 0 | 170.6668 | 101.7373 | 0 | 0
| Notes: | [23 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: | [6 empty] | Weeks | [15 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items | [5 empty] | 3 | [15 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items | [5 empty] | 5 | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) | [5 empty] | 8 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts | [5 empty] | 9 | [15 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts

## Tab C Risk and uncertainty
Cost Center: |  | 9417
Job Number: |  | 4500
Job Title: |  | Title : MPTS _ CSU_Vacuum Vessel Modifications
Job Manager: |  | Job Manager : George Labik
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | x |  | 50
| Design Complexity |  | x |  | 25
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Stray light |  |  |  | Medium | 1. Enlarge Bay L Port 2. Razor blade dump around Bay L |  |  | PPPL Experience | 10 | 20 | 6 | 10
2 | RWM Coils position change. Space available |  |  |  | Medium | Reconfigure coils. Possible impact to Bay JK cap |  |  | PPPL Experience | 50 | 100 | 8 | 12
3 | Bay F rework |  |  |  | Low | 1.Modify the Optics Box and reposition 2. Light cut of Bay F Vessel ID interface |  |  | PPPL Experience | 50 | 100 | 12 | 18
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9417
Job Number: | 4500
Job Title: | Title : MPTS _ CSU_Vacuum Vessel Modifications
Job Manager: | Job Manager : George Labik
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS