## Tab A Description
Work Approval Form (WAF)
Cost Center: 9417
Job Number: 7200
Job Title: NSTX CSU Project Management
Job Manager: Larry Dudek
Description:
Level-of-Effort (LOE) job to cover the oversight of CSU work and to cover engineers time for project cost and schedule reviews.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: 9417
Job Number: 7200
Job Title: NSTX CSU Project Management
Job Manager: Larry Dudek
| FY10 | FY11 | FY12 | FY13 | FTE Total | Cost k$ | Approximate Rate ($k/FTE) | Contingency
Manger - Dudek | 0.45 | 0.45 | 0.4 | 0.4 | 1.7 | 503.71 | 296.3 | 13%
P&C Officer - Guzman (covered in Upgrade Project Job)
Project Engineering - Neumeyer | 0.4 | 0.25 | 0.25 | 0.2 | 1.1 | 337.26 | 306.6 | 13%
Systems Engineering* _ Simmons (covered in Upgrade Project Job)
Bi-Annual Review Support for 4 RLMs** | 0.36 | 0.36 | 0.36 | 0.36 | 1.4545 | 430.9818 | 296.3 | 13%
Other Related Expenses (10%) - Clerical, travel , etc | [5 empty] | 127.1952 |  | 13%
[5 empty] | TOTAL | 1399.1
CD1 Support | FY10
CD2 Support | FY10
CD3 Support |  | FY11
6 month review |  | FY11
6 month review |  |  | FY12
6 month review |  |  | FY12
CD4 Support |  |  |  | FY13
6 month review |  |  |  | FY13
*Systems Engineering covers - development & maintenance of the risk registry; Interface definitiion and documentation
Requirements / documentation; design review-validation (whats required for each review and measure of success)
Analysis and definition documentation
** Titius, Chrzanowski, Viola, Ramakrishnan (each 1 week prep, 1 week followup per review)

## Tab C Risk and uncertainty
Cost Center: 9417
Job Number: 7200
Job Title: NSTX CSU Project Management
Job Manager: Larry Dudek
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | add'l reviews |  |  |  | U |  |  |  | add'l review every other year |  | 107
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended