## Tab A Description
Work Approval Form (WAF)
Cost Center: | 9418
Job Number: | 7300
Job Title: | NBI Project Support & Integration
Job Manager: | Tim Stevenson
Description:
Management and engineering oversight of NBI upgrade through FY2013. Job engineer preparation for reviews every 6 months. (6 engr*80hours*2 reviews/yr.).
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 9418
| Job Number: |  |  | 7300
| 9418 |  |  | NBI Project Support & Integration
| Job Manager: |  |  | Tim Stevenson
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Resp | Duration in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | contingency | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
1 |  |  | Engineering Mgmt of NBI Upgrade FY10 |  | 260 |  | 2009-10-01 | 2009-10-01 | 2010-09-30 | 2009-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 860 | [16 empty] | 13% |  | 50% time of Proj Manager | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
2 |  |  | Job Engineer (6 engr) prep for reviews 2/yr. |  | 10 |  | 2010-05-01 | 2010-05-01 | 2010-05-15 | 2010-05-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 320 |  |  |  | 640 | [12 empty] | 13% |  | 80hrs/ each of 6 engineers 2 times each year to support reviews | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
3 |  |  | Fall review |  | 10 |  | 2010-09-15 | 2010-09-15 | 2010-09-29 | 2010-09-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
4 |  |  | Engineering Mgmt of NBI Upgrade FY11 |  | 260 |  | 2010-10-01 | 2010-10-01 | 2011-09-30 | 2010-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 860 | [16 empty] | 13% |  | 50% time of Proj Manager | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
5 |  |  | Job Engineer (6 engr) prep for reviews 2/yr. |  | 10 |  | 2011-05-01 | 2011-05-01 | 2011-05-15 | 2011-05-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 320 |  |  |  | 640 | [12 empty] | 13% |  | 80hrs/ each of 6 engineers 2 times each year to support reviews | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
6 |  |  | Fall review |  | 10 |  | 2011-09-15 | 2011-09-15 | 2011-09-29 | 2011-09-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
7 |  |  | Engineering Mgmt of NBI Upgrade FY12 |  | 260 |  | 2011-10-01 | 2011-10-01 | 2012-09-29 | 2011-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 1208 | [16 empty] | 13% |  | 70% time of Proj Manager | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
8 |  |  | Job Engineer (6 engr) prep for reviews 2/yr. |  | 10 |  | 2012-05-01 | 2012-05-01 | 2012-05-15 | 2012-05-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 320 |  |  |  | 640 | [12 empty] | 13% |  | 80hrs/ each of 6 engineers 2 times each year to support reviews | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
9 |  |  | Fall review |  | 10 |  | 2012-09-15 | 2012-09-15 | 2012-09-29 | 2012-09-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
10 |  |  | Engineering Mgmt of NBI Upgrade FY13 |  | 260 |  | 2012-10-01 | 2012-10-01 | 2013-09-30 | 2012-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 1208 | [16 empty] | 13% |  | 70% time of Proj Manager | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
11 |  |  | Job Engineer (6 engr) prep for reviews 2/yr. |  | 10 |  | 2013-05-01 | 2013-05-01 | 2013-05-15 | 2013-05-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 320 |  |  |  | 640 | [12 empty] | 13% |  | 80hrs/ each of 6 engineers 2 times each year to support reviews | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
12 |  |  | Fall review |  | 10 |  | 2013-09-15 | 2013-09-15 | 2013-09-29 | 2013-09-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
13 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
14 |  |  | 7300 include 0.1 FTE in mgmt for FY 10-13 for Al von Halle as RLM | [6 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 690.4
15 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
16 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | bar: 2008-10-01 to 2009-09-01; 2010-10-01 to 2011-09-01
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6106.4 | 0 | 0 | 0 | 2560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1468.1938 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058.8498 | 0 | 0 | 0 | 409.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
| (1) Procurement lead time: |  |  |  | Weeks | [13 empty] | CATEGORIZATION CODES:
| Purchase orders-Commercial, off-the-shelf items |  |  |  | 3 | [13 empty] | 1 - National Standards
| Purchase orders-Noncommercial items |  |  |  | 5 | [13 empty] | 2 - Engineering Judgement/Experience
| Subcontracts (non construction) |  |  |  | 8 | [13 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
| Construction subcontracts |  |  |  | 9 | [13 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 9418
Job Number: |  | 7300
9418 | 9418 | NBI Project Support & Integration
Job Manager: |  | Tim Stevenson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | CDR level plan
| Design Complexity |  | X |  |  | CDR level plan
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Increased management oversight due to unscoped additional reviews | [9 empty] | 75
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 9418
Job Number: | 7300
9418 | 9418
Job Manager: | Tim Stevenson
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
NOT APPLICABLE
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS