## Tab A Description
Work Approval Form (WAF)
Cost Center: 1170
Job Number: 1001
Job Title: Center Stack Upgrade (CSU) PFCs
Job Manager: Kelsey Tresemer
Description:
Provide adequate thermal coverage for the upgraded center stack via tiles. 1) Includes the design and analysis for both the CS and IBD plasma facing components. 2) Includes design modifications to the tiles to accommodate surface diagnostics 3) Includes design of tile mounting schemes and routing plan for diagnostics wires 4) Includes generation of required documentation such as checked calculations, specs and procedures. 5) Includes the procurement of all PFC tiles and hardware for the CS and IBD.
Schedule:
Refer Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: 1170
Job Number: 1001
Job Title: Center Stack Upgrade (CSU) PFCs
Job Manager: Kelsey Tresemer
Estimate (user input)
[5 empty] | SCHEDULE | [12 empty] | FY09$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10 | [16 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-02 | 2011-07-03 | 2011-08-04 | 2011-09-05
numb | P3 cross ref (optinal) | [16 empty] | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
|  | Conceptual Design | [9 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
1 |  | Preliminary Planning/Fact Finding |  | Tresemer | 20 |  |  |  | 2009-06-29 | 2009-06-29 | 2009-07-27 | 2009-06-29 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 80 | [6 empty] | 2 |  | 2
2 |  | Tile Layout/Preliminary Tile Design |  | Jariwala | 15 | 1 |  |  | 2009-07-06 | 2009-07-06 | 2009-07-27 | 2009-07-06 | 2009-07-27 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 120 | [11 empty] | 2 |  | 2
3 |  | Diagnostic Layout |  | Jariwala | 10 | 2 |  |  | 2009-07-27 | 2009-07-27 | 2009-08-10 | 2009-07-27 | 2009-07-27 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 80 |  |  |  |  | 20 | [6 empty] | 2 |  | 2
4 |  | PPPL Peer Review Prep |  | Tresemer | 4 | 2 | 3 |  | 2009-08-08 | 2009-08-08 | 2009-08-13 14:24 | 2009-08-08 | 2009-07-27 | 2009-08-10 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 32 |  |  |  |  | 16 | [6 empty] | 2 |  | 2
5 |  | PPPL Peer Review |  | Tresemer | 1 | 4 |  |  | 2009-08-13 | 2009-08-13 | 2009-08-14 09:36 | 2009-08-13 | 2009-08-13 14:24 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 8 |  |  |  |  | 8 | [6 empty] | 2 |  | 2
6 |  | Tile/Diagnostic/Hardware Reconfig, Mat. Research (R&D) |  | Tresemer | 40 | 5 |  |  | 2009-08-14 | 2009-08-14 | 2009-10-09 | 2009-08-14 | 2009-08-14 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 100 |  |  |  |  | 100 | [6 empty] | 2 |  | 2
7 |  | Tile Thermal Analysis |  | Tresemer | 15 | 6 |  |  | 2009-09-14 | 2009-09-14 | 2009-10-05 | 2009-09-14 | 2009-10-09 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [6 empty] | 80 | [5 empty] | 30 | [6 empty] | 2 |  | 2
8 |  | PU CDR prep |  | Tresemer | 5 | 7 | 6 |  | 2009-10-05 | 2009-10-05 | 2009-10-12 | 2009-10-05 | 2009-10-05 | 2009-10-09 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 40 |  |  |  |  | 30 | [6 empty] | 2 |  | 2
9 |  | PPPL CDR |  | Tresemer | 1 | 8 |  |  | 2009-10-13 | 2009-10-13 | 2009-10-14 09:36 | 2009-10-13 | 2009-10-12 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 8 |  |  |  |  | 8 | [6 empty] | 2 |  | 2
10 |  | Preliminary Design | [9 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
11 |  | CDR Chit Resolution |  | Tresemer | 10 | 9 |  |  |  | 2009-11-12 17:25 | 2009-11-26 17:25 | 2009-11-12 17:25 | 2009-10-14 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 30 |  |  |  |  | 40 | [6 empty] | 8 |  | 8
12 |  | Tile Analysis Continued… |  | Tresemer | 30 | 11 |  |  |  | 2009-11-26 17:25 | 2010-01-07 17:25 |  | 2009-11-26 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [6 empty] | 120 | [5 empty] | 60 | [6 empty] | 2 |  | 2
13 |  | FMEA Analysis |  | Tresemer | 15 | 11 |  |  |  | 2009-11-26 17:25 | 2009-12-17 17:25 | 2009-11-12 17:25 | 2009-11-26 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 60 | [6 empty] | 2 |  | 2
14 |  | Order Material Samples |  | Tresemer | 20 | 11 | 12 |  |  | 2010-01-07 17:25 | 2010-02-04 17:25 | 2009-11-12 17:25 | 2009-11-26 17:25 | 2010-01-07 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 |  | 5 |  |  | 5 | [7 empty] | 40 | [6 empty] | 2 |  | 2
15 |  | Material Testing |  | Tresemer | 20 | 14 |  |  |  | 2010-02-04 17:25 | 2010-03-04 17:25 | 2009-11-12 17:25 | 2010-02-04 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 40 | 80 | [5 empty] | 2 |  | 2
16 |  | Update Cost & Schedule Estimate |  | Tresemer | 5 | 9 | 12 | 15 |  | 2010-03-04 17:25 | 2010-03-11 17:25 |  | 2009-10-14 09:36 | 2010-01-07 17:25 | 2010-03-04 17:25 | 2009-11-12 17:25 | [12 empty] | 25 | [6 empty] | 2 |  | 2
17 |  | Design Drawings |  | Jariwala | 80 | 11 | 12 | 15 |  | 2010-03-04 17:25 | 2010-06-24 17:25 |  | 2009-11-26 17:25 | 2010-01-07 17:25 | 2010-03-04 17:25 | 2009-11-12 17:25 | [7 empty] | 640 | [11 empty] | 2 |  | 2
18 |  | PDR Prep |  | Tresemer | 10 |  |  |  | 2010-05-01 | 2010-05-01 | 2010-05-15 | 2010-05-01 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 20 |  |  |  |  | 40 | [6 empty] | 8 |  | 8
19 |  | CONDUCT PDR |  | Tresemer | 1 | 18 |  |  |  | 2010-05-15 | 2010-05-16 09:36 | 2009-11-12 17:25 | 2010-05-15 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 8
[12 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
|  | Final Design | [9 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
20 |  | Disposition PDR Chits |  | Tresemer | 20 | 19 |  |  |  | 2010-05-16 09:36 | 2010-06-13 09:36 | 2009-11-12 17:25 | 2010-05-16 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 60 |  |  |  |  | 80 | [6 empty] | 8 |  | 8
21 |  | Update Analyses |  | Tresemer | 25 | 20 |  |  |  | 2010-06-13 09:36 | 2010-07-18 09:36 | 2009-11-12 17:25 | 2010-06-13 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [6 empty] | 80 | [5 empty] | 50 | [6 empty] | 2 |  | 2
22 |  | Update Cost & Schedule Estimate |  | Tresemer | 5 | 21 |  |  |  | 2010-07-18 09:36 | 2010-07-25 09:36 | 2009-11-12 17:25 | 2010-07-18 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 20 | [6 empty] | 2 |  | 2
23 |  | Design Drawings |  | Tresemer | 250 | 21 |  |  |  | 2010-07-18 09:36 | 2011-07-03 09:36 | 2009-11-12 17:25 | 2010-07-18 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 2000 | [11 empty] | 2 |  | 2
24 |  | Prep Procurement Specs |  | Tresemer | 15 | 23 |  |  |  | 2011-07-03 09:36 | 2011-07-24 09:36 | 2009-11-12 17:25 | 2011-07-03 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 60 | [6 empty] | 2 |  | 2
25 |  | FDR Prep |  | Tresemer | 10 | 22 | 23 |  |  | 2011-07-03 09:36 | 2011-07-17 09:36 | 2009-11-12 17:25 | 2010-07-25 09:36 | 2011-07-03 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | [7 empty] | 16 |  |  |  |  | 40 | [6 empty] | 8 |  | 8
26 |  | CONDUCT FDR |  | Tresemer | 1 | 25 |  |  |  | 2011-07-17 09:36 | 2011-07-18 19:12 | 2009-11-12 17:25 | 2011-07-17 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 8
27 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
Procurement
28 |  | Item 1: Tiles (CFC and any other mat) |  | Tresemer | [7 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 |  | 650 | [17 empty] | 6 | ref tab D | 6
29 |  |  | Prep Requisition and procurement package | Tresemer | 4 | 26 |  |  |  | 2011-07-18 19:12 | 2011-07-24 09:36 | 2009-11-12 17:25 | 2011-07-18 19:12 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 16 | [6 empty] | 2 |  | 2
30 |  |  | SUBMIT REQ TO PROCUREMENT | Tresemer | 2 | 29 |  |  |  | 2011-07-24 09:36 | 2011-07-27 04:48 | 2009-11-12 17:25 | 2011-07-24 09:36 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 8 | [6 empty] | 2 |  | 2
31 |  |  | Procurement lead time (1) | Tresemer | 30 | 30 |  |  |  | 2011-07-27 04:48 | 2011-09-07 04:48 | 2009-11-12 17:25 | 2011-07-27 04:48 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
32 |  |  | AWARD | Tresemer | 1 | 31 |  |  |  | 2011-09-07 04:48 | 2011-09-08 14:24 | 2009-11-12 17:25 | 2011-09-07 04:48 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [19 empty] | 2 |  | 2
33 |  |  | Fabricate or delivery | Tresemer | 60 | 32 |  |  |  | 2011-09-08 14:24 | 2011-12-01 14:24 | 2009-11-12 17:25 | 2011-09-08 14:24 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [19 empty] | 2 |  | 2
34 |  |  | Machining of tiles for diagnostics | Tresemer | 20 | 33 |  |  |  | 2011-12-01 14:24 | 2011-12-29 14:24 | 2009-11-12 17:25 | 2011-12-01 14:24 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 |  | 15 | [11 empty] | 160 | [5 empty] | 2 |  | 2
|  | Item 2: hardware, other materials | [10 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 |  | 150 | [17 empty] | 4 |  | 4
35 |  |  | Prep Requisition and procurement package | Tresemer | 4 | 30 |  |  |  | 2011-07-27 04:48 | 2011-08-01 19:12 | 2009-11-12 17:25 | 2011-07-27 04:48 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 16 | [6 empty] | 2 |  | 2
36 |  |  | SUBMIT REQ TO PROCUREMENT | Tresemer | 2 | 35 |  |  |  | 2011-08-01 19:12 | 2011-08-04 14:24 | 2009-11-12 17:25 | 2011-08-01 19:12 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 8 | [6 empty] | 2 |  | 2
37 |  |  | Procurement lead time (1) | Tresemer | 20 | 36 |  |  |  | 2011-08-04 14:24 | 2011-09-01 14:24 | 2009-11-12 17:25 | 2011-08-04 14:24 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
38 |  |  | AWARD | Tresemer | 1 | 37 |  |  |  | 2011-09-01 14:24 | 2011-09-03 | 2009-11-12 17:25 | 2011-09-01 14:24 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [19 empty] | 2 |  | 2
39 |  |  | Fabricate or delivery | Tresemer | 30 | 38 |  |  |  | 2011-09-03 | 2011-10-15 | 2009-11-12 17:25 | 2011-09-03 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [19 empty] | 2 |  | 2
40 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
41 |  | Fab/Assembly | [9 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
42 |  | Fab/Assy Procedure |  | Tresemer | 20 | 31 | 37 |  |  | 2011-09-07 04:48 | 2011-10-05 04:48 | 2009-11-12 17:25 | 2011-09-07 04:48 | 2011-09-01 14:24 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 80 | [6 empty] | 8 |  | 8
43 |  | Shop Fabrication |  | Tresemer | 20 | 42 |  |  |  | 2011-10-05 04:48 | 2011-11-02 04:48 | 2009-11-12 17:25 | 2011-10-05 04:48 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [13 empty] | 120 | [5 empty] | 8 |  | 8
44 |  | Assembly |  | Tresemer | 20 | 34 | 39 | 43 |  | 2011-12-29 14:24 | 2012-01-26 14:24 | 2009-11-12 17:25 | 2011-12-29 14:24 | 2011-10-15 | 2011-11-02 04:48 | 2009-11-12 17:25 | [13 empty] | 120 | [5 empty] | 8 |  | 8
45 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
46 |  | Installation | [9 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
47 |  | Installation Procedure |  |  | 25 | 26 |  |  |  | 2011-07-18 19:12 | 2011-08-22 19:12 | 2009-11-12 17:25 | 2011-07-18 19:12 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 90 | [6 empty] | 8 |  | 8
48 |  | Machine Installation |  |  | 45 | 44 | 39 |  |  | 2012-01-26 14:24 | 2012-03-29 14:24 | 2009-11-12 17:25 | 2012-01-26 14:24 | 2011-10-15 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 60 | 360 | [5 empty] | 8 |  | 8
49 |  | Tile re-fit and additional machining |  |  | 20 | 44 | 48 |  |  | 2012-03-29 14:24 | 2012-04-26 14:24 | 2009-11-12 17:25 | 2012-01-26 14:24 | 2012-03-29 14:24 | 2009-11-12 17:25 | 2009-11-12 17:25 | [12 empty] | 40 | 160 | [5 empty] | 8 |  | 8
50 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
51 |  | OTHER TASKS | [9 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
52 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
53 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
54 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
55 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
56 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
57 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
58 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
59 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
60 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
61 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
62 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
63 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
64 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
65 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
66 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
67 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
68 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
69 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
70 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
71 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
72 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
73 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
74 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
75 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
76 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
77 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
78 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
79 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
80 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
81 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
82 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
83 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
84 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
85 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
86 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
87 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
88 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
89 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
90 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
91 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
92 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
93 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
94 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
95 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
96 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
97 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
98 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
99 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
100 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
101 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
102 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
103 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
104 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
105 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
106 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
107 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
108 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
109 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
110 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
111 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
112 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
113 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
114 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
115 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
116 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
117 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
118 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
119 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
120 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
121 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
122 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
123 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
124 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
125 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
126 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
127 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
128 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
129 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
130 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
131 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
132 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
133 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
134 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
135 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
136 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
137 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
138 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
139 | [11 empty] | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25 | 2009-11-12 17:25
140
[18 empty] | 820 | 0 | 0 | 5 | 0 | 280 | 3154 | 0 | 0 | 0 | 0 | 1181 | 1000 | 0 | 0 | 0 | 0 | 0 | 146
|  | TOTALS | [15 empty] | 1000.4 | 0 | 0 | 5.5 | 0 | 51.94 | 394.5339 | 0 | 0 | 0 | 0 | 195.302 | 145.35 | 0 | 0 | 0 | 0 | 0 | 21.9
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1814.9258 | [15 empty] | CATEGORIZATION CODES:
| Notes: | [19 empty] | 1 - National Standards
|  | (1) Procurement lead time: |  |  | Weeks | [15 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Commercial, off-the-shelf items |  | 3 | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Purchase orders-Noncommercial items |  | 5 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Subcontracts (non construction) |  | 8 | [15 empty] | 5 - Prototype Data/Test Results
|  |  | Construction subcontracts |  | 9 | [15 empty] | 6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NSTX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: 1170
Job Number: 1001
Job Title: Center Stack Upgrade (CSU) PFCs
Job Manager: Kelsey Tresemer
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Tiles not delivered on time |  |  |  | U | If schedule critical, install tiles in vessel |  |  |  | X |  | X
2 | Special diagnostics for tiles not receiced on time |  |  |  | U | If schedule critical, install tiles in vessel |  |  |  | X |  | X
3 | Tiles requiring unforseen machining |  |  |  | L | If schedule critical, and in-house machinining will not suffice, seek external machining sources. |  |  |  | X |  | X
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M & S breakdown
Material Cost Breakdown
TILES
Approx. 600 tiles
|  |  |  | Spare Parts |  | Handling Loss
| No. of tiles | Avg Dimensions | Volume (in^3) | No. of tiles, +20% | Volume (in^3) | No. of tiles, +10% | Volume (in^3)
Upper
Row 1 | 24 | 2"x7"x7' | 2352 | 30 | 2940 | 33 | 3234
Row 2 - 4 | 72 | 1"x4.5"x4" | 1296 | 87 | 1566 | 95.7 | 1722.6
Row 5 | 24 | 1"x10"x3.7" | 888 | 30 | 1110 | 33 | 1221
Center
Tow 6 - 20 | 360 | .75"x3.4"x5.8" | 5324.4 | 430 | 6359.7 | 473 | 6995.67
Lower
Row 1 | 24 | 2"x7"x7' | 2352 | 30 | 2940 | 33 | 3234
Row 2 - 4 | 72 | 1"x4.5"x4" | 1296 | 87 | 1566 | 95.7 | 1722.6
Row 5 | 24 | 1"x10"x3.7" | 888 | 30 | 1110 | 33 | 1221
Total | 600 |  | 14396.4 | 724 | 17591.7 | 796.4 | 19350.87
|  | Vol/section (in^3) | Vol/section (cm^3) | Density(g/cm^3) | Lbs
Rows 1-5: Silicon Carbide |  | 7900.2 | 129461.083 | 2.7 | 770.6146
Rows 6-20: CFRC |  | 11450.67 | 187642.8621 | 1.45 | 599.8385
SiC Costs: $100 - $500/lb
Cost:
@$100 | 77061.4646
@$500 | 385307.3232
CFRC Costs: $200 - $350/lb
@200 | 119967.6925
@350 | 209943.4619
Worst case: |  | If all CFRC: @$350 | If all CFRC: @$200
595250.7851 |  | 479658.5882 | 274090.6218
Billets for spare parts (not tiles):
50000 |  | 50000 | 50000
TOTAL |  | total | total
645250.7851 |  | 529658.5882 | 324090.6218
~$650,000.00
Hardware
Compared M&S data from old Job Cost Reports (circa 1997 - 2001)
tax adjust
1997 | 0 | 0
1998 | 59720 | 76823.808
1999 | 7070 | 8959.811
2000 | 0 | 0
2001 | 28974 | 34977.4128
TOTAL | 95764 | 120761.0318
Reflect a 25% increase due to increase in sheer amount of material increase
TOTAL
150951.2897
~$150,000.00