## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 1200
Job Title: | Vacuum Vessel & Support Structure
Job Manager: | Danny Mangra
Description:
Includes the analytical and CAD design of the support structures associated with the Magnet upgrade activities. Scope includes 1200-Vacuum Vessel & Structural Support 1201-Outer TF Structures 1202-Outer PF Coil Structures 1203-Umbrella Structural Reinforcement 1204-CS Support Pedestal 1205-Misc. Vacuum Vessel Structural Supports Includes the procurement and fabrication of these structures. Does not include installation costs.
Schedule:
Refer to the Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Est Rev1
Cost | Work |  | Activity Name | Responsible Cog Engr | Start | End | Duration | EAEM1 | EAEM2 | EAEM3 | EAEM4 | EAEM5 | EAEM6 | EAEM7 | EAEM | EAEM | EMEM1 | EMEM2 | EMEM3 | EMEM4 | EMEM5 | EEEM | EASB1 | EASB2 | EASB3 | EASB4 | EASB5 | EASB6 | EASB7 | EASB8 | EMSM1 | EMSM2 | EMSM3 | EMTB1 | EMTB2 | EMTB3 | EMTB4 | EMTB5 | M&S | OS | Travel | Stkrm. | Subtotal | Basis of Estimate | Category
Center | Package | Job # | [5 empty] | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs |  |  |  |  | M&S
[5 empty] | Date | Date | (Weeks) | (Chrzan.) | (Titus) | (Zhang) | (Zolfaghari) | (Avasarala) | (Brooks) | (Raftopoul.) | (general) | (Myatt) | (Mangra) | (Tresmer) | (Willard) | (Prinski) | (Simmons) |  | (Paul) | (Morris) | (Martinelli) | (Upcavage) | (Jariwala) | (Wojtowicz) | (Paluzzi) | (Elect) | (Meighan) | (Jurcz.) |  | (Tech) | (Machinist) | (Welder) | (electrical) | (General) | K$ | k$ | k$ | k$ | k$ | Labor | m&s
Dates for reference only superceded by Primavera Schedule Dates
1170 | 1*** | 1200 | Vacuum Vessel and structural support | Mangra
Metrology-to support design activities
Rapid Prototyping to support design activities
[5 empty] | 2009-10-01 | 2009-12-01 | [10 empty] | 100 |  |  | 200 |  |  |  |  | 40 | [8 empty] | 100 |  |  |  |  | 30 |  |  |  | 30 | 4 | 6
[5 empty] | 2010-01-08 | 2010-06-08 | [10 empty] | 60 |  |  | 88 |  |  |  |  | 40 | [8 empty] | 100 |  |  |  |  | 40 |  |  |  | 40 | 4 | 6
[5 empty] | 2010-06-08 | 2010-10-28 | [10 empty] | 40 | [7 empty] | 100 | [18 empty] | 4
1170 | 1*** | 1201 | Outer TF Structures | Mangra
|  |  | Concept Design Activities |  | 2009-10-01 | 2009-10-28
Concept design of OTF structures
|  |  | CDR |  |  | 2009-10-28 | [10 empty] | 40 | [7 empty] | 40 | [18 empty] | 2, 4, 9
|  |  | Preliminary Design Activities |  | 2009-11-01 | 2010-06-01
|  |  | Complete design of OTF structures |  | 2009-11-01 | 2010-06-01
|  |  | Outer TF Check other PF currents – Only two current cases have been considered |  | 2009-11-01 | 2010-06-01 |  |  |  | 120
|  |  | Tangential radius rods Clevis Shell Intersection |  | 2009-11-01 | 2010-06-01 |  |  | 40
|  |  | Tangential radius rods – interference with support columns, Weldment vs clevis/pin support. |  | 2009-11-01 | 2010-06-01 |  |  | 40
|  |  | Neutral Beam Vacuum Loads |  | 2009-11-01 | 2010-06-01 |  |  | 40
|  |  | Documentation-calculations |  | 2009-11-01 | 2010-06-01 | [14 empty] | 4
|  |  | Generate Cad detail and assembly drawings |  | 2009-11-01 | 2010-06-01
|  |  | PDR |  |  | 2010-05-28 | [10 empty] | 100 | [7 empty] | 160 | [18 empty] | 2, 4, 9
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Complete design of OTF structures |  | 2010-06-01 | 2010-11-01
|  |  | Outer TF Check other PF currents – Only two current cases have been considered |  | 2010-06-01 | 2010-11-01 |  |  |  | 120
|  |  | Tangential radius rods Clevis Shell Intersection |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Tangential radius rods – interference with support columns, Weldment vs clevis/pin support. |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Neutral Beam Vacuum Loads |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Documentation-calculations |  | 2010-06-01 | 2010-11-01 | [14 empty] | 4
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 | [36 empty] | 0
|  |  | FDR |  |  | 2010-10-28 | [10 empty] | 260 | [7 empty] | 900 | [18 empty] | 2, 4, 9
|  |  | Purchase & Fabrication | [39 empty] | 0
|  |  | Prep requisition & submit to procurement |  |  |  | 1
|  |  | Bid & award OTF structures |  |  |  | 6
|  |  | Fabricate components |  |  |  | 18 | [32 empty] | 297.6 | 3 |  | 300.6 |  | 2,6,7, 9
|  |  | Inspect components prior to shipment | [13 empty] | 8 | [23 empty] | 2 |  | 2 | 2
|  |  | Installation costs will be included in M. Viola's installation estimate | [39 empty] | 0
0
1170 | 1*** | 1202 | Outer PF Coil Structures | Mangra | [38 empty] | 0
|  |  | Concept Design Activities |  | 2009-10-01 | 2009-10-28
Concept design of PF structures(PF3,4,5 cage + PF2,PF1c)
|  |  | CDR |  |  | 2009-10-28 | [10 empty] | 100 | [7 empty] | 150 | [18 empty] | 2, 4, 9
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Analysis- Outer PF support – include PF3? What loads |  | 2009-10-01 | 2010-06-01 |  |  | 160
|  |  | Analysis- Local Model of Support Beam/Vessel Intersection |  | 2009-10-01 | 2010-06-01 |  |  | 20
|  |  | Analysis- Outer PF supports – elastomer vs sliding block |  | 2009-10-01 | 2010-06-01 |  |  | 40
|  |  | Analysis- PF2 PF1c Umbrella Load Dome Analysis |  | 2009-10-01 | 2010-06-01 |  |  | 40
|  |  | Documentation-calculations |  | 2009-10-01 | 2010-06-01 | [14 empty] | 4 | [22 empty] | 2
|  |  | Generate Cad detail and assembly drawings |  | 2009-10-01 | 2010-06-01
|  |  | Complete design of Outer PF structures |  | 2009-10-01 | 2010-06-01
|  |  | PDR |  |  | 2010-05-28 | [10 empty] | 260 | [7 empty] | 500 | [18 empty] | 2, 4, 9
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Analysis- Outer PF support – include PF3? What loads |  | 2010-06-01 | 2010-11-01 |  |  | 160
|  |  | Analysis- Local Model of Support Beam/Vessel Intersection |  | 2010-06-01 | 2010-11-01 |  |  | 20
|  |  | Analysis- Outer PF supports – elastomer vs sliding block |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Analysis- PF2 PF1c Umbrella Load Dome Analysis |  | 2010-06-01 | 2010-11-01 |  |  | 40
|  |  | Documentation-calculations |  | 2010-06-01 | 2010-11-01 | [14 empty] | 4
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 | [36 empty] | 0
|  |  | FDR |  |  | 2010-10-28 | [10 empty] | 460 | [7 empty] | 1340 | [18 empty] | 2, 4, 9
|  |  | Purchase & Fabrication | [39 empty] | 0 | 2
|  |  | Prep requisition & submit to procurement |  |  |  | 1 | [9 empty] | 8
|  |  | Bid & award outer PF cage |  |  |  | 4
|  |  | Fabricate Outer PF Cage [PF-3/4/5] |  |  |  | 18 | [9 empty] | 24 | [22 empty] | 350 | 3 |  | 353 | 2 | 2,7, 9
|  |  | Prep requisition & submit to procurement |  |  |  | 1 | [9 empty] | 8 | [26 empty] | 2
|  |  | Bid & award outer PF cage |  |  |  | 4
|  |  | Fabricate PF-2/PF-1c support modifications |  |  |  | 12 | [9 empty] | 16 | [22 empty] | 118.75 | 1 |  | 119.75 | 2
0
|  |  | Installation costs will be included in M. Viola's installation estimate | [39 empty] | 0
0
1170 | 1*** | 1203 | Umbrella Structural Reinforcement | Mangra
|  |  | Concept Design Activities |  | 2009-10-01 | 2009-10-28
Concept design of umbrella reinforcements+lid
|  |  | CDR |  |  | 2009-10-28 |  |  |  | 80 | [6 empty] | 100 | [7 empty] | 150 | [18 empty] | 2,9
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Analysis- Umbrella Arch Reinforcement |  | 2009-10-01 | 2010-06-01
|  |  | Complete design of umbrella structure upgrades |  | 2009-10-01 | 2010-06-01 | [10 empty] | 60 | [26 empty] | 2,9
|  |  | Generate Cad detail and assembly drawings |  | 2009-10-01 | 2010-06-01
|  |  | Complete design of upper and lower umbrella lids |  | 2009-10-01 | 2010-06-01 | [10 empty] | 40 | [26 empty] | 2,9
|  |  | PDR |  |  | 2010-05-28 |  |  |  | 80 | [14 empty] | 160 | [18 empty] | 2,9
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Analysis- Umbrella Arch Reinforcement |  | 2010-06-01 | 2010-11-01
|  |  | Complete design of umbrella structure upgrades |  | 2010-06-01 | 2010-11-01 | [10 empty] | 100
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 | [36 empty] | 0
|  |  | Complete design of upper and lower umbrella lids |  | 2010-06-01 | 2010-11-01 | [10 empty] | 80 | [25 empty] | 0
|  |  | FDR |  |  | 2010-10-28 |  |  |  | 100 | [14 empty] | 400 | [18 empty] | 2,9
Purchase & Fabrication
|  |  | Prep requisition & submit to procurement |  |  |  | 1 | [9 empty] | 8 | [26 empty] | 2
|  |  | Bid & award PO |  |  |  | 5
|  |  | Fabricate structural components |  |  |  | 8 | [32 empty] | 40 |  |  | 40 |  | 2,4,7,9
|  |  | Fabricate umbrella lids |  |  |  | 10 | [32 empty] | 22.4 |  |  | 22.4 |  | 2,4,7,9
0
Installation costs will be included in M. Viola's installation estimate
1170 | 1*** | 1204 | CS Support Pedestal | Mangra
|  |  | Concept Design Activities |  | 2009-10-01 | 2009-10-28
Concept design of pedestal /ground plate/removable ribs
|  |  | CDR |  |  | 2009-10-28 |  |  |  | 80 | [6 empty] | 100 | [7 empty] | 40 | [18 empty] | 2,9
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0
|  |  | Engineering design support |  | 2009-10-01 | 2010-06-01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 120 | [6 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 2,9
|  |  | Generate Cad detail and assembly drawings |  | 2009-10-01 | 2010-06-01
|  |  | PDR |  |  | 2010-05-28 | [18 empty] | 80
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Engineering design support |  | 2010-06-01 | 2010-11-01 | [10 empty] | 200 | [26 empty] | 2,9
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01 | [18 empty] | 200 | [18 empty] | 2,9
|  |  | FDR |  |  | 2010-10-28
Purchase & Fabrication
|  |  | Prep requisition & submit to procurement |  |  |  | 1 | [9 empty] | 8 | [25 empty] | 0 | 2
|  |  | Bid & award PO |  |  |  | 5
|  |  | Fabricate pedestal |  |  |  | 8 | [9 empty] | 40 | [22 empty] | 25 |  |  | 25 | 2,9 | 4,7,9
|  |  | Engr support during installation | [13 empty] | 200 | [25 empty] | 0 | 2,9
1170 | 1*** | 1205 | Other stuff | Mangra
Vessel'legs to ground upgrade
Plate upgrade to disruption
|  |  | CDR of vessel legs |  |  | 2009-10-28 | [10 empty] | 10 | [7 empty] | 80 | [18 empty] | 2,9
|  |  | CDR of plates upgrade |  |  | 2009-10-28 | [10 empty] | 20 | [7 empty] | 40 | [18 empty] | 2,9
|  |  | Preliminary Design Activities |  | 2009-10-01 | 2010-06-01
|  |  | Engineering design support |  | 2009-10-01 | 2010-06-01
|  |  | Generate Cad detail and assembly drawings |  | 2009-10-01 | 2010-06-01 | [18 empty] | 80 | [18 empty] | 2,9
|  |  | PDR of Vessels |  |  | 2010-05-28 | [10 empty] | 20 | [7 empty] | 80 | [18 empty] | 2,9
|  |  | PDR of plates upgrade |  |  | 2010-05-28 | [10 empty] | 20
|  |  | Final Design Activities |  | 2010-06-01 | 2010-11-01
|  |  | Engineering design support |  | 2010-06-01 | 2010-11-01
|  |  | Complete Cad detail and assembly drawings |  | 2010-06-01 | 2010-11-01
|  |  | FDR of Vessels |  |  | 2010-10-28 | [10 empty] | 50 | [7 empty] | 200 | [18 empty] | 2,9
|  |  | FDR of plates upgrade |  |  | 2010-10-28 | [10 empty] | 100 | [7 empty] | 200 | [18 empty] | 2,9
Purchase & Fabrication
Prep requisition & submit to procurement
Bid & award PO
Fabricate pedestal
|  |  | Fabricate legs upgrade | [36 empty] | 50 |  |  | 50 |  | 4,7,9
|  |  | Fabricate PP upgrade | [36 empty] | 50 |  |  | 50 |  | 4,7,9
Engr support during installation
[8 empty] | 0 | 760 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 288 | 16 | 0 | 0 | 0 | 4980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 70 | 953.75 | 9 | 0 | 1032.75
Costs do not include installation
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
[10 empty] | "9" Other | [6 empty] | includes conversations with designers and other engineers to better quantify manhours for each task
including discussions of models and numbers of drawings

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 1200
Job Title: |  | Vacuum Vessel & Support Structure
Job Manager: |  | Danny Mangra
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Man hours requirement to 10 Nov, 1080 analyst, 2040 Eng, 3300 Cad, not available |  |  |  | U | Resources levelling |  |  | Present Available man hours |  |  |  | 20
2 | Accuracy of Existing information |  |  |  | U | ongoing audit |  |  | Present CAD information |  |  |  | 6
3 | Cost of hardware may change at time of contract( vendor not available) |  |  |  | VU | identifying additional vendors |  |  |  | -10% | 25%
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1170
Job Number: | 1200
Job Title: | Vacuum Vessel & Support Structure
Job Manager: | Danny Mangra
Materials and Subcontracts (M&S) |  |  |  | Basis of Estimate
Description:
Metrology
Rapid prototyping | Vendor quote of prototype of beam's port cap/ 2 items |  | $1500.00 each, $2000 each, 35 ( 15 + 20) items total
1201
Fabricate components | pins about 144, catologue price |  | $400 each | 144 x 400 = 57,600
| build to print 400 x 24 = 9,600 lbs | $25 per lb of sst | 400 x 24 25 | 240000
total m&s |  |  | 240,000 + 57,600 |  | 297600
Labor | models and drawings
40 cad models, 20 drawings + redo 50% based on analysis
1202
cad | 70 models, 40 drawings + 25% redo
Fabricate components | build to print 400 x 24 + 200 x 22 + 4750 x 1 | $25 per lb of sst | 9,600 + 4400 = 14,000 lbs | 14,000 x 25 = 350,000 | 350000
| 4750 lbs | $25 per lb of sst | 4750 x 25 =118.8 |  | 119000
1203
umbrella, old cost = $15k, new cost 15K x 1.3 = $20k | modification = old cost | $20k per umbrella | umbrella modification = 2 X 20 = 40K |  | 40000
lid, old cost = $4.2k, new cost = $4.2k x 1.3 =$5.6k | new led = old x 2 for complexity = 5.6 x 2 = $11.2k | 200% of old cost | 2 lids = 2 x 11.2 |  | 22400
10 cad, 6 drawing + 50% redo
1204
pedestal | 20 cad, 10 dwg + 50% redo
old cost = $15, new cost = 15K x 1.3 = $20k | additional gnd plate $5k(cost of lid) | cost of old pedestal + old lid | $20k + $5K |  | 25000
1205
other stuff + cad assembly/layout of above | 30 cad model, 15 dwg( 50% above pedestal-less redo)
vessel legs, old cost = 32k, new cost = 32 x 1.3 = 41.6 | add 10 K for complexity( greater load ratings etc |  | $50K |  | 50000
disruption plate + other stuff | cost of legs for budget |  | $50K |  | 50000
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS