## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 1305
Job Title: | Ohmic Heating Solenoid
Job Manager: | James H. Chrzanowski
Description:
Design & fabricate a new OH solenoid and associated components including a belleville washer spring assembly and support structures for the NSTX upgrades. Estimate includes all analytical & Cad design efforts. Includes advance procurement of the copper conductor and co-wound [glass/Kapton] insulation. Also includes the procurement of the Micro-therm insulation, conductive paint. Includes the procurement and engineering oversite for the combined OH and TF bundle assembly. A single vendor will fabricate both components. Does not include any installation or assembly tasks.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost | Work |  | Activity Name | Responsible Cog Engr | Start | End | Duration | EAEM1 | EAEM2 | EAEM3 | EAEM4 | EAEM5 | EAEM6 | EAEM7 | EAEM | EAEM | EMEM1 | EMEM2 | EMEM3 | EMEM4 | EMEM5 | EEEM | EASB1 | EASB2 | EASB3 | EASB4 | EASB5 | EASB6 | EASB7 | EASB8 | EMSM1 | EMSM2 | EMSM3 | EMTB1 | EMTB2 | EMTB3 | EMTB4 | EMTB5 | M&S | OS | Travel | Stkrm. | Subtotal | Basis of Estimate | Category
Center | Package | Job # | [5 empty] | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs | mhrs |  |  |  |  | M&S
[5 empty] | Date | Date | (Weeks) | (Chrzan.) | (Titus) | (Zhang) | (Zolfaghari) | (Avasarala) | (Brooks) | (Raftopoul.) | (general) | (Myatt) | (Mangra) | (Tresmer) | (Willard) | (Prinski) | (Simmons) |  | (Paul) | (Morris) | (Martinelli) | (Upcavage) | (Jariwala) | (Wojtowicz) | (Paluzzi) | (Elect) | (Meighan) | (Jurcz.) |  | (Technician) | (Machinist) | (Welder) | (electrical) | (General) | K$ | k$ | k$ | k$ | k$
1170 | 1*** | 1305 | OHMIC HEATING COIL (OH) - Design & Fabrication | Chrz/Titus
|  |  | Preliminary Design Activities | [39 empty] | 0
|  |  | Design support for OH coil |  | 2009-10-01 | 2010-06-01 |  | 200 | [34 empty] | 0 |  | 2
|  |  | Generate detail and assembly Cad drawings |  | 2009-10-01 | 2010-06-01 | [16 empty] | 500 |  |  | 80 | [16 empty] | 0 |  | 2
|  |  | Complete Axisymmetric CS Model |  | 2009-10-01 | 2010-06-01 |  |  |  |  | 100 | [31 empty] | 0 |  | 2
|  |  | Size Bellevilles,Spacers,Retaining Bolts |  | 2009-10-01 | 2010-06-01 |  |  |  |  | 40 | [31 empty] | 0 |  | 2
|  |  | OH Stress due to PF1A |  | 2009-10-01 | 2010-06-01 |  |  |  |  | 40 | [31 empty] | 0 |  | 2
|  |  | OH Tension Stress Due to End Fixity |  | 2009-10-01 | 2010-06-01 |  |  |  |  | 10 | [31 empty] | 0 |  | 2
|  |  | Fixture Analyses |  | 2009-10-01 | 2010-06-01 | [36 empty] | 0 |  | 2
|  |  | Documentation-calculations |  | 2009-10-01 | 2010-06-01 | [14 empty] | 10 | [21 empty] | 0 |  | 2
|  |  | Prepare for PDR |  |  |  |  | 40 | [14 empty] | 40 | [19 empty] | 0 |  | 2
|  |  | Final Design Activities | [39 empty] | 0
|  |  | Design support for OH coil |  | 2010-06-01 | 2010-11-01 |  | 240 | [34 empty] | 0 |  | 2
|  |  | Complete Axisymmetric CS Model |  | 2010-06-01 | 2010-11-01 |  |  |  |  | 100 | [31 empty] | 0 |  | 2
|  |  | Size Bellevilles,Spacers,Retaining Bolts |  | 2010-06-01 | 2010-11-01 |  |  |  |  | 40 | [31 empty] | 0 |  | 2
|  |  | OH Stress due to PF1A |  | 2010-06-01 | 2010-11-01 |  |  |  |  | 40 | [31 empty] | 0 |  | 2
|  |  | OH Tension Stress Due to End Fixity |  | 2010-06-01 | 2010-11-01 |  |  |  |  | 10 | [31 empty] | 0 |  | 2
|  |  | Fixture Analyses |  | 2010-06-01 | 2010-11-01 | [8 empty] | 40 | [27 empty] | 0 |  | 2
|  |  | Documentation-calculations |  | 2010-06-01 | 2010-11-01 | [14 empty] | 10 | [21 empty] | 0 |  | 2
|  |  | Complete detail and assembly Cad drawings |  | 2010-06-01 | 2010-11-01 | [16 empty] | 600 | [19 empty] | 0 |  | 2
|  |  | Prepare for FDR |  |  |  |  | 40 | [14 empty] | 40 | [19 empty] | 0 |  | 2
Purchase & Fabrication
Conductor
|  |  | Generate SOW for conductor |  | 2010-11-22 | 2010-12-06 | 2 | 12 | [34 empty] | 0 |  | 2
|  |  | Prep requisition & submit to procurement |  | 2010-12-06 | 2010-12-13 | 1 | 8 | [36 empty] | 2
|  |  | Bid & award conductor order [220%] |  | 2010-12-13 | 2011-01-17 | 5 | [37 empty] | 2
|  |  | Manufacture Copper conductor [extrusion] |  | 2011-01-17 | 2011-04-25 | 14 | 16 | [31 empty] | 105.6 |  |  | 105.6
Miscellaneous parts
|  |  | Prep requisition & submit to procurement [insulation] |  | 2010-11-08 | 2010-11-15 | 1 | [23 empty] | 8 | [7 empty] | 25 |  |  |  | 0
|  |  | Procure Kapton/glass co-wound insulation |  | 2010-11-15 | 2011-01-10 | 10 | [23 empty] | 8 | [11 empty] | 25 |  | 6
|  |  | Prep requisition & submit to procurement [belleville] |  | 2011-04-05 | 2011-04-12 | 1 | 8
|  |  | Bid & Award belleville washer assembly |  | 2011-04-12 | 2011-06-07 | 8 | 8 | [31 empty] | 35 |  |  | 35 |  | 2
|  |  | Procure miscellaneous parts |  | 2010-11-15 | 2011-06-06 |  | 24 | [30 empty] | 15 |  |  |  | 15 |  | 2
0
|  |  | TF/OH FABRICATION | [39 empty] | 0
Note: The OH/TF bundle will be fabricated together as one unit.
|  |  | TF Bundle/OH Solenoid | [39 empty] | 0
|  |  | Generate Manufacturing Procedures & Travelers |  | 2010-10-25 | 2010-11-08 | 3 | 120 | [34 empty] | 0 |  | 2
|  |  | DELETE |  | 2010-11-08 | 2010-11-15 | 1 | 0 | [34 empty] | 0
|  |  | DELETE |  | 2010-11-15 | 2011-01-10 | 0 | 0 | [34 empty] | 0
|  |  | Manufacture OH/TF coil [In-house] |  | 2011-01-10 | 2011-01-17 | 60 | 600 | [22 empty] | 400 | [8 empty] | 1972.5554 |  |  | 1972.5554 |  | 3
|  |  | DELETE |  | 2011-01-17 | 2012-03-19 | 0 | 0 | [32 empty] | 0 |  | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  |  | 0
[5 empty] | 2009-10-01 | 2013-01-07 |  | 1316 | 0 | 0 | 380 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1180 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2113.1554 | 0 | 0 | 2153.1554
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 1305
Job Title: |  | Ohmic Heating Solenoid
Job Manager: |  | James H. Chrzanowski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | No vendor bids were received for manufacturing OH/TF |  |  |  | U | Fabricate coil in-house [Suggest having bid process include both domestic and international] |  |  |  |  | $500.0 k |  | No change
2 | VPI- poor impregnation |  |  |  | U | Evaluate condition of coil- Local dry areas could be repaired, but larger failure would require cutting OH coil from TF and rebuild OH |  |  |  |  | 500 |  | XX
3 | OH coil fails during final testing |  |  |  | U | If fault cannot be repaired- Coil must be cut off and rebuilt |  |  |  |  | XXX |  | XX
4 | [10 empty] | strykowsky estimate
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1170
Job Number: | 1305
Job Title: | Ohmic Heating Solenoid
Job Manager: | James H. Chrzanowski
Materials and Subcontracts (M&S) |  | k$ | Basis of Estimate
Description:
OH Copper conductor |  | 105.6 | 4
Co-wound insulation [Kapton/glass] |  | 25 | 3
OH/TF bundle fabrication |  | 1972.5554 | 4
Belleville washer assembly |  | 35 | 2
Miscellaneous |  | 15 | 9
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS

## OHTF Coil Fabrication
TASK DESCRIPTION | Total | No. of | Hours per | Total | Cad Design | Engr costs
| Shifts | Tech./Shift | Shift | Manhrs | Manhrs | Manhrs
|  |  |  | EM//TB | EAD/SB | EA//EM
Manufacturing Preparation Preparation
Design tooling for manufacturing OH/TF coil | [5 empty] | 400
TF Quadrant mold |  |  |  |  | 120
TF full mold |  |  |  |  | 160
OH mold |  |  |  |  | 160
OH winding clamps |  |  |  |  | 80
Lifting beam- conductors & coil |  |  |  |  | 80
Area layout inc. cleanroom |  |  |  |  | 240
Electrical layout to support winding area |  |  |  |  | 240
Setup Winding area | 25 | 3 | 8 | 600
Setup winding equipment | 20 | 3 | 8 | 480
|  |  |  | 1080 | 1080 | 400
|  |  |  | 97588.8 | 134946 | 74108
TASK DESCRIPTION | Total | No. of | Hours per | Total |  | 306.6428
| Shifts | Tech | Shift | Manhrs
EM//TB
TF BUNDLE
Conductor Receipt and Inspection | SHIFTS | # Tech | Hr/Shift | Total Hrs | FY2009 Hourly Rates
Inspect machined conductors 100% [40 conductors] | 20 | 2 | 8 | 320 | EA//EM | 185.27
Install Inserts [40 conductors] | 50 | 2 | 8 | 800 | EM//EM | 165.16
Solder cooling tubes [40 conductors] | 72 | 2 | 8 | 1152 | EE//EM | 175.71
Cleanup conductors- post solder | 40 | 2 | 8 | 640 | EAD/SB | 124.95
Sandblast conductor length for primer | 40 | 2 | 8 | 640 | EM//SM | 145.16
Apply primer [40 conductors] | 5 | 2 | 8 | 80 | EM//SB | 119.23
[5 empty] | EM//TB | 90.36
Quadrant #1 | SHIFTS | # Tech | Hr/Shift | Total Hrs | M&S | 1.281
Apply turn insulation Quadrant #1 | 5 | 4 | 8 | 160
Assemble Quadrant #1 | 10 | 5 | 8 | 400
Prepare VPI operation | 3 | 4 | 8 | 96
VPI- fill quadrant | 2 | 4 | 8 | 64
Cure VPI'd coil | 8 | 1 | 8 | 64
Remove Quadrant #1 from mold | 1 | 4 | 8 | 32
Cleanup quadrant | 2 | 2 | 8 | 32
Perform T/T electrical tests | 1 | 2 | 8 | 16
Quadrant #2 | SHIFTS | # Tech | Hr/Shift | Total Hrs
Apply turn insulation Quadrant #2 | 5 | 4 | 8 | 160
Assemble Quadrant #2 | 5 | 5 | 8 | 200
Prepare VPI operation | 3 | 4 | 8 | 96
VPI- fill quadrant | 2 | 4 | 8 | 64
Cure VPI'd coil | 8 | 1 | 8 | 64
Remove Quadrant #2 from mold | 1 | 4 | 8 | 32
Cleanup quadrant | 2 | 2 | 8 | 32
Perform T/T electrical tests | 1 | 2 | 8 | 16
Quadrant #3 | SHIFTS | # Tech | Hr/Shift | Total Hrs
Apply turn insulation Quadrant #3 | 5 | 4 | 8 | 160
Assemble Quadrant #3 | 5 | 5 | 8 | 200
Prepare VPI operation | 3 | 4 | 8 | 96
VPI- fill quadrant | 2 | 4 | 8 | 64
Cure VPI'd coil | 8 | 1 | 8 | 64
Remove Quadrant #3 from mold | 1 | 4 | 8 | 32
Cleanup quadrant | 2 | 2 | 8 | 32
Perform T/T electrical tests | 1 | 2 | 8 | 16
Quadrant #4 | SHIFTS | # Tech | Hr/Shift | Total Hrs
Apply turn insulation Quadrant #4 | 5 | 4 | 8 | 160
Assemble Quadrant #4 | 5 | 5 | 8 | 200
Prepare VPI operation | 3 | 4 | 8 | 96
VPI- fill quadrant | 2 | 4 | 8 | 64
Cure VPI'd coil | 8 | 1 | 8 | 64
Remove Quadrant #4 from mold | 1 | 2 | 8 | 16
Cleanup quadrant | 2 | 2 | 8 | 32
Perform T/T electrical tests | 1 | 2 | 8 | 16
Full mold | SHIFTS | # Tech | Hr/Shift | Total Hrs
Assemble quadrants together | 5 | 5 | 8 | 200
Apply groundwrap insulation | 2 | 2 | 8 | 32
Prepare VPI operation | 3 | 4 | 8 | 96
VPI full TF coil | 2 | 4 | 8 | 64
Cure VPI'd coil | 8 | 1 | 8 | 64
Remove full TF from mold and cleanup | 1 | 2 | 8 | 16
Perform Final electrical tests | 1 | 2 | 8 | 16
OH Coil
OH Coil winding operations | SHIFTS | # Tech | Hr/Shift | Total Hrs
Transfer TF to OH station | 1 | 5 | 8 | 40
Prepare TF for OH winding | 5 | 3 | 8 | 120
Apply slip plane, and inner groundwall insulation | 2 | 2 | 8 | 32
Braze first lead and prepare for winding | 5 | 2 | 8 | 80
Wind 1st half of layer #1 | 5 | 3 | 8 | 120
Make [2] in-line brazes | 1 | 2 | 8 | 16
Wind second half of layer #1 | 5 | 3 | 8 | 120
Perform prelim electrical tests | 1 | 2 | 8 | 16
Braze layer to layer joint | 1 | 2 | 8 | 16
Wind 1st half of layer #2 | 5 | 3 | 8 | 120
Make [2] in-line brazes | 1 | 2 | 8 | 16
Wind second half of layer #2 | 5 | 3 | 8 | 120
Perform prelim electrical tests | 1 | 2 | 8 | 16
Braze layer to layer joint | 1 | 2 | 8 | 16
Wind 1st half of layer #3 | 5 | 3 | 8 | 120
Make [2] in-line brazes | 1 | 2 | 8 | 16
Wind second half of layer #3 | 5 | 3 | 8 | 120
Perform prelim electrical tests | 1 | 2 | 8 | 16
Braze layer to layer joint | 1 | 2 | 8 | 16
Wind 1st half of layer #4 | 5 | 3 | 8 | 120
Make [2] in-line brazes | 1 | 2 | 8 | 16
Wind second half of layer #4 | 5 | 3 | 8 | 120
Apply groundwrap insulation | 1 | 2 | 8 | 16
VPI | SHIFTS | # Tech | Hr/Shift | Total Hrs
Mount OH mold around coil | 5 | 4 | 8 | 160
Prepare VPI operation | 3 | 4 | 8 | 96
VPI- mold | 2 | 4 | 8 | 64
Cure VPI'd coil | 8 | 1 | 8 | 64
Remove mold from OH coil | 1 | 4 | 8 | 32
Cleanup OH coil | 2 | 2 | 8 | 32
Silverplate all electrical surfaces [OH/TF] | 3 | 1 | 8 | 24
Perform Final OH electrical tests | 1 | 2 | 8 | 16
Perform hydrostat and flow tests- OH/TF coils | 3 | 2 | 8 | 48
Transport to CS assembly station | 1 | 5 | 8 | 40
8944
|  |  |  | 808179.84 | 808.1798 | Total coil mfg costs
| Machinist | Technician |  | M&S
TOOLING & EQUIPMENT | Man-hours | Man-hours |  | Revised
k$
TF conductor stands- tube soldering |  | 160 |  | 5
TF conductor stands- insulating |  |  |  | 15
Quadrant mold | 160 |  |  | 70
Full coil mold | 160 |  |  | 85
VPI delivery system |  | 160 |  | 20
Lift beam- conductor |  | 80 |  | 15
Lift leam for coil |  | 80 |  | 25
Taping machines [2] |  |  |  | 25
Tension unit | 120 | 80 |  | 10
Braze unit |  |  |  | 100
Braze fixture and work coil |  |  |  | 10
Winding machine for OH |  |  |  | 125
OH winding clamps- 4-sets |  |  |  | 20
OH Mold | 160 |  |  | 85
Miscellaneous tools & fixtures | 160 | 160 |  | 20
| 760 | 720 |  | 630
| 68673.6 | 65059.2 |  |  | 763.7328 | Total toolg /equip costs
| Machinist | Technician | M&S
MATERIAL & SUPPLIES | Man-hours | Man-hours | k$
Coil Supplies
Insulation [fiberglass tape, teflon and ground plane |  |  | 20
Epoxy- CTD-101 [$4500.00 per coil @ assume 20 injections] |  |  | 15
Copper pre-tinned tubing [TF conductor]
1
Filler modifications | 150 |  | 1
Conductor primer |  |  | 2
Safety and PPE equipment and supplies |  |  | 5
Includes gloves, masks, safety equipment & supplies
Miscellaneous supplies |  |  | 20
Includes rags, hardware, etc.
VPI Supplies
RTV and silicone caulking for mold sealing |  |  | 5
Disposable VPI hardware
valves & fittings |  |  | 10
High & low temperature vac. Tubing |  |  | 10
VPI manifolds |  | 200 | 5
| 150 | 200
| hours | hours | 94 | M&S Total | 94
|  |  |  | TOTAL | 1972.5554

## Worksheet
|  | 1997 $ | Inflator % | 2009 $ | x4 k$ | # Orig | # Upgrade
OH solenoid |  | 136.3 | 1.2992 | 177.081 | 708.3238 | 2340 | 6400 | 3
Conductor assume $7.5/lb | 7.5 | 48000 | 2.2 | 105600 | 105.6
OH conductor |  | 40 | 1.2992 | 51.968 | 155.904 | 6400 | 2.2 | 5
|  | FY97 cost | Escal |  |  | 12800 | 92.16
TF bundle |  | 83 | 1.2992 | 107.8336 | 431.3344
|  | Orig Costs | Inflation | New Cost
|  |  |  | TF+OH | 1139.6582
[5 empty] | 1481.5557 | 30% | difficulty
OTF Conductor |  |  |  | 2 x 3 | 23 #/ft | 3450# | 25 ft/length | 6
|  | Orig Costs | Inflation | New Cost
Rotable flanges |  | 13.2 | 1.2992 | 17.1494
Inconel Forgings |  | 30.9 | 1.2992 | 40.1453 | 1.5 | 60.2179
6400
|  | width | Height | Hole Dia | Hole Area | Area | Coil R | Turn | Length/Turn | Length/Coil | Length/Coil |  | Wt/coil
PF Conductors |  | in | in | in | in2 | in2 | in |  | in | in | ft | x 2 | lb | x 2
PF1a |  | 0.591 | 0.591 | 0.217 | 0.118 | 0.23128 | 12.571 | 120 | 78.9459 | 9473.5056 | 789.4588 | 1578.9176 | 701.1334 | 1402.2668
PF1b |  | 0.22 | 0.22 | 0.098 | 0.0024 | 0.046 | 15.763 | 180 | 98.9916 | 17818.4952 | 1484.8746 | 2969.7492 | 262.2882 | 524.5765
PF1c |  | 0.22 | 0.22 | 0.098 | 0.0024 | 0.046 | 21.674 | 162 | 136.1127 | 22050.2606 | 1837.5217 | 3675.0434 | 324.5798 | 649.1597
[15 empty] | x 2.2 | 7.5
[14 empty] | 2576.003 | 5667.2065 | 42.504 | k
[8 empty] | Pi | 3.14
[8 empty] | 0.32 | #/Cu in