## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1180
Job Number: | 2425
Job Title: | NSTX Beamline 2 Relocation
Job Manager: | Martin Denault
Description:
This job includes the efforts to relocate a TFTR neutral beam line and ancillary equipment into the NSTX test cell. This includes the High Voltage Enclosures (HVEs) and the complete beam box.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1180
| Job Number: |  |  | 2425
| Job Title: |  |  | NSTX Beamline 2 Relocation
| Job Manager: |  |  | Martin Denault
Estimate (user input)
[5 empty] | SCHEDULE | [12 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [16 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1
2
3 |  | Conceptual Design |  | Denault | [7 empty] | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
4 |  | PREPARE WORK PLANNING FORM |  |  | 1 |  |  |  | 2009-09-24 | 2009-09-24 | 2009-09-25 09:36 | 2009-09-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | [13 empty] | 4- Experience
5 |  | Prep System Description |  |  | 2 | 4 |  |  |  | 2009-09-25 09:36 | 2009-09-28 04:48 | 2007-10-01 | 2009-09-25 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | 4- Experience
6 |  | Prep System Requirements |  |  | 3 | 5 |  |  |  | 2009-09-28 04:48 | 2009-10-02 09:36 | 2007-10-01 | 2009-09-28 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 24 | [13 empty] | 4- Experience
7 |  | R&D |  |  | 20 | 6 |  |  |  | 2009-10-02 09:36 | 2009-10-30 09:36 | 2007-10-01 | 2009-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 160 | [13 empty] | 4- Experience
8 |  | Analysis |  |  | 20 | 7 |  |  |  | 2009-10-30 09:36 | 2009-11-27 09:36 | 2007-10-01 | 2009-10-30 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 |  |  |  |  | 40 |  |  |  | 160 | [13 empty] | 4- Experience
9 |  | CDR |  |  | 2 | 8 |  |  |  | 2009-11-27 09:36 | 2009-11-30 04:48 | 2007-10-01 | 2009-11-27 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | 4- Experience
10 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
11 |  | Preliminary Design |  | Denault | [7 empty] | 2010-08-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
12 |  | Thermal Analysis |  |  | 5 |  |  |  | 2010-08-03 | 2010-08-03 | 2010-08-10 | 2010-08-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 40 | [8 empty] | 40 | [13 empty] | 4- Experience
13 |  | Seismic Analysis |  |  | 10 | 12 |  |  |  | 2010-08-10 | 2010-08-24 | 2007-10-01 | 2010-08-10 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [8 empty] | 80 | [13 empty] | 4- Experience
14 |  | FMEA Analysis |  |  | 10 | 13 |  |  |  | 2010-08-24 | 2010-09-07 | 2007-10-01 | 2010-08-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [8 empty] | 80 | [13 empty] | 4- Experience
15 |  | Prepare NEPA Form |  |  | 2 | 14 |  |  |  | 2010-09-07 | 2010-09-09 19:12 | 2007-10-01 | 2010-09-07 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | 4- Experience
16 |  | Update Cost & Schedule Estimate |  |  | 10 | 15 |  |  |  | 2010-09-09 19:12 | 2010-09-23 19:12 | 2007-10-01 | 2010-09-09 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | [6 empty] | 80 | [6 empty] | 4- Experience
17 |  | Design Drawings |  |  | 20 | 16 |  |  |  | 2010-09-23 19:12 | 2010-10-21 19:12 | 2007-10-01 | 2010-09-23 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 160 |  |  |  | 80 |  |  |  | 80 | [13 empty] | 4- Experience
18 |  | PDR Prep |  |  | 5 | 17 |  |  |  | 2010-10-21 19:12 | 2010-10-28 19:12 | 2007-10-01 | 2010-10-21 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [13 empty] | 4- Experience
19 |  | CONDUCT PDR |  |  | 2 | 18 |  |  |  | 2010-10-28 19:12 | 2010-10-31 14:24 | 2007-10-01 | 2010-10-28 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | 4- Experience
20 |  | Lehman Review |  |  | 5 |  |  |  | 2010-12-15 | 2010-12-15 | 2010-12-22 | 2010-12-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [13 empty] | 4- Experience
21 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
22 |  | Final Design |  | Denault | [7 empty] | 2011-01-28 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
23 |  | Disposition PDR Chits |  |  | 2 | 21 |  |  | 2011-01-28 | 2011-01-28 | 2011-01-30 19:12 | 2011-01-28 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | 4- Experience
24 |  | Design Drawings |  |  | 10 | 22 |  |  |  | 2007-10-01 | 2007-10-15 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 |  |  |  | 40 |  |  |  | 20 | [13 empty] | 4- Experience
25 |  | Update Analyses |  |  | 5 | 23 |  |  |  | 2011-01-30 19:12 | 2011-02-06 19:12 | 2007-10-01 | 2011-01-30 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [6 empty] | 80 | [8 empty] | 40 | [13 empty] | 4- Experience
26 |  | Update Cost & Schedule Estimate |  |  | 5 | 24 |  |  |  | 2007-10-15 | 2007-10-22 | 2007-10-01 | 2007-10-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [6 empty] | 40 | [6 empty] | 4- Experience
27 |  | Prep Procurement Specs |  |  | 5 | 25 |  |  |  | 2011-02-06 19:12 | 2011-02-13 19:12 | 2007-10-01 | 2011-02-06 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [13 empty] | 4- Experience
28 |  | FDR Prep |  |  | 5 | 26 |  |  |  | 2007-10-22 | 2007-10-29 | 2007-10-01 | 2007-10-22 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | [13 empty] | 4- Experience
29 |  | CONDUCT FDR |  |  | 2 | 27 |  |  |  | 2011-02-13 19:12 | 2011-02-16 14:24 | 2007-10-01 | 2011-02-13 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | [13 empty] | 4- Experience
30 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
31 |  | Procurement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 |  | Steel and Parts | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [23 empty] | 0
33 |  |  | Prep Requisition and procurement package |  | 1 | 28 |  |  | 2011-06-10 | 2011-06-10 | 2011-06-11 09:36 | 2011-06-10 | 2007-10-29 | 2007-10-01 | 2007-10-01 | 2007-10-01
34 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 32 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
35 |  |  | Procurement lead time (1) |  | 30 | 33 |  |  |  | 2011-06-11 09:36 | 2011-07-23 09:36 | 2007-10-01 | 2011-06-11 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01
36 |  |  | AWARD |  | 1 | 34 |  |  |  | 2007-10-02 09:36 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01
37 |  |  | Fabricate or delivery |  | 30 | 35 |  |  |  | 2011-07-23 09:36 | 2011-09-03 09:36 | 2007-10-01 | 2011-07-23 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01
38 |  | Lifting Equip. | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
39 |  |  | Prep Requisition and procurement package |  | 2 | 28 |  |  | 2011-06-10 | 2011-06-10 | 2011-06-12 19:12 | 2011-06-10 | 2007-10-29 | 2007-10-01 | 2007-10-01 | 2007-10-01
40 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 38 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01
41 |  |  | Procurement lead time (1) |  | 30 | 39 |  |  |  | 2011-06-12 19:12 | 2011-07-24 19:12 | 2007-10-01 | 2011-06-12 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
42 |  |  | AWARD |  | 1 | 40 |  |  |  | 2007-10-02 09:36 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01
43 |  |  | Fabricate or delivery |  | 30 | 41 |  |  |  | 2011-07-24 19:12 | 2011-09-04 19:12 | 2007-10-01 | 2011-07-24 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01
44 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
45 |  | Fab/Assembly |  | Denault | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
46 |  | Fab/Assy Procedure | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
47 |  | Shop Fabrication | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
48 |  | Assembly | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
49 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
50 |  | Installation |  | Denault | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
51 |  | Installation Procedure | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
52 |  | Machine Installation | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 |  | PTP Testing | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
54 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
55 |  | Engineering 1 Days Per Week title III |  | 1 | 280 |  |  |  | 2011-02-01 | 2011-02-01 | 2012-02-28 | 2011-02-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [11 empty] | 160 |  |  |  | 448 | [13 empty] | 4- Experience
56 |  | Engineering Support 1/2 Days Per Week title III |  | 0.5 | 280 |  |  |  | 2011-02-02 | 2011-02-02 | 2012-02-29 | 2011-02-02 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 224 | [13 empty] | 4- Experience
57 |  | Drafting Support 1/2 day/week title III |  | 0.5 | 280 |  |  |  | 2011-02-03 | 2011-02-03 | 2012-03-01 | 2011-02-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [8 empty] | 224 | [20 empty] | 4- Experience
58
59 |  | Path | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 15
60 |  |  | Road |  | 5 |  |  |  | 2012-01-01 | 2012-01-01 | 2012-01-08 | 2012-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 40 | 160 | [11 empty] | 4- Experience
61 |  |  | Duct Removal |  | 2 | 59 |  |  | 2012-01-01 | 2012-01-01 | 2012-01-03 19:12 | 2012-01-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
62 |  |  | Lintel Removal |  | 3 | 60 |  |  |  | 2012-01-08 | 2012-01-12 04:48 | 2007-10-01 | 2012-01-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 16 | 8 | 24 | 96 | [11 empty] | 4- Experience
63 |  |  | Lintel Install |  | 2 | 107 |  |  |  | 2007-10-03 19:12 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [14 empty] | 16 | 8 | 16 | 64 | [11 empty] | 4- Experience
64 |  |  | Duct Install |  | 2 | 62 |  |  |  | 2012-01-12 04:48 | 2012-01-15 | 2007-10-01 | 2012-01-12 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
65 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
66 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
67 |  | Metrology | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 3
68 |  |  | Setup |  | 5 |  |  |  | 2009-10-01 | 2009-10-01 | 2009-10-08 | 2009-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 |  | 80 | [11 empty] | 4- Experience
69 |  |  | Measure |  | 15 | 67 |  |  |  | 2007-10-01 | 2007-10-22 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 240 |  | 240 | [11 empty] | 4- Experience
70 |  |  | Model |  | 5 | 68 |  |  |  | 2009-10-08 | 2009-10-15 | 2007-10-01 | 2009-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 80 | [7 empty] | 80 | [13 empty] | 4- Experience
71 |  |  | Lay out |  | 5 | 69 |  |  |  | 2007-10-22 | 2007-10-29 | 2007-10-01 | 2007-10-22 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 |  | 80 | [11 empty] | 4- Experience
72 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
73 |  | Labyrinth Removal |  |  | 10 |  |  |  | 2010-06-01 | 2010-06-01 | 2010-06-15 | 2010-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10 | [12 empty] | 32 |  | 80 | 160 | [11 empty] | 4- Experience
74 | [12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
75 |  | Lift Fixtures | [15 empty] | 15
76 |  |  | Construction |  | 20 |  |  |  | 2010-01-10 | 2010-01-10 | 2010-02-07 | 2010-01-10 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [17 empty] | 480 | [11 empty] | 4- Experience
77 |  |  | Load Test |  | 5 | 75 |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 | 0 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | 40 | 120 | [11 empty] | 4- Experience
78 |  |  | Move |  | 1 | 76 |  |  |  | 2010-02-07 | 2010-02-08 09:36 | 2007-10-01 | 2010-02-07 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [17 empty] | 24 | [11 empty] | 4- Experience
79 |  |  | Trial Runs |  | 5 | 77 |  |  |  | 2007-10-08 | 2007-10-15 | 2007-10-01 | 2007-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 40 | 40 | 120 | [11 empty] | 4- Experience
80 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
81 |  | Box Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2
82 |  |  | Lift onto Rollers |  | 1 | 95 | 155 | 19 | 2012-01-01 | 2012-01-01 | 2012-01-02 09:36 | 2012-01-01 |  |  | 2010-10-31 14:24 | 2007-10-01 | [15 empty] | 152 | 8 | 48 | [11 empty] | 4- Experience
83 |  |  | Move IN |  | 1 | 88 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | 4- Experience
84 |  |  | Over Wall |  | 1 | 89 |  |  |  | 2010-01-02 09:36 | 2010-01-03 19:12 | 2007-10-01 | 2010-01-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | 4- Experience
85 |  |  | Placement |  | 10 | 90 |  |  |  | 2007-10-02 09:36 | 2007-10-16 09:36 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | 80 | 480 | [11 empty] | 4- Experience
86 |  |  | Metrology |  | 10 | 91 |  |  |  | 2007-10-02 09:36 | 2007-10-16 09:36 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 80 | 80 | 160 | [11 empty] | 4- Experience
87 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
88 |  | Source Platform | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
89 |  |  | Off |  | 1 |  |  |  | 2010-01-01 | 2010-01-01 | 2010-01-02 09:36 | 2010-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 24 | [11 empty] | 4- Experience
90 |  |  | Move |  | 1 | 95 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 16 | [11 empty] | 4- Experience
91 |  |  | Lift |  | 1 | 96 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | 4- Experience
92 |  |  | On |  | 1 | 97 |  |  |  | 2007-10-06 14:24 | 2007-10-08 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | 4- Experience
93 |  |  | Metrology |  | 10 | 98 |  |  |  | 2007-10-02 09:36 | 2007-10-16 09:36 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 160 | 80 | 320 | [11 empty] | 4- Experience
94 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
95 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
96 |  | Lid Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 5
97 |  |  | Stabilize |  | 3 | 99 |  |  |  | 2007-10-02 09:36 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 24 | 24 | 120 | [11 empty] | 4- Experience
98 |  |  | Lift onto Rollers |  | 1 | 103 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | 4- Experience
99 |  |  | Move IN |  | 1 | 104 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | 4- Experience
100 |  |  | Over Wall |  | 1 | 105 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 48 | [11 empty] | 4- Experience
101 |  |  | Placement |  | 1 | 106 |  |  |  | 2007-10-06 14:24 | 2007-10-08 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 8 | 16 | [11 empty] | 4- Experience
102 |  |  | Metrology |  | 1 | 107 |  |  |  | 2007-10-03 19:12 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 16 | 8 | 48 | [11 empty] | 4- Experience
103 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
104 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
105 |  | Component Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2
106 |  |  | 90in Flange |  | 2 | 108 |  |  |  | 2007-10-03 19:12 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
107 |  |  | Magnet |  | 2 | 112 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | 4- Experience
108 |  |  | Ion Dump |  | 2 | 113 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | 4- Experience
109 |  |  | Exit Spool |  | 2 | 114 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
110 |  |  | TIV |  | 2 | 115 |  |  |  | 2007-10-05 04:48 | 2007-10-08 | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
111 |  |  | Calorimeter |  | 2 | 116 |  |  |  | 2007-10-06 14:24 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | 4- Experience
112 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
113 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
114 |  | Source Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
115 |  |  | Move 1 |  | 2 | 99 |  |  |  | 2007-10-02 09:36 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
116 |  |  | Align 1 |  | 4 | 121 |  |  |  | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 64 | 32 | 128 | [11 empty] | 4- Experience
117 |  |  | Move 2 |  | 2 | 122 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
118 |  |  | Align 2 |  | 4 | 123 |  |  |  | 2011-06-03 19:12 | 2011-06-09 09:36 | 2007-10-01 | 2011-06-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 64 | 32 | 128 | [11 empty] | 4- Experience
119 |  |  | Move 3 |  | 2 | 124 |  |  |  | 2007-10-12 04:48 | 2007-10-15 | 2007-10-01 | 2007-10-12 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
120 |  |  | Align 3 |  | 4 | 125 |  |  |  | 2007-10-15 | 2007-10-20 14:24 | 2007-10-01 | 2007-10-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 64 | 32 | 128 | [11 empty] | 4- Experience
121 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
122 |  | HVE 1 Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
123 |  |  | Move |  | 2 |  | 19 |  | 2011-06-01 | 2011-06-01 | 2011-06-03 19:12 | 2011-06-01 | 2007-10-01 | 2010-10-31 14:24 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | 4- Experience
124 |  |  | Disassemble |  | 2 | 129 |  |  |  | 2007-10-09 09:36 | 2007-10-12 04:48 | 2007-10-01 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
125 |  |  | Move to Crain Access |  | 2 | 130 |  |  |  | 2007-10-12 04:48 | 2007-10-15 | 2007-10-01 | 2007-10-12 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
126 |  |  | Lift into TFTR |  | 1 | 131 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | 4- Experience
127 |  |  | Move In |  | 1 | 132 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | 4- Experience
128 |  |  | Over Wall |  | 2 | 133 |  |  |  | 2007-10-03 19:12 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 80 | [11 empty] | 4- Experience
129 |  |  | Reassemble |  | 2 | 134 |  |  |  | 2007-10-06 14:24 | 2007-10-09 09:36 | 2007-10-01 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
130 |  |  | Placement |  | 3 | 135 |  |  |  | 2007-10-08 | 2007-10-12 04:48 | 2007-10-01 | 2007-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 24 | 96 | [11 empty] | 4- Experience
131 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
132 |  | HVE 2 Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
133 |  |  | Move |  | 2 |  |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | 4- Experience
134 |  |  | Disassemble |  | 2 | 139 |  |  |  | 2007-10-03 19:12 | 2007-10-06 14:24 | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
135 |  |  | Move to Crain Access |  | 2 | 140 |  |  |  | 2007-10-05 04:48 | 2007-10-08 | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
136 |  |  | Lift into TFTR |  | 1 | 141 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | 4- Experience
137 |  |  | Move In |  | 1 | 142 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | 4- Experience
138 |  |  | Over Wall |  | 2 | 143 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 80 | [11 empty] | 4- Experience
139 |  |  | Reassemble |  | 2 | 144 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
140 |  |  | Placement |  | 3 | 145 |  |  |  | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 24 | 96 | [11 empty] | 4- Experience
141 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
142 |  | HVE 3 Movement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1
143 |  |  | Move |  | 2 |  |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 8 | 16 | 64 | [11 empty] | 4- Experience
144 |  |  | Disassemble |  | 2 | 149 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
145 |  |  | Move to Crain Access |  | 2 | 150 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
146 |  |  | Lift into TFTR |  | 1 | 151 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | 4- Experience
147 |  |  | Move In |  | 1 | 152 |  |  |  | 2007-10-01 | 2007-10-02 09:36 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 8 | 32 | [11 empty] | 4- Experience
148 |  |  | Over Wall |  | 2 | 153 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 80 | [11 empty] | 4- Experience
149 |  |  | Reassemble |  | 2 | 154 |  |  |  | 2007-10-01 | 2007-10-03 19:12 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 16 | 64 | [11 empty] | 4- Experience
150 |  |  | Placement |  | 3 | 155 |  |  |  | 2007-10-01 | 2007-10-05 04:48 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [16 empty] | 24 | 96 | [11 empty] | 4- Experience
[12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [15 empty] | 56 | 0 | 0 | 0 | 0 | 360 | 320 | 224 | 0 | 0 | 320 | 0 | 0 | 64 | 3116 | 1232 | 5736 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1654.6832 | [12 empty] | 68.656 | 0 | 0 | 0 | 0 | 67.896 | 39.968 | 31.2928 | 0 | 0 | 55.488 | 0 | 0 | 5.4016 | 498.2484 | 185.9088 | 683.7312 | 0 | 0 | 0 | 0 | 18.0924 |  | 0 | 0
| Notes: | [19 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  |  | Weeks | [14 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  |  |  | 3 | [14 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  |  |  | 5 | [14 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  |  |  | 8 | [14 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  |  |  | 9 | [14 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
67492

## Tab C Risk and Uncertainty
Cost Center: |  | 1180
Job Number: |  | 2425
Job Title: |  | NSTX Beamline 2 Relocation
Job Manager: |  | Martin Denault
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1180
Job Number: | 2425
Job Title: | NSTX Beamline 2 Relocation
Job Manager: | Martin Denault
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Pipe |  |  | Vendor Pricing
Parts |  |  | Vendor Pricing
MISC |  |  | Experience
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS