## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1180
Job Number: | 2440
Job Title: | NSTX Beamline 2 Refurbishment
Job Manager: | Martin Denault
Description:
This job includes the activities necessary to refurbish a TFTR Neutral Beam beamline for use on NSTX. This scope includes replacing copper impinged parts as required and refurbishment of the seals, thermocouple wiring, and bellows (cal and spool) as needed.
Schedule:
Refer to Primavera Data-Base
Approvals:
________________________________________________________
Job Manager
________________________________________________________
Project Manager
________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
|  |  | Cost Center: | 1180
|  |  | Job Number: | 2440
|  |  | Job Title: | NSTX Beamline 2 Refurbishment
|  |  | Job Manager: | Martin Denault
Estimate (user input)
| Martin Denault |  |  |  | SCHEDULE | [10 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Resp. | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [14 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1 |  |  | Begin refurbishment job parts list |  | 60 |  | 2009-10-01 | 2009-10-01 | 2009-12-24 | 2009-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40
2 |  |  | Prepare drawings |  | 600 |  | 2010-01-04 | 2010-01-04 | 2012-04-23 | 2010-01-04 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 480
|  |  | Engineering Supervision |  | 600 |  | 2010-01-05 | 2010-01-05 | 2012-04-24 | 2010-01-05 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [15 empty] | 960
Fabrication
3 |  |  | Calorimeter parts |  | 20 |  | 2010-03-01 | 2010-03-01 | 2010-03-29 | 2010-03-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1 | [16 empty] | 320
4 |  |  | Ion Dump parts |  | 40 | 3 |  | 2010-03-29 | 2010-05-24 | 2007-10-01 | 2010-03-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1 | [16 empty] | 640
5 |  |  | Magnet parts |  | 20 | 4 |  | 2010-05-24 | 2010-06-21 | 2007-10-01 | 2010-05-24 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 0.5 | [16 empty] | 320
6 |  |  | 90 inch flange and neutralizer parts |  | 40 | 5 |  | 2010-06-21 | 2010-08-16 | 2007-10-01 | 2010-06-21 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 7.2 | [16 empty] | 640
7 |  |  | Exit spool piece parts |  | 20 | 6 |  | 2010-08-16 | 2010-09-13 | 2007-10-01 | 2010-08-16 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 15 | [16 empty] | 320
8 |  |  | BL Lid parts |  | 20 | 7 |  | 2010-09-13 | 2010-10-11 | 2007-10-01 | 2010-09-13 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1.2 | [16 empty] | 320
9 |  |  | BL Box parts |  | 20 | 8 |  | 2010-10-11 | 2010-11-08 | 2007-10-01 | 2010-10-11 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 4 | [16 empty] | 320 | [9 empty] | 2880
10 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
11 |  |  | Calorimeter TC wiring |  | 20 | 9 |  | 2010-11-08 | 2010-12-06 | 2007-10-01 | 2010-11-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 10 | [12 empty] | 160 |  |  |  | 160
12 |  |  | Ion Dump TC wiring |  | 20 | 11 |  | 2010-12-06 | 2011-01-03 | 2007-10-01 | 2010-12-06 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 5 | [12 empty] | 160 |  |  |  | 160
13 |  |  | Magnet TC wiring |  | 20 | 12 |  | 2011-01-03 | 2011-01-31 | 2007-10-01 | 2011-01-03 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2 | [12 empty] | 160 |  |  |  | 160
14 |  |  | 90 inch flange and neutralizer TC wiring |  | 20 | 13 |  | 2011-01-31 | 2011-02-28 | 2007-10-01 | 2011-01-31 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2 | [12 empty] | 160 |  |  |  | 160
15 |  |  | Exit spool piece TC wiring |  | 20 | 14 |  | 2011-02-28 | 2011-03-28 | 2007-10-01 | 2011-02-28 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2 | [12 empty] | 160 |  |  |  | 160
17 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  |  | Refurbishment | [7 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 250 | [26 empty] | Rad Supplies | Decon Actuals
18 |  |  | Refurbish BL Box |  | 50 |  | 2010-10-01 | 2010-10-01 | 2010-12-10 | 2010-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1 | [10 empty] | 160 |  | 640
19 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
20 |  |  | Refurbish BL Lid |  | 50 | 18 |  | 2010-12-10 | 2011-02-18 | 2007-10-01 | 2010-12-10 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 3 | [10 empty] | 160 |  | 640
21 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
22 |  |  | Refurbish 90 inch flange and neutralizer |  | 50 | 20 |  | 2011-02-18 | 2011-04-29 | 2007-10-01 | 2011-02-18 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2 | [10 empty] | 320 |  | 1280
23 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
24 |  |  | Refurbish Bending Magnet |  | 30 | 22 |  | 2011-04-29 | 2011-06-10 | 2007-10-01 | 2011-04-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1 | [10 empty] | 160 |  | 640
25 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
26 |  |  | Refurbish spool piece |  | 20 | 24 |  | 2011-06-10 | 2011-07-08 | 2007-10-01 | 2011-06-10 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 2 | [10 empty] | 320 |  | 1280
27 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
28 |  |  | Refurbish Ion Dump |  | 50 | 26 |  | 2011-07-08 | 2011-09-16 | 2007-10-01 | 2011-07-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 1 | [10 empty] | 480 |  | 1920
29 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
30 |  |  | Refurbish Calorimeter |  | 50 | 28 |  | 2011-09-16 | 2011-11-25 | 2007-10-01 | 2011-09-16 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 40 | [10 empty] | 320 |  | 1280 | 160 |  |  | 200
31 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
33 |  |  | Reassembly & Test |  | 60 |  | 2012-01-02 | 2012-01-02 | 2012-03-26 | 2012-01-02 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 480 |  | 1920
34 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
35 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
36 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
37 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
40 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
41 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
42 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
43 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
44 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
45 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
46 | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[10 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [13 empty] | 350.9 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 2440 | 0 | 10400 | 1120 | 0 | 0 | 3880 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 2265.8074 | [10 empty] | 430.2034 | 0 | 0 | 0 | 0 | 0 | 59.952 | 0 | 0 | 0 | 0 | 368.44 | 0 | 877.76 | 179.088 | 0 | 0 | 350.364 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  | Weeks | [12 empty] | 1 - National Standards
| Purchase orders-Commercial, off-the-shelf items |  |  |  | 3 | [12 empty] | 2 - Engineering Judgement/Experience
| Purchase orders-Noncommercial items |  |  |  | 5 | [12 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
| Subcontracts (non construction) |  |  |  | 8 | [12 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
| Construction subcontracts |  |  |  | 9 | [12 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and Uncertainty
Cost Center: | 1180
Job Number: | 2440
Job Title: | NSTX Beamline 2 Refurbishment
Job Manager: | Martin Denault
Martin Denault
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | Remaking existing parts.
| Design Complexity |  | X |  |  | Calorimeter double bellows.
Refer to Primavera Data-Base
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Further inspections may require additional parts and labor. |  |  |  | U |  |  |  |  | 50 | 50
2 | Existing Copper parts may be reusable. Except for dump. |  |  |  | L | [5 empty] | -234
3
4 | [10 empty] | -184
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1180
Job Number: | 2440
Job Title: | NSTX Beamline 2 Refurbishment
Job Manager: | Martin Denault
Martin Denault
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Copper |  |  | Weight of Cu needed at $4.00 per pound.
RAD Supplies |  |  | Decon actuals scaled to job.
Wire |  |  | Spools of wire needed.
O rings, tools, general supplies |  |  | experience.
Sheet metal |  |  | experience.
Hardware |  |  | experience.
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS