## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1180
Job Number: | 2475
Job Title: | NBI-Controls & Instrumentation
Job Manager: | Mark Cropper
Description:
This work covers the controls and instrumentation for the NB2. The work covers PLC, programming, control racks, new thermocouples, TC scanner, miscellaneous controls, and control cabling. The work also includes the gradient grid upgrade. System integration and testing will be performed
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1180
| Job Number: |  |  | 2475
| Job Title: |  |  | NBI-Controls & Instrumentation
| Job Manager: |  |  | Mark Cropper
Estimate (user input)
[5 empty] | SCHEDULE | [12 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | Logical Pre-requisites (one task numbers in each column ,any order) |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | Subcontact labor | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | P3 cross ref (optinal) | [16 empty] | 1.226 | 1.226 | 1.23 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
1 |  | Preliminary Design | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
2 |  | Control System Lay Out |  |  | 47 |  |  |  | 2010-01-04 | 2010-01-04 | 2010-03-10 19:12 | 2010-01-04 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 272 | 40 | [14 empty] | cropper,rossi
3 |  | Update Cost & Schedule Estimate |  |  | 5 | 1 |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [15 empty] | cropper
4 |  | FMEA Analysis |  |  | 5 |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [15 empty] | cropper
5 |  | Design Drawings |  |  | 100 | 1 |  |  |  | 2007-10-01 | 2008-02-18 | 2007-10-01 |  | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 320 |  |  |  |  | 640 | [15 empty] | cropper
6 |  | PDR Prep PPL |  |  | 2 | 5 |  |  |  | 2008-02-18 | 2008-02-20 19:12 | 2007-10-01 | 2008-02-18 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | cropper
7 |  | PDR Prep PU |  |  | 2 | 6 |  |  |  | 2008-02-20 19:12 | 2008-02-23 14:24 | 2007-10-01 | 2008-02-20 19:12 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | cropper
8 |  | PDR Prep DOE |  |  | 2 | 7 |  |  |  | 2008-02-23 14:24 | 2008-02-26 09:36 | 2007-10-01 | 2008-02-23 14:24 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | cropper
9 |  | CONDUCT PDR |  |  | 1 | 8 |  |  | 2010-06-15 | 2010-06-15 | 2010-06-16 09:36 | 2010-06-15 | 2008-02-26 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 8 | [15 empty] | cropper
10 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
11 |  | Final Design | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [28 empty] | cropper
12 |  | Disposition PDR Chits |  |  | 2 | 9 |  |  |  | 2010-06-16 09:36 | 2010-06-19 04:48 | 2007-10-01 | 2010-06-16 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | cropper
13 |  | Design Drawings |  |  | 20 | 12 |  |  |  | 2010-06-19 04:48 | 2010-07-17 04:48 | 2007-10-01 | 2010-06-19 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 160 | [15 empty] | cropper
14 |  | PLC & RSView Programing |  |  | 40 | 9 |  |  |  | 2010-06-16 09:36 | 2010-08-11 09:36 | 2007-10-01 | 2010-06-16 09:36 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 320 | [15 empty] | cropper
15 |  | TC Scanner Programing |  |  | 20 |  |  |  |  | 2007-10-01 | 2007-10-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | 160 | [14 empty] | cropper,rossi
16 |  | LCC Remote LabView Programing |  |  | 40 |  |  |  |  | 2007-10-01 | 2007-11-26 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | 320 | [14 empty] | cropper,rossi
17 |  | Update Cost & Schedule Estimate |  |  | 5 |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [15 empty] | cropper
18 |  | FDR Prep PPL |  |  | 2 | 17 |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | cropper
19 |  | FDR Prep PU |  |  | 2 | 18 |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | cropper
20 |  | FDR Prep DOE |  |  | 2 | 19 |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 16 | [15 empty] | cropper
21 |  | CONDUCT FDR |  |  | 1 | 20 |  |  | 2010-11-15 | #N/A | #N/A | 2010-11-15 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 8 | [15 empty] | cropper
22 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
23 |  | Procurement | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
24 |  | Item 1: | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
25 |  |  | Prep Requisition and procurement package |  | 5 |  |  |  | 2011-01-01 | #N/A | #N/A | 2011-01-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [15 empty] | cropper
26 |  |  | SUBMIT REQ TO PROCUREMENT |  | 1 | 21 |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 |  | 312 | [10 empty] | 8 | [15 empty] | cropper
27 |  |  | Procurement lead time (1) |  | 15 | 17 |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01
28 |  |  | AWARD | [8 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
29 |  |  | Fabricate or delivery |  | 40 | 18 |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01
30 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
31 |  | Fab/Assembly | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
32 |  | Fab/Assy Procedure |  |  | 5 |  |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | [15 empty] | cropper
33 |  | Shop Fabrication | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
34 |  | Cable Tray |  |  | 40 |  |  |  | 2011-06-01 | #N/A | #N/A | 2011-06-01 | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | [18 empty] | 640
35 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
36 |  | Gradient Grid divider |  |  | 20 |  |  |  |  | 2007-10-01 | 2007-10-29 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 |  | 640 | [13 empty] | cropper
37 |  | Penetrations |  |  | 5 |  |  |  | 2011-01-01 | 2011-01-01 | 2011-01-08 | 2011-01-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  |  |  | 40 | [8 empty] | 8 | [5 empty] | 80 | [9 empty] | cropper
38 |  | Control Rack Cage |  |  | 5 |  |  |  |  | 2007-10-01 | 2007-10-08 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 |  |  |  | 15 | [8 empty] | 8 | [5 empty] | 80 | [9 empty] | cropper
39 |  | Installation | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
40 |  | Installation Procedures |  |  | 5 |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [7 empty] | 40 |  |  |  |  | 40 | [15 empty] | cropper
41 |  | Beam Line Cabling |  |  | 80 | 37 | 38 | 34 |  | #N/A | #N/A | 2007-10-01 | 2011-01-08 | 2007-10-08 | #N/A | 2007-10-01 |  |  |  | 80 | [8 empty] | 320 |  | 1280 |  |  |  | 16 | [9 empty] | cropper
42 |  | Rack relocation |  |  | 25 |  |  |  | 2011-06-01 | 2011-06-01 | 2011-07-06 | 2011-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 |  | 240 |  |  |  | 400 | [9 empty] | cropper
43 |  | Aux Cabling |  |  | 20 | 41 |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 |  | 400 | [13 empty] | cropper
44 |  | TC Scanner |  |  | 20 |  |  |  |  | #N/A | #N/A | 2007-10-01 | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 |  | 400 | [13 empty] | cropper
45 |  | NBOS Station |  |  | 10 |  |  |  |  | #N/A | #N/A |  | #N/A | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 80 |  | 160 | [13 empty] | cropper
46 |  | LCC Remote |  |  | 40 |  |  |  | 2011-06-01 | 2011-06-01 | 2011-07-27 | 2011-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 40 | 640 | 640 | [13 empty] | cropper,rossi
47 |  | Power Supply Upgrade |  |  | 23 |  |  |  |  | 2007-10-01 | 2007-11-02 04:48 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 | 160 | 368 | [13 empty] | cropper,rossi
48 |  | Protective Plate TC's |  |  | 10 |  |  |  |  | 2007-10-01 | 2007-10-15 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 24 |  | 80 | [13 empty] | cropper
49 |  | PTP Testing |  |  | 10 |  |  |  | 2012-06-01 | 2012-06-01 | 2012-06-15 | 2012-06-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [12 empty] | 80 |  | 80 | [13 empty] | cropper
50 |  | Installation Procedure | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | [28 empty] | cropper
51 |  | Machine Installation | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
52 |  | PTP Testing | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
53 | [11 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
54 |  | OTHER TASKS | [9 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
[12 empty] | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01
|  | TOTALS | [15 empty] | 312 | 0 | 135 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 2544 | 1320 | 4288 | 0 | 0 | 0 | 1216 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 1606.462 | [12 empty] | 382.512 | 0 | 166.05 | 0 | 0 | 0 | 44.964 | 0 | 0 | 0 | 0 | 384.144 | 157.08 | 361.9072 | 0 | 0 | 0 | 109.8048 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [19 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  | Weeks | [15 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  |  | 3 | [15 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  |  | 5 | [15 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  |  | 8 | [15 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  |  | 9 | [15 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 1180
Job Number: |  | 2475
Job Title: |  | NBI-Controls & Instrumentation
Job Manager: |  | Mark Cropper
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1
2
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1180
Job Number: | 2475
Job Title: | NBI-Controls & Instrumentation
Job Manager: | Mark Cropper
Materials and Subcontracts (M&S) |  |  |  | Basis of Estimate
Description:
NBOS Stations - 138' & Test cell |  | 14380 |  | catalog prices (see Tab E for breakdown)
PLC equipment |  | 66000 |  | catalog prices (see Tab E for breakdown)
LCC remote NI equipment |  | 50000 |  | catalog prices (see Tab E for breakdown)
Thermocouple Scanner |  | 17000 |  | catalog prices (see Tab E for breakdown)
Vacuum system equipment |  | 23840 |  | catalog prices (see Tab E for breakdown)
Power supply control upgrade |  | 51040 |  | catalog prices (see Tab E for breakdown)
cryo System |  | 8000 |  | catalog prices (see Tab E for breakdown)
Water System equipment |  | 5000 |  | catalog prices (see Tab E for breakdown)
cable |  | 60000 |  | based on previous jobs
Cable Tray ? |  | 2000 |  | based on previous jobs
Cage & Kirk Locks |  | 5000 |  | based on previous jobs
fiber optic cable |  | 2000 |  | catalog price 1000' @ $2.00/ft
Thermocouples for Duct & Protective Plates |  | 2500 |  | catalog price 1000' @ $2.50/ft
Misc |  | 5000 |  | based on previous jobs
| Total | 311760
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS

## Tab E M&S Backup
Detailed M&S Estimates
Cost Center: | 1180
Job Number: | 2475
Job Title: | NBI-Controls & Instrumentation
Job Manager: | Mark Cropper
TFT5EA00003 | 5 Pair Feed Through | 401.75 | 10 | 4017.5
626B11TCE | 10 Torr Baratron | 952 | 6 | 5712
626B13TCE | 1000 Torr Baratron | 952 | 6 | 5712
RGA 100 | Residual Gas Analyzer | 4000 | 2 | 8000
PX219-200G10V | Pressure Transmitter 0-200 psi | 195 | 2 | 390
| Vacuum hardware | Total |  | 23831.5
RSView Station 138' Level
| Dell T3400 Computer & 2 Monitors | 2200 | 1 | 2200
| 1784-PKTX Data Hiway Card | 1835 | 1 | 1835
|  | 0 | 1 | 0
|  |  | Total | 4035
RGA Station 138' Level
| Dell T3400 Computer & 2 Monitors | 2200 | 1 | 2200
| Four Port Serial Card | 102.99 | 1 | 102.99
|  |  | Total | 2302.99
Calorimeter Monitor Station
| Dell T3400 Computer & Monitor | 2000 | 1 | 2000
|  |  | Total | 2200
RSView/RGA Station Test Cell
| Dell T3400 Computer | 1800 | 1 | 1800
| Four Port Serial Card | 102.99 | 1 | 102.99
| 1784-PKTX Data Hiway Card | 1835 | 1 | 1835
| RS-232 Data Switch | 30 | 2 | 60
3797.99
Calorimeter Camera
| Axis 214PTZ network camera | 1300 | 1 | 1300
|  |  | Total | 1300
Network
| 8 Port Gigabit Switch | 120 | 2 | 240
| Cables | 500 | 1 | 500
740
| NBOS Control Stations |  | Total | 14375.98
Racks
1771-A3B | 12 Slot Rack- 19" rack mount | 887 | 5 | 4435
1771-ASB | Remote I/O Com | 1679 | 5 | 8395
|  | 0 | 1 | 0
|  |  | Total | 12830
I/O Modules
1771-IBD | 24 VDC Input Module- 16 | 526 | 13 | 6838
1771-OBD | 24 VDC Output Module- 16 | 752 | 3 | 2256
1771-IGD | TTL Input Module | 637 | 2 | 1274
1771-OW16 | Contact Output | 1308 | 5 | 6540
1771-IFE | Analog Input | 2286 | 5 | 11430
1771-OFE2 | Analog Output | 2221 | 2 | 4442
1771-NT1 | Thermocouple Input | 3905 | 5 | 19525
52305
| PLC equipment | Total |  | 65135
Chassis
779218-01 | 14 Slot Chassis with power supply | 3599 | 1 | 3599
763000-01 | Power Cord | 9 | 1 | 9
778644-01 | Rack Mount Kit | 159 | 1 | 159
|  |  | Total | 3767
Processor
780343-33 | PXI-8183 850MHZ Processor | 1999 | 1 | 1999
778469-512 | 512 MB Ram upgrade | 199 | 1 | 199
2198
I/O
779547-01 | PIX-6255 80 channel Analog Input | 2299 | 1 | 2299
779632-01 | PIX-6259 32 Channel Analog Input | 1599 | 1 | 1599
778998-01 | PIX 6723 32 Channel Analog Output | 1400 | 1 | 1400
192061-02 | SHC68-68-EPM Shielded Cable | 129 | 3 | 387
191945-02 | SCH68-68 Twisted Pair Cable | 89 | 3 | 267
777141-01 | TBX-68 Connector Block | 159 | 6 | 954
778967-01 | PIX-6511 64 Channel Digital Input | 459 | 3 | 1377
778969-01 | PIX-6512 64 Channel Digital Output | 459 | 1 | 459
777812-01 | CB-100 Kit (connecter block & cable) | 259 | 4 | 1036
9778
|  | Total per source |  | 15743
|  | Total for three systems |  | 47229
Network
RSV4000 | Linksys Router | 120.99 | 1 | 120.99
SLM2008 | Linksys 8 port Switch | 119.99 | 1 | 119.99
| Cable & connectors | 500 | 1 | 500
740.98
Display Computer
| Dell T3400 with dual 20" monitors | 2200 | 1 | 2200
2200
| LCC Remote equipment | Grand Total |  | 50169.98
Chassis
778636-01 | 8 Slot Chassis with power supply | 2099 | 1 | 2099
763000-01 | Power Cord | 9 | 1 | 9
778643-01 | Rack Mount Kit | 159 | 1 | 159
|  |  | Total | 2267
Processor
780343-33 | PXI-8183 850MHZ Processor | 1999 | 1 | 1999
778469-512 | 512 MB Ram upgrade | 199 | 1 | 199
2198
I/O
779296-01 | PIX-6225 80 channel Analog Input | 1399 | 5 | 6995
192061-02 | SHC68-68-EPM Shielded Cable | 129 | 5 | 645
191945-02 | SCH68-68 Twisted Pair Cable | 89 | 5 | 445
779313-01 | PIX-6521 8 Channel Relay Output | 529 | 1 | 529
778621-02 | SH37F-37M | 29 | 1 | 29
779491-01 | CB-37F-HVD | 169 | 1 | 169
| Connecters & cable | 1000 | 1 | 1000
9812
| Thermocouple Scanner | Total |  | 14277
Upgrade Parts
| Gradient Grid parts | 14000 | 3 | 42000
| HVST Filament Control Parts | 350 | 4 | 1400
| Decel Control Grid Parts | 350 | 4 | 1400
| Crowbar Parts | 60 | 24 | 1440
| Vac Ion Pump Power Supply | 1200 | 4 | 4800
| Power Supplies |  | Total | 51040
211S | Temperature Monitor | 647 | 1 | 647
2308-12 | VME rack & power supply | 1176 | 1 | 1176
231 | Temperature transmitter | 583 | 7 | 4081
2308-BP | blank panel | 21 | 5 | 105
DT-470-CU-13 | Diode sensor | 254 | 7 | 1778
| Cryo Hardware |  | Total | 7787
M41E1 | 4 Way Solenoid Valve | 150 | 12 | 1800
MM6 | Solenoid Manifold - 6 Station | 60 | 2 | 120
51025K374 | 1/4" tube to 1/8" MPT fitting | 2.79 | 60 | 167.4
6763K11 | Regulator | 35.47 | 2 | 70.94
3844K1 | Gauge | 10.7 | 2 | 21.4
4264k21 | 1/2" ball valve | 7.66 | 2 | 15.32
5078K65 | hex bushing | 2.88 | 4 | 11.52
9151K56 | 1/8" MPT tube | 2.2 | 4 | 8.8
| 1/4" tubing | 0.2 | 1000 | 200
| pneumatic Actuators | 500 | 4 | 2000
| Water System |  | Total | 4415.38