## Tab A Description
Work Approval Form (WAF)
Cost Center: 1180
Job Number: 2480
Job Title: NSTX NB2 Duct & VV Mods
Job Manager: Craig Priniski
Description:
This job includes the design, and fabrication of all components connecting NB Box to NSTX, the connecting ductwork and modifications to NSTX Vacuum Vessel are inculded in this job.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: 1180
Job Number: 2480
Job Title: NSTX NB2 Duct & VV Mods
Job Manager: Craig Priniski
Estimate (user input)
[5 empty] | SCHEDULE | [13 empty] | FY09$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT | [5 empty] | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | Duration in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) |  |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
numb | P3 cross ref | [17 empty] | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
|  | Physics Requirements | [10 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
[13 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
|  | Conceptual Design | [10 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [21 empty] | 4
1 |  | CD for NSTX VV in Bay J-K area |  | PRINISKI | 10 |  |  |  |  | 2009-08-10 | 2009-08-10 | 2009-08-24 | 2009-08-10 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 20 |  |  |  |  | 20 | [8 empty] | 4
2 |  | CD of Port K Extension |  | PRINISKI | 3 | 1 |  |  |  | 2009-08-24 | 2009-08-24 | 2009-08-28 04:48 | 2009-08-24 | 2009-08-24 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 12 |  |  |  |  | 8 | [8 empty] | 4
3 |  | CD Ceramic Break Flanges |  | PRINISKI | 10 |  |  |  |  | 2009-08-10 | 2009-08-10 | 2009-08-24 | 2009-08-10 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 20 |  |  |  |  | 20 | [8 empty] | 2
4 |  | CD Spool Piece |  | PRINISKI | 3 |  |  |  |  | 2009-08-10 | 2009-08-10 | 2009-08-14 04:48 | 2009-08-10 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 16 |  |  |  |  | 8 | [8 empty] | 4
5 |  | C&S Development |  | PRINISKI | 10 |  |  |  |  | 2009-07-13 | 2009-07-13 | 2009-07-27 | 2009-07-13 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 40 | [8 empty] | 4
6 |  | C&S Review |  | PRINISKI | 1 | 5 |  |  |  | 2009-07-29 | 2009-07-29 | 2009-07-30 09:36 | 2009-07-29 | 2009-07-27 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 4 | [8 empty] | 4
7 |  | NSTX J-K Mockup purchase |  | PRINISKI | 25 | 1 |  |  |  |  | 2009-11-17 08:19 | 2009-12-22 08:19 |  |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 4 | [19 empty] | 2
8 |  | Prep for PPPL/Ext CDR |  | PRINISKI | 5 | 2 | 3 | 4 | 6 |  | 2009-11-17 08:19 | 2009-11-24 08:19 | 2009-11-17 08:19 | 2009-08-28 04:48 | 2009-08-24 | 2009-08-14 04:48 | 2009-07-30 09:36 | [7 empty] | 20 |  |  |  |  | 20 | [8 empty] | 4
9 |  | PPPL CDR |  | PRINISKI | 1 | 8 |  |  |  |  | 2009-11-24 08:19 | 2009-11-25 17:55 | 2009-11-17 08:19 | 2009-11-24 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [21 empty] | 4
10 |  | Prep for PU CDR |  | PRINISKI | 5 | 9 |  |  |  | 2009-09-28 | 2009-09-28 | 2009-10-05 |  | 2009-11-25 17:55 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 40 |  |  |  |  | 40 | [8 empty] | 4
11 |  | Prep for DOE CDR |  | PRINISKI | 8 | 10 |  |  |  |  | 2009-11-17 08:19 | 2009-11-28 13:07 |  | 2009-10-05 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 16 |  |  |  |  | 16 | [8 empty] | 4
|  | Preliminary Design | [10 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
12 |  | CDR Chit Resolution (all areas) |  | PRINISKI | 30 | 11 |  |  |  |  | 2009-11-28 13:07 | 2010-01-09 13:07 |  | 2009-11-28 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 40 |  |  |  |  | 120 | 24 | [7 empty] | 4
13 |  | Thermal Analysis |  | PRINISKI | 2 | 12 |  |  |  |  | 2010-01-09 13:07 | 2010-01-12 08:19 |  | 2010-01-09 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [6 empty] | 16
14 |  | Seismic Analysis |  | PRINISKI | 1 | 12 |  |  |  |  | 2010-01-09 13:07 | 2010-01-10 22:43 | 2009-11-17 08:19 | 2010-01-09 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
15 |  | FMEA Analysis |  | PRINISKI | 2 | 12 |  |  |  |  | 2010-01-09 13:07 | 2010-01-12 08:19 | 2009-11-17 08:19 | 2010-01-09 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 16
16 |  | Prepare NEPA Form |  | PRINISKI | 1 | 12 |  |  |  |  | 2010-01-09 13:07 | 2010-01-10 22:43 | 2009-11-17 08:19 | 2010-01-09 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 2 | [8 empty] | 4
17 |  | NSTX VV Modification Prototyping |  | PRINISKI | 15 | 12 | 7 |  |  |  | 2010-01-09 13:07 | 2010-01-30 13:07 |  | 2010-01-09 13:07 | 2009-12-22 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 4 | [5 empty] | 10 |  |  |  |  | 60 | 120 | [7 empty] | 7
18 |  | J-K RWM Coil Redesign |  | PRINISKI | 30 | 17 |  |  |  |  | 2010-01-30 13:07 | 2010-03-13 13:07 |  | 2010-01-30 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [6 empty] | 20 | 60 |  |  |  |  | 100 | [8 empty] | 8
19 |  | Update Cost & Schedule Estimate |  | PRINISKI | 3 | 17 |  |  |  |  | 2010-01-30 13:07 | 2010-02-03 17:55 | 2009-11-17 08:19 | 2010-01-30 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 16 | [8 empty] | 4
20 |  | Design Components |  | PRINISKI | 60 | 11 | 17 |  |  |  | 2010-01-30 13:07 | 2010-04-24 13:07 | 2009-11-17 08:19 | 2009-11-28 13:07 | 2010-01-30 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 240 |  |  |  |  | 80 | [8 empty] | 8
21 |  | PDR Prep |  | PRINISKI | 40 | 18 |  |  |  | 2010-06-08 | 2010-06-08 | 2010-08-03 | 2010-06-08 | 2010-03-13 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 10 |  |  |  |  | 40 | [8 empty] | 4
22 |  | CONDUCT PDR |  | PRINISKI | 1 | 21 |  |  |  |  | 2010-08-03 | 2010-08-04 09:36 | 2009-11-17 08:19 | 2010-08-03 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 8 | [8 empty] | 4
[13 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
[13 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
|  | Final Design | [10 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
23 |  | Disposition PDR Chits |  | PRINISKI | 20 | 21 |  |  |  |  | 2010-08-03 | 2010-08-31 | 2009-11-17 08:19 | 2010-08-03 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 16 |  |  |  |  | 60 | [8 empty] | 4
24 |  | Design Drawings |  | PRINISKI | 25 | 22 |  |  |  |  | 2010-08-04 09:36 | 2010-09-08 09:36 | 2009-11-17 08:19 | 2010-08-04 09:36 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [7 empty] | 180 |  |  |  |  | 40 | [8 empty] | 8
25 |  | Installation Prototyping |  | PRINISKI | 20 | 22 |  |  |  |  | 2010-08-04 09:36 | 2010-09-01 09:36 | 2009-11-17 08:19 | 2010-08-04 09:36 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 5 | [5 empty] | 16 |  |  |  |  | 80 | 160 | [7 empty] | 2
26 |  | Update Analyses |  | PRINISKI | 3 | 22 |  |  |  |  | 2010-08-04 09:36 | 2010-08-08 14:24 | 2009-11-17 08:19 | 2010-08-04 09:36 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [6 empty] | 16 | [14 empty] | 4
27 |  | Update Cost & Schedule Estimate |  | PRINISKI | 3 | 22 | 23 |  |  |  | 2010-08-31 | 2010-09-04 04:48 | 2009-11-17 08:19 | 2010-08-04 09:36 | 2010-08-31 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 20 | [8 empty] | 4
28 |  | Prep Procurement Specs |  | PRINISKI | 30 | 23 |  |  |  |  | 2010-08-31 | 2010-10-12 | 2009-11-17 08:19 | 2010-08-31 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 60 | [8 empty] | 4
29 |  | FDR Prep |  | PRINISKI | 20 | 27 |  |  |  | 2011-01-03 | 2011-01-03 | 2011-01-31 | 2011-01-03 | 2010-09-04 04:48 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [6 empty] | 8 | [5 empty] | 40 | [8 empty] | 4
30 |  | CONDUCT FDR |  | PRINISKI | 1 | 28 |  |  |  |  | 2010-10-12 | 2010-10-13 09:36 | 2009-11-17 08:19 | 2010-10-12 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 8 | [8 empty] | 4
|  | Procurement | [10 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
31 |  | Item 1: 40" VAT VALVES x2 |  | PRINISKI | [8 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 250 | [19 empty] | 6
32 |  |  | Prep Requisition and procurement package | PRINISKI | 2 | 28 |  |  |  |  | 2010-10-12 | 2010-10-14 19:12 | 2009-11-17 08:19 | 2010-10-12 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 8
33 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 | 31 |  |  |  |  | 2009-11-17 08:19 | 2009-11-18 17:55 | 2009-11-17 08:19 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 4
34 |  |  | Procurement lead time (1) | PRINISKI | 25 | 31 |  |  |  |  | 2009-11-17 08:19 | 2009-12-22 08:19 | 2009-11-17 08:19 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
35 |  |  | AWARD | PRINISKI | 1 | 32 |  |  |  | 2009-12-22 08:19 | 2009-12-22 08:19 | 2009-12-23 17:55 | 2009-12-22 08:19 | 2010-10-14 19:12 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
36 |  |  | Fabricate or delivery | PRINISKI | 120 | 33 |  |  |  | 2009-12-23 17:55 | 2009-12-23 17:55 | 2010-06-09 17:55 | 2009-12-23 17:55 | 2009-11-18 17:55 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
37 |  | Item 2: 40" Bellows Section |  | PRINISKI | [8 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 300 | [19 empty] | 2
38 |  |  | Prep Requisition and procurement package | PRINISKI | 2 | 30 |  |  |  | 2010-10-14 19:12 | 2010-10-14 19:12 | 2010-10-17 14:24 | 2010-10-14 19:12 | 2010-10-13 09:36 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 8
39 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 | 36 |  |  |  | 2010-10-17 14:24 | 2010-10-17 14:24 | 2010-10-19 | 2010-10-17 14:24 | 2010-06-09 17:55 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 4
40 |  |  | Procurement lead time (1) | PRINISKI | 25 | 37 |  |  |  | 2010-10-19 | 2010-10-19 | 2010-11-23 | 2010-10-19 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
41 |  |  | AWARD | PRINISKI | 1 | 38 |  |  |  | 2010-11-23 | 2010-11-23 | 2010-11-24 09:36 | 2010-11-23 | 2010-10-17 14:24 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
42 |  |  | Fabricate or delivery | PRINISKI | 120 | 39 |  |  |  | 2010-11-24 09:36 | 2010-11-24 09:36 | 2011-05-11 09:36 | 2010-11-24 09:36 | 2010-10-19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
43 |  | Item 3: Rectangular Bellows Section |  | PRINISKI | [8 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 400 | [19 empty] | 4
44 |  |  | Prep Requisition and procurement package | PRINISKI | 2 | 37 |  |  |  |  | 2009-11-17 08:19 | 2009-11-20 03:31 | 2009-11-17 08:19 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 8
45 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 | 42 |  |  |  | 2009-11-20 03:31 | 2009-11-20 03:31 | 2009-11-21 13:07 | 2009-11-20 03:31 | 2011-05-11 09:36 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 4
46 |  |  | Procurement lead time (1) | PRINISKI | 25 | 43 |  |  |  | 2009-11-21 13:07 | 2009-11-21 13:07 | 2009-12-26 13:07 | 2009-11-21 13:07 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
47 |  |  | AWARD | PRINISKI | 1 | 44 |  |  |  | 2009-12-26 13:07 | 2009-12-26 13:07 | 2009-12-27 22:43 | 2009-12-26 13:07 | 2009-11-20 03:31 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
48 |  |  | Fabricate or delivery | PRINISKI | 180 | 45 |  |  |  | 2009-12-27 22:43 | 2009-12-27 22:43 | 2010-09-05 22:43 | 2009-12-27 22:43 | 2009-11-21 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
49 |  | Item 4: Spool Piece |  | PRINISKI | [8 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 40 | [19 empty] | 4
50 |  |  | Prep Requisition and procurement package | PRINISKI | 2 | 43 |  |  |  |  | 2009-11-17 08:19 | 2009-11-20 03:31 | 2009-11-17 08:19 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 8
51 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 | 48 |  |  |  | 2009-11-20 03:31 | 2009-11-20 03:31 | 2009-11-21 13:07 | 2009-11-20 03:31 | 2010-09-05 22:43 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 4
52 |  |  | Procurement lead time (1) | PRINISKI | 25 | 49 |  |  |  | 2009-11-21 13:07 | 2009-11-21 13:07 | 2009-12-26 13:07 | 2009-11-21 13:07 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
53 |  |  | AWARD | PRINISKI | 1 | 50 |  |  |  | 2009-12-26 13:07 | 2009-12-26 13:07 | 2009-12-27 22:43 | 2009-12-26 13:07 | 2009-11-20 03:31 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
54 |  |  | Fabricate or delivery | PRINISKI | 120 | 51 |  |  |  | 2009-12-27 22:43 | 2009-12-27 22:43 | 2010-06-13 22:43 | 2009-12-27 22:43 | 2009-11-21 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
55 |  | Item 5: Vessel Cap & Port Extension |  | PRINISKI | [8 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 100 | [10 empty] | 40 | [8 empty] | 2
56 |  |  | Prep Requisition and procurement package | PRINISKI | 1 | 49 |  |  |  |  | 2009-11-17 08:19 | 2009-11-18 17:55 | 2009-11-17 08:19 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
57 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 | 55 |  |  |  | 2009-11-18 17:55 | 2009-11-18 17:55 | 2009-11-20 03:31 | 2009-11-18 17:55 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
58 |  |  | Procurement lead time (1) | PRINISKI | 25 | 56 |  |  |  | 2009-11-20 03:31 | 2009-11-20 03:31 | 2009-12-25 03:31 | 2009-11-20 03:31 | 2009-11-18 17:55 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
59 |  |  | AWARD | PRINISKI | 1 | 57 |  |  |  |  | 2009-11-20 03:31 | 2009-11-21 13:07 | 2009-11-17 08:19 | 2009-11-20 03:31 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
60 |  |  | Fabricate or delivery | PRINISKI | 200 | 58 |  |  |  |  | 2009-12-25 03:31 | 2010-10-01 03:31 | 2009-11-17 08:19 | 2009-12-25 03:31 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [13 empty] | 1100
61 |  | Item 6: RWM Coil Fabrication |  | PRINISKI | 100 | 29 |  |  |  |  | 2011-01-31 | 2011-06-20 | 2009-11-17 08:19 | 2011-01-31 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 170 | [19 empty] | 8
62 |  | Misc. Other materials for duct (added shield) |  | PRINISKI | [8 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 |  | 140 | [19 empty] | 3
63 |  |  | Prep Requisition and procurement package | PRINISKI | 1 | 56 |  |  |  |  | 2009-11-18 17:55 | 2009-11-20 03:31 | 2009-11-17 08:19 | 2009-11-18 17:55 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 8
64 |  |  | SUBMIT REQ TO PROCUREMENT | PRINISKI | 1 | 62 |  |  |  |  | 2009-11-17 08:19 | 2009-11-18 17:55 | 2009-11-17 08:19 |  | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 4
65 |  |  | Procurement lead time (1) | PRINISKI | 15 | 63 |  |  |  |  | 2009-11-20 03:31 | 2009-12-11 03:31 | 2009-11-17 08:19 | 2009-11-20 03:31 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
66 |  |  | AWARD | PRINISKI | 1 | 64 |  |  |  |  | 2009-11-18 17:55 | 2009-11-20 03:31 | 2009-11-17 08:19 | 2009-11-18 17:55 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
67 |  |  | Fabricate or delivery | PRINISKI | 30 | 65 |  |  |  |  | 2009-12-11 03:31 | 2010-01-22 03:31 | 2009-11-17 08:19 | 2009-12-11 03:31 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
68 |  | Installation |  | PRINISKI | [8 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [21 empty] | 2
69 |  | Installation Procedure |  | PRINISKI | 20 | 59 |  |  |  |  | 2009-11-21 13:07 | 2009-12-19 13:07 | 2009-11-17 08:19 | 2009-11-21 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 90
70 |  | Machine Installation |  | PRINISKI | 90 | 47 |  |  |  | 2011-10-15 | 2011-10-15 | 2012-02-18 | 2011-10-15 | 2009-12-27 22:43 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [12 empty] | 80 | 1200
71 |  | PTP Testing |  | PRINISKI | 4 | 69 |  |  |  |  | 2009-12-19 13:07 | 2009-12-25 03:31 | 2009-11-17 08:19 | 2009-12-19 13:07 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | [13 empty] | 16
72 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
73 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
74 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
75 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
76 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
77 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
78 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
79 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
80 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
81 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
82 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
83 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
84 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
85 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
86 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
87 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
88 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
89 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
90 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
91 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
92 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
93 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
94 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
95 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
96 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
97 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
98 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
99 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
100 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
101 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
102 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
103 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
104 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
105 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
106 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
107 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
108 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
109 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
110 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
111 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
112 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
113 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
114 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
115 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
116 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
117 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
118 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
119 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
120 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
121 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
122 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
123 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
124 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
125 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
126 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
127 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
128 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
129 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
130 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
131 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
132 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
133 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
134 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
135 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
136 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
137 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
138 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
139 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
140 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
141 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
142 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
143 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
144 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
145 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
146 | [12 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
[13 empty] | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19 | 2009-11-17 08:19
|  | TOTALS | [16 empty] | 1413 | 0 | 0 | 0 | 0 | 60 | 716 | 0 | 0 | 0 | 0 | 1196 | 2620 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 2403.154 | [13 empty] | 1723.86 | 0 | 0 | 0 | 0 | 11.13 | 89.5644 | 0 | 0 | 0 | 0 | 197.7825 | 380.817 | 0 | 0 | 0 | 0 | 0
| Notes: | [18 empty] | CATEGORIZATION CODES:
| (1) Procurement lead time: |  |  |  | Weeks | [14 empty] | 1 - National Standards
|  | Purchase orders-Commercial, off-the-shelf items |  |  | 3 | [14 empty] | 2 - Engineering Judgement/Experience
|  | Purchase orders-Noncommercial items |  |  | 5 | [14 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  | Subcontracts (non construction) |  |  | 8 | [14 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
|  | Construction subcontracts |  |  | 9 | [14 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: 1180
Job Number: 2480
Job Title: NSTX NB2 Duct & VV Mods
Job Manager: Craig Priniski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Vessel Machinng Difficulty |  |  |  | L | Additional Time Need |  |  | Past Vessel machining experince | 10 | 70 | 1 | 8
2 | J-K Cap Fit up issuse |  |  |  | U | New TF outer leg included in CS estimate |  |  |  | ~ | 0 | 4 | 8
3 | Rectangular Bellows Fabrication - Fabricator is not Availble |  |  |  | U | Additional Vendor needed |  |  |  | 10 | 100 | 1 | 12
4
5
Notes: | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(1) | The schedule impacts should be entered as the min and max impacts on the critical path.
(2) | If there is no critical path impact then the schedule entries should be zero.
Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
(3) | VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: 1180
Job Number: 2480
Job Title: NSTX NB2 Duct & VV Mods
Job Manager: Craig Priniski
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
Item 1: 40" VAT VALVES x2 | $250K | Based on quotes for propes upgrade, scaled to FY 09 dollars | 6- Quote
Item 2: 40" Bellows Section | $300K | Based on final vendor costs from original NB bellows for NSTX | 8 - Actual NSTX Hardware Purchase
Item 3: Rectangular Bellows Section | $400K | Based on final vendor costs from original NB bellows for NSTX
Item 4: Spool Piece | $40K | Scale up of costs of other vacuum vessel extensions ordered | 4 - Experience
Item 5: Vessel Cap & Port Extension | $80K | Scale up of costs of other vacuum vessel extensions ordered | 4 - Experience
Item 6: RWM Coil Fabrication | $170K | Represents 1/6th of the Fabrication and Installation Costs of RWM Coils | 8- Actual NSTX Work
Misc. Other materials for duct (added shield) | $140K | Scale up of costs of moly plates purchased in 2007 to cover entire duct | 8- Actual NSTX Work
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS